## selection
Report 1 - Last refresh : 24 Jun 2025 14:23:35 CET
Study historic flag | Trial type description | CDP Managing Type | Number of trial assigments | Active substance name | Therapeutic area desc | Study no | NCT CT.gov | Study status desc with hcs info | Study description | Phase description short | Blinding | Budget manager desc | Department Desc | Budget owner desc | Study full title | Indications | Indication Groups | Study all cross references | SCD Approval planned date | SCD Approval actual date | Protocol App original date | Protocol App actual date | FPFV original date | FPFV actual date | LPFV original date | LPFV actual date | LPLV original date | LPLV actual date | Database Locked original date | Database Locked actual date | Final TFLs Released original date | Final TFLs Released actual date | CSR Approval original date | CSR Approval actual date | Countries setup (excl. cancelled) | Countries setup (Country Status) excl. cancelled w/o 1st Site Initiation | Countries desc with Reg. Approval or 1st Site Initiation or FPFV | Number of sites planned | Number of sites SIV | Number of Sites FPFV | Planned to enter study | Planned to enter treatment | Planned to complete treatment | Conf entered screening | Conf in screening in study | Conf drop screening | Conf entered treatment | Conf in treatment in study | Conf drop treatment | Conf completed treatment | Int1 Final TFLs rel original date | Int1 Final TFLs rel baseline date | Int1 Final TFLs rel planned date | Int1 Final TFLs rel actual date | Int2 Final TFLs rel original date | Int2 Final TFLs rel baseline date | Int2 Final TFLs rel planned date | Int2 Final TFLs rel actual date | Int3 Final TFLs rel original date | Int3 Final TFLs rel baseline date | Int3 Final TFLs rel planned date | Int3 Final TFLs rel actual date | Int4 Final TFL rel original date | Int4 Final TFL rel baseline date | Int4 Final TFL rel planned date | Int4 Final TFL rel actual date | Int5 Final TFL rel original date | Int5 Final TFL rel baseline date | Int5 Final TFL rel planned date | Int5 Final TFL rel actual date | Int6 Final TFL rel planned date | Int6 Final TFL rel actual date
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PS0041 | NCT06011733 | CSR Approved | Evaluate the efficacy and safety of BKZ in PSO subject | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | A PHASE 3, MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL GROUP STUDY TO EVALUATE THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN CHINESE ADULT STUDY PARTICIPANTS WITH MODERATE TO SEVERE PLAQUE PSORIASIS | Psoriasis | Immunology |  | 2022-05-12 | 2022-05-11 | 2022-10-12 | 2022-10-10 | 2023-11-24 | 2023-10-31 | 2024-07-17 | 2024-03-19 | 2025-06-11 | 2025-02-05 | 2025-07-09 | 2025-02-21 | 2025-08-25 | 2025-04-18 | 2025-11-20 | 2025-04-28 | China | China (LPLV) | China | 20 | 18 | 18 | 120 | 120 | 108 | 232 | 0 | 99 | 133 | 0 | 48 | 85 |  |  | 2024-12-16 | 2024-12-10
Yes | Phase I | Managing Type | 1 | BIMZELX | Immunology | UP0119 | NCT05292131 | Study Archived | BE Study 2x1mL SS vs 2mL AI | Phase I | Open | GCSO | Immunology | UCB Pharma Global | AN OPEN-LABEL, RANDOMIZED, PARALLEL-GROUP, SINGLE-DOSE BIOEQUIVALENCE STUDY OF BIMEKIZUMAB GIVEN AS 1X2ML OR 2X1ML SUBCUTANEOUS INJECTION USING AN AUTOINJECTOR IN HEALTHY STUDY PARTICIPANTS | Healthy Volunteers | Central Nervous System |  | 2021-09-15 | 2021-09-15 |  | 2021-11-23 | 2022-03-17 | 2022-03-17 | 2022-09-01 | 2022-08-22 | 2023-01-25 | 2023-01-09 | 2023-02-24 | 2023-02-07 | 2023-03-31 | 2023-03-24 | 2023-05-30 | 2023-05-19 | Germany, United States of America | Germany (LPLV), United States of America (LPLV) | Germany, United States of America | 2 | 2 | 2 | 600 | 120 | 120 | 191 | 0 | 98 | 93 | 0 | 0 | 93
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | AS0010 | NCT03928704 | Study Archived | BKZ phase 3, randomized, double-blind, placebo controlled | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | A PHASE 3, MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED STUDY EVALUATING THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN SUBJECTS WITH ACTIVE NONRADIOGRAPHIC AXIAL SPONDYLOARTHRITIS | Non-Radiographic Axial Spondyloarthritis | Immunology | AS0010 is a "sister" study of AS0011 and is a feeder study of AS0014 | 2016-05-02 | 2016-05-02 |  | 2018-12-04 | 2019-05-08 | 2019-04-25 | 2020-11-16 | 2022-02-17 | 2022-04-11 | 2023-04-17 | 2022-05-09 | 2023-05-05 | 2022-05-23 | 2023-06-05 | 2022-08-17 | 2023-09-14 | Belgium, Bulgaria, China, Czech Republic, France, Germany, Hungary, Japan, Poland, Spain, Turkey, United Kingdom, United States of America | Belgium (LPLV), Bulgaria (LPLV), China (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Japan (LPLV), Netherlands (1st Site Initiation (Cancelled)), Poland (LPLV), Spain (LPLV), Turkey (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Bulgaria, China, Czech Republic, France, Germany, Hungary, Japan, Poland, Spain, Turkey, United Kingdom, United States of America | 97 | 96 | 83 | 840 | 274 | 247 | 878 | 0 | 604 | 274 | 0 | 38 | 236 | 2022-01-06 | 2022-01-06 | 2022-01-06 | 2022-01-06 |  |  | 2022-07-18 | 2022-07-15
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | AS0011 | NCT03928743 | Study Archived | BKZ phase 3, randomized, double-blind, placebo controlled | Phase III | Double Blind | GCSO | Immunology | GCSO | A PHASE 3, MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED STUDY EVALUATING THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN SUBJECTS WITH ACTIVE ANKYLOSING SPONDYLITIS | Ankylosing Spondylitis | Immunology | AS0011 is a "sister" study of AS0010 and is a feeder study of AS0014 | 2016-05-02 | 2016-05-02 |  | 2018-11-27 | 2019-05-01 | 2019-04-25 | 2020-09-04 | 2021-04-21 | 2022-01-26 | 2022-08-08 | 2022-02-23 | 2022-09-09 | 2022-03-09 | 2022-09-30 | 2022-06-03 | 2023-01-31 | Belgium, Bulgaria, China, Czech Republic, France, Germany, Hungary, Japan, Netherlands, Poland, Spain, Turkey, United Kingdom, United States of America | Belgium (LPLV), Bulgaria (LPLV), China (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Japan (LPLV), Netherlands (LPLV), Poland (LPLV), Spain (LPLV), Turkey (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Bulgaria, China, Czech Republic, France, Germany, Hungary, Japan, Netherlands, Poland, Spain, Turkey, United Kingdom, United States of America | 97 | 93 | 83 | 612 | 332 | 299 | 642 | 0 | 310 | 332 | 0 | 34 | 298 | 2021-11-30 | 2021-11-30 | 2021-11-30 08:00 | 2021-11-30 |  |  | 2022-06-16 | 2022-06-16
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | HS0003 | NCT04242446 | Study Archived | A Phase 3a, Randomized, Double-blind, Placebo-Controlled, Mu | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | A PHASE 3, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER STUDY EVALUATING THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN STUDY PARTICIPANTS WITH MODERATE TO SEVERE HIDRADENITIS SUPPURATIVA | Hidradenitis Suppurativa | Immunology | HS0003 is a "sister" study of HS0004 and is a feeder study of HS0005 | 2019-09-06 08:00 | 2019-09-06 | 2019-10-29 | 2019-10-29 | 2020-04-29 | 2020-02-19 | 2021-12-08 | 2021-10-27 | 2023-05-03 | 2023-02-19 | 2023-05-17 | 2023-03-10 | 2023-05-31 | 2023-04-03 | 2023-10-04 | 2023-10-13 | Australia, Belgium, Canada, Denmark, France, Germany, Greece, Israel, Italy, Netherlands, Norway, Spain, Switzerland, Turkey, United States of America | Australia (LPLV), Belgium (LPLV), Canada (LPLV), Denmark (LPLV), France (LPLV), Germany (LPLV), Greece (LPLV), Israel (LPLV), Italy (LPLV), Netherlands (LPLV), Norway (LPLV), Spain (LPLV), Switzerland (LPLV), Turkey (LPLV), United States of America (LPLV) | Australia, Belgium, Canada, Denmark, France, Germany, Greece, Israel, Italy, Netherlands, Norway, Spain, Switzerland, Turkey, United States of America | 103 | 96 | 88 | 759 | 490 | 490 | 806 | 0 | 288 | 518 | 0 | 181 | 333 |  |  | 2023-01-05 08:00
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | HS0004 | NCT04242498 | Study Archived | A Phase 3a, Randomized, Double-blind, Placebo-Controlled, Mu | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | A PHASE 3, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER STUDY EVALUATING THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN STUDY PARTICIPANTS WITH MODERATE TO SEVERE HIDRADENITIS SUPPURATIVA | Hidradenitis Suppurativa | Immunology | HS0004 is a "sister" study of HS0003 and is a feeder study of HS0005 | 2019-05-17 08:00 | 2019-05-17 |  | 2019-10-29 | 2020-02-28 | 2020-03-02 | 2021-10-08 | 2021-07-28 | 2023-02-28 | 2022-09-28 | 2023-03-28 | 2022-10-12 | 2023-04-11 | 2022-11-11 | 2023-07-06 | 2023-02-08 | Australia, Bulgaria, Canada, Czech Republic, France, Germany, Hungary, Ireland, Israel, Japan, Poland, Spain, United Kingdom, United States of America | Australia (LPLV), Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Ireland (LPLV), Israel (LPLV), Japan (LPLV), Poland (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Bulgaria, Canada, Czech Republic, France, Germany, Hungary, Ireland, Israel, Japan, Poland, Spain, United Kingdom, United States of America | 117 | 100 | 91 | 761 | 490 | 490 | 754 | 1 | 236 | 517 | 22 | 128 | 368 |  |  | 2022-07-28 08:00 | 2022-08-12
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PS0015 | NCT03536884 | Study Archived | a multicenter, randomized, double-blind, secukinumab-control | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | A MULTICENTER, RANDOMIZED, DOUBLE-BLIND, SECUKINUMAB-CONTROLLED, PARALLEL-GROUP STUDY TO EVALUATE THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN ADULT SUBJECTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIASIS. | Psoriasis | Immunology |  | 2017-08-25 08:00 | 2017-08-25 | 2017-11-10 | 2018-03-26 | 2018-09-26 | 2018-06-13 | 2019-09-10 | 2019-04-12 | 2020-12-15 | 2023-08-09 | 2021-01-12 | 2023-09-11 | 2021-01-26 | 2023-09-29 | 2021-04-22 | 2024-02-13 | Australia, Belgium, Canada, France, Germany, Netherlands, Poland, Spain, Turkey, United Kingdom, United States of America | Australia (LPLV), Belgium (LPLV), Canada (LPLV), France (LPLV), Germany (LPLV), Netherlands (LPLV), Poland (LPLV), Spain (LPLV), Turkey (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Belgium, Canada, France, Germany, Netherlands, Poland, Spain, Turkey, United Kingdom, United States of America | 89 | 82 | 77 | 937 | 700 | 700 | 1022 | 0 | 279 | 743 | 0 | 168 | 562 | 2020-05-19 | 2020-05-19 | 2020-07-13 | 2020-07-13
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PS0032 | NCT05020249 | Study Archived | Double-blind, randomized study of Bimekizumab in Korean | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | A phase 3, multicenter, randomized, double blind, placebo-controlled, parallel group study to evaluate the efficacy and safety of Bimekizumab in adult Korean study participants with moderate to severe Plaque psoriasis | Psoriasis | Immunology |  | 2020-07-08 08:00 | 2020-07-08 |  | 2020-12-18 | 2021-06-18 | 2021-09-27 | 2021-12-17 | 2022-04-19 | 2022-09-02 | 2022-09-06 | 2022-09-30 | 2022-11-18 | 2022-10-14 | 2023-03-01 | 2023-01-10 | 2023-03-14 | South Korea | South Korea (LPLV) | South Korea | 9 | 9 | 9 | 54 | 45 | 38 | 87 | 0 | 40 | 47 | 0 | 1 | 46
Yes | Phase I | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0231 | NCT06312566 | Study Archived | A multi-dose, open-label, randomized, 2-way cross-over study | Phase I | Open | GCSO | Neurology | UCB Pharma Global | A MULTIPLE-DOSE, OPEN-LABEL, RANDOMIZED, 2-WAY CROSS-OVER STUDY TO ASSESS THE BIOEQUIVALENCE BETWEEN BRIVARACETAM TABLET AND DRY SYRUP IN HEALTHY MALE JAPANESE PARTICIPANTS. | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2023-05-11 | 2023-05-15 | 2023-07-28 | 2023-07-28 | 2024-04-22 | 2024-03-25 | 2024-10-18 | 2024-05-17 | 2024-10-25 | 2024-06-04 | 2024-12-12 | 2024-07-29 | 2025-01-13 | 2024-09-11 | 2025-04-09 | 2024-10-25 | Japan | Japan (LPLV) | Japan | 1 | 1 | 1 | 140 | 96 | 96 | 130 | 0 | 66 | 64 | 0 | 1 | 63
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0043 | NCT01550003 | CSR Approved | Phase 3, multicenter, open label study | Phase III | Open | GCSO | Immunology | UCB Pharma Global | PHASE 3, MULTICENTER, OPEN-LABEL STUDY TO ASSESS THE PHARMACOKINETICS, SAFETY AND EFFICACY OF CERTOLIZUMAB PEGOL IN CHILDREN AND ADOLESCENTS WITH MODERATELY TO SEVERELY ACTIVE POLYARTICULAR JUVENILE IDIOPATHIC ARTHRITIS | Juvenile Idiopathic Arthritis | Immunology |  | 2010-01-19 | 2010-01-19 | 2010-01-19 | 2010-01-19 | 2011-12-01 | 2012-03-08 | 2013-03-28 | 2022-05-24 | 2015-11-17 | 2024-04-08 | 2015-12-22 | 2024-05-31 | 2016-02-16 | 2024-07-09 | 2016-07-14 | 2024-09-18 | Argentina, Brazil, Canada, Chile, Mexico, Russian Federation, United States of America | Argentina (LPLV), Brazil (LPLV), Canada (LPLV), Chile (LPLV), Mexico (LPLV), Russian Federation (LPLV), United States of America (LPLV) | Argentina, Brazil, Canada, Chile, Mexico, Russian Federation, United States of America | 51 | 47 | 36 | 203 | 156 | 109 | 245 | 0 | 50 | 195 | 0 | 192 | 3 | 2015-11-30 | 2015-11-30 | 2015-11-30 | 2015-12-15 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-03-02
Yes | Phase I | Managing Type | 1 | CIMZIA | Immunology | RA0138 | NCT04740814 | Study Archived | PK Cimzia Adult US | Phase I | Open | GCSO | Immunology | UCB Pharma Global | A MULTI-CENTER, OPEN-LABEL STUDY TO EVALUATE THE PHARMACOKINETICS OF CERTOLIZUMAB PEGOL IN ADULTS WITH ACTIVE RHEUMATOID ARTHRITIS USING AN ELECTROCHEMILUMINESCENT IMMUNO-ASSAY | Rheumatoid Arthritis | Immunology |  | 2020-01-30 08:00 | 2020-01-30 |  | 2020-03-27 | 2020-10-05 | 2021-02-11 | 2021-09-06 | 2021-10-05 | 2022-02-21 | 2022-06-27 | 2022-03-21 | 2022-08-30 | 2022-04-04 | 2022-11-07 | 2022-06-27 | 2023-01-27 | United States of America | United States of America (LPLV) | United States of America | 15 | 13 | 9 | 46 | 33 | 25 | 47 | 0 | 14 | 33 | 0 | 7 | 26
Yes | Phase I | Managing Type | 1 | CIMZIA | Immunology | UP0085 | NCT04163016 | Study Archived | A MULTICENTER, LONGITUDINAL PROSPECTIVE PHARMACOKINETIC PHAS | Phase I | Not Applicable | GCSO | Immunology | UCB Pharma Global | A POSTMARKETING, MULTICENTER, LONGITUDINAL, PROSPECTIVE, PHARMACOKINETIC, PHASE 1B STUDY IN PREGNANT WOMEN WITH CHRONIC INFLAMMATORY DISEASES TREATED WITH CIMZIA (CERTOLIZUMAB PEGOL) | Ankylosing Spondylitis; Crohn's disease; Psoriatic Arthritis; Rheumatoid Arthritis | Immunology; Immunology; Immunology; Immunology |  | 2019-06-05 08:00 | 2019-06-05 | 2019-08-01 | 2019-08-02 | 2019-10-15 | 2020-06-19 | 2020-10-15 | 2022-06-23 | 2021-10-22 | 2023-05-23 | 2021-11-24 | 2023-06-29 | 2021-12-16 | 2023-08-21 | 2022-03-17 | 2023-11-09 | France, Germany, Netherlands, Spain, Switzerland, United States of America | Canada (1st Site Initiation (Cancelled)), France (LPLV), Germany (LPLV), Netherlands (LPLV), Spain (LPLV), Switzerland (LPLV), United States of America (LPLV) | France, Germany, Netherlands, Spain, Switzerland, United States of America | 11 | 11 | 9 | 20 | 20 | 12 | 27 | 0 | 5 | 22 | 0 | 6 | 16
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Dapirolizumab pegol | Immunology | SL0043 | NCT04294667 | Study Archived | Evaluation of efficacy and safety of Dapimab in active syste | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | A MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL-GROUP STUDY TO EVALUATE THE EFFICACY AND SAFETY OF DAPIROLIZUMAB PEGOL IN STUDY PARTICIPANTS WITH MODERATELY TO SEVERELY ACTIVE SYSTEMIC LUPUS ERYTHEMATOSUS | Systemic Lupus Erythematosus | Immunology | SL0043 is a "sister" study of SL0044, SL0045 and is a feeder study of SL0046 | 2019-05-13 | 2019-05-13 |  | 2019-12-03 | 2020-02-17 | 2020-08-12 | 2021-09-21 | 2023-06-08 | 2022-10-19 | 2024-06-04 | 2022-11-15 | 2024-07-23 | 2022-11-29 | 2024-08-09 | 2023-02-23 | 2024-10-30 | Argentina, Australia, Austria, Belgium, Bulgaria, Canada, Chile, Colombia, Czech Republic, Denmark, France, Germany, Greece, Hong Kong, Hungary, Italy, Mexico, Peru, Philippines, Poland, Portugal, Romania, Serbia, South Korea, Spain, Taiwan, United Kingdom, United States of America | Argentina (LPLV), Australia (LPLV), Austria (LPLV), Belgium (LPLV), Bulgaria (LPLV), Canada (LPLV), Chile (LPLV), Colombia (LPLV), Czech Republic (LPLV), Denmark (LPLV), France (LPLV), Germany (LPLV), Greece (LPLV), Hong Kong (1st Site Initiation), Hungary (LPLV), Italy (LPLV), Mexico (LPLV), Peru (LPLV), Philippines (LPLV), Poland (LPLV), Portugal (1st Site Initiation), Romania (LPLV), Serbia (LPLV), South Korea (LPLV), Spain (LPLV), Taiwan (LPLV), United Kingdom (1st Site Initiation), United States of America (LPLV) | Argentina, Australia, Austria, Belgium, Bulgaria, Canada, Chile, Colombia, Czech Republic, Denmark, France, Germany, Greece, Hong Kong, Hungary, Italy, Mexico, Peru, Philippines, Poland, Portugal, Romania, Serbia, South Korea, Spain, Taiwan, United Kingdom, United States of America | 237 | 237 | 177 | 312 | 312 | 280 | 713 | 0 | 391 | 322 | 0 | 43 | 279 | 2023-04-26 | 2023-04-26 | 2023-06-09 | 2023-06-09
No | Phase I | Managing Type | 1 | Galvokimig | Immunology | UP0118 | NCT06315335 | CSR Approved | PK study of sc administration of UCB9741 and Japanese PK stu | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | A single center, randomized, investigator‑ and participant‑blind, placebo‑controlled, parallel group, ethnobridging Phase 1 study to evaluate safety, tolerability, and pharmacokinetics (PK) after single‑dose of UCB9741 in healthy Caucasian and Japanese participants | Atopic Dermatitis; Healthy Volunteers | Immunology; Immunology |  | 2024-01-01 | 2023-09-04 | 2024-02-19 | 2023-12-05 | 2024-03-12 | 2024-07-01 | 2024-06-03 | 2024-10-30 | 2024-07-29 | 2025-01-01 | 2024-08-28 | 2025-02-07 | 2024-09-20 | 2025-03-07 | 2025-01-01 | 2025-05-23 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 40 | 40 | 40 | 92 | 0 | 52 | 40 | 0 | 0 | 40
Yes | Phase I | Managing Type | 1 | Galvokimig | Immunology | UP0089 | NCT04643457 | CSR Approved | bispectific antibody targeting IL-13/IL-17 in healthy partic | Phase I | Single Blind | GCSO | Immunology | UCB Pharma Global | A PHASE I/IIA, RANDOMIZED, PLACEBO-CONTROLLED, SINGLE-ASCENDING DOSE (PART A, PARTICIPANT- AND INVESTIGATOR-BLIND) AND REPEATED-DOSE (PART B, PARTICIPANT-, INVESTIGATOR-, AND SPONSOR-BLIND) STUDY TO INVESTIGATE THE SAFETY, PHARMACOKINETICS, AND EFFICACY OF UCB9741 IN HEALTHY STUDY PARTICIPANTS (PART A) AND IN STUDY PARTICIPANTS WITH MODERATE-TO-SEVERE ATOPIC DERMATITIS (PART B) | Atopic Dermatitis; Patients and Healthy Volunteers | Immunology; Immunology |  | 2020-07-19 08:00 | 2020-07-19 | 2020-07-27 | 2020-08-03 | 2020-08-03 | 2020-11-27 | 2019-01-30 | 2024-01-04 | 2019-01-30 | 2024-06-06 | 2019-03-01 | 2024-07-18 | 2019-03-22 | 2024-08-07 | 2023-02-21 | 2024-12-10 | Belgium, Bulgaria, Germany, Netherlands, Poland, Spain, United Kingdom | Belgium (1st Site Initiation), Bulgaria (LPLV), Germany (LPLV), Netherlands (LPLV), Poland (1st Site Initiation), Spain (1st Site Initiation), United Kingdom (LPLV) | Belgium, Bulgaria, Germany, Netherlands, Poland, Spain, United Kingdom | 25 | 24 | 10 | 113 | 113 | 113 | 274 | 0 | 167 | 107 | 0 | 25 | 82 | 2023-07-17 | 2023-07-17 | 2023-09-07 | 2023-09-27 | 2023-12-25 | 2023-12-25 | 2023-11-14 | 2023-12-04 | 2024-09-25 | 2024-09-25 | 2024-05-28 | 2024-06-18
Yes | Phase I | Managing Type | 1 | Glovadalen | Central Nervous System | UP0091 | NCT04867642 | Study Archived | FIM Study | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | A FIRST-IN-HUMAN, RANDOMIZED, PARTICIPANT-BLIND, INVESTIGATOR-BLIND, PLACEBO-CONTROLLED, SINGLE- AND MULTIPLE-DOSE, DOSE-ESCALATING STUDY EVALUATING THE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF UCB0022 IN HEALTHY PARTICIPANTS AND PARTICIPANTS WITH PARKINSON'S DISEASE | Patients and Healthy Volunteers; Parkinson's disease | Central Nervous System; Central Nervous System |  | 2020-09-01 08:00 | 2020-09-01 |  | 2021-01-29 | 2021-06-07 | 2021-04-29 | 2022-02-14 | 2023-01-23 | 2022-04-29 | 2023-02-27 | 2022-05-27 | 2023-04-20 | 2022-06-10 | 2023-07-11 | 2022-09-06 | 2023-09-12 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 92 | 68 | 68 | 254 | 0 | 154 | 100 | 0 | 9 | 91
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | KEPPRA | Central Nervous System | EP0100 | NCT03340064 | Study Archived | open-label study with LEV add-on tx or monotherapy | Phase III | Open | GCSO | Neurology | Affiliates | AN OPEN-LABEL, SINGLE-ARM, MULTICENTER STUDY OF LEVETIRACETAM AS MONOTHERAPY OR ADJUNCTIVE TREATMENT OF PARTIAL SEIZURES IN PEDIATRIC EPILEPTIC SUBJECTS RANGING FROM 1 MONTH TO LESS THAN 4 YEARS OF AGE | Epilepsy | Central Nervous System |  | 2016-10-19 08:00 | 2016-10-19 |  | 2017-02-07 | 2017-06-27 | 2017-11-30 | 2019-08-27 | 2021-04-15 | 2022-01-28 | 2023-07-28 | 2022-02-25 | 2023-08-29 | 2022-04-22 | 2023-09-12 | 2022-07-19 | 2023-11-17 | Japan | Japan (LPLV) | Japan | 22 | 22 | 21 | 52 | 48 | 48 | 43 | 0 | 5 | 38 | 0 | 23 | 15 |  |  | 2021-11-25 08:00 | 2021-11-25 |  |  | 2022-06-08 | 2022-05-11
No | Phase I | Managing Type | 1 | Minzasolmin | New Medicines | UP0152 | NCT06533475 | Study Archived | Relative bioavailability of a new minzasolmin formulation | Phase I | Open | GCSO | Neurology | UCB Pharma Global | An Open-Label, Randomized Study To Evaluate The Relative Bioavailability Of A New Tablet Formulation Of Minzasolmin And The Potential Effect Of Food On The Pharmacokinetics Of Minzasolmin In Healthy Participants | Healthy Volunteers | Central Nervous System |  | 2024-02-28 | 2024-02-14 | 2024-03-25 | 2024-03-26 | 2024-09-27 | 2024-09-06 | 2024-10-14 | 2024-10-07 | 2024-11-11 | 2024-11-17 | 2024-12-11 | 2024-11-25 | 2025-01-10 | 2025-01-17 | 2025-04-08 | 2025-03-26 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 50 | 18 | 12 | 64 | 0 | 46 | 18 | 0 | 0 | 18
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Minzasolmin | New Medicines | PD0053 | NCT04658186 | CSR Approved | PHASE 2A STUDY TO EVA THE SAFETY, TOLERABILITY, PHARMACOKINE | Phase II | Double Blind | GCSO | Neurology | UCB Pharma Global | A DOUBLE-BLIND, PLACEBO-CONTROLLED, RANDOMIZED, 18-MONTH PHASE 2A STUDY TO EVALUATE THE EFFICACY, SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF ORAL UCB0599 IN STUDY PARTICIPANTS WITH EARLY PARKINSON’S DISEASE | Parkinson's disease | Central Nervous System | PD0053 is a parent study of PD0055 | 2020-09-03 08:00 | 2020-09-03 |  | 2020-10-15 | 2020-12-22 | 2020-12-30 | 2022-02-03 | 2023-02-02 | 2023-10-12 | 2024-09-06 | 2023-11-13 | 2024-10-24 | 2023-12-11 | 2024-11-22 | 2024-03-06 | 2025-03-14 | Canada, France, Germany, Italy, Netherlands, Poland, Spain, United Kingdom, United States of America | Canada (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Netherlands (LPLV), Poland (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Canada, France, Germany, Italy, Netherlands, Poland, Spain, United Kingdom, United States of America | 125 | 121 | 115 | 450 | 450 | 428 | 862 | 0 | 365 | 497 | 0 | 65 | 430
Yes | Phase I | Managing Type | 1 | Minzasolmin | New Medicines | UP0073 | NCT05845645 | Study Archived | Relative BA and ethnobridging study | Phase I | Double Blind to Open Label | GCSO | NewMeds | UCB Pharma Global | A 2-PART STUDY TO EVALUATE THE RELATIVE BIOAVAILABILTY OF 2 NEW FORMULATIONS OF MINZASOLMIN AND THE EFFECT OF ESOMEPRAZOLE ON THE PK OF MINZASOLMIN (UCB0599) (PART A) IN HEALTHY CAUCASIAN PARTICIPANTS AND TO ASSESS THE SAFETY/TOLERABILITY AND PK OF MINZASOLMIN (UCB0599) IN HEALTHY PARTICIPANTS OF JAPANESE AND CHINESE ORIGIN (PART B) | Healthy Volunteers; Parkinson's disease | Central Nervous System; Central Nervous System |  | 2024-04-01 | 2022-12-05 | 2023-12-05 | 2023-03-06 | 2024-02-29 | 2023-05-18 | 2024-10-07 | 2024-03-31 | 2024-11-04 | 2024-04-13 | 2024-12-02 | 2024-05-15 | 2025-01-13 | 2024-06-26 | 2025-05-22 | 2024-09-24 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 220 | 72 | 72 | 176 | 0 | 103 | 73 | 0 | 3 | 70
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | NEUPRO | Central Nervous System | SP1006 | NCT03728933 | Study Archived | Science 37 metasite study | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global | A REMOTE, DOUBLE-BLIND, RANDOMIZED, PLACEBO-CONTROLLED STUDY OF ROTIGOTINE TRANSDERMAL SYSTEM IN ADOLESCENT SUBJECTS WITH IDIOPATHIC RESTLESS LEGS SYNDROME | Restless legs syndrome | Central Nervous System | SP1006 is a parent study of RL0007 | 2014-08-11 08:00 | 2014-08-11 |  | 2018-02-07 | 2018-07-18 | 2018-12-20 | 2023-05-17 | 2022-06-27 | 2023-10-04 | 2022-07-25 | 2023-11-14 | 2023-04-26 | 2024-02-01 | 2023-06-08 | 2024-02-02 | 2023-08-30 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 198 | 138 | 125 | 48 | 0 | 25 | 23 | 0 | 4 | 19
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | AIE001 | NCT04875975 | Study Archived | Rozanolixizumab participants with LGI1 autoimmune encephal | Phase II | Double Blind | GCSO | Neurology | UCB Pharma Global | A RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER, PHASE 2 STUDY TO EVALUATE THE EFFICACY, SAFETY, AND PHARMACOKINETICS OF ROZANOLIXIZUMAB IN ADULT STUDY PARTICIPANTS WITH LEUCINE-RICH GLIOMA INACTIVATED 1 AUTOIMMUNE ENCEPHALITIS | LGI1 Autoimmune Encephalitis | Central Nervous System |  | 2019-11-04 | 2019-11-04 |  | 2020-07-31 | 2020-08-04 | 2021-09-27 | 2021-08-10 | 2023-10-13 | 2022-01-25 | 2024-04-26 | 2022-02-22 | 2024-05-29 | 2022-03-08 | 2024-08-05 | 2022-06-02 | 2024-12-12 | Belgium, France, Germany, Italy, Netherlands, Spain, United Kingdom, United States of America | Australia (1st Site Initiation (Cancelled)), Belgium (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Netherlands (LPLV), Portugal (1st Site Initiation (Cancelled)), South Korea (1st Site Initiation (Cancelled)), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, France, Germany, Italy, Netherlands, Spain, United Kingdom, United States of America | 28 | 34 | 12 | 68 | 68 | 60 | 24 | 0 | 12 | 12 | 0 | 7 | 5
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | FM0001 | NCT05643794 | CSR Approved | A proof-of-concept study to evaluate the efficacy and safe | Phase II | Double Blind | GCSO | NewMeds | UCB Pharma Global | A RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER, PHASE 2A, PROOF-OF-CONCEPT STUDY TO EVALUATE THE EFFICACY AND SAFETY OF ROZANOLIXIZUMAB TO TREAT ADULT STUDY PARTICIPANTS WITH SEVERE FIBROMYALGIA SYNDROME | Fibromyalgia | Immunology |  | 2022-04-05 | 2022-05-31 |  | 2022-06-24 | 2022-09-28 | 2022-12-21 | 2023-04-24 | 2023-11-01 | 2024-01-05 | 2024-07-09 | 2024-02-02 | 2024-08-30 | 2024-03-07 | 2024-09-23 | 2024-06-03 | 2024-12-09 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 5 | 7 | 7 | 132 | 60 | 48 | 177 | 0 | 114 | 63 | 0 | 9 | 54
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | MG0020 | NCT05681715 | CSR Approved | Phase 3, open label, randomized self administration study | Phase III | Open | GCSO | Neurology | UCB Pharma Global | AN OPEN-LABEL, CROSSOVER STUDY TO EVALUATE ROZANOLIXIZUMAB SELF-ADMINISTRATION BY STUDY PARTICIPANTS WITH GENERALIZED MYASTHENIA GRAVIS | Myasthenia gravis | Central Nervous System |  | 2022-03-31 | 2022-03-31 |  | 2022-08-04 | 2022-12-02 | 2023-04-17 | 2023-08-01 | 2023-10-27 | 2024-01-22 | 2024-04-24 | 2024-02-19 | 2024-05-10 | 2024-03-22 | 2024-07-08 | 2024-06-18 | 2024-08-27 | Canada, Georgia, Germany, Italy, Japan, Poland, Serbia, Spain, United Kingdom, United States of America | Canada (LPLV), Georgia (LPLV), Germany (LPLV), Italy (LPLV), Japan (LPLV), Poland (LPLV), Serbia (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Canada, Georgia, Germany, Italy, Japan, Poland, Serbia, Spain, United Kingdom, United States of America | 34 | 29 | 27 | 33 | 33 | 30 | 75 | 0 | 13 | 62 | 0 | 16 | 46
Yes | Phase I | Managing Type | 1 | Staccato Alprazolam | Central Nervous System | UP0104 | NCT05626439 | Study Archived | A single-centre study to assess the safety, tolerability and | Phase I | Not Applicable | GCSO | Neurology | UCB Pharma Global | AN OPEN-LABEL, RANDOMIZED, SINGLE-DOSE, 2-WAY CROSSOVER STUDY TO EVALUATE THE RELATIVE BIOAVAILABILITY OF STACCATO ALPRAZOLAM COMPARED TO ORAL ALPRAZOLAM IN HEALTHY STUDY PARTICIPANTS | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2022-11-01 08:00 | 2021-10-28 |  | 2022-09-23 |  | 2022-12-28 |  | 2023-02-07 |  | 2023-02-24 |  | 2023-04-25 |  | 2023-05-30 |  | 2023-10-11 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 65 | 20 | 20 | 54 | 0 | 33 | 21 | 0 | 1 | 20
Yes | Phase I | Managing Type | 1 | UCB7853 | not defined | UP0092 | NCT04651153 | Study Archived | Multicenter, Participant Blind, Investigator Blind, Randomiz | Phase I | Double Blind | GCSO | Neurology | UCB Pharma Global | A MULTICENTER, PARTICIPANT-BLIND, INVESTIGATOR BLIND, RANDOMIZED, PLACEBO CONTROLLED STUDY TO EVALUATE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF SINGLE ASCENDING DOSES OF UCB7853 IN HEALTHY MALE STUDY PARTICIPANTS AND MULTIPLE ASCENDING DOSES IN PATIENTS WITH PARKINSON’S DISEASE. | Patients and Healthy Volunteers; Parkinson's disease | Central Nervous System; Central Nervous System |  | 2019-07-01 | 2019-07-01 |  | 2020-08-14 | 2020-12-03 | 2020-12-14 | 2021-10-13 | 2022-12-13 | 2022-06-08 | 2023-07-20 | 2022-07-06 | 2023-08-25 | 2022-07-29 | 2023-11-30 | 2022-10-21 | 2024-09-10 | Netherlands, United Kingdom | Netherlands (LPLV), United Kingdom (LPLV) | Netherlands, United Kingdom | 2 | 2 | 2 | 128 | 64 | 64 | 136 | 0 | 79 | 57 | 0 | 1 | 56
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0017 | NCT05514873 | CSR Approved | Study of Pts Switching from other treatments to ZLP | Phase III | Not Applicable | GCSO | Neurology | UCB Pharma Global | A PHASE 3B, MULTICENTER, OPEN-LABEL, SINGLE-ARM STUDY TO EVALUATE THE SAFETY, TOLERABILITY, AND EFFICACY OF ZILUCOPLAN IN PARTICIPANTS WITH GENERALIZED MYASTHENIA GRAVIS SWITCHING FROM INTRAVENOUS COMPLEMENT COMPONENT 5 INHIBITORS TO SUBCUTANEOUS ZILUCOPLAN | Myasthenia gravis | Central Nervous System |  | 2021-12-16 | 2021-12-16 |  | 2022-05-24 | 2022-09-05 | 2022-10-31 | 2023-09-11 | 2023-10-23 | 2024-02-09 | 2024-10-23 | 2024-03-12 | 2024-11-07 | 2024-04-11 | 2024-12-04 | 2024-07-08 | 2025-03-20 | United States of America | United States of America (LPLV) | United States of America | 20 | 17 | 12 | 20 | 20 | 17 | 34 | 0 | 8 | 26 | 0 | 25 | 1

## Report 1 (hidden)
Report 1 - Last refresh : 24 Jun 2025 14:23:35 CET
Study historic flag | Trial type description | CDP Managing Type | Number of trial assigments | Active substance name | Therapeutic area desc | Study no | Study status desc with hcs info | Study description | Phase description short | Blinding | Budget manager desc | Department Desc | Budget owner desc | CPM | CPM Line Manager | CLIN Strategic Partner | Monitoring comments | SEP critical path flag | SEP assessment | Patient Population | Volunteer study flag | Study full title | Indications | Indication Groups | Study all cross references | SCD Approval planned date | SCD Approval actual date | Protocol App original date | Protocol App actual date | FPFV original date | FPFV actual date | LPFV original date | LPFV actual date | LPLV original date | LPLV actual date | Database Locked original date | Database Locked actual date | Final TFLs Released original date | Final TFLs Released actual date | CSR Approval original date | CSR Approval actual date | Countries setup (excl. cancelled) | Countries setup (Country Status) excl. cancelled w/o 1st Site Initiation | Countries desc with Reg. Approval or 1st Site Initiation or FPFV | Number of sites planned | Number of sites SIV | Number of Sites FPFV | Planned to enter study | Planned to enter treatment | Planned to complete treatment | Conf entered screening | Conf in screening in study | Conf drop screening | Conf entered treatment | Conf in treatment in study | Conf drop treatment | Conf completed treatment | Int1 Final TFLs rel original date | Int1 Final TFLs rel baseline date | Int1 Final TFLs rel planned date | Int1 Final TFLs rel actual date | Int2 Final TFLs rel original date | Int2 Final TFLs rel baseline date | Int2 Final TFLs rel planned date | Int2 Final TFLs rel actual date | Int3 Final TFLs rel original date | Int3 Final TFLs rel baseline date | Int3 Final TFLs rel planned date | Int3 Final TFLs rel actual date | Int4 Final TFL rel original date | Int4 Final TFL rel baseline date | Int4 Final TFL rel planned date | Int4 Final TFL rel actual date | Int5 Final TFL rel original date | Int5 Final TFL rel baseline date | Int5 Final TFL rel planned date | Int5 Final TFL rel actual date | Int6 Final TFL rel planned date | Int6 Final TFL rel actual date | choose
No | Light Support Studies | Managing Type | 1 | Glovadalen | Central Nervous System | PCOR0001 | LPLV | Qualitative research in advanced Parkinson's disease | Patient Centered Outcomes Research | Not Applicable | Global Medical Affairs | Neurology | UCB Pharma Global | Williamson N |  |  | N/A |  |  | other | No | Qualitative research in advanced Parkinson's Disease | Parkinson's disease | Central Nervous System |  |  |  |  | 2024-09-04 |  | 2024-11-12 |  | 2025-04-04 |  | 2025-04-04 | [6 empty] | Germany, Spain, United States of America | Germany (LPLV), Spain (LPLV), United States of America (LPLV) | Germany, Spain, United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 14 | 46 | 0 | 0 | 46
No | Light Support Studies | Managing Type | 1 | Rystiggo | Central Nervous System | MG0035 | Created | Post Marketing Surveillance for Rystiggo in MG patients | Non Interventional Study - Prospective | Not Applicable | GCSO | Neurology | UCB Pharma Global | Namgoong K | Beinhauer-Zellenka U | N/A | IQVIA | No | No | adults | No | A PROSPECTIVE, MULTICENTER, POST MARKETING SURVEILLANCE STUDY, ASSESSING THE SAFETY AND EFFECTIVENESS OF RYSTIGGO® (ROZANOLIXIZUMAB) IN ADULT PATIENTS WITH GENERALIZED MYASTHENIA GRAVIS (GMG) WHO ARE ANTI-ACETYLCHOLINE RECEPTOR (ACHR) OR ANTI-MUSCLE-SPECIFIC TYROSINE KINASE (MUSK) ANTIBODY POSITIVE | Myasthenia gravis | Central Nervous System |  | 2025-09-18 08:00 | [15 empty] | South Korea | South Korea (Created) |  | 10 | 0 | 0 | 150 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Light Support Studies | Managing Type | 1 | Staccato Alprazolam | Central Nervous System | PCOR0005 | Created | Qualitative research in STAP Clinical Trial Patients and Car |  |  | UCB Pharma Global |  | UCB Pharma Global | [7 empty] | No | [20 empty] | Czech Republic, Hungary, Japan, United States of America | Czech Republic (Created), Hungary (Created), Japan (Created), United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | BIMZELX | Immunology | AS0021 | FPFV | CNUP Study Template (AS) | Managed Access Program | Open | GCSO | Immunology | UCB Pharma Global | Kaur G, Rocha M | Slader C | N/A | N/A |  |  | adults | No | AS0021 AxSpA PTA | Ankylosing Spondylitis | Immunology |  |  |  | 2022-05-19 | 2022-05-19 | 2023-01-16 | 2023-02-05 | 2023-02-06 |  | 2024-02-23 | [7 empty] | Czech Republic, Hungary, Poland | Czech Republic (LPLV), Hungary (FPFV), Poland (FPFV) | Czech Republic, Hungary, Poland | 11 | 0 | 0 | 150 | 150 | 150 | 15 | 0 | 0 | 62 | 11 | 0 | 51
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | BIMZELX | Immunology | HS0008 | FPFV | Bimekizumab MAP Studies | Managed Access Program | Open | Global Medical Affairs |  | UCB Pharma Global | Rocha M | Slader C |  | N/A |  |  |  | No | CL Bimekizumab MAP Studies | Hidradenitis Suppurativa | Immunology |  |  |  |  | 2022-11-11 | 2024-03-21 | 2023-08-23 | 2023-11-15 |  | 2024-03-06 | [5 empty] | 2024-11-04 |  | Australia, Czech Republic, Hungary, Ireland, Italy, Netherlands, Poland, Turkey | Australia (FPFV), Czech Republic (FPFV), Hungary (FPFV), Ireland (FPFV), Italy (Created), Netherlands (FPFV), Poland (FPFV), Turkey (FPFV) | Australia, Czech Republic, Hungary, Ireland, Netherlands, Poland, Turkey | 0 | 0 | 0 | 304 | 0 | 0 | 41 | 0 | 1 | 46 | 46 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | BIMZELX | Immunology | HS0009 | FPFV | Bimekizumab MAP Studies | Managed Access Program | Not Applicable | Global Medical Affairs | Immunology | UCB Pharma Global | Rocha M | Slader C | N/A | N/A |  |  | other | No | CL Bimekizumab MAP Studies | Hidradenitis Suppurativa | Immunology |  |  |  |  | 2022-11-11 | 2021-06-02 | 2023-07-23 | 2024-07-22 |  | 2026-07-20 | [5 empty] | 2026-11-09 |  | Australia, Austria, Belgium, Ireland, Italy, United Kingdom | Australia (FPFV), Austria (FPFV), Belgium (FPFV), Ireland (FPFV), Italy (FPFV), United Kingdom (FPFV) | Australia, Austria, Belgium, Ireland, Italy, United Kingdom | 0 | 0 | 0 | 111 | 111 | 111 | 0 | 0 | 0 | 63 | 63 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | BIMZELX | Immunology | PA0017 | FPFV | CNUP Study Template (PSA) | Managed Access Program | Not Applicable | GCSO | Immunology | UCB Pharma Global | Kaur G | Slader C | N/A | N/A |  |  | adults | No | PsA Post Trial Access Program for patients who completed PA0012 clinical trial. | Psoriatic Arthritis | Immunology |  |  |  | 2022-05-19 | 2022-11-11 | 2023-01-16 | 2023-02-27 | 2023-03-03 |  | 2024-12-31 | [5 empty] | 2024-12-31 |  | Czech Republic, Hungary, Poland | Czech Republic (LPLV), Hungary (FPFV), Poland (FPFV) | Czech Republic, Hungary, Poland | 26 | 0 | 0 | 350 | 350 | 350 | 0 | 0 | 0 | 193 | 15 | 0 | 178
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | BIMZELX | Immunology | PS0034 | LPFV | Managed Access Program in Korea linked to PS0032 | Managed Access Program | Not Applicable | GCSO | Immunology | UCB Pharma Global | Park S | Beinhauer-Zellenka U | Parexel | N/A |  |  | adults | No | MANAGED ACCESS PROGRAM WITH BIMEKIZUMAB IN PATIENTS WITH MODERATE TO SEVERE PLAQUE PSORIASIS WHO COMPLETED PS0032 OR PS0014 | Psoriasis | Immunology |  |  |  |  | 2021-07-15 | 2022-01-18 | 2022-02-11 | 2022-06-20 | 2022-08-31 | 2023-05-22 | [7 empty] | South Korea | South Korea (LPFV) | South Korea | 9 | 0 | 0 | 48 | 48 | 48 | 48 | 0 | 0 | 48 | 25 | 23 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | BIMZELX | Immunology | PS0040 | FPFV | CL - 02 Local Study Workpackage | Managed Access Program | Open | Affiliates | Immunology | UCB Pharma Global | Kaur G | Slader C | N/A | N/A |  |  | other | No | Post Trial Access | Psoriasis | Immunology |  |  |  | 2022-11-29 | 2021-12-13 | 2021-12-01 | 2022-01-19 |  |  | 2025-01-01 | [5 empty] | 2025-09-01 |  | Turkey, United Kingdom | Turkey (Created), United Kingdom (LPLV) | United Kingdom | 2 | 0 | 0 | 7 | 7 | 7 | 0 | 0 | 0 | 13 | 0 | 0 | 13
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | BIMZELX | Immunology | PS0043 | FPFV | approved drug supply until reimbursement in Australia | Managed Access Program | Not Applicable | Affiliates | Immunology | UCB Pharma Global | Rocha M | Slader C | N/A | N/A |  |  | adults | No | Psoriasis compassionate use for Bimzelx – to supply patients while we await for Australian government reimbursement | Psoriasis | Immunology |  |  |  | 2021-08-06 | 2022-03-01 | 2021-11-16 | 2022-03-25 |  |  | 2025-10-10 | [7 empty] | Australia | Australia (FPFV) | Australia | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 2 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0225 | FPFV | Post Trial Access Program | Managed Access Program | Not Applicable | Global Medical Affairs | Neurology | UCB Pharma Global |  |  | N/A | N/A |  |  | other | No | Brivaracetam EP0225 MAP (Post-Trial Access Program) | Epilepsy | Central Nervous System | [6 empty] | 2024-06-21 | [10 empty] | Georgia, Hungary, Italy, Mexico, Poland, Romania, Slovakia, Ukraine | Georgia (Created), Hungary (Created), Italy (Created), Mexico (FPFV), Poland (FPFV), Romania (Created), Slovakia (Created), Ukraine (Created) | Mexico, Poland | 0 | 0 | 0 | 129 | 129 | 129 | 12 | 0 | 0 | 34 | 34 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0236 | FPFV | CL - 02 Local Study Workpackage | Managed Access Program | Open | Global Medical Affairs | Neurology | UCB Pharma Global | Rocha M | Slader C | N/A | N/A |  |  | other | No | BRV Named Patient Access Program in Portugal | Epilepsy | Central Nervous System | [6 empty] | 2021-03-29 | [10 empty] | Portugal | Portugal (FPFV) | Portugal | 10 | 0 | 0 | 10 | 10 | 10 | 2 | 0 | 0 | 2 | 2 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0244 | Created | Briviact unapproved product in New Zealand | Managed Access Program |  | Global Medical Affairs | Neurology | UCB Pharma Global | Rocha M | Slader C | N/A |  |  |  |  | No | [20 empty] | New Zealand | New Zealand (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | BRIVIACT | Central Nervous System | N01317 | FPFV | CUNP for pts from N01125, 1199, 1379, 1315, 1372 & EP0083 | Managed Access Program | Open | GCSO | Neurology | GCSO | Cayli G | Slader C | N/A | N/A | No | No | adults | No | COMPASSIONATE USE PROGRAM WITH BRIVARACETAM FOR THE TREATMENT OF PATIENTS WITH EPILEPSY | Epilepsy | Central Nervous System |  |  |  |  | 2015-04-24 | 2015-06-18 | 2015-10-28 | 2016-06-18 |  | 2030-01-04 | [7 empty] | Australia, Brazil, Czech Republic, Estonia, Germany, Hong Kong, India, Italy, Latvia, Lithuania, Malaysia, Norway, Philippines, Russian Federation, Singapore, Spain, Switzerland, Taiwan, Thailand, United Kingdom | Australia (LPLV), Brazil (FPFV), Czech Republic (LPLV), Estonia (LPLV), Germany (LPLV), Hong Kong (LPLV), India (LPLV), Italy (LPLV), Latvia (LPLV), Lithuania (LPLV), Malaysia (FPFV), Norway (LPLV), Philippines (FPFV), Russian Federation (LPLV), Singapore (LPLV), Spain (LPLV), Switzerland (LPLV), Taiwan (LPLV), Thailand (FPFV), United Kingdom (LPLV) | Australia, Brazil, Czech Republic, Estonia, Germany, Hong Kong, India, Italy, Latvia, Lithuania, Malaysia, Norway, Philippines, Russian Federation, Singapore, Spain, Switzerland, Taiwan, Thailand, United Kingdom | 170 | 0 | 0 | 1167 | 1167 | 1167 | 404 | 0 | 0 | 454 | 205 | 0 | 249
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | CIMZIA | Immunology | JA0007 | FPFV | MAP Brazil JIA | Managed Access Program | Not Applicable | Affiliates | Immunology | UCB Pharma Global | Kaur G, Rocha M | Slader C | N/A | N/A |  |  | paediatrics | No | Cimzia Post Trial Access Program Juvenile Idiopathic Arthritis. | Juvenile Idiopathic Arthritis | Immunology |  |  |  | 2022-10-13 | 2023-06-29 | 2023-12-15 | 2024-02-27 | 2024-02-01 |  | 2024-02-29 | [5 empty] | 2033-06-30 |  | Brazil | Brazil (FPFV) | Brazil | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | CIMZIA | Immunology | JA0008 | Created (Cancelled) | PTA (MAP) following RA0043 | Managed Access Program | Open | Affiliates | Immunology | UCB Pharma Global | Weinsberg F | Anderson K | N/A | Bionical |  |  | paediatrics | No |  | Juvenile Idiopathic Arthritis | Immunology | [20 empty] | 10 | 0 | 0 | 33 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | CIMZIA | Immunology | RA0039 | FPFV | Named Patient program (NPP) with Cimzia - RA | Managed Access Program | Open | GCSO | Immunology | UCB Pharma Global | Rocha M | Slader C | N/A | N/A |  |  | adults | No | NAMED PATIENT PROGRAM WITH CERTOLIZUMAB PEGOL IN ADULTS SUFFERING FROM RHEUMATOID ARTHRITIS (RA) WHO PARTICIPATED IN OPEN LABEL STUDIES C87015, C87028 AND C87051. (GUIDANCE BOOKLET) Not a protocol but a Guidance Booklet | Rheumatoid Arthritis | Immunology |  |  |  |  | 2010-02-01 | 2010-08-02 | 2010-07-29 |  |  | 2021-01-01 | [7 empty] | Argentina, Bulgaria, Chile, Croatia, Czech Republic, Estonia, Israel, Latvia, Lithuania, New Zealand, Poland, Serbia | Argentina (LPLV), Bulgaria (LPLV), Chile (LPLV), Croatia (LPLV), Czech Republic (LPLV), Estonia (FPFV), Israel (LPLV), Latvia (LPLV), Lithuania (LPLV), New Zealand (FPFV), Poland (LPLV), Serbia (LPLV) | Argentina, Bulgaria, Chile, Croatia, Czech Republic, Estonia, Israel, Latvia, Lithuania, New Zealand, Poland, Serbia | 87 | 0 | 0 | 829 | 829 | 0 | 377 | 0 | 10 | 374 | 8 | 366 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | CIMZIA | Immunology | RA0139 | FPFV | Available Managed Access compassionate suppl (off label use) | Managed Access Program | Open | Affiliates | Immunology | UCB Pharma Global | Kaur G | Slader C | N/A | N/A |  |  |  | No | Certolizumab pegol Available Managed Access compassionate suppl (off label use) Rheumatoid Arthritis | Rheumatoid Arthritis | Immunology |  |  |  | 2016-08-08 | 2016-08-08 | 2017-01-31 | 2017-01-31 | 2017-04-25 |  | 2025-06-03 | [5 empty] | 2026-01-30 |  | Australia | Australia (FPFV) | Australia | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 0 | 0 | 170 | 170 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | Dapirolizumab pegol | Immunology | SL0047 | Created | Dapimab PTA | Managed Access Program | Not Applicable | Global Medical Affairs | Immunology | UCB Pharma Global | Rocha M | Slader C | N/A | N/A |  |  | adults | No | Dapirolizumab pegol Post Trial Access Program (PTA) SL0047 | Systemic Lupus Erythematosus | Immunology | [17 empty] | Argentina, Belgium, Canada, Chile, Germany, Hungary, Poland, Spain, United States of America | Argentina (Created), Belgium (Created), Canada (Created), Chile (Created), Germany (Created), Hungary (Created), Poland (Created), Spain (Created), United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | O0163 | Created | CL_O0163 DoxTM for POLG (exceptional approval) | Managed Access Program |  | Global Medical Affairs | Neurology | UCB Pharma Global |  |  | N/A |  |  |  |  | No | [23 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0113 | FPFV | CL - 02 Local Study Workpackage | Managed Access Program | Open | Affiliates | Neurology | UCB Pharma Global | Kaur G | Slader C | N/A | N/A |  |  | other | No | CL TK0113 doxTM (MT1621) MAP | Thymidine kinase 2 (TK2) deficiency | Central Nervous System |  |  |  | 2021-06-11 | 2018-08-01 | 2021-01-04 | 2020-07-07 | 2021-04-22 |  | 2027-12-06 | [5 empty] | 2028-08-03 |  | Argentina, Brazil, Chile, Costa Rica, Finland, France, Germany, Ghana, India, Ireland, Israel, Italy, Mexico, Netherlands, Romania, Spain, Taiwan, Turkey, Ukraine, United Kingdom, United States of America | Argentina (FPFV), Brazil (FPFV), Chile (FPFV), Costa Rica (FPFV), Finland (FPFV), France (FPFV), Germany (FPFV), Ghana (FPFV), India (FPFV), Ireland (FPFV), Israel (FPFV), Italy (FPFV), Mexico (FPFV), Netherlands (FPFV), Romania (FPFV), Spain (FPFV), Taiwan (FPFV), Turkey (FPFV), Ukraine (FPFV), United Kingdom (FPFV), United States of America (FPFV) | Argentina, Brazil, Chile, Costa Rica, Finland, France, Germany, Ghana, India, Ireland, Israel, Italy, Mexico, Netherlands, Romania, Spain, Taiwan, Turkey, Ukraine, United Kingdom, United States of America | 20 | 0 | 0 | 40 | 40 | 40 | 81 | 2 | 0 | 79 | 73 | 6 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0115 | FPFV | CL TK0115 doxTM EAP | Managed Access Program | Open | Global Medical Affairs | Neurology | UCB Pharma Global | Kaur G | Slader C | N/A | N/A |  |  | other | No | Company-sponsored Intermediate-size Cohort Expanded Access Program for Doxecitine and Doxribtimine for Patients with Thymidine Kinase 2 Deficiency (TK2d) with an Age of Symptom Onset <= 12 Years | Thymidine kinase 2 (TK2) deficiency | Central Nervous System |  |  |  |  | 2024-05-23 |  | 2024-11-18 | [10 empty] | France, Germany, Italy, Spain, United Kingdom, United States of America | France (Created), Germany (Regulatory Approval), Italy (Created), Spain (Created), United Kingdom (Created), United States of America (FPFV) | Germany, United States of America | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0118 | FPFV | CL - 02 Local Study Workpackage | Managed Access Program | Open | Global Medical Affairs | Neurology | Global Medical Affairs |  |  | N/A | N/A |  |  | other | No | CL TK0118 Dr. Hirano CUP for doxTM | Thymidine kinase 2 (TK2) deficiency | Central Nervous System |  |  |  | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2025-03-12 |  | 2027-03-10 | [5 empty] | 2027-06-30 |  | United States of America | United States of America (FPFV) | United States of America | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | Fintepla | not defined | EP0226 | FPFV | Global MAP (PTA and NPA) | Managed Access Program | Open | GCSO | Neurology | UCB Pharma Global | Kaur G | Slader C | N/A | N/A |  |  | other | No | Fintepla Global MAP (PTA and NPA) | All Indications | Immunology |  |  |  | 2021-06-11 | 2021-02-01 | 2021-01-04 | 2021-02-12 | 2027-12-06 |  | 2028-03-27 | [5 empty] | 2028-11-23 |  | Australia, Austria, Belgium, Bulgaria, Canada, Croatia, Czech Republic, Denmark, Ecuador, Egypt, Finland, France, Greece, Honduras, Hong Kong, Hungary, Iceland, India, Ireland, Italy, Luxembourg, Mexico, New Zealand, Poland, Portugal, Romania, Serbia, Slovakia, Slovenia, Spain, Sweden, Switzerland, Ukraine, United Arab Emirates, United Kingdom | Australia (FPFV), Austria (LPLV), Belgium (FPFV), Bulgaria (FPFV), Canada (FPFV), Croatia (FPFV), Czech Republic (LPLV), Denmark (LPLV), Ecuador (FPFV), Egypt (FPFV), Finland (LPLV), France (FPFV), Greece (LPLV), Honduras (FPFV), Hong Kong (FPFV), Hungary (FPFV), Iceland (FPFV), India (FPFV), Ireland (FPFV), Italy (LPLV), Luxembourg (FPFV), Mexico (FPFV), New Zealand (FPFV), Poland (LPLV), Portugal (LPLV), Romania (FPFV), Serbia (FPFV), Slovakia (LPLV), Slovenia (FPFV), Spain (LPLV), Sweden (LPLV), Switzerland (FPFV), Ukraine (FPFV), United Arab Emirates (FPFV), United Kingdom (LPLV) | Australia, Austria, Belgium, Bulgaria, Canada, Croatia, Czech Republic, Denmark, Ecuador, Egypt, Finland, France, Greece, Honduras, Hong Kong, Hungary, Iceland, India, Ireland, Italy, Luxembourg, Mexico, New Zealand, Poland, Portugal, Romania, Serbia, Slovakia, Slovenia, Spain, Sweden, Switzerland, Ukraine, United Arab Emirates, United Kingdom | 0 | 0 | 0 | 0 | 0 | 0 | 493 | 0 | 0 | 728 | 432 | 0 | 296
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | Ginisortamab | Oncology | ONC002 | Created | Post Trial Acess Program for patients coming out of ONC001 | Managed Access Program | Open | Global Medical Affairs | Oncology | UCB Pharma Global | Kaur G | Slader C | N/A | N/A |  |  | adults | No |  | All Indications | Oncology | [17 empty] | United Kingdom, United States of America | United Kingdom (Created), United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | KEPPRA | Central Nervous System | EP0233 | Created | CL - 02 Local Study Workpackage | Managed Access Program | Open | Global Medical Affairs | Neurology | UCB Pharma Global | Rocha M | Slader C | N/A | N/A |  |  | other | No | CL EP0233 Keppra Compassionate use in New Zealand Medsafe Section 29 | Epilepsy | Central Nervous System | [17 empty] | New Zealand | New Zealand (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | NEUPRO | Central Nervous System | PD0061 | FPFV | Compassionate use in New Zealand Medsafe Section 29 | Managed Access Program | Open | Affiliates | Neurology | UCB Pharma Global | Rocha M | Slader C | Parexel | N/A |  |  |  | No | PD0061 Compassionate use in New Zealand Medsafe Section 29 | Parkinson's disease | Central Nervous System |  |  |  | 2021-09-08 | 2021-09-08 |  | 2022-01-20 | 2022-04-14 |  | 2022-08-04 | [5 empty] | 2025-04-01 |  | New Zealand | New Zealand (FPFV) | New Zealand | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | NOOTROPIL | Central Nervous System | EP0173 | Created | unapproved drug in Australia special access | Managed Access Program | Open | Affiliates | Neurology | UCB Pharma Global | Kaur G | Slader C | N/A | N/A |  |  | adults | No |  | Lennox Gastaut Syndrome (LGS) | Central Nervous System | [17 empty] | Australia | Australia (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | Rystiggo | Central Nervous System | MG0016 | FPFV | MAP - patients coming from MG0020 study and MG0007 study | Managed Access Program | Not Applicable | GCSO | Neurology | UCB Pharma Global |  |  | N/A | N/A |  |  | adults | No | Roximab, Post Trial Access Program, Myasthenia Gravis | Myasthenia gravis | Central Nervous System |  |  |  | 2023-03-29 | 2023-05-24 | 2023-10-03 | 2023-09-27 | 2024-07-05 |  | 2027-07-16 | [5 empty] | 2028-03-15 |  | Czech Republic, Denmark, Georgia, Germany, Italy, Poland, Russian Federation, Serbia, Spain, Taiwan, United Kingdom | Czech Republic (FPFV), Denmark (FPFV), Georgia (FPFV), Germany (Regulatory Approval), Italy (FPFV), Poland (FPFV), Russian Federation (Created), Serbia (FPFV), Spain (FPFV), Taiwan (Created), United Kingdom (FPFV) | Czech Republic, Denmark, Georgia, Germany, Italy, Poland, Serbia, Spain, United Kingdom | 0 | 0 | 0 | 69 | 69 | 69 | 0 | 0 | 0 | 26 | 26 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | Rystiggo | Central Nervous System | MG0024 | FPFV | CL - 02 Local Study Workpackage | Managed Access Program | Open | GCSO | Neurology | UCB Pharma Global |  |  | N/A | N/A |  |  | other | No | CL MG0024 Rozanolixizumab (UCB7665) MG CUP Global | Myasthenia gravis | Central Nervous System |  |  |  |  | 2022-06-22 |  | 2022-04-01 | [10 empty] | Australia, France, Germany, Greece, Italy, Spain, United Kingdom, United States of America | Australia (Created), France (FPFV), Germany (LPLV), Greece (LPLV), Italy (FPFV), Spain (FPFV), United Kingdom (Created), United States of America (Created) | France, Germany, Greece, Italy, Spain | 0 | 0 | 0 | 60 | 60 | 60 | 61 | 12 | 0 | 49 | 45 | 0 | 4
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | Rystiggo | Central Nervous System | MG0028 | Created | Post trial access | Managed Access Program | Not Applicable | Global Medical Affairs | Neurology | UCB Pharma Global | Kaur G, Teichmann R | Slader C, Tillery N | N/A |  |  |  | paediatrics | No |  | Myasthenia gravis | Central Nervous System | [17 empty] | Italy, Poland, Saudi Arabia, Taiwan, Turkey | Italy (Created), Poland (Created), Saudi Arabia (Created), Taiwan (Created), Turkey (Created) |  | 12 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | Rystiggo | Central Nervous System | MOG006 | Created | PTA for patients from MOG001 | Managed Access Program |  | GCSO | Neurology | UCB Pharma Global | Kaur G, Rocha M | Slader C | N/A | N/A |  |  |  | No |  | MOG-AD Disease | Central Nervous System | [17 empty] | Australia, Belgium, Brazil, Germany, Italy, Mexico, Portugal, South Korea, Spain, Sweden, Switzerland, Taiwan, Ukraine, United Kingdom, United States of America | Australia (Created), Belgium (Created), Brazil (Created), Germany (Created), Italy (Created), Mexico (Created), Portugal (Created), South Korea (Created), Spain (Created), Sweden (Created), Switzerland (Created), Taiwan (Created), Ukraine (Created), United Kingdom (Created), United States of America (Created) |  | 65 | 0 | 0 | 65 | 65 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | VIMPAT | Central Nervous System | EP0169 | FPFV | Post Trial Access Program | Managed Access Program | Open | GCSO | Neurology | UCB Pharma Global | Rocha M | Slader C | N/A | N/A |  |  | paediatrics | No | Vimpat Post Trial Access Program | Epilepsy | Central Nervous System |  |  |  |  | 2022-04-03 | 2022-04-07 | 2022-04-07 |  |  | 2032-12-29 | [7 empty] | Brazil | Brazil (FPFV) | Brazil | 8 | 0 | 0 | 20 | 20 | 20 | 15 | 0 | 2 | 13 | 9 | 0 | 4
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | VIMPAT | Central Nervous System | EP0170 | FPFV | Post Trial Access Program | Managed Access Program | Open | Affiliates |  | UCB Pharma Global | Rocha M | Slader C | N/A | N/A |  |  | paediatrics | No | Vimpat Post Trial Access Program | Epilepsy | Central Nervous System |  |  |  | 2019-01-12 | 2018-10-18 | 2019-01-14 | 2018-10-18 | 2020-01-14 |  | 2023-11-14 | [7 empty] | Brazil | Brazil (FPFV) | Brazil | 3 | 0 | 0 | 5 | 5 | 5 | 4 | 0 | 0 | 4 | 4 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | VIMPAT | Central Nervous System | EP0172 | FPFV | approved drug in Australia supply off label use | Managed Access Program | Not Applicable | Affiliates | Neurology | UCB Pharma Global | Kaur G | Slader C | N/A | N/A |  |  | adults | No | Vimpat Special Access Scheme requests, as approved by TGA | Epilepsy | Central Nervous System |  |  |  | 2013-06-10 | 2011-04-20 | 2013-09-02 | 2011-04-20 | 2013-11-25 |  | 2025-06-03 | [5 empty] | 2026-01-30 |  | Australia | Australia (FPFV) | Australia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | VIMPAT | not defined | EP0238 | FPFV | Post Trial Access Program | Managed Access Program | Not Applicable | Global Medical Affairs | Neurology | UCB Pharma Global |  |  | N/A | N/A |  |  | paediatrics | No | Lacosamide EP0238 MAP (Post-Trial Access) | Epilepsy | Central Nervous System |  |  |  | 2024-02-07 | 2024-08-09 | 2024-10-31 | 2024-11-19 | 2025-01-23 |  | 2034-01-02 | [5 empty] | 2034-08-31 |  | Georgia, Hungary, Romania, Ukraine | Georgia (Created), Hungary (Created), Romania (Created), Ukraine (FPFV) | Ukraine | 0 | 0 | 0 | 33 | 32 | 32 | 0 | 0 | 0 | 13 | 13 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | XYREM | Central Nervous System | NA0003 | FPFV | Unapproved drug in Australia special access | Managed Access Program | Open | Affiliates | Neurology | UCB Pharma Global | Kaur G | Slader C | N/A | N/A |  |  | adults | No | Compassionate use for Xyrem on a named patient basis – to supply patients as the product is unapproved in Australia | Cataplexy; Narcolepsy | Central Nervous System; Central Nervous System |  |  |  | 2014-11-07 | 2014-11-07 | 2015-03-02 | 2015-03-02 |  |  | 2025-03-04 | [5 empty] | 2025-10-31 |  | Australia | Australia (FPFV) | Australia | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 0 | 0 | 106 | 106 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | XYREM | Central Nervous System | NA0004 | Created | Xyrem Named Patient Program in Portugal | Managed Access Program |  | Global Medical Affairs | Neurology | UCB Pharma Global | Rocha M | Slader C | N/A | N/A |  |  |  | No |  | Narcolepsy | Central Nervous System | [17 empty] | Portugal | Portugal (Created) |  | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0025 | FPFV | CL MG CUP Global | Managed Access Program | Open | GCSO | Neurology | UCB Pharma Global | Kaur G | Slader C | N/A | N/A |  |  | adults | No | CL MG0025 Zilucoplan (RA101495) MG CUP Global | Myasthenia gravis | Central Nervous System | [6 empty] | 2021-12-14 | [10 empty] | Australia, France, Germany, Greece, Italy, Spain, United Kingdom, United States of America | Australia (FPFV), France (FPFV), Germany (LPLV), Greece (LPLV), Italy (LPLV), Spain (LPLV), United Kingdom (FPFV), United States of America (Created) | Australia, France, Germany, Greece, Italy, Spain, United Kingdom | 6 | 0 | 0 | 60 | 60 | 60 | 12 | 0 | 0 | 87 | 18 | 0 | 69
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0029 | Created | Available Managed Access | Managed Access Program | Not Applicable | Global Medical Affairs | Neurology | UCB Pharma Global | Kaur G | Slader C | N/A |  |  |  | other | No |  | Myasthenia gravis | Central Nervous System | [20 empty] | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | MAP (e.g. CUP, NPP) | Managing Type | 1 | Zilucoplan | Central Nervous System | PNH004 | LPFV | Managed Access Program | Managed Access Program | Not Applicable | GCSO | Immunology | UCB Pharma Global | Rocha M | Slader C | N/A | N/A |  |  | adults | No | PNH004 Zilucoplan Post Trial Access Program | Paroxysmal Nocturnal Hemoglobinuria | Immunology |  |  |  |  | 2021-05-21 |  | 2021-08-03 |  | 2021-08-24 | [8 empty] | New Zealand | New Zealand (LPFV) | New Zealand | 1 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 0 | 0
No | NIS (Prospective and Retrospective) | Managing Type | 1 | BIMZELX | Immunology | HS0010 | FPFV | Long-term treatment of HS in routine clinical practice | Non Interventional Study - Prospective | Not Applicable | RWE/GCSO | Immunology | UCB Pharma Global | Boes H | Bonny M | Parexel | UCB | No | No | adults | No | Hidradenitis suppurativa patients treated with bimekizumab: a real-life long-term prospective observation of health outcomes (Hi-LiGHT) | Hidradenitis Suppurativa | Immunology |  | 2024-03-01 | 2023-12-19 | 2024-05-02 | 2024-05-02 | 2024-09-03 | 2024-10-17 | 2027-06-23 |  | 2029-10-15 |  | 2029-12-10 |  | 2030-02-04 |  | 2030-06-13 |  | Austria, Belgium, Denmark, France, Germany, Greece, Italy, Netherlands, Spain, Sweden | Austria (Created), Belgium (Created (Held)), Denmark (FPFV), France (Created), Germany (FPFV), Greece (Created), Italy (Created), Netherlands (Created), Spain (Created), Sweden (Created (Held)) | Denmark, Germany | 100 | 37 | 27 | 650 | 0 | 0 | 107 | 1 | 0 | 106 | 97 | 4 | 5
No | NIS (Prospective and Retrospective) | Managing Type | 1 | BIMZELX | Immunology | PS0035 | FPFV | BKZ PSO NIS Adults HRQoL | Non Interventional Study - Prospective | Not Applicable | RWE/GCSO | Immunology | UCB Pharma Global | Forbes M | Bonny M | Parexel | PAREXEL | No | No | adults | No | Observational study of treatment history, Quality of life, treatment satisfaction, and Disease symptom severity in adult patients with Moderate to severe plaque psoriasis treated With bimekizumab in routine clinical practice (elevate) | Psoriasis | Immunology |  | 2021-06-07 08:00 | 2021-06-07 |  | 2021-09-08 | 2021-12-02 | 2021-11-25 | 2023-12-04 |  | 2025-01-14 |  | 2025-03-11 |  | 2025-05-06 |  | 2025-09-12 |  | France, Germany, Greece, Italy, United Kingdom | France (FPFV), Germany (FPFV), Greece (FPFV), Italy (FPFV), United Kingdom (FPFV) | France, Germany, Greece, Italy, United Kingdom | 155 | 156 | 145 | 1500 | 1500 | 1500 | 1383 | 0 | 0 | 1383 | 1030 | 276 | 77
No | NIS (Prospective and Retrospective) | Managing Type | 1 | BIMZELX | Immunology | PS0045 | Protocol Approved | Post Marketing Surveillance for Bimzelx in PSO patients | Non Interventional Study - Prospective | Not Applicable | GCSO | Immunology | UCB Pharma Global | Park S | Beinhauer-Zellenka U | N/A | IQVIA | No | No | adults | No | Post marketing surveillance study for BIMZELX® (bimekizumab) in adult Korean patients with moderate to severe plaque psoriasis | Psoriasis | Immunology |  | 2024-11-01 08:00 | 2024-09-02 |  | 2025-02-03 | [12 empty] | South Korea | South Korea (Created) |  | 30 | 0 | 0 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | NIS (Prospective and Retrospective) | Managing Type | 1 | BIMZELX | Immunology | SPA001 | FPFV | NIS study in PsA and axSpA patients initiating treatment | Non Interventional Study - Prospective | Not Applicable | RWE/GCSO | Immunology | UCB Pharma Global | Heinrichs A | Bonny M | N/A | acromion | No | No | adults | No | SPONDYLOARTHRITIS (PSORIATIC ARTHRITIS AND AXIAL SPONDYLOARTHRITIS) PATIENT-CENTERED EXPERIENCE INITIATING BIMEKIZUMAB IN ROUTINE CLINICAL PRACTICE: A MULTI-COUNTRY, PROSPECTIVE, OBSERVATIONAL STUDY (SPEAK) | Psoriatic Arthritis | Immunology |  | 2023-05-01 | 2023-02-28 | 2023-05-26 | 2023-04-28 | 2023-10-06 | 2023-09-20 | 2025-10-10 |  | 2026-09-21 |  | 2026-10-19 |  | 2026-11-02 |  | 2027-03-02 |  | Belgium, Czech Republic, France, Germany, Greece, Spain, United Kingdom | Belgium (FPFV), Czech Republic (FPFV), France (FPFV), Germany (FPFV), Greece (FPFV), Spain (FPFV), United Kingdom (FPFV) | Belgium, Czech Republic, France, Germany, Greece, Spain, United Kingdom | 100 | 144 | 122 | 900 | 900 | 810 | 0 | 0 | 0 | 886 | 410 | 284 | 192
No | NIS (Prospective and Retrospective) | Managing Type | 1 | BIMZELX | Immunology | SPA002 | FPFV | adult patients with axSpA who are newly treated with BKZ | Non Interventional Study - Prospective | Not Applicable | RWE/GCSO | Immunology | UCB Pharma Global | Ozkan Y | Tillery N |  |  |  |  | adults | No |  | Axial Spondyloarthritis (axSpA) | Immunology |  | 2024-07-08 08:00 |  |  | 2024-12-19 |  | 2025-05-21 | [10 empty] | Austria, Belgium, France, Germany, Greece, Italy, Netherlands, Poland, Spain, Sweden, Switzerland, United Kingdom | Austria (IRB / IEC Submission), Belgium (IRB / IEC Submission), France (Regulatory Approval), Germany (FPFV), Greece (Created), Italy (Created), Netherlands (IRB / IEC Submission), Poland (IRB / IEC Approval), Spain (Created), Sweden (Created), Switzerland (Created), United Kingdom (1st Site Initiation) | France, Germany, United Kingdom | 100 | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
No | NIS (Prospective and Retrospective) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0099 | CSR Approved | NIS prospective on Briviact adjuctive therapy in POS | Non Interventional Study - Prospective | Open | RWE/GCSO | Neurology | UCB Pharma Global | Reichel C | Anderson K | Parexel | PAREXEL | No | No | other | No | A NONINTERVENTIONAL PROSPECTIVE STUDY OF BRIVARACETAM UTILIZATION AND EFFECTIVENESS AS AN ADJUNCTIVE THERAPY IN THE TREATMENT OF PARTIAL ONSET SEIZURES IN STANDARD MEDICAL PRACTICE IN A MULTINATIONAL SETTING | Epilepsy | Central Nervous System |  |  |  |  | 2021-04-14 | 2021-10-19 | 2021-12-13 | 2023-04-20 | 2023-07-31 | 2025-04-24 | 2024-07-29 | 2025-05-26 | 2024-10-10 | 2025-06-16 | 2025-01-15 | 2025-09-10 | 2025-03-19 | Bulgaria, Czech Republic, Greece, Hungary, Poland, Romania | Bulgaria (LPLV), Czech Republic (LPLV), Greece (LPLV), Hungary (LPLV), Poland (LPLV), Romania (LPLV) | Bulgaria, Czech Republic, Greece, Hungary, Poland, Romania | 99 | 98 | 85 | 900 | 900 | 720 | 804 | 0 | 0 | 804 | 410 | 137 | 257
No | NIS (Prospective and Retrospective) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0127 | Protocol Approved (Cancelled) | Briviact, Post Marketing Surveillance for Epilepsy | Non Interventional Study - Prospective | Open | GCSO | Neurology | UCB Pharma Global | Namgoong K | Beinhauer-Zellenka U | Parexel | PAREXEL | No | No | adults | No | POST MARKETING SURVEILLANCE STUDY FOR BRIVARACETAM IN SUBJECTS AGED 16 YEARS OF AGE AND OLDER WITH PARTIAL-ONSET SEIZURES | Epilepsy | Central Nervous System |  | 2017-12-04 | 2017-12-04 |  | 2019-03-29 | 2021-12-01 |  | 2024-08-05 |  | 2024-10-28 |  | 2024-12-17 |  | 2025-01-16 |  | 2025-05-20 |  |  |  |  | 50 | 0 | 0 | 600 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | NIS (Prospective and Retrospective) | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0117 | FPFV | Non-Interventional source data verification project | Non Interventional Study - Retrospective | Not Applicable | GCSO | Neurology | UCB Pharma Global | Pifer C | Tillery N | Parexel | PAREXEL | Yes | No | other | No | NONINTERVENTIONAL CLINICAL STUDY TO CONFIRM ORIGINAL SOURCES AND VERIFY SOURCE DATA FOR UNTREATED PATIENT DATA COMPILED FROM TK2D PUBLICATIONS. | Thymidine kinase 2 (TK2) deficiency | Central Nervous System |  |  |  |  | 2024-07-01 |  | 2024-11-08 | [10 empty] | Argentina, Chile, China, Czech Republic, France, Germany, Greece, Mexico, Norway, Spain, Sweden, Taiwan, United Kingdom, United States of America | Argentina (Created), Chile (Created), China (Created), Czech Republic (Created), France (Created), Germany (Created), Greece (Created), Mexico (Created), Norway (Created (Held)), Spain (FPFV), Sweden (Created), Taiwan (FPFV), United Kingdom (Created), United States of America (FPFV) | Spain, Taiwan, United States of America | 36 | 7 | 6 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | NIS (Prospective and Retrospective) | Managing Type | 1 | Fintepla | Central Nervous System | EP0218 | FPFV | EU CV REGISTRY (PASS) (Zogenix 2101) | Registry | Not Applicable | Real World Evidence | Neurology | UCB Pharma Global | Pilla S | Copetti C | Parexel | CLUEPOINTS;PAREXEL | No | No | other | No | A Registry of Patients Treated with Fintepla | Dravet Syndrome | Central Nervous System |  | 2021-06-01 08:00 | 2021-02-20 | 2022-10-03 | 2022-09-01 | 2023-03-20 | 2023-06-09 |  |  | 2033-03-25 | [5 empty] | 2033-11-23 |  | Austria, France, Germany, Spain, United Kingdom | Austria (FPFV), France (FPFV), Germany (FPFV), Spain (FPFV), United Kingdom (FPFV) | Austria, France, Germany, Spain, United Kingdom | 80 | 75 | 51 | 400 | 400 | 400 | 205 | 1 | 0 | 204 | 189 | 15 | 0
No | NIS (Prospective and Retrospective) | Managing Type | 1 | Fintepla | Central Nervous System | EP0219 | FPFV | A Drug Utilization Study of Fenfluramine in Europe | Non Interventional Study - Retrospective | Not Applicable | Affiliates | Neurology | UCB Pharma Global | Chheda J | Copetti C | Parexel | PAREXEL | No | No | other | No | A Drug Utilisation Study of Fenfluramine in Europe | Dravet Syndrome | Central Nervous System |  |  |  |  | 2023-01-26 |  | 2025-03-31 | [10 empty] | Austria, Denmark, France, Germany, Italy, Spain, Sweden, United Kingdom | Austria (Created), Denmark (Created), France (Created), Germany (FPFV), Italy (Created), Spain (Created), Sweden (Created), United Kingdom (Regulatory Approval) | Germany, United Kingdom | 0 | 4 | 2 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
No | NIS (Prospective and Retrospective) | Managing Type | 1 | Fintepla | Central Nervous System | EP0237 | Protocol Approved | Dravet <2Y | Non Interventional Study - Prospective | Not Applicable | RWE/GCSO | Neurology | UCB Pharma Global | Chheda J | Copetti C | Parexel | PAREXEL | No | No | paediatrics | No | Evaluating the safety of fenfluramine (Fintepla®) for Dravet syndrome, Lennox-Gastaut syndrome, and other epilepsy patients aged less than 2 years at treatment initiation: a US retrospective chart review. | Dravet Syndrome | Central Nervous System |  |  |  |  | 2024-07-12 | [12 empty] | United States of America | United States of America (1st Site Initiation) | United States of America | 40 | 2 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | NIS (Prospective and Retrospective) | Managing Type | 1 | UCB2744 | not defined | GTEP01 | Protocol Approved | Natural History Study of patients with SLC6A1 | Non Interventional Study - Prospective | Not Applicable | GCSO | Neurology | UCB Pharma Global | Dyer J | Russell R | ICON | UCB | No | Yes | paediatrics | No | SLC6A1-NDD PROSPECTIVE LONGITUDINAL NATURAL HISTORY STUDY | Epilepsy | Central Nervous System |  | 2024-08-01 | 2025-01-27 |  | 2025-04-07 | 2025-07-23 |  | 2027-04-08 |  | 2029-04-06 |  | 2029-06-01 |  | 2029-07-27 |  | 2029-12-05 |  | Denmark, France, Germany, Italy, Spain, United Kingdom, United States of America | Denmark (Created), France (Created), Germany (Created), Italy (Created), Spain (Created), United Kingdom (Created), United States of America (Created) |  | 8 | 0 | 0 | 60 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | NIS (Prospective and Retrospective) | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0034 | Protoc. Summary Approved | Post Marketing Surveillance for Zilbrysq in MG patients | Non Interventional Study - Prospective |  | GCSO | Neurology | UCB Pharma Global | Namgoong K | Beinhauer-Zellenka U | N/A | IQVIA | No | No | adults | No |  | Myasthenia gravis | Central Nervous System |  | 2026-04-30 | 2025-04-11 | [14 empty] | South Korea | South Korea (Created) |  | 10 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | BIMZELX | Immunology | PS0031 | FPFV | PsoBest – German Psoriasis registry on systemic antipsoriat | Registry | Not Applicable | Affiliates | Immunology | UCB Pharma Global | [6 empty] | adults | No | PsoBest – German Psoriasis registry on systemic antipsoriatic treatment | Psoriatic Arthritis | Immunology | [5 empty] | 2018-08-01 | 2018-08-01 |  |  | 2023-07-28 | [5 empty] | 2023-11-28 |  | Germany | Germany (FPFV) | Germany | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353 | 353 | 0 | 0
No | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | AS0015 | FPFV | RABBIT SpA (National Registry SpondyloArthritis) | Registry | Not Applicable | Affiliates | Immunology | UCB Pharma Global | Dombrowsky W | [5 empty] | adults | No | Long-term Observation with Biologics in SpA | [8 empty] | 2017-05-01 | [10 empty] | Germany | Germany (FPFV) | Germany | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228 | 228 | 0 | 0
No | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | PS0028 | FPFV | BADBIR British Association of Dermatologists Biologic Inter | Registry |  | GCSO | Immunology | UCB Pharma Global | [6 empty] | adults | No | British Association of Dermatologists Biologic Interventions Register | [8 empty] | 2018-09-04 | [10 empty] | Ireland, United Kingdom | Ireland (Created), United Kingdom (FPFV) | United Kingdom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 19 | 0 | 0
No | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | RA0023 | FPFV | RA0023 MotherToBaby | Registry | Open | Real World Evidence | Immunology | UCB Pharma Global | Schelstraete I | Driver D | N/A | UCB |  |  | other | No | Cimzia Pregnancy Exposure Registry | [7 empty] | 2012-05-22 | 2012-03-28 | [10 empty] | Canada, United States of America | Canada (FPFV), United States of America (FPFV) | Canada, United States of America | 1 | 0 | 0 | 300 | 300 | 300 | 0 | 0 | 0 | 568 | 568 | 0 | 0
No | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | RA0137 | FPFV | BioReg Austria (Registry) | Registry | Not Applicable | Affiliates | Immunology | UCB Pharma Global | [6 empty] | adults | No |  | Rheumatoid Arthritis | Immunology | [6 empty] | 2010-02-17 | [10 empty] | Austria | Austria (FPFV) | Austria | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 154 | 0 | 0
No | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | Fintepla | not defined | UP0140 | FPFV | PMR Prospective NAAED Pregnancy Registry | Registry |  | GCSO | Neurology | UCB Pharma Global | Schelstraete I | Driver D |  |  |  |  | adults | No | AED Pregnancy Registry | Epilepsy | Central Nervous System | [6 empty] | 2020-06-25 | [10 empty] | Canada, United States of America | Canada (FPFV), United States of America (FPFV) | Canada, United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
No | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | VIMPAT | Central Nervous System | UP0121 | FPFV | PK study on LCM PK changes during pregnancy and post-partum | Phase I | Not Applicable | Affiliates | Neurology | UCB Pharma Global | Mcclung C | [5 empty] | adults | No | A multicenter, open-label, longitudinal, prospective, pharmacokinetic Phase 1B study in pregnant women with epilepsy treated with lacosamide | [8 empty] | 2022-11-22 | [10 empty] | Australia | Australia (FPFV) | Australia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0
No | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0036 | Created | Severe MG Exacerbation Research Collaboration | Phase IV | Not Applicable | GCSO | Neurology | UCB Pharma Global | Harvey B | Russell R | [5 empty] | No |  | Myasthenia gravis | Central Nervous System | [17 empty] | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 15 | 15 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase I | Managing Type | 1 | Bepranemab | Central Nervous System | PSP002 | LPFV | OLE to evaluate UCB0107 safety +tolerability in PSP subjects | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Van Den Steen B | Cain D | ICON | ICON | Yes | Yes | adults | No | An open-label extension study to evaluate the safety and tolerability of long-term UCB0107 administration in Study participants with Progressive Supranuclear Palsy | PSP Progressive supranuclear palsy | Central Nervous System | PSP002 is an extension of PSP003 | 2020-05-08 08:00 | 2020-05-08 |  | 2020-06-26 | 2020-12-15 | 2020-11-16 | 2021-11-22 | 2021-10-19 | 2026-11-20 |  | 2026-12-14 |  | 2027-01-29 |  | 2027-04-23 |  | Belgium, Germany, Spain, United Kingdom | Belgium (LPFV), Germany (LPFV), Spain (LPFV), United Kingdom (LPLV) | Belgium, Germany, Spain, United Kingdom | 18 | 11 | 11 | 19 | 19 | 19 | 19 | 0 | 0 | 19 | 7 | 12 | 0
No | Phase I | Managing Type | 1 | BIMZELX | Immunology | PA0019 | Protoc. Summary Approved | Study to compare PK of BKZ given sc or iv | Phase I |  | GCSO | Immunology | UCB Pharma Global | Goldammer N, Passmore G | Beinhauer-Zellenka U | Parexel |  | Yes | Yes |  | No |  | Psoriatic Arthritis | Immunology |  | 2025-05-09 | 2025-05-27 | [17 empty] | 80 | 0 | 0 | 450 | 374 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase I | Managing Type | 1 | BIMZELX | Immunology | UP0122 | Protocol Approved | BKZ Lactation Study | Phase I | Open | GCSO | Immunology | UCB Pharma Global | Rice K | Bonny M | Parexel | PAREXEL | No | Yes | adults | No | A MULTICENTER, OPEN-LABEL, PROSPECTIVE STUDY TO ASSESS THE CONCENTRATION OF BIMEKIZUMAB IN THE BREAST MILK OF MOTHERS RECEIVING TREATMENT WITH BIMZELX® (BIMEKIZUMAB) | Psoriasis | Immunology |  | 2022-05-04 | 2022-05-04 |  | 2022-06-28 | 2024-01-17 |  | 2024-07-03 |  | 2025-12-31 |  | 2026-01-28 |  | 2026-03-03 |  | 2026-06-30 |  | Canada, Germany, Spain, Switzerland, United States of America | Canada (1st Site Initiation), Germany (Created), Spain (Created), Switzerland (Created), United States of America (Regulatory Approval) | Canada, United States of America | 10 | 1 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase I | Managing Type | 1 | BIMZELX | Immunology | UP0154 | Created (Cancelled) | Study to compare PK of BKZ given sc or iv | Phase I |  | GCSO | Immunology | UCB Pharma Global | Goldammer N | Beinhauer-Zellenka U | Parexel |  | Yes | Yes |  | No |  | Psoriatic Arthritis | Immunology |  | 2025-04-29 08:00 | [18 empty] | 2 | 0 | 0 | 350 | 270 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase I | Managing Type | 1 | CIMZIA | Immunology | AS0019 | Created (Held) | Evaluate pk & safety of CZP in healthy chinese subjects | Phase I | Double Blind | GCSO | Immunology | UCB Pharma Global |  |  | Parexel | PAREXEL | No | No |  | Yes |  | Healthy Volunteers; Axial Spondyloarthritis (axSpA) | Immunology; Immunology |  | 2018-11-30 08:00 | [18 empty] | 1 | 0 | 0 | 30 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase I | Managing Type | 1 | Dapirolizumab pegol | Immunology | SL0040 | Created (Held) | PK Study | Phase I |  | GCSO | NewMeds | UCB Pharma Global |  |  | Parexel |  |  |  | adults | No |  | All Indications | Immunology |  | 2022-08-01 08:00 | [15 empty] | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase I | Managing Type | 1 | Donzakimig | Immunology | UP0110 | LPFV | Safety Study | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Sacre J | Copetti C | Parexel | PAREXEL;UCB | Yes | Yes | adults | Yes | A PHASE 1/2A, RANDOMIZED, PLACEBO-CONTROLLED, SINGLE-ASCENDING DOSE (PART A, PARTICIPANT- AND INVESTIGATOR-BLIND) AND REPEAT-DOSE (PART B, PARTICIPANT-, INVESTIGATOR-, AND SPONSOR-BLIND) STUDY TO INVESTIGATE THE SAFETY, PHARMACOKINETICS, AND EFFICACY (PART B ONLY) OF UCB1381 IN HEALTHY STUDY PARTICIPANTS (PART A) AND IN STUDY PARTICIPANTS WITH MODERATE TO SEVERE ATOPIC DERMATITIS (PART B) | Atopic Dermatitis; Patients and Healthy Volunteers | Immunology; Immunology |  | 2021-04-09 | 2021-07-19 |  | 2021-12-16 | 2022-03-01 | 2022-03-07 | 2024-07-02 | 2025-03-29 | 2024-12-25 |  | 2025-03-13 |  | 2025-04-03 |  | 2025-06-30 |  | United States of America | United States of America (LPFV) | United States of America | 24 | 24 | 16 | 152 | 152 | 109 | 271 | 1 | 161 | 109 | 5 | 10 | 94 |  |  | 2024-08-20 | 2024-08-07
No | Phase I | Managing Type | 1 | Donzakimig | Immunology | UP0142 | Database Locked | PK study of sc UCB1381/donzakimig in Chinese and Japanese | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Theys A | Cain D | ICON | ICON | Yes | Yes | adults | No | A single center, randomized, Investigator and participant blind, placebo controlled, Phase 1 study to evaluate safety, tolerability, and pharmacokinetics after a single dose of donzakimig in healthy Chinese and Japanese participants. | Atopic Dermatitis | Immunology |  | 2024-07-11 | 2024-07-12 |  | 2024-09-19 | 2024-12-12 | 2024-12-06 | 2024-12-20 | 2025-01-30 | 2025-03-14 | 2025-04-04 | 2025-04-15 | 2025-05-30 | 2025-05-15 |  | 2025-08-12 |  | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 57 | 32 | 32 | 64 | 0 | 32 | 32 | 0 | 0 | 32
No | Phase I | Managing Type | 1 | Fintepla | Central Nervous System | UP0132 | LPLV | Phase 1 DDI | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Rice K | Bonny M | Parexel | PAREXEL | No | No | adults | No | A PHASE 1, SINGLE-CENTER, REPEAT-DOSE, OPEN-LABEL, FIXED-SEQUENCE DRUG-DRUG INTERACTION STUDY OF ZX008 IN HEALTHY MALE OR FEMALE STUDY PARTICIPANTS 18 TO 55 YEARS OF AGE | Epilepsy | Central Nervous System |  | 2024-04-09 | 2024-04-09 | 2024-06-21 | 2024-06-21 | 2024-12-02 | 2024-12-04 | 2025-05-19 | 2025-02-03 | 2025-07-24 | 2025-06-12 | 2025-08-25 |  | 2025-09-24 |  | 2025-12-19 |  | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 22 | 22 | 22 | 109 | 0 | 87 | 22 | 0 | 0 | 22
No | Phase I | Managing Type | 1 | Galvokimig | Immunology | UP0118 | CSR Approved | PK study of sc administration of UCB9741 and Japanese PK stu | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Theys A | Cain D | Parexel | PAREXEL | Yes | Yes | adults | Yes | A single center, randomized, investigator‑ and participant‑blind, placebo‑controlled, parallel group, ethnobridging Phase 1 study to evaluate safety, tolerability, and pharmacokinetics (PK) after single‑dose of UCB9741 in healthy Caucasian and Japanese participants | Atopic Dermatitis; Healthy Volunteers | Immunology; Immunology |  | 2024-01-01 | 2023-09-04 | 2024-02-19 | 2023-12-05 | 2024-03-12 | 2024-07-01 | 2024-06-03 | 2024-10-30 | 2024-07-29 | 2025-01-01 | 2024-08-28 | 2025-02-07 | 2024-09-20 | 2025-03-07 | 2025-01-01 | 2025-05-23 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 40 | 40 | 40 | 92 | 0 | 52 | 40 | 0 | 0 | 40 | [22 empty] | yes
No | Phase I | Managing Type | 1 | Glovadalen | Central Nervous System | UP0135 | FPFV | An EBS to assess safety tolerability PK of UCB0022 in HV | Phase I | Double Blind | GCSO | Neurology |  | Watanabe S | Cain D | Parexel | CLUEPOINTS;PAREXEL | Yes | No | other | Yes | A single-center, placebo-controlled, participant-blind, investigator-blind, randomized, multiple ascending dose in titration study to assess the safety, tolerability, and pharmacokinetics of UCB0022 in healthy Caucasian, Japanese, and Chinese participants | Parkinson's disease | Central Nervous System |  | 2024-02-01 | 2023-09-26 |  | 2025-02-10 |  | 2025-04-28 | [10 empty] | United States of America | United States of America (FPFV) | United States of America | 1 | 1 | 1 | 32 | 32 | 32 | 22 | 0 | 11 | 11 | 11 | 0 | 0
No | Phase I | Managing Type | 1 | Glovadalen | Central Nervous System | UP0159 | Protoc. Summary Approved | Relative bioavailability | Phase I |  | GCSO | NewMeds | UCB Pharma Global | Leach S | Cain D | ICON |  | No | Yes |  | No |  | Parkinson's disease | Central Nervous System |  | 2025-06-18 | 2025-06-12 | [17 empty] | 1 | 0 | 0 | 32 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase I | Managing Type | 1 | Minzasolmin | New Medicines | UP0152 | Study Archived | Relative bioavailability of a new minzasolmin formulation | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Watanabe S | Cain D | Parexel | PAREXEL | No | Yes | adults | Yes | An Open-Label, Randomized Study To Evaluate The Relative Bioavailability Of A New Tablet Formulation Of Minzasolmin And The Potential Effect Of Food On The Pharmacokinetics Of Minzasolmin In Healthy Participants | Healthy Volunteers | Central Nervous System |  | 2024-02-28 | 2024-02-14 | 2024-03-25 | 2024-03-26 | 2024-09-27 | 2024-09-06 | 2024-10-14 | 2024-10-07 | 2024-11-11 | 2024-11-17 | 2024-12-11 | 2024-11-25 | 2025-01-10 | 2025-01-17 | 2025-04-08 | 2025-03-26 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 50 | 18 | 12 | 64 | 0 | 46 | 18 | 0 | 0 | 18 | [22 empty] | yes
No | Phase I | Managing Type | 1 | Rystiggo | Central Nervous System | UP0141 | FPFV | ASSESS CONCENTRATION OF ROZIMAB IN BREAST MILK OF HEALTHY LA | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Murphy C | Russell R | ICON | ICON | Yes | Yes | adults | Yes | AN OPEN-LABEL, SINGLE-DOSE STUDY TO ASSESS THE CONCENTRATION OF ROZANOLIXIZUMAB IN THE BREAST MILK OF HEALTHY LACTATING WOMEN | Healthy Volunteers | Central Nervous System |  | 2023-11-30 | 2023-11-09 |  | 2024-09-11 | 2024-12-04 | 2024-12-03 | 2025-08-06 |  | 2025-12-03 |  | 2026-01-02 |  | 2026-02-03 |  | 2026-04-30 |  | United States of America | United States of America (FPFV) | United States of America | 2 | 2 | 1 | 4 | 4 | 4 | 20 | 0 | 5 | 15 | 0 | 0 | 15
No | Phase I | Managing Type | 1 | Staccato Alprazolam | Central Nervous System | UP0127 | FPFV | EEG Crossover Study IV vs Nasal in Healthy Volunteers | Phase I |  | GCSO | Neurology | UCB Pharma Global | Lelij G | Tillery N | Parexel |  | No | Hybrid |  | No |  | Epilepsy | Central Nervous System |  | 2025-01-23 |  | 2025-03-19 | 2025-03-18 | 2025-06-12 | 2025-06-12 | 2025-12-15 |  | 2025-12-22 |  | 2026-01-21 |  | 2026-02-20 |  | 2026-05-26 |  | United States of America | United States of America (FPFV) | United States of America | 1 | 1 | 1 | 50 | 50 | 48 | 2 | 1 | 1 | 0 | 0 | 0 | 0
No | Phase I | Managing Type | 1 | TREM 1 | Central Nervous System | ALS006 | Protoc. Summary Approved | Phase 1 OLE | Phase I |  | UCB Pharma Global | Neurology | UCB Pharma Global | Payne N | Cain D | ICON |  | No |  | adults | No |  | Amyotrophic Lateral Sclerosis (ALS) | Central Nervous System |  | 2023-01-12 | 2023-01-12 | [17 empty] | 12 | 0 | 0 | 48 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase I | Managing Type | 1 | TREM 1 | Central Nervous System | ALS007 | Created | Phase 1 b safety, tolerability PK | Phase I |  | GCSO | Neurology | UCB Pharma Global | Padda A |  |  |  | Yes |  |  | No |  | Amyotrophic Lateral Sclerosis (ALS) | Central Nervous System |  | 2025-11-07 08:00 | [18 empty] | 0 | 0 | 0 | 300 | 75 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase I | Managing Type | 1 | TREM 1 | Central Nervous System | UP0124 | FPFV | A FIRST-IN-HUMAN, RANDOMIZED, INVESTIGATOR-BLIND, PARTICIPAN | Phase I | Double Blind | GCSO | Neurology | UCB Pharma Global | Krautz I | Russell R | ICON | ICON | No | No | adults | Yes | A FIRST-IN-HUMAN, RANDOMIZED, INVESTIGATOR-BLIND, PARTICIPANT-BLIND, PLACEBO-CONTROLLED STUDY TO EVALUATE THE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF SINGLE ASCENDING DOSES OF UCB3101 IN HEALTHY PARTICIPANTS | Healthy Volunteers; Ankylosing Spondylitis | Central Nervous System; Central Nervous System |  | 2023-01-13 | 2023-01-12 | 2024-04-01 | 2024-03-15 | 2024-07-31 | 2024-07-31 | 2025-07-31 |  | 2026-01-13 |  | 2026-02-12 |  | 2026-03-02 |  | 2026-05-05 |  | Belgium | Belgium (FPFV) | Belgium | 1 | 1 | 1 | 176 | 64 | 64 | 154 | 12 | 94 | 48 | 16 | 0 | 32
No | Phase I | Managing Type | 1 | UCB6936 Gene Therapy | not defined | GTFD01 | Created | Safety Study | Phase I |  | GCSO | Neurology | UCB Pharma Global | Dyer J | Russell R | N/A |  | Yes | Yes |  | No |  | Frontotemporal Dementia | Central Nervous System |  | 2025-03-03 08:00 | [18 empty] | 12 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase I | Managing Type | 1 | Zilucoplan | Central Nervous System | DV0012 | Final TFLs released | Health Volunteer Bioequivalance study | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Dyer J | Russell R | ICON | CLUEPOINTS;ICON;UCB | Yes | Yes | adults | Yes | AN OPEN-LABEL, SINGLE CENTER, RANDOMIZED, 2-way CROSSOVER, SINGLE-DOSE, BIOEQUIVALENCE STUDY OF ZILUCOPLAN INJECTED SUBCUTANEOUSLY EITHER BY A PREFILLED SYRINGE OR AN AUTO‑INJECTOR IN HEALTHY ADULT PARTICIPANTS | Myasthenia gravis; Healthy Volunteers | Central Nervous System; Central Nervous System |  | 2023-11-01 | 2023-10-23 | 2024-01-01 | 2023-12-11 | 2024-07-29 | 2024-08-05 | 2024-11-11 | 2024-08-23 | 2025-02-24 | 2024-11-26 | 2025-03-12 | 2025-01-23 | 2025-04-23 | 2025-02-28 | 2025-06-23 |  | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 14 | 12 | 12 | 35 | 0 | 21 | 14 | 0 | 0 | 14
No | Phase I | Managing Type | 1 | Zilucoplan | Central Nervous System | UP0096 | Created (Cancelled) | RA101495-04.102 Ph1 SAD/MAD PLGA | Phase I | Double Blind | GCSO | Neurology | UCB Pharma Global |  |  | N/A | Quotient Sciences |  |  | adults | No |  | Healthy Volunteers | Central Nervous System |  |  |  | 2020-07-24 |  | 2021-01-13 |  | 2021-06-10 |  | 2021-08-12 |  | 2021-09-13 |  | 2021-10-21 |  | 2022-01-11 |  |  |  |  | 1 | 0 | 0 | 64 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase I | Managing Type | 1 | Zilucoplan | Central Nervous System | UP0137 | Protocol Approved | ASSESS THE STEADY STATE CONCENTRATION IN THE BREAST MILK | Phase I | Not Applicable | GCSO | Neurology | UCB Pharma Global | Murphy C | Russell R | ICON | ICON | Yes | Yes | adults | No | AN OPEN-LABEL, REPEATED-DOSE ASSESSMENT OF ZILUCOPLAN CONCENTRATION IN BREAST MILK OF HEALTHY LACTATING WOMEN | Healthy Volunteers | Central Nervous System |  | 2023-11-29 | 2023-12-05 | 2025-02-12 | 2025-02-12 | 2025-05-12 |  | 2026-04-27 |  | 2026-05-25 |  | 2026-06-24 |  | 2026-07-24 |  | 2026-10-20 |  | United States of America | United States of America (1st Site Initiation) | United States of America | 2 | 2 | 0 | 20 | 15 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Bepranemab | Central Nervous System | AH0003 | LPFV | investigate the effect of UCB0107 vs plb on the CDR-SB at Wk | Phase II | Double Blind | GCSO | Neurology | UCB Pharma Global | Van Den Steen B | Cain D | ICON | ICON | Yes | Yes | adults | No | A PATIENT- AND INVESTIGATOR-BLIND, PLACEBO-CONTROLLED STUDY TO EVALUATE THE EFFICACY, SAFETY, AND TOLERABILITY OF BEPRANEMAB (UCB0107) IN STUDY PARTICIPANTS WITH PRODROMAL TO MILD ALZHEIMER’S DISEASE (AD), FOLLOWED BY AN OPEN-LABEL EXTENSION PERIOD | Alzheimer's Disease | Central Nervous System |  | 2020-12-01 08:00 | 2020-12-01 |  | 2021-03-01 | 2021-06-01 | 2021-06-09 | 2025-08-05 | 2024-06-05 | 2025-12-23 |  | 2026-01-22 |  | 2026-02-12 |  | 2026-05-11 |  | Belgium, Canada, France, Germany, Italy, Netherlands, Poland, Spain, United Kingdom, United States of America | Belgium (LPFV), Canada (LPFV), France (LPFV), Germany (LPFV), Italy (LPFV), Netherlands (LPLV), Poland (LPFV), Spain (LPFV), United Kingdom (LPFV), United States of America (LPFV) | Belgium, Canada, France, Germany, Italy, Netherlands, Poland, Spain, United Kingdom, United States of America | 125 | 118 | 103 | 1000 | 450 | 284 | 1664 | 0 | 1198 | 466 | 0 | 122 | 344
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | AS0014 | LPFV | Open-label extension study to evalutae the long-term effect | Phase III | Open | GCSO | Immunology | UCB Pharma Global | Kaspar M, Li C, Matano M | Bonny M, Guo J, Matsuo T | Parexel | PAREXEL | No | Yes | adults | No | A MULTICENTER, OPEN-LABEL EXTENSION STUDY TO ASSESS THE LONG-TERM SAFETY, TOLERABILITY, AND EFFICACY OF BIMEKIZUMAB IN THE TREATMENT OF STUDY PARTICIPANTS WITH ACTIVE AXIAL SPONDYLOARTHRITIS, ANKYLOSING SPONDYLITIS, AND NONRADIOGRAPHIC AXIAL SPONDYLOARTHRITIS | Ankylosing Spondylitis | Immunology | AS0014 is an extension of AS0010, AS0011 | 2019-02-12 | 2019-02-12 |  | 2019-10-23 | 2020-08-06 | 2020-06-16 | 2021-12-21 | 2023-02-24 | 2024-07-08 |  | 2024-08-05 |  | 2024-08-19 |  | 2024-11-13 |  | Belgium, Bulgaria, China, Czech Republic, France, Germany, Hungary, Japan, Netherlands, Poland, Spain, Turkey, United Kingdom, United States of America | Belgium (LPLV), Bulgaria (LPLV), China (LPFV), Czech Republic (LPLV), France (LPLV), Germany (LPFV), Hungary (LPLV), Japan (LPFV), Netherlands (LPLV), Poland (LPLV), Spain (LPLV), Turkey (LPLV), United Kingdom (LPLV), United States of America (LPFV) | Belgium, Bulgaria, China, Czech Republic, France, Germany, Hungary, Japan, Netherlands, Poland, Spain, Turkey, United Kingdom, United States of America | 95 | 76 | 75 | 510 | 510 | 470 | 508 | 0 | 0 | 508 | 81 | 65 | 362
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | HS0005 | LPFV | A Phase 3, Open-label Extenstion Study in Subjects with Mod | Phase III | Not Applicable | GCSO | Immunology | UCB Pharma Global | Matano M, Webers T | Bonny M, Matsuo T | Parexel | PAREXEL | Yes | Yes | adults | No | A Phase 3, open-label, parallel group, multicenter, extension study evaluating the long-term treatment of bimekizumab in study participants with moderate to severe hidradenitis suppurativa | Hidradenitis Suppurativa | Immunology | HS0005 is an extension of HS0003, HS0004 | 2020-11-03 08:00 | 2020-11-03 |  | 2020-11-03 | 2021-05-21 | 2021-05-27 | 2023-01-06 | 2023-01-10 | 2025-04-07 |  | 2025-05-05 |  | 2025-05-19 |  | 2025-08-13 |  | Australia, Belgium, Bulgaria, Canada, Czech Republic, France, Germany, Greece, Hungary, Ireland, Italy, Japan, Netherlands, Poland, Spain, Switzerland, Turkey, United Kingdom, United States of America | Australia (LPLV), Belgium (LPLV), Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), France (LPFV), Germany (LPFV), Greece (LPLV), Hungary (LPLV), Ireland (LPLV), Israel (1st Site Initiation (Cancelled)), Italy (LPFV), Japan (LPLV), Netherlands (LPLV), Poland (LPLV), Spain (LPLV), Switzerland (LPLV), Turkey (LPLV), United Kingdom (LPLV), United States of America (LPFV) | Australia, Belgium, Bulgaria, Canada, Czech Republic, France, Germany, Greece, Hungary, Ireland, Italy, Japan, Netherlands, Poland, Spain, Switzerland, Turkey, United Kingdom, United States of America | 190 | 148 | 145 | 833 | 833 | 658 | 669 | 0 | 0 | 669 | 108 | 296 | 262
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | HS0006 | FPFV | PK in Adolescents diagnosed with Hidradenitis Suppur | Phase III |  | GCSO | Immunology | UCB Pharma Global | Byerly R | Bonny M | Parexel |  | Yes |  | adolescents | No | A MULTICENTER, OPEN-LABEL STUDY TO ASSESS THE PHARMACOKINETICS AND SAFETY OF BIMEKIZUMAB IN PUBERTAL CHILDREN AND ADOLESCENTS WITH MODERATE TO SEVERE HIDRADENITIS SUPPURATIVA | Hidradenitis Suppurativa | Immunology | HS0006 will be pulled by HS0003, HS0004 | 2023-03-15 | 2023-02-15 | 2024-11-25 | 2024-12-03 | 2025-03-31 | 2025-04-07 | 2028-02-14 |  | 2030-11-11 |  | 2030-12-09 |  | 2030-12-23 |  | 2031-03-19 |  | Germany, Poland, United States of America | Germany (Created), Poland (Created), United States of America (FPFV) | United States of America | 10 | 6 | 2 | 20 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | JA0005 | FPFV | Open label bimab study in pediatric participants with JIA | Phase III | Open | Affiliates | Immunology | UCB Pharma Global | Michaels K | Bonny M | ICON | UCB | Yes | Yes | paediatrics | No | OPEN-LABEL, SINGLE-ARM TRIAL TO EVALUATE THE PHARMACOKINETICS AND SAFETY OF BIMEKIZUMAB IN PEDIATRIC STUDY PARTICIPANTS FROM 2 TO LESS THAN 18 YEARS OF AGE WITH ACTIVE JUVENILE IDIOPATHIC ARTHRITIS SUBTYPES ENTHESITIS-RELATED ARTHRITIS AND JUVENILE PSORIATIC ARTHRITIS. | Juvenile Idiopathic Arthritis | Immunology |  | 2023-05-15 | 2023-05-15 | 2024-04-01 | 2024-03-04 | 2024-10-01 | 2025-03-11 | 2028-03-28 |  | 2030-06-12 |  | 2030-07-10 |  | 2030-07-24 |  | 2031-01-17 |  | Canada, France, Germany, Poland, Spain, United Kingdom | Canada (1st Site Initiation), France (1st Site Initiation), Germany (1st Site Initiation), Poland (FPFV), Spain (1st Site Initiation), United Kingdom (1st Site Initiation) | Canada, France, Germany, Poland, Spain, United Kingdom | 20 | 20 | 1 | 50 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PA0011 | Study Archived | Randomized, double-blind, placebo control | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Bonny M, Heinrichs A | Bonny M, Grose-Hodge R | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, PHASE 3, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED STUDY EVALUATING THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN THE TREATMENT OF SUBJECTS WITH ACTIVE PSORIATIC ARTHRITIS | Psoriatic Arthritis | Immunology | PA0011 is a "sister" study of PA0010 and is a feeder study of PA0012 |  |  |  | 2018-11-29 | 2019-03-29 | 2019-03-28 | 2020-10-28 | 2021-07-15 | 2021-06-23 | 2022-02-14 | 2021-07-07 | 2022-03-04 | 2021-07-21 | 2022-04-19 | 2021-10-15 | 2022-06-29 | Australia, Canada, Czech Republic, Germany, Hungary, Italy, Japan, Poland, Russian Federation, United Kingdom, United States of America | Australia (LPLV), Canada (LPLV), Czech Republic (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Japan (LPLV), Poland (LPLV), Russian Federation (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Canada, Czech Republic, Germany, Hungary, Italy, Japan, Poland, Russian Federation, United Kingdom, United States of America | 116 | 126 | 92 | 583 | 390 | 351 | 585 | 0 | 185 | 400 | 0 | 12 | 388
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PA0012 | LPFV | Multicenter open-label extension study to access long-term s | Phase III | Open | GCSO | Immunology | UCB Pharma Global | Heinrichs A | Bonny M | Parexel | PAREXEL | No | Yes | adults | No | A MULTICENTER, OPEN-LABEL EXTENSION STUDY TO ASSESS THE LONG-TERM SAFETY, TOLERABILITY, AND EFFICACY OF BIMEKIZUMAB IN THE TREATMENT OF SUBJECTS WITH ACTIVE PSORIATIC ARTHRITIS | Psoriatic Arthritis | Immunology | PA0012 is a follow up of PA0010, PA0011 and is linked to sub study DV0004 | 2018-11-13 | 2018-11-13 |  | 2019-01-30 | 2019-08-02 | 2019-08-13 | 2022-01-31 | 2022-04-28 | 2025-02-24 |  | 2025-03-24 |  | 2025-04-07 |  | 2025-07-02 |  | Australia, Belgium, Canada, Czech Republic, France, Germany, Hungary, Italy, Japan, Poland, Russian Federation, Spain, United Kingdom, United States of America | Australia (LPFV), Belgium (LPFV), Canada (LPLV), Czech Republic (LPFV), France (LPFV), Germany (LPFV), Hungary (LPFV), Italy (LPLV), Japan (LPFV), Poland (LPFV), Russian Federation (LPFV), Spain (LPLV), United Kingdom (LPFV), United States of America (LPFV) | Australia, Belgium, Canada, Czech Republic, France, Germany, Hungary, Italy, Japan, Poland, Russian Federation, Spain, United Kingdom, United States of America | 140 | 140 | 139 | 1130 | 1130 | 888 | 1132 | 0 | 0 | 1132 | 115 | 264 | 752
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PA0016 | FPFV | PsA H2H | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Kaspar M, Knapp B | Bonny M | Parexel | PAREXEL | No | Yes | adults | No | A Multicenter, Randomized, Double-Blind, Risankizumab-Controlled, Parallel-Group Study to Evaluate the Efficacy and Safety of Bimekizumab in Adult Study Participants with Active Psoriatic Arthritis. | Psoriatic Arthritis | Immunology |  | 2021-08-21 | 2021-08-21 | 2024-04-02 | 2024-04-02 | 2024-10-18 | 2024-10-21 | 2025-10-21 |  | 2026-08-11 |  | 2026-09-08 |  | 2026-09-22 |  | 2027-05-28 |  | Australia, Bulgaria, Canada, Czech Republic, Germany, Hungary, Japan, Poland, Spain, United Kingdom, United States of America | Australia (FPFV), Bulgaria (FPFV), Canada (FPFV), Czech Republic (FPFV), Germany (FPFV), Hungary (FPFV), Japan (FPFV), Poland (FPFV), Spain (FPFV), United Kingdom (FPFV), United States of America (FPFV) | Australia, Bulgaria, Canada, Czech Republic, Germany, Hungary, Japan, Poland, Spain, United Kingdom, United States of America | 130 | 134 | 100 | 733 | 550 | 468 | 528 | 83 | 47 | 398 | 388 | 10 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PPP001 | Protocol Approved | Efficacy/Safety of BKZ in palmoplantar pustulosis | Phase III |  | GCSO | Immunology | UCB Pharma Global | Li X, Vandebriel L, Yates T | Bonny M | Parexel |  | Yes | Yes |  | No |  | Palmoplantar pustulosis | Immunology |  | 2024-11-26 08:00 | 2024-11-25 |  | 2025-05-22 | 2025-09-23 |  | 2027-05-12 |  | 2029-08-22 |  | 2029-09-19 |  | 2029-10-17 |  | 2030-02-25 |  |  |  |  | 104 | 0 | 0 | 463 | 300 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PS0020 | Database Locked | Multicenter open-labe rando study in adolescents with PSO | Phase II | Open | GCSO | Immunology | UCB Pharma Global | Conrath P | Copetti C | Parexel | PAREXEL | Yes | Yes | adolescents | No | A MULTICENTER, OPEN-LABEL, RANDOMIZED STUDY TO ASSESS THE PHARMACOKINETICS, SAFETY, AND EFFICACY OF TWO DOSES OF BIMEKIZUMAB IN ADOLESCENT STUDY PARTICIPANTS WITH MODERATE TO SEVERE PLAQUE PSORIASIS | Psoriasis | Immunology | PS0020 is a "sister" study of PS0021 | 2019-10-31 | 2019-10-31 |  | 2020-06-30 | 2021-04-06 | 2021-04-06 | 2022-06-24 | 2022-07-20 | 2025-03-10 | 2025-03-12 | 2025-04-07 | 2025-04-10 | 2025-04-21 |  | 2025-07-16 |  | Canada, Germany, Poland, United States of America | Canada (LPLV), Germany (LPLV), Poland (LPLV), United States of America (LPLV) | Canada, Germany, Poland, United States of America | 25 | 23 | 11 | 40 | 40 | 40 | 46 | 0 | 5 | 41 | 0 | 7 | 34 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PS0021 | FPFV | Multicenter double-blind study in children with psoriasis | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Kleine E, Matano M | Bonny M, Matsuo T | Parexel | PAREXEL | Yes | Yes | paediatrics | No | A MULTICENTER, RANDOMIZED, PARALLEL-GROUP, DOUBLE-BLIND, ACTIVE-CONTROLLED STUDY TO EVALUATE THE EFFICACY AND SAFETY OF BIMEKIZUMAB COMPARED TO USTEKINUMAB IN CHILDREN AND ADOLESCENTS FROM 6 YEARS TO LESS THAN 18 YEARS OF AGE WITH MODERATE TO SEVERE PLAQUE PSORIASIS | Psoriasis | Immunology | PS0021 is a "sister" study of PS0020 | 2022-11-30 | 2022-11-10 |  | 2023-10-26 | 2024-03-28 | 2024-06-25 | 2027-08-13 |  | 2030-11-08 |  | 2030-12-06 |  | 2030-12-23 |  | 2031-03-20 |  | Belgium, Canada, Czech Republic, France, Germany, Hungary, Italy, Japan, Poland, Spain, United States of America | Belgium (1st Site Initiation), Canada (FPFV), Czech Republic (FPFV), France (1st Site Initiation), Germany (FPFV), Hungary (FPFV), Italy (FPFV), Japan (FPFV), Poland (FPFV), Spain (FPFV), United States of America (FPFV) | Belgium, Canada, Czech Republic, France, Germany, Hungary, Italy, Japan, Poland, Spain, United States of America | 50 | 46 | 31 | 168 | 168 | 143 | 116 | 17 | 10 | 89 | 89 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PS0039 | FPFV | BKZ Mechanistic Study (BE UNIQUE) | Phase III | Open | GCSO | Immunology | UCB Pharma Global | Pendergast K | Bonny M | Parexel | PAREXEL | No | No | adults | No | A PHASE 3B EXPLORATORY MULTICENTER OPEN-LABEL STUDY TO EVALUATE THE EFFECT OF BIMEKIZUMAB ON GENE EXPRESSION BIOMARKERS IN STUDY PARTICIPANTS WITH MODERATE TO SEVERE PLAQUE PSORIASIS | Psoriasis; Psoriatic Arthritis | Immunology; Immunology |  | 2022-05-24 | 2022-06-24 | 2024-01-10 | 2023-12-07 | 2024-04-15 | 2024-07-29 | 2024-12-23 |  | 2027-01-18 |  | 2027-02-15 |  | 2027-03-19 |  | 2027-06-15 |  | Germany, Poland, United States of America | Germany (FPFV), Poland (FPFV), United States of America (FPFV) | Germany, Poland, United States of America | 16 | 16 | 13 | 90 | 90 | 90 | 62 | 6 | 8 | 48 | 46 | 2 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PS0041 | CSR Approved | Evaluate the efficacy and safety of BKZ in PSO subject | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Lei T | Guo J | Parexel | PAREXEL | Yes | Yes | adults | No | A PHASE 3, MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL GROUP STUDY TO EVALUATE THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN CHINESE ADULT STUDY PARTICIPANTS WITH MODERATE TO SEVERE PLAQUE PSORIASIS | Psoriasis | Immunology |  | 2022-05-12 | 2022-05-11 | 2022-10-12 | 2022-10-10 | 2023-11-24 | 2023-10-31 | 2024-07-17 | 2024-03-19 | 2025-06-11 | 2025-02-05 | 2025-07-09 | 2025-02-21 | 2025-08-25 | 2025-04-18 | 2025-11-20 | 2025-04-28 | China | China (LPLV) | China | 20 | 18 | 18 | 120 | 120 | 108 | 232 | 0 | 99 | 133 | 0 | 48 | 85 |  |  | 2024-12-16 | 2024-12-10 | [18 empty] | yes
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0085 | CSR Approved | EP0085 Asia BRV POS add-on long term follow-up study | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Li X, Soma T | Matsuo T | Parexel | PAREXEL | No | Yes | adults | No | AN OPEN-LABEL, MULTICENTER, FOLLOW-UP STUDY TO EVALUATE THE LONG-TERM SAFETY AND EFFICACY OF BRIVARACETAM USED AS ADJUNCTIVE TREATMENT IN SUBJECTS >=16 YEARS OF AGE WITH PARTIAL SEIZURES WITH OR WITHOUT SECONDARY GENERALIZATION | Epilepsy | Central Nervous System | EP0085 is a follow up of EP0083 | 2016-06-13 08:00 | 2016-06-13 |  | 2016-11-22 | 2017-08-01 | 2017-08-05 | 2017-08-01 | 2022-06-15 | 2024-05-31 | 2024-12-24 | 2024-06-28 | 2025-02-06 | 2024-07-26 | 2025-03-10 | 2024-11-11 | 2025-05-20 | China, Japan | China (LPLV), Japan (LPLV) | China, Japan | 71 | 59 | 59 | 206 | 206 | 206 | 211 | 0 | 2 | 209 | 0 | 72 | 137 |  |  | 2023-02-10 | 2023-02-10 |  |  | 2023-08-02 | 2023-08-03
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0132 | Final TFLs released | BRV absence epilepsy open-label 4yrs-25yrs | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Reichel C | Anderson K | N/A | N/A | No | Yes | other | No | A MULTICENTER, OPEN-LABEL, SINGLE-ARM STUDY TO EVALUATE LONG-TERM SAFETY, TOLERABILITY, AND EFFICACY OF BRIVARACETAM IN STUDY PARTICIPANTS 2 TO 26 YEARS OF AGE WITH CHILDHOOD ABSENCE EPILEPSY OR JUVENILE ABSENCE EPILEPSY | Epilepsy | Central Nervous System | EP0132 is an extension of N01269 and is a feeder study of EP0224 | 2019-06-14 08:00 | 2019-06-14 |  | 2020-06-15 | 2021-02-01 | 2022-03-30 | 2023-12-04 | 2024-11-06 | 2025-12-03 | 2025-03-04 | 2026-01-08 | 2025-04-10 | 2026-01-22 | 2025-04-24 | 2026-04-20 |  | Georgia, Italy, Romania, Slovakia, Spain, Ukraine, United States of America | Georgia (LPLV), Italy (LPLV), Romania (LPLV), Slovakia (LPLV), Spain (1st Site Initiation), Ukraine (LPLV), United States of America (LPLV) | Georgia, Italy, Romania, Slovakia, Spain, Ukraine, United States of America | 18 | 30 | 24 | 141 | 44 | 0 | 84 | 0 | 0 | 84 | 0 | 20 | 64
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0156 | FPFV | BRV Long Term Follow up study | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Payne N | Cain D | ICON | ICON | No | Yes | paediatrics | No | Open-label, single-arm, multicenter study to evaluate Long-TERM safety and Tolerability of brivaracetam used as adjunctive treatment in pediatric study participants with epilepsy. | Epilepsy | Central Nervous System | EP0156 is a follow up of EP0065, N01266, N01349 | 2020-06-29 08:00 | 2020-06-29 |  | 2020-09-04 | 2021-01-18 | 2021-03-11 | 2021-07-05 |  | 2025-01-03 |  | 2025-01-31 |  | 2025-02-14 |  | 2025-05-13 |  | Hungary, Italy, Japan, Mexico, Poland, Spain, United States of America | Belgium (1st Site Initiation (Cancelled)), Czech Republic (1st Site Initiation (Cancelled)), France (1st Site Initiation (Cancelled)), Germany (1st Site Initiation (Cancelled)), Hungary (LPLV), Italy (LPLV), Japan (FPFV), Mexico (LPLV), Poland (LPLV), Spain (LPLV), United States of America (LPLV) | Hungary, Italy, Japan, Mexico, Poland, Spain, United States of America | 60 | 35 | 27 | 160 | 160 | 135 | 78 | 2 | 6 | 70 | 19 | 13 | 38 |  |  | 2027-12-23 08:00
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0224 | FPFV | LONG-TERM SAFETY AND TOLERABILITY CHILDHOOD ABSENCE EPILEPSY | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Reichel C | Anderson K | Parexel | PAREXEL | Yes | Yes | adolescents | No | A multicenter, open-label, single-arm study to evaluate long-term safety and tolerability of brivaracetam in study participants with childhood absence epilepsy or juvenile absence epilepsy | Epilepsy | Central Nervous System | EP0224 is a follow up of EP0132, N01269 | 2023-08-01 | 2023-08-01 | 2023-09-27 | 2023-09-27 | 2024-04-01 | 2024-07-10 | 2026-02-26 |  | 2029-02-28 |  | 2029-04-25 |  | 2029-06-20 |  | 2029-10-29 |  | Georgia, Italy, Romania, Slovakia, Spain, Ukraine, United States of America | Georgia (FPFV), Italy (FPFV), Romania (FPFV), Slovakia (FPFV), Spain (1st Site Initiation), Ukraine (1st Site Initiation), United States of America (FPFV) | Georgia, Italy, Romania, Slovakia, Spain, Ukraine, United States of America | 0 | 22 | 10 | 70 | 0 | 0 | 47 | 0 | 0 | 47 | 47 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BRIVIACT | Central Nervous System | N01269 | FPFV | BRV Absence epilepsy | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global | Reichel C | Anderson K | N/A | IQVIA | Yes | Yes | paediatrics | No | A Randomized, Dose-Finding and Confirmatory, Double-Blind, Placebo-Controlled, Parallel-Group Multicenter Study with a 2-Stage Adaptive Design and Randomized Withdrawal to Evaluate the Efficacy, Safety and Tolerability of brivaracetam as Monotherapy in Patients 2 to 25 Years of Age with Childhood Absence Epilepsy or Juvenile Absence Epilepsy (Phase 2/3) | Epilepsy | Central Nervous System | N01269 is a feeder study of EP0224 and is a parent study of EP0132 | 2019-04-04 08:00 | 2019-04-04 |  | 2020-06-15 | 2020-11-09 | 2021-07-29 | 2023-06-26 |  | 2023-12-04 |  | 2024-01-01 |  | 2024-01-17 |  | 2024-03-18 |  | Bulgaria, Denmark, Estonia, Georgia, Greece, Italy, Latvia, Lithuania, Netherlands, New Zealand, Norway, Portugal, Romania, Singapore, Slovakia, Spain, Taiwan, Thailand, Ukraine, United Kingdom, United States of America | Australia (1st Site Initiation (Cancelled)), Belgium (1st Site Initiation (Cancelled)), Bulgaria (Created), Denmark (Created), Estonia (Created), Georgia (FPFV), Greece (Created), Italy (FPFV), Latvia (Created), Lithuania (Created), Netherlands (Created), New Zealand (Created), Norway (Created), Poland (1st Site Initiation (Cancelled)), Portugal (Created), Romania (FPFV), Singapore (Created), Slovakia (FPFV), Spain (FPFV), Taiwan (Created), Thailand (Created), Ukraine (FPFV), United Kingdom (Created), United States of America (FPFV) | Georgia, Italy, Romania, Slovakia, Spain, Ukraine, United States of America | 65 | 53 | 35 | 182 | 155 | 144 | 152 | 0 | 15 | 137 | 13 | 26 | 98
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | CIMZIA | Immunology | PS0007 | FPFV | CZP safety and efficacy study in pediatric patients with PsO | Phase III | Double Blind / Double Dummy | GCSO | Immunology | GCSO | Payne N | Cain D | Parexel | PAREXEL | Yes | Yes | paediatrics | No | MULTICENTER, RANDOMIZED, PARALLEL GROUP, DOUBLE BLIND, PLACEBO-CONTROLLED (12 17 YEARS) INCLUDING A SINGLE OPEN LABEL ARM (6 11 YEARS) STUDY TO EVALUATE THE EFFICACY, SAFETY, AND PHARMACOKINETICS OF CERTOLIZUMAB PEGOL (CZP) IN PEDIATRIC STUDY PARTICIPANTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIASIS (PSO) | Psoriasis | Immunology |  | 2018-08-12 08:00 | 2018-08-12 |  | 2019-06-24 | 2019-10-21 | 2020-01-21 | 2022-04-18 |  | 2025-06-16 |  | 2025-07-14 |  |  |  | 2025-10-22 |  | Canada, Puerto Rico, United States of America | Canada (FPFV), Puerto Rico (FPFV), United States of America (FPFV) | Canada, Puerto Rico, United States of America | 60 | 51 | 19 | 150 | 150 | 150 | 66 | 4 | 11 | 51 | 34 | 16 | 1 |  |  | 2029-10-19 08:00
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Dapirolizumab pegol | Immunology | SL0044 | FPFV | Evaluation of efficacy and safety of Dapimab in active syste | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Conrath P, Li C, Spaete C, Will E, Yoon H | Beinhauer-Zellenka U, Copetti C, Guo J | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL-GROUP STUDY TO EVALUATE THE EFFICACY AND SAFETY OF DAPIROLIZUMAB PEGOL IN STUDY PARTICIPANTS WITH MODERATELY TO SEVERELY ACTIVE SYSTEMIC LUPUS ERYTHEMATOSUS | Systemic Lupus Erythematosus | Immunology | SL0044 is a "sister" study of SL0043, SL0045 and is a feeder study of SL0046 |  |  |  | 2021-03-15 | 2022-04-01 | 2024-11-21 | 2023-07-14 |  | 2024-06-28 |  | 2024-08-09 |  | 2024-08-26 |  | 2024-11-20 |  | Argentina, Belgium, Canada, Chile, China, Denmark, France, Germany, Greece, Italy, Japan, Mexico, Netherlands, Peru, Poland, Puerto Rico, Serbia, South Korea, Spain, Taiwan, United Kingdom, United States of America | Argentina (FPFV), Belgium (1st Site Initiation), Canada (IRB / IEC Approval), Chile (Regulatory Approval), China (FPFV), Denmark (1st Site Initiation), France (IRB / IEC Approval), Germany (FPFV), Greece (FPFV), Italy (FPFV), Japan (FPFV), Mexico (Created), Netherlands (1st Site Initiation), Peru (Regulatory Approval), Poland (FPFV), Puerto Rico (FPFV), Serbia (1st Site Initiation), South Korea (FPFV), Spain (FPFV), Taiwan (1st Site Initiation), United Kingdom (IRB / IEC Approval), United States of America (FPFV) | Argentina, Belgium, Canada, Chile, China, Denmark, France, Germany, Greece, Italy, Japan, Netherlands, Peru, Poland, Puerto Rico, Serbia, South Korea, Spain, Taiwan, United Kingdom, United States of America | 215 | 142 | 41 | 693 | 312 | 312 | 41 | 15 | 5 | 21 | 20 | 1 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Dapirolizumab pegol | Immunology | SL0046 | FPFV | Evaluation of long-term efficacy and safety of Dapimab in ac | Phase III | Open | GCSO | Immunology | UCB Pharma Global | Spaete C | Copetti C | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, OPEN-LABEL EXTENSION STUDY TO ASSESS THE LONG-TERM SAFETY AND TOLERABILITY OF DAPIROLIZUMAB PEGOL TREATMENT IN STUDY PARTICIPANTS WITH SYSTEMIC LUPUS ERYTHEMATOSUS | Systemic Lupus Erythematosus | Immunology | SL0046 is an extension of SL0043, SL0044, SL0045 | 2020-08-03 | 2020-08-03 |  | 2020-11-03 | 2021-08-09 | 2021-07-27 | 2024-07-15 |  | 2026-08-14 |  | 2026-09-11 |  | 2026-09-28 |  | 2026-12-23 |  | Argentina, Belgium, Bulgaria, Canada, Chile, China, Colombia, Czech Republic, Denmark, France, Germany, Greece, Hungary, Italy, Japan, Mexico, Netherlands, Peru, Philippines, Poland, Puerto Rico, Romania, Serbia, South Korea, Spain, Taiwan, United Kingdom, United States of America | Argentina (FPFV), Belgium (FPFV), Bulgaria (LPFV), Canada (FPFV), Chile (FPFV), China (Created), Colombia (FPFV), Czech Republic (LPFV), Denmark (IRB / IEC Approval), France (IRB / IEC Approval), Germany (FPFV), Greece (FPFV), Hungary (FPFV), Italy (FPFV), Japan (Created), Mexico (FPFV), Netherlands (Created), Peru (FPFV), Philippines (FPFV), Poland (FPFV), Puerto Rico (Created (Held)), Romania (LPLV), Serbia (FPFV), South Korea (FPFV), Spain (FPFV), Taiwan (FPFV), United Kingdom (Created), United States of America (FPFV) | Argentina, Belgium, Bulgaria, Canada, Chile, Colombia, Czech Republic, Denmark, France, Germany, Greece, Hungary, Italy, Mexico, Peru, Philippines, Poland, Romania, Serbia, South Korea, Spain, Taiwan, United States of America | 258 | 99 | 96 | 543 | 543 | 462 | 233 | 0 | 0 | 233 | 84 | 63 | 86
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0102 | LPFV | Ph 2 OL of Continuation of Treatment with Combination Pyrimi | Phase II | Open | GCSO | Neurology | UCB Pharma Global | Peele T | Tillery N | N/A | CTI | No | No | other | No | A Phase 2 Open-Label Study of Continuation Treatment with Combination Pyrimidine Nucleosides in Patients with Thymidine Kinase 2 Deficiency (TK2) | Thymidine kinase 2 (TK2) deficiency; Mitochondrial DNA Depletion syndrome | Central Nervous System; Central Nervous System |  | 2018-10-01 | 2019-01-07 |  | 2019-01-07 | 2019-07-05 | 2019-07-05 | 2020-01-31 | 2020-06-28 | 2024-06-25 |  | 2024-07-23 |  | 2024-08-26 |  | 2024-11-20 |  | Israel, Spain, United States of America | Israel (LPFV), Spain (LPFV), United States of America (LPFV) | Israel, Spain, United States of America | 6 | 8 | 8 | 47 | 47 | 47 | 47 | 0 | 0 | 47 | 46 | 1 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Fintepla | Central Nervous System | EP0213 | FPFV | Open label to evaluate safety, tolerability and PK (ORCHID) | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Duclos T | Copetti C | ICON | ICON | No | No | other | No | Open-Label, Single-Arm, Phase 3 Study to Evaluate Safety, Tolerability, and Pharmacokinetics of ZX008 in Infants 1 Year to Less Than 2 Years of Age with Dravet Syndrome | Dravet Syndrome | Central Nervous System |  | 2022-04-01 | 2022-04-18 | 2022-04-29 | 2022-08-04 | 2023-05-15 | 2024-05-21 | 2024-03-18 |  | 2025-03-10 |  | 2025-04-07 |  | 2025-05-09 |  | 2025-08-05 |  | Belgium, Germany, Italy, Spain, United Kingdom, United States of America | Belgium (FPFV), Germany (FPFV), Italy (FPFV), Spain (1st Site Initiation), United Kingdom (FPFV), United States of America (FPFV) | Belgium, Germany, Italy, Spain, United Kingdom, United States of America | 15 | 19 | 11 | 27 | 20 | 20 | 23 | 3 | 4 | 16 | 13 | 2 | 1
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Fintepla | Central Nervous System | EP0216 | LPFV | Efficacy/safety using adjunct therapy (Zogenix 2103) | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global | Soma T, White Y | Copetti C, Matsuo T | ICON | CLUEPOINTS | Yes | No | other | No | A Phase 3, Randomized, Double-Blind, Placebo-Controlled, Fixed-Dose, Multicenter Study to Examine the Efficacy and Safety of ZX008 in Subjects with CDKL5 Deficiency Disorder Followed by an Open-Label Extension | CDKL5 Deficiency Disorder (CDD) | Central Nervous System |  | 2021-06-05 | 2021-05-21 | 2021-06-07 | 2021-06-07 | 2022-03-08 | 2022-03-08 | 2024-07-10 | 2024-12-19 | 2026-05-13 |  | 2026-06-10 |  | 2026-07-14 |  | 2026-10-08 |  | Austria, Belgium, Georgia, Germany, Ireland, Israel, Italy, Japan, Netherlands, Portugal, Spain, United Arab Emirates, United Kingdom, United States of America | Austria (LPFV), Belgium (LPFV), Georgia (LPFV), Germany (LPFV), Ireland (LPLV), Israel (LPFV), Italy (LPFV), Japan (LPFV), Netherlands (LPFV), Portugal (LPFV), Spain (LPFV), United Arab Emirates (LPFV), United Kingdom (LPFV), United States of America (LPFV) | Austria, Belgium, Georgia, Germany, Ireland, Israel, Italy, Japan, Netherlands, Portugal, Spain, United Arab Emirates, United Kingdom, United States of America | 77 | 64 | 46 | 108 | 100 | 80 | 106 | 0 | 19 | 87 | 60 | 19 | 8
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Fintepla | Central Nervous System | EP0247 | Created | Efficacy and Safety Rett Syndrome | Phase III |  | GCSO | Neurology | UCB Pharma Global | Heinzen L | Smit R | ICON |  | Yes | Yes |  | No |  | Rett Syndrome | Central Nervous System |  | 2025-03-06 08:00 | [18 empty] | 70 | 0 | 0 | 250 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Fintepla | not defined | EP0215 | Database Locked | OL Ext to assess long-term safety (Zogenix 1900) | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Roop R | Copetti C | Parexel | PAREXEL | No | No | other | No | An Open-Label Extension Trial to Assess the Long-Term Safety of ZX008 (Fenfluramine Hydrochloride) Oral Solution as an Adjunctive Therapy for Seizures in Patients with Rare Seizure Disorders Such as Epileptic Encephalopathies Including Dravet Syndrome and Lennox-Gastaut Syndrome | Lennox Gastaut Syndrome (LGS); Dravet Syndrome | Central Nervous System; Central Nervous System | EP0215 is an extension of EP0207, EP0212, EP0214 |  |  | 2017-05-01 | 2019-03-01 | 2019-06-03 | 2019-04-22 | 2021-04-21 | 2021-07-20 | 2025-07-09 |  | 2025-08-06 | 2025-05-22 | 2025-09-09 |  | 2025-12-04 |  | Australia, Belgium, Canada, Denmark, France, Germany, Italy, Mexico, Netherlands, Poland, Spain, Sweden, United Kingdom, United States of America | Australia (LPLV), Belgium (LPLV), Canada (LPLV), Denmark (LPLV), France (LPLV), Germany (LPLV), Italy (LPFV), Mexico (LPLV), Netherlands (LPFV), Poland (LPFV), Spain (LPFV), Sweden (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Belgium, Canada, Denmark, France, Germany, Italy, Mexico, Netherlands, Poland, Spain, Sweden, United Kingdom, United States of America | 51 | 69 | 71 | 413 | 413 | 206 | 413 | 0 | 0 | 413 | 2 | 123 | 288
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Galvokimig | Immunology | ATD002 | Protoc. Summary Approved | Moderate to severe Atopic Dermatitis | Phase II |  | GCSO | Immunology | UCB Pharma Global | Kurihara Y, Sacre J | Copetti C, Matsuo T | ICON | ICON | Yes | Yes |  | No |  | Atopic Dermatitis | Immunology |  | 2025-04-14 08:00 | 2025-03-28 | [17 empty] | 80 | 0 | 0 | 200 | 160 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Glovadalen | Central Nervous System | PD0060 | Database Locked | Proof of concept in participants with Parkinson's' disease | Phase II | Double Blind | GCSO | NewMeds | UCB Pharma Global | Leach S, Maxfield A | Cain D | ICON | UCB | Yes | Yes | adults | No | A MULTICENTER PHASE 2, DOUBLE-BLIND, PLACEBO-CONTROLLED, RANDOMIZED, PARALLEL GROUP STUDY TO EVALUATE THE EFFICACY, SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF UCB0022 IN STUDY PARTICIPANTS WITH ADVANCED PARKINSON’S DISEASE | Parkinson's disease | Central Nervous System |  | 2023-01-02 | 2022-12-21 | 2023-04-17 | 2023-04-17 | 2023-10-31 | 2023-11-17 | 2024-07-09 | 2024-12-06 | 2024-10-08 | 2025-04-11 | 2024-11-19 | 2025-05-20 | 2024-12-31 |  | 2025-03-27 |  | United States of America | United States of America (LPLV) | United States of America | 67 | 70 | 61 | 252 | 189 | 156 | 354 | 0 | 147 | 207 | 0 | 15 | 192
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Minzasolmin | New Medicines | PD0053 | CSR Approved | PHASE 2A STUDY TO EVA THE SAFETY, TOLERABILITY, PHARMACOKINE | Phase II | Double Blind | GCSO | Neurology | UCB Pharma Global | Quade J | Cain D | Parexel | PAREXEL | Yes | Yes | adults | No | A DOUBLE-BLIND, PLACEBO-CONTROLLED, RANDOMIZED, 18-MONTH PHASE 2A STUDY TO EVALUATE THE EFFICACY, SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF ORAL UCB0599 IN STUDY PARTICIPANTS WITH EARLY PARKINSON’S DISEASE | Parkinson's disease | Central Nervous System | PD0053 is a parent study of PD0055 | 2020-09-03 08:00 | 2020-09-03 |  | 2020-10-15 | 2020-12-22 | 2020-12-30 | 2022-02-03 | 2023-02-02 | 2023-10-12 | 2024-09-06 | 2023-11-13 | 2024-10-24 | 2023-12-11 | 2024-11-22 | 2024-03-06 | 2025-03-14 | Canada, France, Germany, Italy, Netherlands, Poland, Spain, United Kingdom, United States of America | Canada (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Netherlands (LPLV), Poland (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Canada, France, Germany, Italy, Netherlands, Poland, Spain, United Kingdom, United States of America | 125 | 121 | 115 | 450 | 450 | 428 | 862 | 0 | 365 | 497 | 0 | 65 | 430 | [22 empty] | yes
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Minzasolmin | New Medicines | PD0055 | LPFV | Extension study from PD0053 | Phase II | Double Blind | GCSO | Neurology | UCB Pharma Global | Moloudi A | Cain D | Parexel | PAREXEL | No | Yes | adults | No | A dose-blinded extension study to evaluate the long-term efficacy, safety, and tolerability of UCB0599 in study participants with Parkinson’s disease | Parkinson's disease | Central Nervous System | PD0055 is an extension of PD0053 | 2022-08-24 08:00 | 2022-03-17 |  | 2022-05-02 | 2022-10-17 | 2022-08-29 | 2024-07-22 | 2024-09-06 | 2030-01-28 |  | 2030-02-25 |  | 2030-03-11 |  | 2030-06-05 |  | Canada, France, Germany, Italy, Netherlands, Poland, Spain, United Kingdom, United States of America | Canada (LPLV), France (LPFV), Germany (LPFV), Italy (LPLV), Netherlands (LPFV), Poland (LPFV), Spain (LPFV), United Kingdom (LPFV), United States of America (LPLV) | Canada, France, Germany, Italy, Netherlands, Poland, Spain, United Kingdom, United States of America | 102 | 96 | 96 | 372 | 372 | 298 | 426 | 1 | 2 | 423 | 215 | 207 | 1
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | DV0009 | Created | OL study to evalaute On Body Delivery System (OBDS) | Phase III |  | GCSO | Neurology | UCB Pharma Global |  |  | ICON |  | Yes | Yes |  | No |  | Myasthenia gravis | Central Nervous System |  | 2025-08-18 08:00 | [18 empty] | 35 | 0 | 0 | 50 | 40 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | DV0011 | Created | BE study to evalaute On Body Delivery System (OBDS) | Phase III |  | GCSO | Neurology | UCB Pharma Global |  |  | ICON |  | Yes | Yes |  | No |  | Myasthenia gravis | Central Nervous System |  | 2025-08-18 08:00 | [18 empty] | 5 | 0 | 0 | 550 | 500 | 462 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | FM0002 | Created (Held) | severe Fibromyalgia | Phase III |  | GCSO | Immunology | UCB Pharma Global |  |  |  |  | Yes |  |  | No |  | Fibromyalgia | Immunology |  | 2024-05-01 08:00 | [15 empty] | United States of America | United States of America (Created) |  | 40 | 0 | 0 | 575 | 460 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | FM0003 | Created (Held) | severe Fibromyalgia | Phase III |  | GCSO | Immunology | UCB Pharma Global |  |  |  |  | Yes |  |  | No |  | Fibromyalgia | Immunology |  | 2024-04-30 08:00 | [15 empty] | United States of America | United States of America (Created) |  | 40 | 0 | 0 | 575 | 460 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | FM0004 | Created (Held) | severe Fibromyalgia | Phase III |  | GCSO | Immunology | UCB Pharma Global |  |  |  |  | Yes |  |  | No |  | Fibromyalgia | Immunology |  | 2024-04-30 08:00 | [15 empty] | United States of America | United States of America (Created) |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | MG0006 | FPFV | pediatric study in Myasthenia Gravis | Phase II | Open | GCSO | Neurology | UCB Pharma Global | Fukazawa A, Hanashima T, Ikeda K, Teichmann R | Matsuo T, Tillery N | Parexel | PAREXEL;UCB | No | Yes | paediatrics | No | STUDY TITLE: AN OPEN-LABEL, SINGLE ARM STUDY EVALUATING THE ACTIVITY, SAFETY, AND PHARMACOKINETICS OF ROZANOLIXIZUMAB IN PEDIATRIC STUDY PARTICIPANTS WITH GENERALIZED MYASTHENIA GRAVIS. Phase 2/3 | Myasthenia gravis | Central Nervous System | MG0006 is a parent study of MG0008 | 2022-06-15 | 2022-06-15 | 2022-11-14 | 2022-11-14 | 2023-06-13 | 2024-06-14 | 2026-04-14 |  | 2026-08-18 |  | 2026-09-02 |  | 2026-09-24 |  | 2026-11-23 |  | Hungary, Italy, Japan, Poland, Saudi Arabia, Taiwan, Turkey, United States of America | Hungary (Created (Held)), Italy (FPFV), Japan (Regulatory Approval), Poland (FPFV), Saudi Arabia (Created), Taiwan (1st Site Initiation), Turkey (Regulatory Approval), United States of America (1st Site Initiation) | Italy, Japan, Poland, Taiwan, Turkey, United States of America | 14 | 8 | 4 | 15 | 15 | 12 | 5 | 0 | 0 | 5 | 0 | 4 | 1
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | MG0008 | FPFV | pediatric study in Myasthenia Gravis | Phase II | Open | GCSO | Neurology | UCB Pharma Global | Hanashima T, Ikeda K, Teichmann R | Matsuo T, Tillery N | Parexel | PAREXEL;UCB | No | Yes | paediatrics | No | AN OPEN-LABEL EXTENSION STUDY TO EVALUATE ROZANOLIXIZUMAB IN PEDIATRIC STUDY PARTICIPANTS WITH GENERALIZED MYASTHENIA GRAVIS | Myasthenia gravis | Central Nervous System | MG0008 is an extension of MG0006 | 2022-06-15 | 2022-06-15 | 2022-12-01 | 2022-12-01 | 2023-10-17 | 2024-10-08 | 2026-08-17 |  | 2027-08-16 |  | 2027-09-01 |  | 2027-09-15 |  | 2027-11-15 |  | Italy, Japan, Poland, Saudi Arabia, Taiwan, Turkey | Italy (FPFV), Japan (1st Site Initiation), Poland (FPFV), Saudi Arabia (Created), Taiwan (1st Site Initiation), Turkey (Created) | Italy, Japan, Poland, Taiwan | 12 | 8 | 2 | 12 | 12 | 12 | 2 | 0 | 0 | 2 | 0 | 1 | 1
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | MG0033 | Created | ph4,open-label, single-arm study in Adult Chinese patients | Phase IV |  | GCSO | Neurology | UCB Pharma Global | Gao L | Guo J | Parexel |  | No | Yes |  | No |  | Myasthenia gravis | Central Nervous System |  | 2024-03-21 08:00 | [15 empty] | China | China (Created) |  | 12 | 0 | 0 | 57 | 40 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | MG0038 | Created | Ph3, double blind study in adult ocular MG patients | Phase III |  | GCSO | Neurology | UCB Pharma Global |  |  |  |  | Yes | Yes |  | No |  | Myasthenia gravis | Central Nervous System |  | 2025-09-23 08:00 | [18 empty] | 100 | 0 | 0 | 150 | 130 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | MOG001 | FPFV | Evaluate Efficacy and Safety MOG Ab-associated Disease | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global | Baukens C, Brown E, Grasses T, Kurihara Y | Matsuo T, Tillery N | Parexel | PAREXEL;UCB | Yes | Yes | adults | No | A randomized, double-blind, placebo-controlled, multicenter, phase 3, pivotal study with an open-lable extension period to evaluate the efficacy and safety of rozanolixizumab in adult participants with myelin oligodendrocyte glycoprotein (MOG) antibody-associated disease (MOG-AD) | MOG-AD Disease | Central Nervous System | MOG001 is a parent study of MOG002 | 2020-03-20 08:00 | 2020-03-20 |  | 2021-03-26 | 2021-08-02 | 2022-02-02 | 2023-12-29 |  | 2025-05-20 |  | 2025-06-05 |  | 2025-06-23 |  | 2025-09-17 |  | Australia, Belgium, Brazil, China, Czech Republic, France, Germany, Greece, Italy, Japan, Mexico, Poland, Portugal, South Korea, Spain, Sweden, Switzerland, Taiwan, Turkey, Ukraine, United Kingdom, United States of America | Australia (FPFV), Belgium (FPFV), Brazil (FPFV), China (Regulatory Approval), Czech Republic (FPFV), France (FPFV), Germany (FPFV), Greece (Created), Italy (FPFV), Japan (FPFV), Mexico (FPFV), Poland (Created), Portugal (FPFV), South Korea (FPFV), Spain (FPFV), Sweden (FPFV), Switzerland (FPFV), Taiwan (1st Site Initiation), Turkey (FPFV), Ukraine (FPFV), United Kingdom (FPFV), United States of America (FPFV) | Australia, Belgium, Brazil, China, Czech Republic, France, Germany, Italy, Japan, Mexico, Portugal, South Korea, Spain, Sweden, Switzerland, Taiwan, Turkey, Ukraine, United Kingdom, United States of America | 82 | 77 | 45 | 104 | 104 | 104 | 180 | 13 | 89 | 78 | 60 | 18 | 0 |  |  | 2023-09-07 | 2023-09-11
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Staccato Alprazolam | Central Nervous System | EP0162 | FPFV | A double-blind, placebo-controlled, Multicenter, outpatient, | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global | Bullock E, Sasamoto H, Zhao C | Grose-Hodge R, Guo J, Matsuo T | Parexel | PAREXEL | Yes | Yes | other | No | A DOUBLE-BLIND, RANDOMIZED, PLACEBO-CONTROLLED, MULTICENTER, OUTPATIENT, PARALLEL-GROUP STUDY TO ASSESS THE EFFICACY AND SAFETY OF STACCATO ALPRAZOLAM IN STUDY PARTICIPANTS 12 YEARS OF AGE AND OLDER WITH STEREOTYPICAL PROLONGED SEIZURES | Epilepsy | Central Nervous System | EP0162 is a parent study of EP0165 | 2020-12-01 08:00 | 2020-12-01 |  | 2021-07-02 | 2021-10-01 | 2021-12-07 | 2023-01-23 |  | 2023-05-22 |  | 2023-06-12 |  | 2023-06-26 |  | 2023-08-23 |  | Australia, Bulgaria, China, Czech Republic, France, Germany, Hungary, Italy, Japan, Poland, Spain, United Kingdom, United States of America | Australia (FPFV), Bulgaria (FPFV), China (FPFV), Czech Republic (FPFV), France (FPFV), Germany (FPFV), Hungary (FPFV), Italy (FPFV), Japan (FPFV), Poland (FPFV), Spain (FPFV), United Kingdom (FPFV), United States of America (FPFV) | Australia, Bulgaria, China, Czech Republic, France, Germany, Hungary, Italy, Japan, Poland, Spain, United Kingdom, United States of America | 169 | 165 | 116 | 350 | 350 | 350 | 377 | 12 | 105 | 260 | 8 | 17 | 235 |  |  | 2024-06-05 08:00 | 2024-06-05
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Staccato Alprazolam | Central Nervous System | EP0165 | FPFV | Open-Label, Multicenter, Outpatient Study To Evaluate Safety | Phase III | Not Applicable | GCSO | Neurology | UCB Pharma Global | Esch M, Sasamoto H, Zhao C | Copetti C, Guo J, Matsuo T | Parexel | PAREXEL | Yes | No | other | No | An open-label, multicenter, outpatient extension study to evaluate the safety and tolerability of Staccato alprazolam in STUDY participants 12 years of age and older with stereotypical prolonged seizures | Epilepsy | Central Nervous System | EP0165 is an extension of EP0162 | 2020-12-01 08:00 | 2020-12-01 |  | 2021-07-02 | 2021-10-04 | 2022-02-03 | 2023-05-24 |  | 2025-08-22 |  | 2025-09-19 |  | 2025-10-03 |  | 2025-12-30 |  | Australia, Bulgaria, China, Czech Republic, Germany, Hungary, Italy, Japan, Poland, Spain, United Kingdom, United States of America | Australia (FPFV), Bulgaria (FPFV), China (FPFV), Czech Republic (FPFV), Germany (FPFV), Hungary (FPFV), Italy (FPFV), Japan (FPFV), Poland (FPFV), Spain (FPFV), United Kingdom (1st Site Initiation), United States of America (FPFV) | Australia, Bulgaria, China, Czech Republic, Germany, Hungary, Italy, Japan, Poland, Spain, United Kingdom, United States of America | 169 | 159 | 89 | 286 | 286 | 286 | 201 | 3 | 14 | 184 | 130 | 54 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | UCB7853 | not defined | PD0059 | Protocol Approved (Cancelled) | Phase 2b Study to Evaluate the Efficacy, Safety, Tolerabilit | Phase II | Double Blind | GCSO | Neurology | UCB Pharma Global | Jabbarzadegan P | Cain D | ICON |  | Yes | Yes | adults | No | A MULTICENTER, DOUBLE-BLIND, PLACEBO-CONTROLLED, RANDOMIZED, PHASE 2 STUDY TO EVALUATE THE EFFICACY, SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF UCB7853 IN STUDY PARTICIPANTS WITH EARLY-STAGE PARKINSON’S DISEASE | Parkinson's disease | Central Nervous System |  | 2023-07-06 08:00 | 2023-07-06 |  | 2024-01-18 | [15 empty] | 100 | 0 | 0 | 715 | 495 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | VIMPAT | Central Nervous System | EP0151 | Database Locked | STUDY OF LCM IN PATIENTS COMPLETING EP0034 OR SP0848 | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Bretschneider M | Tillery N | ICON | PRA | No | No | paediatrics | No | A MULTICENTER, OPEN-LABEL, FOLLOW-UP STUDY TO ASSESS THE LONG-TERM USE OF ORAL LACOSAMIDE IN STUDY PARTICIPANTS WHO COMPLETED EP0034 OR SP848 AND RECEIVED LACOSAMIDE TREATMENT | Epilepsy | Central Nervous System | EP0151 is an extension of EP0034, SP0848 | 2020-02-12 08:00 | 2020-02-12 |  | 2020-04-14 | 2020-10-15 | 2020-12-28 | 2022-06-22 | 2022-02-16 | 2025-08-13 | 2025-02-12 | 2025-09-10 | 2025-03-18 | 2025-09-24 |  | 2025-12-19 |  | Georgia, Hungary, Moldavia, Romania, Taiwan, Ukraine | Georgia (LPLV), Hungary (LPLV), Moldavia (LPLV), Romania (LPLV), Taiwan (LPLV), Ukraine (LPLV) | Georgia, Hungary, Moldavia, Romania, Taiwan, Ukraine | 40 | 16 | 15 | 65 | 65 | 55 | 48 | 0 | 0 | 48 | 0 | 10 | 38
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | VIMPAT | Central Nervous System | SP0968 | Final TFLs released | LCM treatment of neonatal seizures | Phase II | Open | GCSO | Neurology | UCB Pharma Global | Weinsberg F | Anderson K | ICON | PRA | Yes | Yes | paediatrics | No | A MULTICENTER, OPEN-LABEL, RANDOMIZED, ACTIVE COMPARATOR STUDY TO EVALUATE THE EFFICACY, SAFETY, AND PHARMACOKINETICS OF LACOSAMIDE IN NEONATES WITH REPEATED ELECTROENCEPHALOGRAPHIC NEONATAL SEIZURES | Electroencephalographic neonatal seizure | Central Nervous System | SP0968 is a parent study of EP0158 |  |  |  | 2020-03-04 | 2020-08-27 | 2021-03-31 | 2021-08-19 | 2024-08-06 | 2021-09-28 | 2024-08-27 | 2021-10-28 | 2025-04-28 | 2021-11-11 | 2025-05-13 | 2022-02-07 |  | Australia, Canada, United States of America | Australia (LPLV), Canada (LPLV), United States of America (LPLV) | Australia, Canada, United States of America | 30 | 25 | 19 | 32 | 32 | 30 | 59 | 0 | 30 | 29 | 0 | 4 | 25
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Zilucoplan | Central Nervous System | DV0013 | Final TFLs released | ZLP Auto-Injector Clinical Use Study | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Krautz I | Russell R | ICON | CLUEPOINTS;UCB | Yes | Yes | adults | No | A MULTICENTER, OPEN-LABEL, outpatient STUDY TO EVALUATE THE SAFE AND EFFECTIVE USE OF A ZILUCOPLAN AUTO‑INJECTOR COMBINATION PRODUCT FOR SUBCUTANEOUS SELF-ADMINISTRATION BY STUDY PARTICIPANTS WITH GENERALIZED MYASTHENIA GRAVIS | Myasthenia gravis | Central Nervous System |  | 2023-10-12 | 2023-10-23 |  | 2023-12-15 |  | 2024-08-27 |  | 2025-01-13 |  | 2025-02-03 |  | 2025-03-12 |  | 2025-04-14 |  |  | Poland, United Kingdom, United States of America | Poland (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Poland, United Kingdom, United States of America | 14 | 11 | 11 | 28 | 25 | 15 | 32 | 0 | 1 | 31 | 0 | 0 | 31
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0011 | LPFV | RA101495-02.302 Open Label Extension Study | Phase III | Double Blind / Double Dummy | GCSO | NewMeds | UCB Pharma Global | Ionescu I | Beinhauer-Zellenka U | ICON | PRA | Yes | No | adults | No | Phase 3, Multicenter, Open-Label Extension Study of Zilucoplan in Subjects with Generalized Myasthenia Gravis | Myasthenia gravis | Central Nervous System | MG0011 is an extension of MG0009, MG0010 |  |  | 2019-04-10 | 2019-04-11 | 2019-04-10 | 2019-12-23 | 2021-03-25 | 2022-03-14 | 2023-03-24 |  | 2023-04-21 |  | 2023-05-05 |  | 2023-08-01 |  | Canada, France, Germany, Italy, Japan, Norway, Poland, Spain, United Kingdom, United States of America | Canada (LPFV), France (LPLV), Germany (LPLV), Italy (LPFV), Japan (LPLV), Norway (LPFV), Poland (LPFV), Spain (LPFV), United Kingdom (LPFV), United States of America (LPFV) | Canada, France, Germany, Italy, Japan, Norway, Poland, Spain, United Kingdom, United States of America | 71 | 75 | 70 | 200 | 200 | 200 | 200 | 0 | 0 | 200 | 110 | 52 | 38
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0014 | FPFV | pediatric study in Myasthenia Gravis | Phase II | Open | GCSO | Neurology | UCB Pharma Global | Moeltgen H, Namgoong K | Beinhauer-Zellenka U, Russell R | Parexel | PAREXEL;UCB | No | Yes | paediatrics | No | A multicenter open label, uncontrolled, study to evaluate the pharmacokinetics, pharmacodynamics, safety, tolerability, and activity of Zilucoplan in pediatric study participants from two to less than eighteen years of age with Acetylcholine receptor antibody positive generalize myasthenia gravis. | Myasthenia gravis | Central Nervous System | MG0014 is a parent study of MG0015 | 2022-09-07 | 2022-09-07 | 2023-05-01 | 2023-03-09 | 2023-09-01 | 2024-10-16 | 2026-08-31 |  | 2026-12-04 |  | 2026-12-22 |  | 2027-01-14 |  | 2027-03-16 |  | Italy, Mexico, Poland, South Korea, United Kingdom, United States of America | Italy (1st Site Initiation), Mexico (Created), Poland (1st Site Initiation), South Korea (FPFV), United Kingdom (FPFV), United States of America (1st Site Initiation) | Italy, Poland, South Korea, United Kingdom, United States of America | 12 | 9 | 2 | 8 | 8 | 8 | 4 | 0 | 0 | 4 | 2 | 0 | 2
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0015 | FPFV | pediatric study in Myasthenia Gravis | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Moeltgen H, Namgoong K | Beinhauer-Zellenka U, Russell R | Parexel | PAREXEL;UCB | No | Yes | paediatrics | No | AN OPEN-LABEL EXTENSION STUDY TO EVALUATE THE LONG-TERM SAFETY, TOLERABILITY, PHARMACOKINETICS, PHARMACODYNAMICS, AND ACTIVITY OF ZILUCOPLAN IN PEDIATRIC STUDY PARTICIPANTS WITH ACETYLCHOLINE RECEPTOR ANTIBODY POSITIVE GENERALIZED MYASTHENIA GRAVIS | Myasthenia gravis | Central Nervous System | MG0015 is an extension of MG0014 | 2022-09-07 | 2022-09-07 | 2023-05-01 | 2023-03-10 | 2023-10-27 | 2024-12-05 | 2026-10-26 |  | 2027-12-06 |  | 2027-12-22 |  | 2028-01-13 |  | 2028-03-14 |  | Italy, Mexico, Poland, South Korea, United Kingdom, United States of America | Italy (1st Site Initiation), Mexico (Created), Poland (1st Site Initiation), South Korea (FPFV), United Kingdom (FPFV), United States of America (1st Site Initiation) | Italy, Poland, South Korea, United Kingdom, United States of America | 12 | 9 | 2 | 8 | 8 | 8 | 4 | 0 | 0 | 4 | 4 | 0 | 0
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0017 | CSR Approved | Study of Pts Switching from other treatments to ZLP | Phase III | Not Applicable | GCSO | Neurology | UCB Pharma Global | Harvey B | Russell R | Parexel | PAREXEL;UCB | No | Yes | adults | No | A PHASE 3B, MULTICENTER, OPEN-LABEL, SINGLE-ARM STUDY TO EVALUATE THE SAFETY, TOLERABILITY, AND EFFICACY OF ZILUCOPLAN IN PARTICIPANTS WITH GENERALIZED MYASTHENIA GRAVIS SWITCHING FROM INTRAVENOUS COMPLEMENT COMPONENT 5 INHIBITORS TO SUBCUTANEOUS ZILUCOPLAN | Myasthenia gravis | Central Nervous System |  | 2021-12-16 | 2021-12-16 |  | 2022-05-24 | 2022-09-05 | 2022-10-31 | 2023-09-11 | 2023-10-23 | 2024-02-09 | 2024-10-23 | 2024-03-12 | 2024-11-07 | 2024-04-11 | 2024-12-04 | 2024-07-08 | 2025-03-20 | United States of America | United States of America (LPLV) | United States of America | 20 | 17 | 12 | 20 | 20 | 17 | 34 | 0 | 8 | 26 | 0 | 25 | 1 | [22 empty] | yes
No | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0032 | Protocol Approved | PK, PD, efficacy & safety of MG pts in China | Phase IV |  | GCSO | Neurology | UCB Pharma Global | Lei T | Guo J |  |  | No | Yes | adults | No | A SINGLE-ARM, OPEN-LABEL, MULTICENTER STUDY TO EVALUATE CLINICAL EFFICACY, SAFETY, AND TOLERABILITY OF ZILUCOPLAN IN CHINESE ADULT PARTICIPANTS WITH GENERALIZED MYASTHENIA GRAVIS. | Myasthenia gravis | Central Nervous System |  | 2024-03-01 | 2024-02-02 |  | 2024-06-06 | [12 empty] | China | China (Created) |  | 15 | 0 | 0 | 45 | 45 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | BIMZELX | Immunology | AS0022 | Created | Comparison of the risk of IBD in patients with Axial spondyl | Non Interventional Study - Prospective | Not Applicable | Affiliates | Immunology | UCB Pharma Global | Tokumasu T | Hosoi K |  | N/A |  |  | other | No |  | Ankylosing Spondylitis | Immunology | [17 empty] | Japan | Japan (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | BIMZELX | Immunology | PS0033 | Protocol Approved | Comparison of the risk of malignancy and serious infections | Non Interventional Study - Retrospective |  | Real World Evidence | Immunology | UCB Pharma Global | Tokumasu T | Hosoi K |  | N/A |  |  | other | No | Comparison of the risk of serious infections in patients with psoriasis prescribed Bimzelx Subcutaneous Injection 160 mg Syringe and Bimzelx Subcutaneous Injection 160 mg Autoinjector versus patients prescribed other biologic agents: A cohort study using acute phase-hospital based claims data | Psoriasis | Immunology |  |  |  |  | 2023-10-12 | [12 empty] | Japan | Japan (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | BIMZELX | Immunology | PS0036 | FPFV | OTIS Registry (RWE04560) | Registry | Not Applicable | GCSO | Immunology | UCB Pharma Global | Ozkan Y | Tillery N |  | N/A |  |  | adults | No | Bimekizumab Pregnancy Exposure and Outcome Registry: An OTIS Autoimmune Diseases in Pregnancy Study | Psoriasis | Immunology |  |  |  |  | 2022-12-14 |  | 2024-10-11 | [10 empty] | Canada, United States of America | Canada (Created), United States of America (FPFV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | BIMZELX | Immunology | PS0037 | FPFV | Pregnancy Retrospective Database Analysis (RWE0561) | Non Interventional Study - Retrospective | Not Applicable | GCSO | Immunology | UCB Pharma Global | Chheda J | Copetti C |  | N/A |  |  | adults | No | Cohort Study to Evaluate Fetal and Infant Outcomes Following Maternal Exposure to Bimekizumab for Treatment of Psoriasis during Pregnancy. | Psoriasis | Immunology |  |  |  |  | 2022-08-09 |  | 2024-11-01 | [10 empty] | United States of America | United States of America (FPFV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | BIMZELX | Immunology | PS0038 | Protocol Approved | PASS (base case scenario) (RWE0559) | Non Interventional Study - Retrospective | Not Applicable | GCSO | Immunology | UCB Pharma Global | Chheda J | Copetti C |  | N/A |  |  | adults | No | COHORT STUDY ON THE SAFETY OF BIMEKIZUMAB IN PATIENTS WITH PLAQUE PSORIASIS: A NON INTERVENTIONAL POST AUTHORIZATION STUDY. | Psoriasis | Immunology |  |  |  |  | 2022-12-14 | [12 empty] | France, United States of America | France (Regulatory Approval), United States of America (Created) | France | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | BIMZELX | Immunology | PS0042 | Created | Post approval to meet FDA post-marketing reqs (RWE0813) | Non Interventional Study - Retrospective |  | GCSO | Immunology | UCB Pharma Global | Ozkan Y | Tillery N |  | N/A |  |  | adults | No | Cohort study on the safety of bimekizumab in patients with plaque psoriasis: a non-interventional post-authorozation study. | Psoriasis | Immunology |  |  |  | 2024-01-31 |  | 2025-03-28 |  |  |  | 2037-03-30 | [5 empty] | 2037-10-30 |  | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | BIMZELX | Immunology | PS0047 | Protocol Approved (Held) | Retrospective chart review of plaque psoriasis patients | Non Interventional Study - Retrospective |  | Affiliates | Immunology | Affiliates | Heidbrede T | [5 empty] | adults | No | Longitudinal chart review of plaque psoriasis patients treated with bimekizumab from a single centre in the UK. | Psoriasis | Immunology |  |  |  | 2023-10-02 | 2023-08-29 | 2024-01-10 |  |  |  | 2025-01-22 | [5 empty] | 2025-06-13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | BIMZELX | Immunology | PS0048 | Protocol Approved | Comparison of the risk of malignancy in patients | Non Interventional Study - Prospective | Not Applicable | Affiliates | Immunology | UCB Pharma Global | Tokumasu T | Hosoi K |  | N/A |  |  | other | No | Comparison of the risk of malignancy in patients with psoriasis prescribed Bimzelx Subcutaneous Injection 160 mg Syringe and Bimzelx Subcutaneous Injection 160 mg Autoinjector versus patients prescribed other biologic agents: A cohort study using acute phase-hospital based claims data. | Psoriatic Arthritis | Immunology |  |  |  |  | 2023-10-12 | [12 empty] | Japan | Japan (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | CIMZIA | Immunology | UP0126 | Protocol Approved | Retrospective Database Analysis | Registry | Not Applicable | RWE/GCSO | Neurology | UCB Pharma Global | [6 empty] | adults | No | RETROSPECTIVE DATABASE ANALYSIS TO EXAMINE PREGNANCY AND NEONATAL OUTCOMES FOLLOWING MATERNAL EXPOSURE TO CIMZIA DURING PREGNANCY | All Indications | Central Nervous System |  |  |  |  | 2020-01-27 | 2026-03-13 |  |  |  | 2027-01-01 | [5 empty] | 2027-09-02 |  | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0109 | Created | SAFETY AND CLINICAL OUTCOMES OF DOXECITINE AND DOXRIBTIMINE | Non Interventional Study - Prospective |  | Real World Evidence | Neurology | UCB Pharma Global | Harvey B, Lelij G, Ozkan Y | Russell R, Tillery N |  |  |  |  | other | No |  | Thymidine kinase 2 (TK2) deficiency | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | EVENITY | Bones | OP0004 | FPFV | PASS: serious cardiovascular events and all-cause mortality | Non Interventional Study - Retrospective |  | Real World Evidence | Bone | UCB Pharma Global | Moayyeri A |  |  | N/A |  |  | adults | No | European non-interventional post authorization safety study (PASS) related to serious cardiovascular (CV) events of myocardial infarction (MI) and stroke, and all-cause mortality for romosozumab by the EU ADR Alliance | Osteoarthritis; Osteoporosis | Bones; Bones |  |  |  | 2020-02-28 | 2020-09-17 | 2020-02-28 | 2020-11-16 |  |  | 2028-03-08 | [5 empty] | 2026-10-30 |  | Denmark, Germany, Netherlands, Spain, United Kingdom | Denmark (FPFV), Germany (FPFV), Netherlands (FPFV), Spain (FPFV), United Kingdom (FPFV) | Denmark, Germany, Netherlands, Spain, United Kingdom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
No | Real World Evidence | Managing Type | 1 | EVENITY | Bones | OP0005 | FPFV | PASS: Risk minimization measures for romosozumab | Non Interventional Study - Retrospective |  | Real World Evidence | Bone | UCB Pharma Global | Moayyeri A |  |  | N/A |  |  | adults | No | European non-interventional post authorization safety study (PASS) related to adherence to the risk minimization measures (RMMs) for romosozumab by the EU-ADR Alliance | [5 empty] | 2020-02-28 | 2020-09-17 | 2020-05-01 | 2020-11-16 |  |  | 2027-10-07 | [5 empty] | 2028-06-06 |  | Denmark, Germany, Netherlands, Spain, United Kingdom | Denmark (FPFV), Germany (FPFV), Netherlands (FPFV), Spain (FPFV), United Kingdom (FPFV) | Denmark, Germany, Netherlands, Spain, United Kingdom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
No | Real World Evidence | Managing Type | 1 | EVENITY | Bones | OP0006 | FPFV | PASS related to serious infections for romosozumab | Non Interventional Study - Retrospective |  | Real World Evidence | Bone | UCB Pharma Global | Moayyeri A |  |  | N/A |  |  | adults | No | European non-interventional post authorization safety study (PASS) related to serious infections (SIs) for romosozumab by the EU ADR Alliance | [5 empty] | 2020-02-28 | 2020-09-17 | 2020-05-01 | 2020-11-16 |  |  | 2023-10-05 | [5 empty] | 2026-10-30 |  | Denmark, Germany, Netherlands, Spain, United Kingdom | Denmark (FPFV), Germany (FPFV), Netherlands (FPFV), Spain (FPFV), United Kingdom (FPFV) | Denmark, Germany, Netherlands, Spain, United Kingdom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
No | Real World Evidence | Managing Type | 1 | EVENITY | Bones | OP0007 | FPFV | Validation Study for the PASS Studies OP004/5/6 | Non Interventional Study - Retrospective |  | Real World Evidence | Bone | UCB Pharma Global | Moayyeri A |  |  | N/A |  |  | adults | No | Validation study for “EU non-interv post-auth safety study related to serious CV events of myocardial infarction and stroke and all-cause mortality for romosozumab by EU-ADR Alli (OP0004)” & “EU non interv post auth safety study related to serious infections for romosozumab by EU-ADR Alli (OP0006).” | [5 empty] | 2020-06-09 | 2020-09-17 | 2020-10-01 | 2020-11-16 |  |  | 2021-04-15 | [5 empty] | 2026-11-02 |  | Germany, Netherlands, Spain | Germany (FPFV), Netherlands (FPFV), Spain (FPFV) | Germany, Netherlands, Spain | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | EVENITY | Bones | OP0009 | FPFV | EU Romosozumab Observational/NIS study | Non Interventional Study - Prospective | Not Applicable | Global Medical Affairs | Bone | UCB Pharma Global | Dubois F | Anderson K |  | UCB |  |  | adults | No | Patient characteristics and utilization patterns of romosozumab in routine clinical practice: a European, multi-country, non-interventional study (PRIME) | Osteoporosis | Bones |  |  |  |  | 2024-08-08 | 2025-01-31 | 2025-04-02 |  |  | 2026-06-19 | [5 empty] | 2027-02-17 |  | Belgium, Germany, Greece, Italy, Spain, Sweden, Switzerland, United Kingdom | Belgium (IRB / IEC Approval), Germany (IRB / IEC Submission), Greece (Created), Italy (FPFV), Spain (IRB / IEC Approval), Sweden (IRB / IEC Approval), Switzerland (IRB / IEC Submission), United Kingdom (IRB / IEC Approval) | Italy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Fintepla | Central Nervous System | EP0220 | CSR Approved | A European Study of the Effectiveness of Risk Minimisation | Non Interventional Study - Prospective | Not Applicable | Real World Evidence | Neurology | UCB Pharma Global | Chheda J | Copetti C |  | N/A |  |  | other | No | A European Study of the Effectiveness of Risk Minimisation Measures for Fenfluramine in Dravet Syndrome | Dravet Syndrome; Epilepsy | Central Nervous System; Central Nervous System |  |  |  |  | 2022-07-27 | 2023-01-03 | 2022-08-30 |  |  | 2025-12-30 | 2024-12-05 |  |  |  |  | 2026-04-21 | 2025-04-09 | Austria, France, Germany, Italy, Spain, United Kingdom | Austria (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Spain (LPLV), United Kingdom (LPLV) | Austria, France, Germany, Italy, Spain, United Kingdom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Fintepla | Central Nervous System | EP0222 | FPFV | Fintepla Japan PMS study (long-term Use) | Non Interventional Study - Prospective | Not Applicable | Affiliates | Neurology | UCB Pharma Global | Tokumasu T | Hosoi K |  | N/A |  |  | other | No | SPECIAL DRUG USE-RESULT observational study of FINTEPLA® Oral Solution 2.2 mg/mL (Long-term Use) | Dravet Syndrome | Central Nervous System |  |  |  |  | 2022-11-25 |  | 2023-01-23 | [10 empty] | Japan | Japan (FPFV) | Japan | 300 | 0 | 0 | 600 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Fintepla | Central Nervous System | EP0232 | Created (Cancelled) | French NIS | Non Interventional Study - Prospective |  | GCSO | Neurology | UCB Pharma Global | [7 empty] | No |  | Epilepsy | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Fintepla | Central Nervous System | EP0239 | Protocol Approved | Sleep Impact | Non Interventional Study - Prospective | Not Applicable | RWE/GCSO | Neurology | UCB Pharma Global | Roop R | Copetti C |  | PAREXEL |  |  | other | No | SLEEP DISTURBANCES, BEHAVIOR, ACTIVITIES OF DAILY LIVING, AND CAREGIVER BURDEN AMONG PATIENTS DIAGNOSED WITH DRAVET SYNDROME AND LENNOX-GASTAUT SYNDROME INITIATING TREATMENT WITH FENFLURAMINE (FINTEPLA®): A PROSPECTIVE MULTICENTER STUDY | Epilepsy | Central Nervous System |  |  |  | 2024-04-03 | 2024-09-12 | 2025-04-29 |  |  |  | 2027-01-28 | [5 empty] | 2027-09-28 |  | Italy, Spain, United States of America | Italy (Created), Spain (IRB / IEC Submission), United States of America (IRB / IEC Approval) |  | 25 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Fintepla | Central Nervous System | EP0241 | Protocol Approved | RWE Data from REMS | Non Interventional Study - Prospective | Not Applicable | RWE/GCSO | Neurology | UCB Pharma Global | Ranopa M | Roberts J |  | N/A |  |  | other | No |  | Epilepsy | Central Nervous System |  |  |  | 2024-06-26 | 2024-07-08 | [10 empty] | 2024-11-25 |  | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Fintepla | Central Nervous System | EP0242 | Created | Post Marketing Surveillance for Fintepla in DS patients | Non Interventional Study - Prospective |  | Affiliates | Neurology | UCB Pharma Global | Namgoong K | Beinhauer-Zellenka U | N/A | IQVIA | No | No | other | No |  | Dravet Syndrome | Central Nervous System | [17 empty] | South Korea | South Korea (Created) |  | 10 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Fintepla | not defined | EP0217 | FPFV | US CV Registry (Zogenix 2100) | Registry | Open | GCSO | Neurology | UCB Pharma Global | Roop R | Copetti C |  | N/A |  |  | other | No | FINTEPLA® (fenfluramine) Cardiovascular Safety Registry Study: a long-term observational study of the cardiovascular safety of FINTEPLA exposure | All Indications; Lennox Gastaut Syndrome (LGS); Dravet Syndrome; CDKL5 Deficiency Disorder (CDD) | Central Nervous System; Central Nervous System; Central Nervous System; Central Nervous System |  |  |  | 2021-08-02 | 2021-08-02 | 2022-08-01 | 2020-07-13 |  |  | 2032-03-01 | [5 empty] | 2032-10-28 |  | United States of America | United States of America (FPFV) | United States of America | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Fintepla | not defined | UP0131 | FPFV | Pharmacovigilance from the UCB safety database | Non Interventional Study - Retrospective | Not Applicable | GCSO | Neurology | UCB Pharma Global | Guye S | Butler L |  | THE NORTH AMERICAN AED REGISTRY |  |  | adults | No | FINTEPLA® (FENFLURAMINE) PREGNANCY SAFETY STUDY: AN OBSERVATIONAL STUDY EVALUATING THE SAFETY OF FINTEPLA EXPOSURE DURING PREGNANCY AMONG RETROSPECTIVELY REPORTED PREGNANCIES | Epilepsy | Central Nervous System |  |  |  | 2020-07-13 | 2022-06-14 | 2022-10-28 | 2020-06-25 |  |  | 2031-10-01 | [5 empty] | 2032-01-21 |  | United States of America | United States of America (FPFV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Rystiggo | Central Nervous System | MG0027 | Created | Rozanolixizumab PASS in patients with gMG (RWE 0826) | Non Interventional Study - Retrospective |  | GCSO | Neurology | UCB Pharma Global | Murphy C | Russell R |  | N/A |  |  | adults | No | A multi-national cohort study to assess the implementation of the risk minimization measures to prevent meningococcal infection in patients with generalized myasthenia gravis initiating zilucoplan, and zilucoplan safety in real-world settings. | Myasthenia gravis | Central Nervous System | [17 empty] | France, Germany, United States of America | France (Created), Germany (Created), United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Rystiggo | Central Nervous System | MG0031 | FPFV | Japan-PMS Study of Rozmab for gMG | Non Interventional Study - Prospective |  | Affiliates | Neurology | UCB Pharma Global | Tokumasu T | Hosoi K |  | N/A |  |  | other | No | GENERAL DRUG USE-RESULT OBSERVATIONAL STUDY OF RYSTIGGO ® 280 MG FOR S.C INJECTION | Myasthenia gravis | Central Nervous System |  |  |  |  | 2023-10-18 |  | 2024-03-07 | [10 empty] | Japan | Japan (FPFV) | Japan | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Rystiggo | Central Nervous System | UP0146 | Protocol Approved | prospective cohort study | Registry |  | RWE/GCSO | Neurology | UCB Pharma Global | Chheda J | Copetti C |  | MSBASE FOUNDATION |  |  | adults | No | DESCRIPTIVE COHORT STUDY OF PREGNANCY, MATERNAL, FETAL, NEONATAL, AND INFANT OUTCOMES FOLLOWING MATERNAL EXPOSURE TO ROZANOLIXIZUMAB-NOLI FOR TREATMENT OF MYASTHENIA GRAVIS DURING PREGNANCY AND/OR LACTATION | Myasthenia gravis | Central Nervous System |  |  |  | 2025-09-01 | 2025-01-31 | 2025-01-31 |  |  |  | 2035-05-04 | [5 empty] | 2035-06-04 |  | Australia, Canada, Croatia, Greece, Hungary, Iran, Italy, Kuwait, Latvia, Mexico, South Africa, Turkey | Australia (Created), Canada (Created), Croatia (Created), Greece (Created), Hungary (Created), Iran (Created), Italy (Created), Kuwait (Created), Latvia (Created), Mexico (Created), South Africa (Created), Turkey (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Rystiggo | Central Nervous System | UP0147 | Protocol Approved (Held) | retrospective cohort study | Registry | Not Applicable | RWE/GCSO | Neurology | UCB Pharma Global | Chheda J | Copetti C |  |  |  |  | adults | No | Descriptive Retrospective Cohort Study of Pregnancy, Maternal, Fetal, Neonatal, and Infant Outcomes Following Maternal Exposure to Rozanolixizumab-noli for Treatment of Myasthenia Gravis during Pregnancy | Myasthenia gravis | Central Nervous System |  |  |  | 2025-06-20 | 2024-03-26 | 2024-03-26 |  |  |  | 2034-08-29 | [5 empty] | 2034-09-27 |  | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | VIMPAT | not defined | EP0223 | Protocol Approved | Collect data regarding long-term neurocognitive development | Non Interventional Study - Retrospective | Not Applicable | Real World Evidence | Neurology | UCB Pharma Global | Kaur M |  |  | PEDSnet |  |  | paediatrics | No | Retrospective observational study- describing long-term neurocognitive development outcomes in neonates treated with Lacosamide | Epilepsy | Central Nervous System |  |  |  | 2024-05-10 | 2025-05-15 | 2024-05-12 |  |  |  | 2024-07-12 | [5 empty] | 2026-02-02 |  | United States of America | United States of America (Created) |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0026 | Created | Zilucoplan PASS in patients with gMG (RWE 0856) | Non Interventional Study - Retrospective |  | GCSO | Neurology | UCB Pharma Global | Murphy C | Russell R |  | N/A | No | Hybrid | adults | No | A multi-national cohort study to assess the implementation of the risk minimization measures to prevent meningococcal infection in patients with generalized myasthenia gravis initiating zilucoplan, and zilucoplan safety in real-world settings. | Myasthenia gravis | Central Nervous System | [17 empty] | Denmark, France, Germany, Sweden, United States of America | Denmark (Created), France (Created), Germany (Created), Sweden (Created), United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0030 | FPFV | Japan-PMS Study of ZLP for gMG | Non Interventional Study - Prospective |  | Affiliates | Neurology | UCB Pharma Global | Tokumasu T | Hosoi K |  | N/A |  |  | adults | No | GENERAL DRUG USE-RESULT OBSERVATIONAL STUDY of ZILBRYSQ® 16.6 MG , 23.0 MG , 32.4 MG SYRINGE FOR S.C INJECTION | Myasthenia gravis | Central Nervous System |  |  |  |  | 2023-10-16 | 2024-04-12 | 2024-02-21 |  |  | 2030-04-18 | [5 empty] | 2031-05-20 |  | Japan | Japan (FPFV) | Japan | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Zilucoplan | Central Nervous System | UP0148 | Protocol Approved | prospective cohort study | Registry | Not Applicable | RWE/GCSO | Neurology | UCB Pharma Global | Chheda J | Copetti C |  | MSBASE FOUNDATION |  |  | adults | No | Descriptive Cohort Study of Pregnancy, maternal, Fetal, neonatal, and Infant Outcomes Following Maternal Exposure to Zilucoplan for Treatment of Myasthenia Gravis During Pregnancy and/or lactation | Myasthenia gravis | Central Nervous System |  |  |  | 2025-08-29 | 2025-03-31 | 2025-03-31 |  |  |  | 2034-05-02 | [5 empty] | 2035-10-01 |  | Australia, Canada, Croatia, Greece, Hungary, Iran, Italy, Kuwait, Latvia, Mexico, South Africa, Turkey | Australia (Created), Canada (Created), Croatia (Created), Greece (Created), Hungary (Created), Iran (Created), Italy (Created), Kuwait (Created), Latvia (Created), Mexico (Created), South Africa (Created), Turkey (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Real World Evidence | Managing Type | 1 | Zilucoplan | Central Nervous System | UP0149 | Protocol Approved (Held) | retrospective cohort study | Registry | Not Applicable | RWE/GCSO | Neurology | UCB Pharma Global | Chheda J | Copetti C |  |  |  |  | adults | No | Descriptive Retrospective Cohort Study of Pregnancy, Maternal, Fetal, Neonatal, and Infant Outcomes Following Maternal Exposure to Zilucoplan for Treatment of Myasthenia Gravis during Pregnancy | Myasthenia gravis | Central Nervous System |  |  |  | 2025-08-29 | 2024-05-22 | 2024-05-22 |  |  |  | 2034-11-22 | [5 empty] | 2034-12-21 |  | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Managing Type | 1 | CIMZIA | not defined | EPD101 | CSR Approved | Evaluate influence of anti-TNFs, esp. Cimzia&other biologics | Non Interventional Study - Retrospective |  | GMAP | Immunology | UCB Pharma Global | Toth E | [5 empty] | adults | No | A RETROSPECTIVE DATABASE STUDY TO ASSESS HEALTH OUTCOMES BEFORE AND AFTER ANTI-TNF INITIATION IN RHEUMATOID ARTHRITIS AND CROHN’S DISEASE PATIENTS IN THE USA | [6 empty] | 2015-03-01 |  | 2015-03-15 |  |  |  | 2016-03-14 | [5 empty] | 2016-05-09 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Managing Type | 1 | CIMZIA | not defined | EPD102 | CSR Approved | Evaluate influence of anti-TNFs, esp. Cimzia&other biologics | Non Interventional Study - Retrospective |  | GMAP | Immunology | UCB Pharma Global | Toth E | [5 empty] | adults | No | A RETROSPECTIVE DATABASE STUDY TO ASSESS HEALTH OUTCOMES BEFORE AND AFTER ANTI-TNF INITIATION IN ANKYLOSING SPONDYLITIS AND PSORIATIC ARTHRITIS PATIENTS IN THE USA | [6 empty] | 2015-03-01 |  | 2015-03-15 |  |  |  | 2016-02-22 | [5 empty] | 2016-05-09 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Managing Type | 1 | CIMZIA | not defined | GPE_IMMUN_1 | CSR Approved | Impact of Route of Administration on Biologic Utilization | Non Interventional Study - Retrospective |  | GMAP | Immunology | UCB Pharma Global | Toth E | [5 empty] | adults | No | Cimzia Site of Care Analysis Amendment: The Impact of Route of Administration on Biologic Utilization | [6 empty] | 2015-11-30 |  | 2015-12-01 |  |  |  | 2015-12-17 | [5 empty] | 2016-01-05 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Managing Type | 1 | EVENITY | Bones | GPE_BONE_1 | CSR Approved | To describe osteoporosis related health outcomes in a popula | Non Interventional Study - Retrospective |  | GMAP | Bone | UCB Pharma Global | Toth E | [5 empty] | adults | No | EGB claims database analysis on osteoporosis and bone fractures in France | [6 empty] | 2015-04-24 |  | 2013-12-19 |  |  |  | 2015-06-29 | [5 empty] | 2016-02-05 | France | France (LPLV) | France | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Managing Type | 1 | EVENITY | Bones | GPE_BONE_3 | CSR Approved | Treatment pathways, patient characteristics, and imminent ri | Non Interventional Study - Retrospective |  | GMAP | Bone | UCB Pharma Global | Toth E | [5 empty] | adults | No | Treatment pathways, patient characteristics, and imminent risk of fracture in osteoporosis in Sweden | [6 empty] | 2016-02-15 |  | 2016-02-16 |  |  |  | 2016-09-16 | [5 empty] | 2016-12-15 | Sweden | Sweden (LPLV) | Sweden | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Managing Type | 1 | KEPPRA | Central Nervous System | EPD113 | CSR Approved | Compare direct HC cost between treatment w. enzyme inducing | Non Interventional Study - Retrospective |  | GMAP | Neurology | UCB Pharma Global | Borghs S | [5 empty] | adults | No | The effect of enzyme inducing antiepileptic drugs and valproate on long-term healthcare costs, compared with non-enzyme active antiepileptic drugs. | [6 empty] | 2014-04-01 |  | 2014-06-30 |  |  |  | 2015-08-01 | [5 empty] | 2016-03-01 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Managing Type | 1 | KEPPRA | Central Nervous System | EPD113B | CSR Approved | Compare direct HC cost between treatment with enzyme | Non Interventional Study - Retrospective |  | GMAP | Neurology | UCB Pharma Global | Borghs S | [5 empty] | geriatrics | No | The effect of enzyme inducing antiepileptic drugs and valproate on long-term healthcare costs, compared with non-enzyme active antiepileptic drugs, in elderly patients. | [6 empty] | 2016-02-29 |  | 2016-05-29 |  |  |  | 2016-08-01 | [5 empty] | 2016-08-31 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Managing Type | 1 | KEPPRA | Central Nervous System | EPD140B | CSR Approved | effectiveness of initial monotherapy in paediatric epilepsy | Non Interventional Study - Retrospective |  | GMAP | Neurology | UCB Pharma Global | Borghs S | [5 empty] | paediatrics | No | AED treatment sequencing and effectiveness in paediatric epilepsy patients, in real life clinical practice in England. | [6 empty] | 2015-02-15 |  | 2015-05-16 |  |  |  | 2017-08-17 | [5 empty] | 2018-06-15 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Managing Type | 1 | KEPPRA | Central Nervous System | EPD140C | CSR Approved | Effectiveness of initial monotherapy in elderly in the UK | Non Interventional Study - Retrospective |  | GMAP | Neurology | UCB Pharma Global | Borghs S | [5 empty] | geriatrics | No | AED treatment sequencing and effectiveness in elderly epilepsy patients, in real life clinical practice in England. | [6 empty] | 2015-02-15 |  | 2015-05-16 |  |  |  | 2017-08-17 | [5 empty] | 2018-06-15 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Managing Type | 1 | VIMPAT | Central Nervous System | EPD083 | CSR Approved | effectiveness of lacosamide, carbamazepine and lamotrigine i | Non Interventional Study - Retrospective | Not Applicable | GMAP | Neurology | UCB Pharma Global | Thieffry S |  |  | N/A |  |  | adults | No | The comparative effectiveness of lacosamide, carbamazepine and lamotrigine in monotherapy treatment in epilepsy patients | [6 empty] | 2016-04-01 |  | 2016-04-01 |  |  |  | 2016-04-01 | [5 empty] | 2016-11-30 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Managing Type | 1 | XYREM | Central Nervous System | NA0002 | Created (Cancelled) | Xyrem EU-RMP: Effectiveness Assessment Protocol of Education | Non Interventional Study - Prospective |  | GCSO | Neurology | UCB Pharma Global | Guitart M | Copetti C | N/A | PAREXEL | No | No | paediatrics | No |  | Narcolepsy | Central Nervous System | [17 empty] | Spain | Spain (Created) |  | 6 | 0 | 0 | 200 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Managing Type | 2 | KEPPRA | Central Nervous System | EPD140 | CSR Approved | To assess the effectiveness of initial monotherapy in the UK | Non Interventional Study - Retrospective |  | GMAP | Neurology | UCB Pharma Global | Borghs S | [5 empty] | adults | No | AED treatment sequencing and effectiveness in epilepsy patients, in real life clinical practice in England. | [6 empty] | 2015-02-15 |  | 2015-05-16 |  |  |  | 2017-08-17 | [5 empty] | 2018-06-15 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Managing Type | 2 | VIMPAT | Central Nervous System | EPD167 | Protocol Approved (Cancelled) | comparative effectiveness of Vimpat in 2nd line monotherapy | Non Interventional Study - Retrospective |  | Affiliates | Neurology | UCB Pharma Global | Borghs S | [5 empty] | adults | No | Comparative effectiveness of Vimpat in 2nd line monotherapy, in adult POS patients. | [6 empty] | 2016-04-01 | [12 empty] | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Managing Type | 2 | VIMPAT | Central Nervous System | EPD169 | CSR Approved | Treatment use and comparative effectiveness of lacosamide vs | Non Interventional Study - Retrospective |  | GMAP | Neurology | UCB Pharma Global | Thieffry S | [5 empty] | paediatrics | No | [7 empty] | 2017-07-14 |  | 2017-09-01 |  |  |  | 2018-05-01 | [5 empty] | 2018-01-01 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Non-managing Type | 2 | KEPPRA | Central Nervous System | EPD167 | Protocol Approved (Cancelled) | comparative effectiveness of Vimpat in 2nd line monotherapy | Non Interventional Study - Retrospective |  | Affiliates | Neurology | UCB Pharma Global | Borghs S | [5 empty] | adults | No | Comparative effectiveness of Vimpat in 2nd line monotherapy, in adult POS patients. | [6 empty] | 2016-04-01 | [12 empty] | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Non-managing Type | 2 | KEPPRA | Central Nervous System | EPD169 | CSR Approved | Treatment use and comparative effectiveness of lacosamide vs | Non Interventional Study - Retrospective |  | GMAP | Neurology | UCB Pharma Global | Thieffry S | [5 empty] | paediatrics | No | [7 empty] | 2017-07-14 |  | 2017-09-01 |  |  |  | 2018-05-01 | [5 empty] | 2018-01-01 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Health Outcomes Research | Non-managing Type | 2 | VIMPAT | Central Nervous System | EPD140 | CSR Approved | To assess the effectiveness of initial monotherapy in the UK | Non Interventional Study - Retrospective |  | GMAP | Neurology | UCB Pharma Global | Borghs S | [5 empty] | adults | No | AED treatment sequencing and effectiveness in epilepsy patients, in real life clinical practice in England. | [6 empty] | 2015-02-15 |  | 2015-05-16 |  |  |  | 2017-08-17 | [5 empty] | 2018-06-15 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | CD0006 | CSR Approved | Val of Clin Demo predictors of maintaining remission CR | Non Interventional Study - Retrospective |  | Affiliates | Immunology | UCB Pharma Global | Pisenti L |  | N/A |  |  |  | other | No |  |  |  |  | 2014-08-29 | 2015-03-20 |  | 2015-03-20 | [7 empty] | 2015-08-31 |  |  |  | 2015-09-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | RA0035 | Study Archived | Observational study to evaluate efficacy & safety Cimzia | Non Interventional Study - Prospective | Open | GCSO | Immunology | UCB Pharma Global | Petko A | Beinhauer-Zellenka U | N/A | McKesson Specialty (CRO) |  |  | adults | No | A PROSPECTIVE, MULTICENTRE, OBSERVATIONAL, NONINTERVENTIONAL STUDY TO EVALUATE THE SAFETY AND EFFECTIVENESS OF TNF ALPHA INHIBITOR THERAPY WITH CERTOLIZUMAB PEGOL (CIMZIA™) OBSERVED IN DAILY PRACTICE IN ADULT RA PATIENTS IN CANADA. | Rheumatoid Arthritis | Immunology |  | 2009-12-09 | 2010-02-17 |  | 2010-05-26 | 2010-12-22 | 2010-12-22 | 2014-09-30 | 2014-08-27 |  | 2016-12-06 |  | 2017-02-17 |  |  |  | 2017-08-11 | Canada | Canada (LPLV) | Canada | 50 | 0 | 0 | 545 | 545 | 0 | 546 | 0 | 0 | 546 | 0 | 0 | 546
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | RA0036 | CSR Approved | CaliRA study | Non Interventional Study - Retrospective |  | UCB Pharma Global |  | UCB Pharma Global | Del Campo I | [6 empty] | No | Epidemiologic Results of a National Survey Efficiency (cost effectiveness) of Certolizumab pegol in RA patients that can be treated with biological therapies CALIRA |  |  |  | 2008-04-24 | 2008-09-26 |  | 2008-09-26 |  | 2008-11-13 |  |  |  | 2009-04-30 | [5 empty] | 2009-12-22 | Spain | Spain (LPLV) | Spain | 42 | 0 | 0 | 828 | 0 | 0 | 828 | 0 | 0 | 828 | 828 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | RA0042 | Study Archived | RA-PROACTIVE - NIS of CZP in RA (UK) | Non Interventional Study - Prospective | Open | GCSO | Immunology | UCB Pharma Global | Sacre J | Copetti C | N/A | Chiltern | No | No | adults | No | A Uk multicentre non interventional prospective cohort study to evaluate the long term clinical, patient reported and health care resource utilisation effects of an early response to Certolizumab pegol in RA patients in daily clinical practice. The RA-Proactive (RA patient reported outcomes and Cimzia treatment in vivo evaluation) study | Rheumatoid Arthritis | Immunology |  | 2010-12-30 | 2010-07-28 |  | 2010-12-14 | 2011-03-31 | 2011-07-26 | 2012-02-20 | 2013-04-01 |  | 2014-12-17 |  | 2015-03-24 |  |  |  | 2016-03-01 | Ireland, United Kingdom | Ireland (LPLV), United Kingdom (LPLV) | Ireland, United Kingdom | 25 | 0 | 0 | 187 | 187 | 187 | 152 | 0 | 0 | 152 | 0 | 0 | 152
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | RA0046 | Study Archived | NIS of CZP in RA re. work productivity (Belgium) | Non Interventional Study - Prospective | Open | GCSO | Immunology | Affiliates | Sacre J | Copetti C | N/A | clintrialnet |  |  | adults | No | AN OBSERVATIONAL, NONINTERVENTIONAL, PROSPECTIVE STUDY IN RHEUMATOID ARTHRITIS PATIENTS TREATED WITH CERTOLIZUMAB PEGOL (CIMZIA) | Rheumatoid Arthritis | Immunology |  | 2009-12-31 | 2010-06-25 |  | 2010-08-07 | 2010-12-15 | 2010-12-24 | 2011-12-15 | 2013-12-04 |  | 2014-12-05 |  | 2015-04-07 |  |  |  | 2016-03-18 | Belgium | Belgium (LPLV) | Belgium | 30 | 0 | 0 | 151 | 0 | 0 | 131 | 0 | 0 | 131 | 0 | 0 | 131
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | RA0049 | Study Archived | NIS of CZP in RA (Greece) | Non Interventional Study - Prospective | Open | Affiliate Greece |  | Affiliate Greece | Mitas G |  | N/A | Qualitis ltd |  |  | adults | No | Open label, prospective, observational, study for the safety and efficacy of Certolizumab Pegol in patients with Rheumatoid Arthritis in everyday routine practice. PHASE IV |  |  |  | 2010-09-30 | 2010-09-28 |  | 2010-12-08 | 2011-04-11 | 2011-06-17 | 2012-01-09 | 2012-06-15 |  | 2012-12-12 |  | 2013-06-11 |  |  |  | 2014-04-04 | Greece | Greece (LPLV) | Greece | 10 | 0 | 0 | 150 | 0 | 0 | 150 | 0 | 0 | 150 | 150 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | RA0053 | CSR Approved | SONAR - NIS of CZP in RA (Spain) | Non Interventional Study - Prospective | Open | Affiliates | Immunology | Affiliates | Cara C, Talavera P | Ionescu L | N/A | RPS Research Iberica S.L.U. | No | No | adults | No | AN OPEN-LABEL, OBSERVATIONAL 12-WEEK STUDY TO ASSESS HEALTH-RELATED QUALITY OF LIFE AND PATIENTREPORTED OUTCOMES IN PATIENTS WITH RHEUMATOID ARTHRITIS TREATED WITH CERTOLIZUMAB PEGOL |  |  |  | 2010-11-13 | 2010-12-13 |  | 2011-01-05 | 2011-08-03 | 2012-01-12 | 2012-03-05 | 2013-10-31 |  | 2014-02-28 |  | 2015-03-20 |  |  |  | 2016-05-26 | Spain | Spain (LPLV) | Spain | 20 | 0 | 0 | 100 | 45 | 0 | 81 | 0 | 0 | 81 | 0 | 0 | 81
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | RA0068 | Study Archived | NIS of CZP in RA re. smoking status | Non Interventional Study - Prospective | Open | GCSO | Immunology | Affiliates | Kleine E, Markus Z | Bonny M, Gorski P | N/A | UCB MSLs | No | No | adults | No | EFFECT OF CIGARETTE SMOKING ON CERTOLIZUMAB PEGOL TREATMENT IN RHEUMATOID ARTHRITIS PATIENTS | Rheumatoid Arthritis | Immunology |  | 2010-09-30 | 2010-09-08 |  | 2010-09-08 | 2010-12-29 | 2011-01-17 | 2011-01-26 | 2013-10-08 |  | 2015-09-10 |  | 2016-02-26 |  |  |  | 2016-08-04 | Czech Republic, Hungary, Slovakia | Czech Republic (LPLV), Hungary (LPLV), Slovakia (LPLV) | Czech Republic, Hungary, Slovakia | 115 | 0 | 0 | 300 | 0 | 0 | 273 | 0 | 0 | 273 | 0 | 113 | 160
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | RA0070 | Study Archived | SWITCH AUT- NIS of CZP in RA | Non Interventional Study - Prospective | Open | GCSO | Immunology | Affiliates | Bollmann J | Beinhauer-Zellenka U | N/A | N/A | No | No | adults | No | A MULTICENTER, OBSERVATIONAL, NONINTERVENTIONAL STUDY TO OBSERVE THE SAFETY AND EFFICACY OF CERTOLIZUMAB PEGOL (CIMZIA®) IN PATIENTS WITH RHEUMATOID ARTHRITIS THAT ARE TNFINHIBITOR NAÏVE OR TNF-INHIBITOR FAILURES OBSERVED IN DAILY PRACTICE IN AUSTRIA AND SWITZERLAND |  |  |  | 2010-10-01 | 2011-01-18 |  | 2011-01-13 | 2011-05-18 | 2011-03-16 | 2011-10-14 | 2013-03-28 |  | 2014-01-27 |  | 2015-03-02 |  |  |  | 2015-07-24 | Austria, Switzerland | Austria (LPLV), Switzerland (LPLV) | Austria, Switzerland | 20 | 0 | 0 | 196 | 196 | 196 | 134 | 0 | 0 | 134 | 0 | 0 | 134
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | RA0090 | Study Archived | ECLAIR - NIS of CZP in RA (France) | Non Interventional Study - Prospective | Not Applicable | GCSO | Immunology | Affiliates | Dubois F | Anderson K | N/A | Mapi |  |  | adults | No | DISEASE OUTCOME IN PATIENTS WITH RHEUMATOID ARTHRITIS (RA) TREATED WITH CIMZIA® IN REAL LIFE IN FRANCE ECLAIR STUDY | Rheumatoid Arthritis | Immunology |  | 2011-01-31 | 2011-06-06 |  | 2011-06-06 | 2012-05-01 | 2011-12-22 | 2013-04-30 | 2013-12-23 |  | 2017-02-28 |  | 2017-09-08 |  |  |  | 2018-04-30 | France | France (LPLV) | France | 250 | 0 | 0 | 750 | 750 | 0 | 792 | 0 | 0 | 792 | 0 | 337 | 455 |  |  | 2014-11-05 | 2014-11-05 |  |  | 2015-07-30
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | RA0105 | Study Archived | Open-label NIS survey for Japanese RA patients | Non Interventional Study - Prospective | Open | Affiliates | Immunology | Affiliates | Tokumasu T | Hosoi K | N/A | Bell Medical Solutions Inc. |  |  | adults | No | Cimzia®200mg Syringe for subcutaneous injection Drug-Use Survey | Osteoarthritis | Immunology | RA0105 is a parent study of RA0106 | 2013-02-28 | 2013-02-28 |  | 2013-02-28 | 2013-03-12 | 2013-03-15 | 2014-09-11 | 2016-09-29 | 2015-03-25 | 2017-03-16 | 2015-09-23 | 2019-03-22 |  |  | 2016-02-17 | 2020-02-27 | Japan | Japan (LPLV) | Japan | 600 | 0 | 0 | 3000 | 3000 | 3000 | 3727 | 0 | 0 | 3727 | 0 | 0 | 3727
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | RA0106 | Study Archived | RA0106 OL multi-centers non-intervational survey for Japane | Non Interventional Study - Prospective |  | Affiliates | Immunology | Affiliates | Tokumasu T | Hosoi K | N/A | Bell Medical Solutions Inc. |  |  | adults | No | Cimzia®200mg Syringe for subcutaneous injection Specified Drug-Use Survey (on Long-Term Use) | Rheumatoid Arthritis | Immunology | RA0106 is an extension of RA0105 | 2013-05-28 |  |  |  |  | 2013-09-09 |  | 2016-03-02 |  | 2018-09-11 |  | 2019-03-22 |  |  |  | 2020-02-27 | Japan | Japan (LPLV) | Japan | 200 | 0 | 0 | 500 | 500 | 500 | 0 | 0 | 0 | 790 | 0 | 34 | 756
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | RA0113 | Study Archived | Retrospective study of Cimzia & other Anti-TNF´s in RA in UK | Non Interventional Study - Retrospective |  | Affiliates - UK | GMA Allergy/Respiratory/Inflam | Global Medical Affairs US | Vandendriessche A | Beaman M | N/A | Oxon |  |  | adults | No | Retrospective Cohort Study of Certolizumab Pegol (Cimzia®) and Other Subcutaneous Anti‐Tumour Necrosis Factor‐Alpha Drugs in Rheumatoid Arthritis to Explore Usage Patterns and Clinical Outcomes in daily clinical practice in the United Kingdom | Indication for Rheumato GI | Immunology |  | 2012-06-14 | 2012-06-14 |  | 2012-09-17 | 2013-03-11 | 2013-03-15 |  |  |  | 2013-10-08 |  | 2013-10-30 |  |  |  | 2014-12-18 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 8 | 0 | 0 | 532 | 532 | 532 | 197 | 0 | 0 | 197 | 0 | 0 | 197
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | RA0121 | Study Archived | SURVEY OF EFFECTIVENESS AND SAFETY (MALIGNANCY AND SERIOUS I | Non Interventional Study - Prospective |  | Affiliates | Immunology | UCB Pharma Global | Tokumasu T | Hosoi K | N/A |  | No | No | adults | No |  | Rheumatoid Arthritis | Immunology |  |  |  |  | 2013-06-19 |  | 2013-03-08 |  | 2013-06-05 |  | 2014-06-04 |  | 2015-05-01 |  |  |  | 2016-10-14 | Japan | Japan (LPLV) | Japan | 40 | 0 | 0 | 347 | 347 | 347 | 342 | 0 | 153 | 189 | 0 | 20 | 169
Yes | Light Support Studies | Managing Type | 1 | CIMZIA | Immunology | UP0038 | Study Archived | HCP&Patient Surveys-Effectiveness eval. of EU RMP Educ Mats | Non Interventional Study - Prospective | Open | GCSO | Immunology | UCB Pharma Global | Qvistorff K |  | N/A | N/A |  |  | adults | No | Healthcare Professional and Patient Surveys to Evaluate the Effectiveness of the Risk Minimisation Educational Materials for Certolizumab Pegol (CZP; CIMZIA®) | Rheumatoid Arthritis | Immunology |  | 2016-05-19 | 2016-07-19 | 2016-06-10 | 2016-07-19 | 2016-07-20 | 2016-08-01 |  |  | 2016-08-31 | 2019-07-31 | 2016-09-01 | 2019-08-01 |  |  | 2016-09-14 | 2019-11-22 | France, Germany, Greece, Norway, Sweden, United Kingdom | France (LPLV), Germany (LPLV), Greece (LPLV), Norway (LPLV), Sweden (LPLV), United Kingdom (LPLV) | France, Germany, Greece, Norway, Sweden, United Kingdom | 0 | 0 | 0 | 0 | 0 | 0 | 421 | 0 | 229 | 192 | 0 | 0 | 192
Yes | Light Support Studies | Managing Type | 1 | EPILEPSY FRANCHISE | Central Nervous System | EP0102 | CSR Approved | EXPLORATORY,NISR RECORD REVIEW IN SUPPORT OF ANTIEPILEPTIC | Non Interventional Study - Retrospective | Not Applicable | GCSO | Neurology | UCB Pharma Global | Bretschneider M | Tillery N |  | N/A |  |  | adults | No | "EXPLORATORY, NONINTERVENTIONAL RETROSPECTIVE RECORD REVIEW IN SUPPORT OF THE DEVELOPMENT OF THE ANTIEPILEPTIC DRUG TREATMENT CLINICAL DECISION SUPPORT TOOL" | Epilepsy | Central Nervous System |  | 2017-11-16 |  | 2017-11-16 | 2017-12-04 | 2018-01-31 | 2018-02-19 | 2018-05-14 | 2018-03-01 | 2018-05-14 | 2018-03-01 | 2018-05-23 | 2018-03-01 |  |  | 2018-08-17 | 2018-04-06 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 0 | 0 | 149 | 0 | 0 | 149
Yes | Light Support Studies | Managing Type | 1 | Fintepla | Central Nervous System | EP0205 | Study Archived | OL to evaluate safety and tolerability (Zogenix 1903) | Phase I |  | GCSO | Neurology | UCB Pharma Global | Schelstraete I | Driver D | N/A |  | No | No |  | No | Ph1, Open-label to evaluate safety, tolerability and PK of Fintepla in subjects with varying degrees of hepactic impairment | Lennox Gastaut Syndrome (LGS) | Central Nervous System |  |  |  |  | 2019-09-27 |  | 2019-12-06 |  |  |  | 2021-10-21 |  | 2022-01-07 |  |  |  | 2022-02-28 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | Fintepla | Central Nervous System | EP0207 | CSR Approved | CBD SAFETY (Zogenix 1602) | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Mccleod O | Wall P | N/A |  | No |  | other | No | An Open-Label Trial to Assess the Safety of ZX008 (Fenfluramine Hydrochloride) Oral Solution in Combination with Cannabidiol, as an Adjunctive Therapy in Children and Young Adults with Dravet Syndrome or Lennox-Gastaut Syndrome | Dravet Syndrome | Central Nervous System | EP0207 is a feeder study of EP0215 |  |  |  | 2017-11-15 | 2018-01-09 | 2018-01-19 |  | 2018-08-27 | 2020-06-24 | 2020-06-24 |  | 2023-08-04 |  |  | 2023-06-30 | 2023-11-21 | United States of America | United States of America (LPLV) | United States of America | 2 | 0 | 0 | 10 | 10 | 0 | 14 | 0 | 4 | 10 | 0 | 1 | 9 | [22 empty] | yes
Yes | Light Support Studies | Managing Type | 1 | INNOVAIR | Immunology | A00437 | CSR Approved | NIS effectiveness INUVAIR adult patients treatment BE | Non Interventional Study - Prospective |  | Affiliates | GMA Allergy/Respiratory/Inflam | Affiliates | Hollanders W | [6 empty] | No | A multicentre 12-month non-inteventional study of the real-life effectiveness of Innuvair in the treatment of adult patients with persistent asthma in Belgium |  |  |  |  | 2008-10-22 |  | 2008-10-17 |  | 2008-12-31 |  | 2009-10-30 |  | 2011-03-24 |  | 2011-03-25 |  |  |  | 2011-04-21 | Belgium | Belgium (LPLV) | Belgium | 100 | 0 | 0 | 624 | 0 | 0 | 619 | 0 | 0 | 619 | 0 | 0 | 619
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | EP0058 | CSR Approved | E Keppra for I.V. infusion 500 mg Drug Use Results Survey in | Non Interventional Study - Retrospective | Open | Affiliates | Neurology | UCB Pharma Global | Tokumasu T | Hosoi K | N/A | N/A | No | No | other | No | E Keppra for I.V. infusion 500 mg Drug Use Results Survey in Japan | Epilepsy | Central Nervous System |  | 2015-10-23 | 2015-10-29 |  | 2015-10-29 | 2015-12-19 | 2015-12-02 | 2019-06-12 | 2018-10-30 | 2018-11-06 | 2018-11-06 | 2019-06-06 | 2019-11-06 |  |  | 2020-02-13 | 2020-04-23 | Japan | Japan (LPLV) | Japan | 350 | 0 | 0 | 280 | 280 | 280 | 2616 | 0 | 0 | 2616 | 0 | 22 | 2594
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | EP0075 | Study Archived | Open-labeled multicenter non-interventional survey of E Kepp | Non Interventional Study - Prospective | Open | Affiliates | Neurology | Affiliates | Tokumasu T | Hosoi K | N/A | N/A | No | No | other | No | E-Keppra tablets 250 mg, E-Keppra tablets 500 mg, E-Keppra dry syrup 50 % Drug Use Result Survey - Monotherapy for partial onset seizure in patient with epilepsy- | Epilepsy | Central Nervous System |  | 2015-04-15 | 2015-03-04 |  | 2015-03-04 | 2015-04-15 | 2015-05-20 | 2016-08-29 | 2016-08-31 | 2017-05-31 | 2017-02-22 | 2018-04-02 | 2018-04-30 |  |  | 2020-10-02 | 2019-06-25 | Japan | Japan (LPLV) | Japan | 350 | 0 | 0 | 500 | 500 | 500 | 653 | 0 | 0 | 653 | 0 | 1 | 652
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | EP0082 | Study Archived | E Keppra Tablets/Dry syrup Drug-use Survey for GTC in Japan | Non Interventional Study - Prospective | Open | Affiliates | Neurology | Affiliates | Tokumasu T | Hosoi K | N/A | N/A | No | No | other | No | E KEPPRA TABLETS 250MG,E KEPPRA TABLETS 500MG,E KEPPRA DRY SYRUP 50% Drug use result survey -Add-on therapy for Generalized Tonic-clonic Seizure in patient with epilepsy- | Epilepsy | Central Nervous System |  | 2015-09-10 | 2016-03-02 |  | 2016-03-02 | 2016-06-01 | 2016-07-06 | 2018-12-06 | 2018-10-31 | 2019-06-20 | 2019-05-15 | 2020-01-03 | 2020-01-22 |  |  | 2020-10-02 | 2020-04-23 | Japan | Japan (LPLV) | Japan | 200 | 0 | 0 | 300 | 300 | 300 | 506 | 0 | 0 | 506 | 0 | 3 | 503
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01283 | Study Archived | Leviteracetam: Long term evaluat.-NIS:BG, RO, CZ, HU and SK | Non Interventional Study - Prospective | Open | Affiliates | GMA Neurology / Psychiatry | Affiliates | Baukens C | Tillery N | N/A | N/A | No | No | other | No | Long-term evaluation of the efficacy and safety of levetiracetam in routine clinical practice in Bulgaria, Czech and Slovak Republics, Hungary and Romania - non-interventional study. | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-04-11 | 2006-12-14 |  | 2006-12-14 | 2007-04-19 | 2007-03-01 | 2009-10-01 |  |  | 2009-06-30 |  | 2010-12-31 |  |  |  | 2015-12-18 | Czech Republic, Hungary, Romania, Slovakia | Czech Republic (LPLV), Hungary (LPLV), Romania (LPLV), Slovakia (LPLV) | Czech Republic, Hungary, Romania, Slovakia | 0 | 0 | 0 | 3500 | 0 | 0 | 2569 | 0 | 0 | 2569 | 2569 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01319 | CSR Approved | Efficacité et Utilisation du LEV en vie réelle - EULEVp | Non Interventional Study - Prospective |  | Affiliates |  | Affiliates | [7 empty] | No | Efficacité et Utilisation du Lévétiracétam En Vie réelle en Pédiatrie | [8 empty] | 2006-10-01 |  |  |  | 2008-03-31 | [5 empty] | 2008-12-22 | France | France (LPLV) | France | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01320 | CSR Approved | LVTM in the trt. of ped. epilepsy:impact on cognition QoLMul | Non Interventional Study - Prospective |  | Affiliates | Neurology | Affiliates | [7 empty] | No | [7 empty] | 2007-10-01 |  | 2007-12-01 |  |  |  | 2009-03-24 | [5 empty] | 2009-06-15 | Taiwan | Taiwan (LPLV) | Taiwan | 6 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01321 | CSR Approved | Patients Perception of Value of LVTM & Impact on Qol & cogn | Non Interventional Study - Prospective |  | Affiliates |  | Affiliates | Lin D | [6 empty] | No | [9 empty] | 2006-07-12 |  |  |  | 2007-12-25 | [5 empty] | 2008-12-17 | Taiwan | Taiwan (LPLV) | Taiwan | 3 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01322 | CSR Approved | Post Marketing Surveillance on Keppra® | Non Interventional Study - Prospective | Open | Affiliates |  | Affiliates | Kim S | [6 empty] | No | Post Marketing Surveillance on Keppra® |  |  |  | 2006-08-10 | 2006-08-10 |  | 2006-10-19 | 2007-04-01 | 2007-12-05 |  | 2009-10-01 |  | 2010-02-13 |  | 2011-07-29 |  |  |  | 2013-06-25 | South Korea | South Korea (LPLV) | South Korea | 140 | 0 | 0 | 10000 | 6000 | 0 | 6000 | 0 | 0 | 6000 | 6000 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01323 | CSR Approved | Efficacité et Utilisation du LEV en vie réelle - EULEV | Non Interventional Study - Prospective |  | Affiliates |  | Affiliates | [7 empty] | No | Efficacité et Utilisation du Lévétiracétam En Vie réelle | [8 empty] | 2005-01-01 |  |  |  | 2007-08-31 | [5 empty] | 2008-12-22 | France | France (LPLV) | France | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01324 | Study Archived | NI Obs. study Keppra® concentrate in clinical practice | Non Interventional Study - Prospective | Open | Affiliates |  | Affiliates | Hummel F | [6 empty] | No | Non interventional observational study Keppra® concentrate in clinical practice |  |  |  | 2005-12-12 | 2005-12-12 |  | 2006-05-04 |  | 2006-07-01 |  | 2006-07-29 |  | 2008-06-18 | [5 empty] | 2011-07-30 | Germany | Germany (LPLV) | Germany | 75 | 0 | 0 | 500 | 236 | 0 | 236 | 0 | 0 | 236 | 236 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01325 | CSR Approved | Real Life OS Compar. of Keppra with carbamazepine in monoth | Non Interventional Study - Prospective |  | Affiliates |  | Affiliates | Berkels R, Hummel F | [6 empty] | No | Real Life observational study - Comparison of Keppra® with carbamazepine in monotherapy |  |  |  | 2006-03-27 | 2006-03-27 |  | 2006-09-24 | 2006-10-16 | 2006-10-16 |  |  |  | 2008-12-30 | [5 empty] | 2010-04-09 | Germany | Germany (LPLV) | Germany | 0 | 0 | 0 | 1000 | 992 | 992 | 997 | 0 | 0 | 997 | 997 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01341 | Study Archived | Keppra in patients of 65 years or older: a non-interventiona | Non Interventional Study - Prospective | Open | Affiliates | GMA Neurology / Psychiatry | Affiliates | Berkels R | [6 empty] | No |  |  |  |  | 2002-12-26 | 2002-12-26 |  | 2003-06-15 |  | 2003-07-17 |  | 2004-01-15 |  | 2005-05-31 | [5 empty] | 2011-10-21 | Germany | Germany (LPLV) | Germany | 40 | 0 | 0 | 389 | 0 | 0 | 389 | 0 | 0 | 389 | 389 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01342 | Study Archived | Keppra use over 12 months as add-on: a non-interventional st | Non Interventional Study - Prospective | Open | Affiliates | GMA Neurology / Psychiatry | Affiliates | Berkels R, Hummel F | [6 empty] | No |  |  |  |  | 2003-05-12 | 2003-05-12 |  | 2003-09-25 |  | 2003-11-29 |  | 2003-12-27 |  | 2005-09-30 | [5 empty] | 2011-10-24 | Germany | Germany (LPLV) | Germany | 40 | 0 | 0 | 1100 | 1087 | 1078 | 1078 | 0 | 0 | 1078 | 1078 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01356 | CSR Approved | PMS for Keppra concentrate for solution for infusion | Non Interventional Study - Prospective | Open | Affiliates | GMA Neurology / Psychiatry | Affiliates | Park M | Matsuoka K | N/A | N/A | No | No | adults | No | POST MARKETING SURVEILLANCE FOR KEPPRA® (LEVETIRACETAM) CONCENTRATE FOR SOLUTION FOR INFUSION | Epilepsy | Central Nervous System |  | 2008-12-24 | 2009-09-11 |  | 2010-03-24 | 2010-06-25 | 2010-06-25 | 2014-04-28 | 2014-02-24 |  | 2014-03-12 |  | 2014-08-13 |  |  |  | 2015-02-13 | South Korea | South Korea (LPLV) | South Korea | 50 | 0 | 0 | 600 | 600 | 600 | 627 | 0 | 0 | 627 | 0 | 0 | 627
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01387 | Study Archived | Drug use result survey | Non Interventional Study - Prospective | Open | Affiliates | Neurology | Affiliates | Bouchard S, Tokumasu T | Hosoi K | N/A | N/A |  |  | adults | No | E Keppra® Tablets 250mg, E Keppra® Tablets 500mg Drug Use Results Survey | Epilepsy | Central Nervous System |  | 2010-10-15 | 2010-08-13 |  | 2010-08-13 | 2011-05-07 | 2011-05-06 | 2015-09-30 | 2016-03-31 | 2016-07-22 | 2016-07-21 | 2017-12-01 | 2017-12-01 |  |  | 2019-06-03 | 2019-08-13 | Japan | Japan (LPLV) | Japan | 600 | 0 | 0 | 4000 | 0 | 0 | 4337 | 0 | 0 | 4337 | 0 | 8 | 4329
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01388 | Study Archived | QOL Special Survey | Non Interventional Study - Prospective | Open | Affiliates | Neurology | Affiliates | Tokumasu T | Hosoi K | N/A | N/A |  |  | adults | No | "E Keppra® Tablets 250mg, E Keppra® Tablets 500mg Specified Drug Use Survey -Investigation on QOL, Safety and Efficacy of Add-on Levetiracetam in Patients who Developed Epilepsy at Age 50 or Older-" | Epilepsy | Central Nervous System |  | 2010-11-18 | 2010-11-18 |  | 2010-08-13 | 2011-02-28 | 2011-02-03 | 2012-12-31 | 2012-12-29 |  | 2013-06-22 |  | 2014-02-07 |  |  |  | 2015-01-05 | Japan | Japan (LPLV) | Japan | 200 | 0 | 0 | 80 | 0 | 0 | 116 | 0 | 0 | 116 | 0 | 0 | 116
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01389 | Study Archived | Add-on to mono special survey | Non Interventional Study - Prospective | Open | Affiliates | Neurology | Affiliates | Tokumasu T | Hosoi K | N/A | N/A |  |  | adults | No | E Keppra® Tablets 250mg, E Keppra® Tablets 500mg Specified Drug Use Survey －Efficacy and safety of add-on Levetiracetam in patients receiving antiepileptic monotherapy－ | Epilepsy | Central Nervous System |  | 2010-11-18 | 2010-08-13 |  | 2010-08-13 | 2011-02-05 | 2011-02-04 | 2012-12-27 | 2012-12-27 |  | 2013-06-20 |  | 2014-02-07 |  |  |  | 2015-01-05 | Japan | Japan (LPLV) | Japan | 300 | 0 | 0 | 300 | 0 | 0 | 307 | 0 | 0 | 307 | 0 | 0 | 307
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01390 | Study Archived | Drug use result survey (Long Term) | Non Interventional Study - Prospective | Open | Affiliates | Neurology | Affiliates | Bouchard S, Tokumasu T | Hosoi K | N/A | N/A |  |  | adults | No | E Keppra® Tablets 250mg, E Keppra® Tablets 500mg Specified Drug Use Survey (on Long-term Use) | Epilepsy | Central Nervous System |  | 2010-10-15 | 2010-08-13 |  | 2010-08-13 | 2011-05-23 | 2011-05-22 | 2016-02-01 | 2016-08-05 | 2018-03-01 | 2018-02-28 | 2019-05-22 | 2019-08-13 |  |  | 2019-09-17 | 2019-08-13 | Japan | Japan (LPLV) | Japan | 300 | 0 | 0 | 300 | 0 | 0 | 946 | 0 | 0 | 946 | 0 | 9 | 937
Yes | Light Support Studies | Managing Type | 1 | KEPPRA | Central Nervous System | N01398 | Study Archived | Open Label Safety Study of E-Keppra for POS | Non Interventional Study - Prospective | Open | Affiliates | Neurology | Affiliates | Tokumasu T | Hosoi K | N/A | N/A |  |  | adults | No | E Keppra® Tablets 250mg, E Keppra® Tablets 500mg Specified Drug Use Survey at Shizuoka Epilepsy Center | Epilepsy | Central Nervous System |  | 2010-11-18 | 2010-08-13 |  | 2010-08-13 | 2011-03-22 | 2010-09-24 | 2012-10-31 | 2011-10-04 |  | 2012-03-20 |  | 2014-05-14 |  |  |  | 2015-01-05 | Japan | Japan (LPLV) | Japan | 0 | 0 | 0 | 300 | 0 | 0 | 300 | 0 | 0 | 300 | 0 | 0 | 300
Yes | Light Support Studies | Managing Type | 1 | Metadate/Equasym | Central Nervous System | C10311 | CSR Approved | Equasym Post marketing study in ADHS | Non Interventional Study - Prospective |  | Affiliates |  | Affiliates | Haeck H | [6 empty] | No |  |  |  |  | 2005-12-01 | 2006-10-26 |  | 2006-08-31 | 2006-12-21 | 2006-11-01 |  |  |  | 2007-08-01 | [5 empty] | 2010-06-30 | Germany | Germany (LPLV) | Germany | 40 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | NEUPRO | Central Nervous System | PD0009 | Study Archived | SWITCHING FROM PRAMIPEXOLE OR ROPINIROLE TO THE ROTIGOTINE | Phase IV | Open | Clinical Development Europe | CNS | Clinical Development Europe | Thierfelder S | Driver D | N/A | Quintiles |  |  | adults | No | AN OPEN-LABEL, MULTICENTER, MULTINATIONAL STUDY TO ASSESS THE FEASIBILITY OF SWITCHING THERAPY FROM PRAMIPEXOLE OR ROPINIROLE TO THE ROTIGOTINE TRANSDERMAL SYSTEM AND ITS EFFECT ON MOTOR AND NON-MOTOR SYMPTOMS IN SUBJECTS WITH ADVANCED IDIOPATHIC PARKINSON’S DISEASE | Parkinson's disease (advanced) | Central Nervous System |  | 2012-04-03 |  |  | 2012-06-14 | 2012-09-24 | 2012-09-25 | 2012-11-27 | 2013-01-15 |  | 2013-03-27 |  | 2013-05-16 |  |  |  | 2013-12-20 | Malaysia, Singapore, South Korea, Taiwan, United States of America | Malaysia (LPLV), Singapore (LPLV), South Korea (LPLV), Taiwan (LPLV), United States of America (LPLV) | Malaysia, Singapore, South Korea, Taiwan, United States of America | 30 | 0 | 0 | 60 | 60 | 60 | 111 | 0 | 0 | 111 | 111 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | NEUPRO | Central Nervous System | PD0015 | Study Archived | Investigate Safety and efficiacy of rotigotine add-on therap | Phase III | Open | Clinical Development Europe | CNS | Clinical Development Europe | Thierfelder S | Driver D | N/A | EPS |  |  | adults | No | An open-label study to investigate the safety and the efficacy of rotigotine add-on therapy with low doses of pramipexole or ropinirole in patients with advanced Parkinson’s disease. | Parkinson's disease (advanced) | Central Nervous System |  | 2012-04-25 |  |  | 2012-06-01 |  | 2012-09-25 |  | 2013-01-15 |  | 2013-04-18 |  | 2013-05-22 |  |  |  | 2013-12-20 | Australia, Malaysia, Singapore, South Korea, Taiwan | Australia (LPLV), Malaysia (LPLV), Singapore (LPLV), South Korea (LPLV), Taiwan (LPLV) | Australia, Malaysia, Singapore, South Korea, Taiwan | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 112 | 112 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | NEUPRO | Central Nervous System | RL0001 | Study Archived | Post Marketing Surveillance for Restless Leg Syndrome | Non Interventional Study - Prospective | Open | GCSO | Neurology | Affiliates | Namgoong K | Beinhauer-Zellenka U | N/A | N/A |  |  | adults | No | Post-Marketing Surveillance for Neupro® Transdermal Patch (Rotigotine) in Patients with Moderate-to-Severe Idiopathic Restless Legs Syndrome | Restless legs syndrome | Central Nervous System |  | 2011-04-16 | 2011-04-16 |  | 2011-04-16 | 2013-09-28 | 2013-12-23 | 2015-03-28 | 2016-01-21 |  | 2016-04-14 |  | 2016-09-06 |  |  |  | 2016-12-12 | South Korea | South Korea (LPLV) | South Korea | 50 | 0 | 0 | 600 | 600 | 600 | 162 | 0 | 0 | 162 | 0 | 0 | 162
Yes | Light Support Studies | Managing Type | 1 | NEUPRO | Central Nervous System | SP0948 | Study Archived | RLS-PRACTISE - NIS of RTG in RLS (Germany) | Non Interventional Study - Prospective | Open | Affiliates - Germany | GMA Neurology / Psychiatry | Affiliates - Germany | Berkels R | [6 empty] | No | RLS-Practise: Non Interventional Study (NIS) in Patients with Restless Legs Syndrome (RLS) to Assess the Effectiveness and Safety of Neupro® in Daily Practise |  |  |  | 2009-04-09 | 2010-01-25 |  | 2010-02-25 |  | 2010-05-04 |  | 2011-03-21 |  | 2011-07-09 |  | 2011-07-13 |  |  |  | 2012-06-29 | Germany | Germany (LPLV) | Germany | 140 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | NEUPRO | Central Nervous System | SP0990 | Study Archived | ICARUS - NIS of RTG and other Tx in PD re. ICD (Italy) | Non Interventional Study - Prospective | Open | Affiliates | Neurology | Affiliates | Annoni K | Alcazar J | N/A | Hippocrates Research srl | No | No | adults | No | A PROSPECTIVE NON-INTERVENTIONAL STUDY ON THE PREVALENCE AND INCIDENCE OF IMPULSE CONTROL DISORDERS AND THE ASSOCIATION OF NEUROPSYCHIATRIC SYMPTOMS, COGNITION AND QUALITY OF LIFE IN PARKINSON DISEASE | Parkinson's disease | Central Nervous System |  | 2010-05-05 | 2010-04-01 |  | 2010-06-03 | 2010-12-30 | 2011-01-31 | 2011-12-30 | 2012-02-01 |  | 2014-02-03 |  | 2014-08-07 |  |  |  | 2016-01-11 | Italy | Italy (LPLV) | Italy | 50 | 0 | 0 | 1000 | 1000 | 1000 | 1091 | 0 | 0 | 1091 | 0 | 0 | 1091
Yes | Light Support Studies | Managing Type | 1 | NEUPRO | Central Nervous System | SP1013 | Study Archived | Post Marketing Surveillance for Parkinson's disease | Non Interventional Study - Prospective | Open | GCSO | Neurology | Affiliates | Namgoong K | Beinhauer-Zellenka U | N/A | N/A |  |  | adults | No | Post-Marketing Surveillance for Neupro® Transdermal Patch (Rotigotine) in Patients with Idiopathic Parkinson’s Disease | Parkinson's disease | Central Nervous System |  | 2011-04-14 | 2011-04-13 |  | 2011-04-13 | 2013-02-04 | 2013-01-08 | 2015-03-28 | 2016-01-18 |  | 2016-05-03 |  | 2016-09-06 |  |  |  | 2016-12-12 | South Korea | South Korea (LPLV) | South Korea | 50 | 0 | 0 | 600 | 600 | 600 | 221 | 0 | 0 | 221 | 0 | 0 | 221
Yes | Light Support Studies | Managing Type | 1 | NEUPRO | Central Nervous System | SP1018 | Study Archived | Non-interventional, retrospective, post-marketing study. | Non Interventional Study - Retrospective | Open | Affiliates - Spain | CNS | Affiliates - Spain | Alcazar J, Whitesides J |  | N/A | Pivotal |  |  | adults | No | NON-INTERVENTIONAL, RETROSPECTIVE, MULTI-CENTER STUDY TO EVALUATE NON-MOTOR SYMPTOMS IN ADVANCED PD PATIENTS ALREADY TREATED WITH ROTIGOTINE |  |  |  | 2011-02-21 | 2011-02-21 |  | 2011-03-07 |  | 2011-09-05 |  | 2012-12-04 |  | 2012-12-12 |  | 2013-04-11 |  |  |  | 2013-12-11 | Spain | Spain (LPLV) | Spain | 80 | 0 | 0 | 400 | 390 | 390 | 391 | 0 | 0 | 391 | 391 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | NOOTROPIL | Central Nervous System | N01318 | CSR Approved | Outline of Drug Use Investigation for MYOCALM Solution (Pira | Phase IV |  | Affiliates |  | Affiliates | Tokumasu T | Hosoi K | [5 empty] | No |  |  |  |  | 1999-07-27 | 1999-07-27 |  | 1999-07-27 | 1999-09-22 | 1999-09-22 |  |  |  | 2009-02-20 |  | 2009-08-31 |  |  |  | 2009-12-17 | Japan | Japan (LPLV) | Japan | 0 | 0 | 0 | 1000 | 0 | 0 | 502 | 0 | 0 | 502 | 502 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | Tefidera | not defined | MS0008 | LPLV (Stopped) | Tecfidera Post Marketing Surveillance | Non Interventional Study - Prospective | Open | GCSO | Neurology | Affiliates | Namgoong K | Beinhauer-Zellenka U | N/A | N/A | No | No | adults | No | POST MARKETING SURVEILLANCE STUDY FOR TECFIDERA (DIMETHYL FUMARATE) CAPSULES IN KOREAN PATIENTS WITH RELAPSING-REMITTING MULTIPLE SCLEROSIS | Multiple sclerosis | Central Nervous System |  | 2016-04-01 | 2016-04-01 |  | 2016-04-01 | 2016-12-20 | 2017-06-27 | 2019-12-31 | 2017-12-26 |  | 2017-12-26 | [6 empty] | South Korea | South Korea (LPLV) | South Korea | 10 | 0 | 0 | 150 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | VIMPAT | Central Nervous System | EP0015 | LPLV | Named Patient Program (NPP) | Named Patient Program | Open | Affiliates | GMA Neurology / Psychiatry | UCB Pharma Global |  |  | N/A | NA |  |  | other | No | NAMED PATIENT PROGRAM WITH VIMPAT® (LACOSAMIDE) AS ADJUNCTIVE THERAPY IN THE TREATMENT OF PARTIAL-ONSET SEIZURES WITH OR WITHOUT SECONDARY GENERALIZATION IN PATIENTS WITH EPILEPSY | Epilepsy | Central Nervous System |  |  |  |  | 2011-09-08 |  | 2011-02-15 |  | 2012-04-10 |  | 2012-12-30 | [6 empty] | Austria, Belgium, Finland, France, Germany, Ireland, Spain, Sweden, United Kingdom | Austria (LPLV), Belgium (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Ireland (LPLV), Spain (LPLV), Sweden (LPLV), United Kingdom (LPLV) | Austria, Belgium, Finland, France, Germany, Ireland, Spain, Sweden, United Kingdom | 0 | 0 | 0 | 250 | 250 | 250 | 124 | 0 | 0 | 124 | 0 | 124 | 0
Yes | Light Support Studies | Managing Type | 1 | VIMPAT | Central Nervous System | EP0033 | Database Locked | Vimpat 10 mg/ml Medical Need Program | Named Patient Program | Open | Global Medical Affairs Europe | GMA Neurology / Psychiatry | Affiliates | Van Woensel R | Leffers K | N/A | N/A |  |  | adults | No | EP0033 - Medical Need Program for Individual Patient Supply of VIMPAT® 10 mg/ml syrup for adjunctive therapy in the treatment of partial-onset seizures with or without generalisation in patients with epilepsy aged 16 years and older | Epilepsy | Central Nervous System |  |  | 2012-06-06 |  | 2012-06-06 | 2012-06-08 | 2012-07-01 | 2013-08-01 | 2013-07-01 |  | 2013-07-01 |  | 2013-07-01 |  |  |  |  | Belgium | Belgium (LPLV) | Belgium | 10 | 0 | 0 | 30 | 30 | 30 | 15 | 0 | 0 | 15 | 0 | 2 | 13
Yes | Light Support Studies | Managing Type | 1 | VIMPAT | Central Nervous System | EP0090 | CSR Approved | Vimpat Tablets Drug-use Survey for POS Mono-Therapy in Japan | Non Interventional Study - Prospective | Open | Affiliates | Neurology | Affiliates | Tokumasu T | Hosoi K | N/A | N/A | No | No | adults | No | Vimpat Tablets 50mg, Vimpat Tablets100mg Drug Use Results Survey - Monotherapy for partial onset seizure in patient with epilepsy- | Epilepsy | Central Nervous System |  | 2017-06-01 08:00 | 2017-06-01 |  | 2017-09-26 | 2018-01-29 | 2018-01-11 | 2020-01-28 | 2020-03-30 | 2020-08-11 | 2020-09-28 | 2021-01-07 | 2021-09-01 |  |  | 2021-08-02 | 2021-12-15 | Japan | Japan (LPLV) | Japan | 50 | 0 | 0 | 100 | 100 | 100 | 291 | 0 | 0 | 291 | 0 | 0 | 291
Yes | Light Support Studies | Managing Type | 1 | VIMPAT | Central Nervous System | EP0126 | CSR Approved | GENERAL DRUG USE-RESULTS SURVEY | Non Interventional Study - Prospective | Not Applicable | Real World Evidence | Neurology | UCB Pharma Global | Tokumasu T | Hosoi K | N/A | N/A | No | No | adults | No | Vimpat IV 100mg, 200mg General Drug Use Results Survey | Epilepsy | Central Nervous System |  |  |  | 2019-02-20 | 2019-02-20 | 2019-10-18 | 2019-10-18 | 2022-05-25 | 2022-05-25 | 2022-05-25 | 2022-05-25 |  |  |  |  | 2023-10-02 | 2023-10-23 | Japan | Japan (LPLV) | Japan | 50 | 0 | 0 | 100 | 100 | 100 | 142 | 0 | 0 | 142 | 0 | 0 | 142
Yes | Light Support Studies | Managing Type | 1 | VIMPAT | Central Nervous System | EP0130 | CSR Approved | SPECIFIED DRUG USE-RESULTS SURVEY | Non Interventional Study - Prospective | Open | Real World Evidence | Neurology | UCB Pharma Global | Tokumasu T | Hosoi K | N/A | N/A | No | No | paediatrics | No | VIMPAT® TABLETS 50MG, VIMPAT® TABLETS 100MG VIMPAT® DRY SYRUP 10% SPECIFIED DRUG USE-RESULTS SURVEY -MONOTHERAPY FOR PARTIAL ONSET SEIZURES IN PEDIATRIC PATIENTS WITH EPILEPSY | Epilepsy | Central Nervous System |  |  |  | 2019-02-20 | 2019-02-20 | 2019-08-30 | 2019-08-16 | 2023-04-03 | 2021-12-23 | 2023-09-29 | 2022-07-13 | 2024-04-02 | 2023-07-03 |  |  | 2024-08-01 | 2023-10-23 | Japan | Japan (LPLV) | Japan | 75 | 0 | 0 | 150 | 150 | 150 | 204 | 0 | 0 | 204 | 0 | 10 | 194
Yes | Light Support Studies | Managing Type | 1 | VIMPAT | Central Nervous System | EP0167 | CSR Approved | J-PMS: PGTCS in PEDIATRIC | Non Interventional Study - Prospective | Open | Real World Evidence | Neurology |  | Karino T, Tokumasu T | Hosoi K | N/A | N/A | No | No | paediatrics | No | VIMPAT TABLETS 50 MG, VIMPAT TABLETS 100 MG, VIMPAT DRY SYRUP 10% SPECIFIED DRUG USE-RESULTS SURVEILLANCE STUDY - SURVEILLANCE STUDY ON PEDIATRIC EPILEPTIC PATIENTS WITH PRIMARY GENERALIZED TONIC-CLONIC SEIZURES | Epilepsy | Central Nervous System |  | 2020-10-08 08:00 | 2020-10-08 |  | 2021-01-07 | 2021-04-01 | 2021-06-07 | 2023-06-19 | 2023-10-17 | 2024-01-01 | 2024-04-19 | 2024-07-02 | 2024-08-09 |  |  | 2024-12-31 | 2024-11-22 | Japan | Japan (LPLV) | Japan | 50 | 0 | 0 | 135 | 135 | 100 | 89 | 0 | 0 | 89 | 0 | 0 | 89
Yes | Light Support Studies | Managing Type | 1 | VIMPAT | Central Nervous System | EP0168 | CSR Approved | J-PMS: PGTCS treated with I.V. infusion | Non Interventional Study - Prospective | Open | Real World Evidence | Neurology |  | Karino T, Tokumasu T | Hosoi K | N/A | N/A | No | No | adults | No | VIMPAT I.V. INFUSION 100 MG, VIMPAT I.V. INFUSION 200 MG GENERAL DRUG USE-RESULTS SURVEILLANCE STUDY - SURVEILLANCE STUDY ON PRIMARY GENERALIZED TONIC-CLONIC SEIZURES - | Epilepsy | Central Nervous System |  | 2020-10-08 08:00 | 2020-10-08 | 2021-01-01 | 2021-01-18 | 2021-04-13 | 2021-12-18 | 2024-05-21 | 2023-12-25 |  | 2023-12-27 | 2025-01-29 | 2024-08-09 |  |  | 2025-03-04 | 2024-11-22 | Japan | Japan (LPLV) | Japan | 10 | 0 | 0 | 25 | 25 | 20 | 27 | 0 | 0 | 27 | 0 | 0 | 27
Yes | Light Support Studies | Managing Type | 1 | VIMPAT | Central Nervous System | SP0973 | CSR Approved | VITOBA - NIS of LCM as single add-on in POS (Germany) | Non Interventional Study - Prospective | Open | Affiliates - Germany | CNS | UCB Pharma Global | Noack-Rink M | Janssen E | N/A | Acromion |  |  | adults | No | A non-interventional post-marketing study, evaluating seizure control and tolerability of Vimpat® as adjunctive therapy to one baseline antiepileptic drug in epilepsy patients with partial-onset seizures with or without secondary generalization in daily clinical practice in Germany VITOBA Study (VImpaT added to One Baseline AED) |  |  |  | 2009-08-10 | 2009-10-16 |  | 2010-02-10 | 2010-06-23 | 2010-03-31 | 2011-06-23 | 2012-12-31 |  | 2013-07-19 |  | 2013-12-09 |  |  |  | 2014-07-10 | Germany | Germany (LPLV) | Germany | 158 | 0 | 0 | 600 | 154 | 0 | 573 | 0 | 0 | 573 | 573 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | VIMPAT | Central Nervous System | SP0985 | CSR Approved | Local Retro. Study to eval impact of VIMPAT for pat epil POS | Non Interventional Study - Retrospective |  | UCB Pharma Global |  | UCB Pharma Global | Coulbaut S | [6 empty] | No |  |  |  |  | 2008-03-12 |  |  |  |  | 2008-10-01 |  |  |  | 2009-04-30 | [5 empty] | 2009-10-30 | France | France (LPLV) | France | 30 | 0 | 0 | 300 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | VIMPAT | Central Nervous System | SP0992 | CSR Approved | PROMETEO - NIS of LCM as single add-on in POS (Italy) | Non Interventional Study - Prospective | Open | Affiliates | Neurology | Affiliates | Ferro B | Leffers K | N/A | Hippocrates Research srl | No | No | adults | No | A Prospective Observational study to assess the treatMent Effect after introduction of a different AED in paTients with partial Epilepsy fulfilling the 2010 ILAE criteria Of drug resistant epilepsy | Epilepsy | Central Nervous System |  | 2010-04-09 | 2010-09-22 |  | 2010-11-22 | 2011-02-15 | 2011-03-31 | 2012-01-16 | 2012-12-03 |  | 2015-04-21 |  | 2015-08-07 |  |  | 2016-10-03 | 2016-11-03 | Italy | Italy (LPLV) | Italy | 43 | 0 | 0 | 1082 | 1082 | 1082 | 1090 | 0 | 0 | 1090 | 0 | 0 | 1090
Yes | Light Support Studies | Managing Type | 1 | VIMPAT | Central Nervous System | SP1022 | Study Archived | NIS of LCM in POS | Non Interventional Study - Prospective | Open | GCSO | Neurology | Affiliates | Schmidt A | Grose-Hodge R | N/A | UCB: The monitoring is taken in charge by the Medical department, Czech republic. | No | No | other | No | OPEN-LABEL, PROSPECTIVE, NON-INTERVENTIONAL MULTICENTER STUDY TO EVALUATE EFFICACY AND SAFETY OF ADJUNCTIVE VIMPAT® IN PATIENTS WITH PARTIAL-ONSET SEIZURES IN ROUTINE CLINICAL PRACTICE IN THE CZECH REPUBLIC AND HUNGARY | Epilepsy | Central Nervous System |  | 2011-06-03 | 2011-05-17 |  | 2011-05-17 | 2011-09-15 | 2011-10-24 | 2012-09-13 | 2013-07-28 |  | 2014-07-30 |  | 2015-07-28 |  |  |  | 2016-04-06 | Czech Republic, Hungary | Czech Republic (LPLV), Hungary (LPLV) | Czech Republic, Hungary | 60 | 0 | 0 | 300 | 300 | 0 | 348 | 0 | 0 | 348 | 0 | 46 | 302
Yes | Light Support Studies | Managing Type | 1 | VIMPAT | Central Nervous System | SP1040 | Study Archived | VIMPAT Tablet and Syrup Post Marketing Surveillance | Non Interventional Study - Prospective | Open | GCSO | Neurology | Affiliates | Yoon J |  | N/A | N/A | No | No | adults | No | POST MARKETING SURVEILLANCE STUDY FOR VIMPAT® (LACOSAMIDE) TABLET/ SYRUP IN KOREAN SUBJECTS | Epilepsy | Central Nervous System |  | 2011-08-31 | 2011-08-31 |  | 2012-02-07 | 2013-03-01 | 2013-01-25 | 2015-03-17 | 2016-06-27 |  | 2016-07-28 |  | 2016-09-02 |  |  |  | 2016-11-02 | South Korea | South Korea (LPLV) | South Korea | 50 | 0 | 0 | 3300 | 3300 | 3000 | 388 | 0 | 0 | 388 | 0 | 83 | 305
Yes | Light Support Studies | Managing Type | 1 | XYREM | Central Nervous System | C00304 | CSR Approved | Registry NIS of Xyrem (France) | Registry | Open | Affiliates | Neurology | Affiliates | Le Lievre L |  | N/A | N/A |  |  | adults | No | Pharmacovigilence Plan | Cataplexy | Immunology |  |  | 2005-10-19 |  | 2005-10-19 | 2006-10-12 | 2006-10-12 | 2006-11-09 | 2021-01-26 | 2021-01-01 | 2021-01-26 |  |  |  |  | 2022-01-14 | 2021-12-09 | France | France (LPLV) | France | 0 | 0 | 0 | 709 | 709 | 709 | 1495 | 0 | 0 | 1495 | 0 | 0 | 1495
Yes | Light Support Studies | Managing Type | 1 | XYREM | Central Nervous System | C00305 | LPLV | Xyrem MNP | Named Patient Program | Open | UCB Pharma Global | GMA Neurology / Psychiatry | UCB Pharma Global | Dedeken P | Laranjo S | N/A | UCB |  |  |  | No | Sodium Oxybate Medical Need Program - Belgium | [6 empty] | 2007-03-14 | 2008-04-04 | 2007-07-04 |  |  |  | 2012-03-23 | [6 empty] | Belgium | Belgium (LPLV) | Belgium | 10 | 0 | 0 | 49 | 2 | 0 | 49 | 0 | 0 | 49 | 0 | 49 | 0
Yes | Light Support Studies | Managing Type | 1 | XYREM | Central Nervous System | NA0001 | Study Archived | Effectiveness assessment protocol of educational materials | Non Interventional Study - Prospective | Open | Epidemiology | NewMeds | Epidemiology | Qvistorff K |  | N/A | N/A | No | No | adults | No | XYREM EU-RMP: Effectiveness Assessment Protocol of Educational Materials | Indication for Neuro Psychiatry | Central Nervous System |  | 2015-12-08 | 2015-12-01 |  | 2015-12-01 | 2016-04-01 | 2016-04-01 | 2016-10-01 | 2018-04-14 |  | 2018-04-14 |  | 2018-05-01 |  |  |  | 2018-10-12 | Belgium, Germany, Italy, Spain, Sweden, United Kingdom | Belgium (LPLV), Germany (LPLV), Italy (LPLV), Spain (LPLV), Sweden (LPLV), United Kingdom (LPLV) | Belgium, Germany, Italy, Spain, Sweden, United Kingdom | 0 | 0 | 0 | 200 | 200 | 200 | 113 | 71 | 0 | 42 | 0 | 4 | 38
Yes | Light Support Studies | Managing Type | 1 | XYZAL | Immunology | A00421 | CSR Approved | NIS:Safety and treatment satisfation w/ Xyzal; CZ and SK Rep | Non Interventional Study - Prospective |  | Affiliates |  | Affiliates | Prikrylova K | [6 empty] | No | Long-term evaluation of safety and treatment satisfaction with levocetirizine in routine clinical practice in the Czech and Slovak Republics - non-interventional study |  |  |  | 2007-02-14 | 2006-12-08 |  | 2007-06-15 |  | 2007-09-05 |  |  |  | 2008-09-18 | [5 empty] | 2009-12-16 | Czech Republic, Slovakia | Czech Republic (LPLV), Slovakia (LPLV) | Czech Republic, Slovakia | 0 | 0 | 0 | 9000 | 0 | 0 | 7420 | 0 | 0 | 7420 | 0 | 0 | 7420
Yes | Light Support Studies | Managing Type | 1 | XYZAL | Immunology | A00425 | CSR Approved | NIS:Evaluates treatmt on QoL w/dermatitis w/pruritus symptom | Non Interventional Study - Prospective |  | Affiliates |  | Affiliates | Kang H, Kim J | [6 empty] | No | Evaluation of treatment on the quality of life of patients with dermatitis with pruritus symptoms |  |  |  |  | 2007-05-14 |  |  |  | 2007-04-16 |  |  |  | 2008-12-01 | [5 empty] | 2010-02-11 | South Korea | South Korea (LPLV) | South Korea | 80 | 0 | 0 | 1500 | 1477 | 1477 | 1477 | 0 | 0 | 1477 | 0 | 0 | 1477
Yes | Light Support Studies | Managing Type | 1 | XYZAL | Immunology | A00435 | CSR Approved | Eval of trt. Satisfaction in patient suffering ALLERGIC RHIN | Non Interventional Study - Prospective |  | Affiliates |  | Affiliates | Kang H, Lee S | [6 empty] | No | Evaluation of the Treatment Satisfaction in patient suffering from ALLERGIC RHINITIS | [8 empty] | 2007-09-08 |  |  |  | 2007-12-14 | [5 empty] | 2009-02-25 | South Korea | South Korea (LPLV) | South Korea | 36 | 0 | 0 | 500 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | XYZAL | Immunology | A00436 | CSR Approved | Post marketing surveillance on Xyzal® tablet and solution | Phase IV |  | Affiliates |  | Affiliates | Kim J | [6 empty] | No | [9 empty] | 2004-11-01 |  |  |  | 2008-06-30 | [5 empty] | 2008-08-26 | South Korea | South Korea (LPLV) | South Korea | 735 | 0 | 0 | 9815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Light Support Studies | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0009 | Study Archived | RA101495-02.201 Safety, Tolerability,& Preliminary Efficacy | Phase II | Double Blind / Double Dummy | GCSO | NewMeds | UCB Pharma Global | Leskovec T |  | N/A |  | No | No | adults | No | A Phase 2, Multicenter, Randomized, Double‑Blind, Placebo-Controlled Study to Evaluate the Safety, Tolerability, and Preliminary Efficacy of RA101495 in Subjects with Generalized Myasthenia Gravis | Myasthenia gravis | Central Nervous System | MG0009 is a feeder study of MG0011 |  |  | 2017-06-14 | 2017-06-14 | 2013-10-17 | 2017-11-28 | 2018-08-03 | 2018-07-20 | 2020-10-01 | 2020-11-19 | 2020-10-29 | 2021-05-19 |  |  | 2021-02-08 | 2022-04-29 | Canada, United States of America | Canada (LPLV), United States of America (LPLV) | Canada, United States of America | 71 | 0 | 0 | 72 | 36 | 36 | 45 | 0 | 1 | 44 | 0 | 0 | 44
Yes | Light Support Studies | Managing Type | 1 | ZYRTEC | Immunology | A00442 | CSR Approved | Cetirizine pediatric Drug use result survey | Non Interventional Study - Prospective | Open | Affiliates |  | Affiliates | Kanada S |  |  | N/A |  |  |  | No | Zyrtec(R) Dry Syrup 1.25%, Zyrtec(R) tab. 5 mg Drug use results survey protocol |  |  |  | 2009-03-12 | 2009-03-31 |  | 2009-03-31 | 2009-10-07 | 2009-10-07 |  | 2011-06-30 |  | 2011-09-27 |  | 2012-09-03 |  |  |  | 2013-07-19 | Japan | Japan (LPLV) | Japan | 600 | 0 | 0 | 3000 | 0 | 0 | 3993 | 0 | 0 | 3993 | 0 | 0 | 3993
Yes | Light Support Studies | Managing Type | 2 | KEPPRA | Central Nervous System | N01326 | Study Archived | UCB AED Pregnancy Registry | Registry | Open | GCSO | Neurology | Affiliates | Melton K | Beaman M | N/A | N/A | No | No | adults | No | KEPPRAÒ (levetiracetam) PREGNANCY REGISTRY | Epilepsy | Central Nervous System |  | 2004-06-15 |  |  | 2004-12-03 | 2004-12-03 | 2005-01-05 | 2015-12-31 | 2012-10-10 |  | 2016-05-09 |  | 2016-04-30 |  |  |  | 2016-11-23 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 496 | 0 | 0 | 496 | 0 | 0 | 496 | 0 | 0 | 496
Yes | Light Support Studies | Non-managing Type | 2 | VIMPAT | Central Nervous System | N01326 | Study Archived | UCB AED Pregnancy Registry | Registry | Open | GCSO | Neurology | Affiliates | Melton K | Beaman M | N/A | N/A | No | No | adults | No | KEPPRAÒ (levetiracetam) PREGNANCY REGISTRY | Epilepsy | Central Nervous System |  | 2004-06-15 |  |  | 2004-12-03 | 2004-12-03 | 2005-01-05 | 2015-12-31 | 2012-10-10 |  | 2016-05-09 |  | 2016-04-30 |  |  |  | 2016-11-23 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 496 | 0 | 0 | 496 | 0 | 0 | 496 | 0 | 0 | 496
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0108 | LPLV | make BRV (not yet commercialized) available to pts according | Managed Access Program | Open | Affiliates | Neurology | UCB Pharma Global | Ferriere F |  | N/A | N/A | No | No | other | No | Medical Need Program for individual patient supply of BRIVIACT® intravenous (BRIVARACETAM) as adjunctive treatment of partial-onset seizures with or without secondary generalisation in adults, adolescents and childrenfrom 4 yearsof age with epilepsy | Epilepsy | Central Nervous System |  |  |  |  | 2016-01-27 | 2016-06-10 | 2016-06-01 |  |  | 2018-12-03 | 2021-12-03 | [6 empty] | Belgium | Belgium (LPLV) | Belgium | 0 | 0 | 0 | 0 | 0 | 0 | 267 | 0 | 0 | 267 | 0 | 75 | 192
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | CIMZIA | Immunology | AS0020 | LPLV | MAP for Brazil | Managed Access Program |  | Affiliates | Immunology | UCB Pharma Global | Guilherme D |  |  | N/A |  |  | adults | No | Managed Access Program Cimzia Brazil | Axial Spondyloarthritis (axSpA) | Immunology |  |  |  | 2015-08-25 | 2017-02-06 | 2016-01-06 | 2017-02-06 | 2032-06-07 |  | 2032-07-05 | 2021-10-25 | [6 empty] | Brazil | Brazil (LPLV) | Brazil | 5 | 0 | 0 | 6 | 6 | 6 | 2 | 0 | 0 | 2 | 0 | 0 | 2
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | CIMZIA | Immunology | C87092 | LPLV | Compassionate use Cimzia (COMPAS) | Managed Access Program | Open | GCSO | Immunology | UCB Pharma Global | Baukens C | Tillery N | N/A | N/A |  |  | adults | No | Compassionate Use Program Certolizumab pegol | Crohn's disease | Immunology |  |  |  | 2005-09-30 | 2006-03-27 | 2006-04-20 | 2006-04-01 |  |  | 2008-01-01 | 2024-01-19 | [6 empty] | Austria, Belgium, Canada, Czech Republic, Denmark, Finland, France, Germany, Greece, Ireland, Italy, Netherlands, Norway, Portugal, Spain, Sweden, Switzerland, United Kingdom | Austria (LPLV), Belgium (LPLV), Canada (LPLV), Czech Republic (LPLV), Denmark (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Greece (LPLV), Ireland (LPLV), Italy (LPLV), Netherlands (LPLV), Norway (LPLV), Portugal (LPLV), Spain (LPLV), Sweden (LPLV), Switzerland (LPLV), United Kingdom (LPLV) | Austria, Belgium, Canada, Czech Republic, Denmark, Finland, France, Germany, Greece, Ireland, Italy, Netherlands, Norway, Portugal, Spain, Sweden, Switzerland, United Kingdom | 219 | 0 | 0 | 800 | 800 | 200 | 803 | 0 | 0 | 803 | 0 | 803 | 0
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | Fintepla | Central Nervous System | EP0211 | CSR Approved | EXPANDED ACCESS PROGRAM (ZX008-1800) | Managed Access Program | Not Applicable | GCSO | Neurology | UCB Pharma Global | Mccleod O | Wall P | N/A | N/A | No | No | other | No | ZX008 Expanded Access Program – Dravet Syndrome Treatment Plan | Dravet Syndrome | Central Nervous System |  |  |  |  | 2019-01-04 |  | 2019-01-04 |  |  | 2016-01-01 | 2020-12-23 |  |  |  |  | 2023-11-23 | 2024-04-15 | United States of America | United States of America (LPLV) | United States of America | 16 | 0 | 0 | 0 | 0 | 0 | 132 | 0 | 4 | 128 | 0 | 63 | 65
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | KEPPRA | Central Nervous System | N01015-ASIA | LPLV | Compassionate Use Program | Managed Access Program |  | UCB Pharma Global | Neurology | R & D | Thambypillai V | [6 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [6 empty] | 2002-07-03 |  |  |  | 2005-12-31 | [6 empty] | Australia, Hong Kong, Malaysia, Singapore, Taiwan | Australia (LPLV), Hong Kong (LPLV), Malaysia (LPLV), Singapore (LPLV), Taiwan (LPLV) | Australia, Hong Kong, Malaysia, Singapore, Taiwan | 0 | 0 | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | KEPPRA | Central Nervous System | N01058 | LPLV | Named patient programme | Compassionate Use | Open | Affiliates | Neurology | R & D | [7 empty] | No | Keppra (Levetiracetam) for named patients suffering from epilepsy having previously participated in a clinical trial | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 2000-11-10 |  | 2000-11-29 |  |  |  | 2010-07-01 | [6 empty] | Belgium | Belgium (LPLV (Stopped)) | Belgium | 29 | 0 | 0 | 83 | 35 | 0 | 0 | 0 | 0 | 63 | 3 | 0 | 60
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | KEPPRA | Central Nervous System | N01091 | Study Archived | Open label LEV NPP | Compassionate Use | Open | Affiliates | Neurology | R & D | [7 empty] | No | open-label follow-up treatment with Keppra TM (Levetiracetam), for patients suffering from epilepsy having previously participated in a monotherapy trial. | Indication for Neuro Psychiatry | Central Nervous System | N01091 is a feeder study of N01061 |  |  |  | 2002-04-10 | 2003-06-30 | 2004-07-13 |  | 2005-10-24 | 2009-12-31 | 2005-10-24 | [6 empty] | Belgium, Finland, France, Germany, Italy, Netherlands, South Africa, Spain | Belgium (LPLV (Stopped)), Finland (LPLV), France (LPLV (Stopped)), Germany (LPLV (Stopped)), Italy (LPLV (Stopped)), Netherlands (LPLV (Stopped)), South Africa (LPLV), Spain (LPLV (Stopped)) | Belgium, Finland, France, Germany, Italy, Netherlands, South Africa, Spain | 70 | 0 | 0 | 127 | 61 | 61 | 0 | 0 | 0 | 62 | 62 | 0 | 0
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | KEPPRA | Central Nervous System | N01137 | LPLV | Named Patient Program | Compassionate Use |  | Clinical Development Asia | CNS | R & D | Beh K, Kang H | [6 empty] | No | Guidance Book | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 2002-12-18 |  | 2004-06-21 |  | 2004-09-24 |  | 2007-01-18 | [6 empty] | South Korea | South Korea (LPLV) | South Korea | 9 | 0 | 0 | 100 | 100 | 100 | 0 | 0 | 0 | 92 | 0 | 28 | 64
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | KEPPRA | Central Nervous System | N01183 | Study Archived | PED compassionate use | Compassionate Use | Open | GCSO | Neurology |  | Wajskop M |  | N/A | PRA International |  |  | paediatrics | No | NAMED PATIENT PROGRAM WITH LEVETIRACETAM ORAL SOLUTION, FOR PEDIATRIC PATIENTS SUFFERING FROM EPILEPSY HAVING PREVIOUSLY PARTICIPATED IN STUDY N01148 (and for Mexico) & STUDY N157 Guidance Book June 06th and July 20th, 2005 | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2007-09-21 | 2004-06-24 | 2005-11-15 | 2006-01-18 |  |  | 2009-12-31 | 2013-07-31 | [6 empty] | Brazil, France, India, Italy, Mexico, Romania, South Africa | Brazil (LPLV), France (LPLV), India (LPLV), Italy (LPLV), Mexico (LPLV), Romania (LPLV), South Africa (LPLV) | Brazil, France, India, Italy, Mexico, Romania, South Africa | 29 | 0 | 0 | 90 | 90 | 90 | 0 | 0 | 0 | 55 | 25 | 8 | 22
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | KEPPRA | Central Nervous System | N01186 | LPLV | Named patient partial seizures from N01102 FU- China | Compassionate Use |  | Clinical Development Asia | GMA Neurology / Psychiatry | Global Medical Affairs | He G | [6 empty] | No | Open-label follow-up treatment with KeppraTM (Levetiracetam) for patients suffering from epilepsy having previously participated in a doubel-blind placebo control Chinese registration trial. | Indication for Neuro Psychiatry | Central Nervous System | [6 empty] | 2004-10-14 |  | 2005-04-26 |  | 2007-03-15 | [6 empty] | China | China (LPLV) | China | 6 | 0 | 0 | 190 | 190 | 190 | 0 | 0 | 0 | 188 | 164 | 24 | 0
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | KEPPRA | Central Nervous System | N01245 | LPLV | LVTM-XR Name Patient Program | Compassionate Use |  | UCB Pharma Global | Neurology | R & D | Sykes D | [6 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 2006-10-25 |  | 2007-03-28 |  |  |  | 2010-03-30 | [6 empty] | Ukraine | Ukraine (LPLV) | Ukraine | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | NEUPRO | Central Nervous System | SP1048 | CSR Approved | Med. Need Progr. Neupro- Transdermal Patch - idiopathic PD | Managed Access Program | Open | Affiliates | Neurology | Affiliates | Ferriere F |  | N/A | N/A | No | No | adults | No | SP1048 - Medical Need Program of NEUPRO Transdermal Patch for the treatment of idiopathic Parkinson’s disease. Guidance booklet for Physicians | Parkinson's disease | Central Nervous System |  |  |  |  | 2010-05-12 | 2010-07-01 | 2010-07-01 |  |  | 2021-01-01 | 2022-10-31 | [5 empty] | 2022-10-31 | Belgium | Belgium (LPLV) | Belgium | 2 | 0 | 0 | 6 | 6 | 0 | 4 | 0 | 0 | 4 | 0 | 2 | 2
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | Rystiggo | Central Nervous System | CIDP07 | Study Archived | Rozanolixizumab Post Trial Access Program | Managed Access Program | Open | GCSO | Neurology | UCB Pharma Global | Rocha M | Slader C | N/A | N/A |  |  | adults | No | CIDP07 Rozanolixizumab Post-Trial Access Program in participants with chronic inflammatory demyelinating polyradiculoneuropathy (CIDP) | Chronic Inflammatory Demyelinating Polyr | Central Nervous System |  |  |  | 2020-12-02 | 2020-12-02 | 2021-05-31 | 2021-06-22 | 2021-06-25 | 2021-08-11 | 2024-01-01 | 2024-02-19 |  |  |  |  | 2024-08-20 | 2024-02-19 | Belgium, United Kingdom, United States of America | Belgium (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, United Kingdom, United States of America | 10 | 0 | 0 | 27 | 27 | 27 | 4 | 0 | 0 | 4 | 0 | 2 | 2
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | Rystiggo | Central Nervous System | TP0009 | Study Archived | CL - 02 Local Study Workpackage | Managed Access Program | Open | GCSO | Immunology | UCB Pharma Global | Kaur G | Slader C | N/A | Bionical |  |  | other | No | CL Rozanolixizumab (UCB7665) MAP | Idiopathic Thrombocytopenic Purpura | Immunology |  |  |  | 2021-07-02 | 2021-07-27 | 2021-11-15 | 2022-08-08 |  |  | 2024-11-04 | 2023-12-19 | [5 empty] | 2023-12-19 | Spain, Taiwan, United Kingdom | Spain (LPLV), Taiwan (LPLV), United Kingdom (LPLV) | Spain, Taiwan, United Kingdom | 28 | 0 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | 3 | 0 | 0 | 3
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | VIMPAT | Central Nervous System | EP0020 | LPLV | Compassionate use program for patients enrolled in SP954 | Compassionate Use |  | Affiliates | Neurology | Affiliates | Epik G | Kasabaligil A | N/A | NA |  |  | adults | No | COMPASSIONATE USE PROGRAM WITH LACOSAMIDE AS ADJUNCTIVE THERAPY IN THE TREATMENT OF PARTIAL-ONSET SEIZURES WITH OR WITHOUT SECONDARY GENERALIZATION IN PATIENTS WITH EPILEPSY IN TURKEY | Epilepsy | Central Nervous System | EP0020 is a follow up of SP0954 |  |  |  | 2011-10-13 |  | 2012-01-23 |  | 2012-09-03 |  | 2014-02-17 | [6 empty] | Turkey | Turkey (LPLV) | Turkey | 9 | 0 | 0 | 30 | 30 | 30 | 7 | 0 | 0 | 7 | 0 | 3 | 4
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | VIMPAT | Central Nervous System | EP0072 | Study Archived | Managed access program with Lacosamide | Managed Access Program | Not Applicable | GCSO | Neurology | GCSO | Dubois F | Anderson K | N/A | N/A | No | No | adults | No | COMPASSIONATE USE PROGRAM WITH LACOSAMIDE IN PATIENTS WITH PARTIAL-ONSET OR GENERALIZED TONIC-CLONIC SEIZURES >=16 YEARS OF AGE COMING FROM THE SP0994 STUDY | Epilepsy | Central Nervous System |  |  |  |  | 2015-07-28 | 2015-10-15 | 2016-04-09 | 2016-04-27 | 2016-09-21 | 2019-10-01 | 2019-10-01 | [6 empty] | Australia, Belgium, Czech Republic, Portugal, Spain | Australia (LPLV), Belgium (LPLV), Czech Republic (LPLV), Portugal (LPLV), Spain (LPLV) | Australia, Belgium, Czech Republic, Portugal, Spain | 61 | 0 | 0 | 123 | 123 | 123 | 97 | 0 | 0 | 97 | 0 | 43 | 54
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | VIMPAT | Central Nervous System | EP0152 | Study Archived | MANAGED ACCESS FOR LCM PATIENTS COMPLETING EP0034 OR SP848 | Managed Access Program | Open | GCSO | Neurology | UCB Pharma Global | Dehaas C | Tillery N |  | CLUEPOINTS |  |  | adults | No | MANAGED ACCESS PROGRAM WITH LACOSAMIDE IN PATIENTS WITH EPILEPSY WHO COMPLETED EP0034 OR SP848 | Epilepsy | Central Nervous System |  |  |  | 2020-03-02 | 2020-03-16 | 2020-08-24 | 2021-04-26 | 2022-06-24 | 2021-10-15 | 2025-02-14 | 2022-08-22 | [6 empty] | Italy | Italy (LPLV) | Italy | 40 | 0 | 0 | 65 | 65 | 55 | 1 | 0 | 0 | 1 | 0 | 0 | 1
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | VIMPAT | Central Nervous System | SP1002 | Study Archived | Adj. therapy in trt. POS in pat. w/epilepsy 16y and more | Compassionate Use | Open | Affiliates | GMA Neurology / Psychiatry | Affiliates | Dedeken P | Laranjo S | [5 empty] | No | Medical Need Program for Individual Patient Supply of VIMPAT for adjunctive therapy in the treatment of partial-onset seizures with or without generalisation in patients with epilepsy aged 16 years and older - Belgium | [6 empty] | 2009-09-14 |  | 2009-11-23 |  | 2010-02-23 |  | 2010-03-07 | [6 empty] | Belgium | Belgium (LPLV) | Belgium | 0 | 0 | 0 | 70 | 70 | 0 | 85 | 0 | 0 | 85 | 0 | 85 | 0
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | VIMPAT | Central Nervous System | SP1064 | LPLV | Vimpat IV solution MNP | Managed Access Program | Open | Affiliates | Neurology | Affiliates | Ferriere F |  | N/A | N/A | No | No | adults | No | SP1064 - Medical Need Program for Individual Patient Supply of VIMPAT® IV SOLUTION for adjunctive therapy in the treatment of partial-onset seizures with or without generalisation in patients with epilepsy aged 16 years and older | Epilepsy | Central Nervous System |  |  |  |  | 2010-06-30 | 2010-11-03 | 2010-11-03 |  |  | 2021-01-01 | 2020-11-01 | [6 empty] | Belgium | Belgium (LPLV) | Belgium | 2 | 0 | 0 | 115 | 115 | 0 | 302 | 0 | 0 | 302 | 0 | 0 | 302
Yes | MAP (e.g. CUP, NPP) | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0021 | Created (Cancelled) | Post trial program supporting MG0017 | Managed Access Program | Open | GCSO | Neurology | UCB Pharma Global |  |  | N/A | Bionical |  |  |  | No |  | Myasthenia gravis | Central Nervous System | [20 empty] | 25 | 0 | 0 | 25 | 25 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | NIS (Prospective and Retrospective) | Managing Type | 1 | Alprolix | not defined | HE0005 | Created (Cancelled) | Alprolix, Post Marketing Surveillance for Hemophilia B | Non Interventional Study - Prospective |  | Affiliates | NewMeds | UCB Pharma Global | Yoon J |  | Parexel |  | No | No | adults | No |  | Hemophilia B | Immunology |  | 2017-09-01 | [15 empty] | South Korea | South Korea (Created) |  | 10 | 0 | 0 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | NIS (Prospective and Retrospective) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0088 | Study Archived | BRV registry US | Non Interventional Study - Prospective | Open | GCSO | Neurology | UCB Pharma Global | Michaels K | Bonny M | PRA | UCB;PRA | No | No | other | No | MULTICENTER 1-YEAR OBSERVATIONAL STUDY OF PATIENTS WHO ARE INITIATING BRIVARACETAM | Epilepsy | Central Nervous System |  | 2016-06-10 | 2016-06-10 |  | 2016-11-01 | 2017-04-14 | 2017-06-05 04:00 | 2018-09-26 | 2019-05-14 04:00 | 2020-06-02 | 2020-04-17 04:00 | 2020-06-30 | 2020-06-15 | 2020-07-28 | 2020-06-30 | 2020-10-22 | 2020-09-17 | United States of America | United States of America (LPLV) | United States of America | 40 | 36 | 33 | 450 | 450 | 450 | 304 | 0 | 22 | 282 | 0 | 122 | 160
Yes | NIS (Prospective and Retrospective) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0103 | Study Archived | NIS prospective on Briviact in combination with 1st line AED | Non Interventional Study - Prospective | Open | RWE/GCSO | Neurology | UCB Pharma Global | Reichel C | Anderson K | Parexel | PAREXEL | No | No | adults | No | BRITOBA: BRIVARACETAM ADJUNCTIVE THERAPY IN EARLY TREATMENT LINE COMBINATIONS. | Epilepsy | Central Nervous System |  | 2019-10-21 08:00 | 2019-10-21 |  | 2020-03-23 | 2020-10-05 | 2020-12-11 | 2022-10-06 | 2022-12-23 | 2023-10-06 | 2024-01-10 | 2023-11-07 | 2024-02-20 | 2023-11-28 | 2024-04-19 | 2024-02-22 | 2024-10-23 | Canada, France, Germany, Italy, Spain | Canada (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Spain (LPLV) | Canada, France, Germany, Italy, Spain | 80 | 81 | 62 | 380 | 380 | 380 | 403 | 0 | 0 | 403 | 0 | 103 | 300
Yes | NIS (Prospective and Retrospective) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0104 | Study Archived | Retrospective data collection on effectiveness and tolerabil | Non Interventional Study - Retrospective | Open | GCSO | Neurology | UCB Pharma Global | Rowley K | Smit R | N/A | Acromion | No | No | other | No | NON-INTERVENTIONAL STUDY PROTOCOL EP0104 EFFECTIVENESS OF INITIATING BRIVARACETAM ADD-ON THERAPY IN PATIENTS WITH EPILEPSY REQUIRING A CHANGE IN ANTIEPILEPTIC DRUG REGIMEN: A RETROSPECTIVE DATA COLLECTION. | Epilepsy | Central Nervous System |  |  |  |  | 2017-05-02 | 2017-08-08 | 2017-08-22 | 2017-11-01 | 2018-03-15 | 2018-03-19 | 2018-07-19 | 2018-08-14 | 2018-08-14 | 2018-10-05 | 2018-10-15 | 2019-02-22 | 2019-02-12 | Germany | Germany (LPLV) | Germany | 30 | 20 | 20 | 743 | 743 | 743 | 507 | 0 | 0 | 507 | 0 | 0 | 507
Yes | NIS (Prospective and Retrospective) | Managing Type | 1 | CIMZIA | Immunology | DV0005 | Study Archived | PsA, or axSpA using the Cimzia ava eDevice or other TNF-bloc | Non Interventional Study - Prospective | Not Applicable | GCSO | Immunology | UCB Pharma Global |  |  | N/A | ACROMION | No | No | adults | No | A MULTICENTER, OBSERVATIONAL POST-MARKET CLINICAL FOLLOW-UP STUDY IN PATIENTS WITH RA, PsA, OR axSpA ASSESSING THE PATIENT EXPERIENCE WITH THE CIMZIA AVA DEVICE OR OTHER TNF-BLOCKER AUTO-INJECTOR DEVICES | Ankylosing Spondylitis; Psoriatic Arthritis; Rheumatoid Arthritis | Immunology; Immunology; Immunology |  | 2018-08-24 08:00 | 2018-08-24 | 2018-11-30 | 2018-11-30 | 2019-04-17 | 2019-11-15 | 2020-04-01 | 2021-02-01 | 2021-01-08 | 2021-11-03 | 2021-02-05 | 2022-01-31 | 2021-02-19 | 2022-02-14 | 2021-05-14 | 2022-05-24 | Belgium, Germany, Italy, Spain | Belgium (LPLV), Germany (LPLV), Italy (LPLV), Spain (LPLV) | Belgium, Germany, Italy, Spain | 50 | 36 | 31 | 200 | 200 | 180 | 37 | 0 | 6 | 178 | 0 | 50 | 128
Yes | NIS (Prospective and Retrospective) | Managing Type | 1 | CIMZIA | Immunology | PS0026 | Study Archived | Multicenter, noninterventional prospective study | Non Interventional Study - Prospective | Open | GCSO | Immunology | UCB Pharma Global | Kadima H | Grose-Hodge R | Parexel | PAREXEL | No | No | adults | No | A MULTICENTER, NONINTERVENTIONAL, PROSPECTIVE STUDY TO ASSESS THE EFFECTIVENESS OF CERTOLIZUMAB PEGOL IN PATIENTS WITH MODERATE TO SEVERE PLAQUE PSORIASIS IN DAILY PRACTICE (CIMREAL) | Psoriasis | Immunology |  | 2018-10-31 08:00 | 2018-10-31 |  | 2019-02-08 | 2019-06-03 | 2019-08-21 | 2021-01-01 | 2021-11-24 | 2022-01-28 | 2022-12-02 | 2022-02-28 | 2023-02-15 | 2022-03-18 | 2023-03-08 | 2022-06-13 | 2023-09-14 | Belgium, Canada, Czech Republic, France, Germany, Greece, Italy, Spain, United Kingdom | Belgium (LPLV), Canada (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Greece (LPLV), Italy (LPLV), Spain (LPLV), United Kingdom (LPLV) | Belgium, Canada, Czech Republic, France, Germany, Greece, Italy, Spain, United Kingdom | 97 | 101 | 79 | 400 | 400 | 295 | 413 | 0 | 0 | 413 | 0 | 95 | 318
Yes | NIS (Prospective and Retrospective) | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0101 | CSR Approved | Retrospective OL Natural History controlled Pivotal Trial | Non Interventional Study - Retrospective |  | GCSO | Neurology | UCB Pharma Global | Pifer C | Tillery N | N/A |  | No | No | other | No | Ph 2 Retrospective study of the combination of pyrimidine nucleos (t)ides in patients with thymidine kinase 2 deficiency (TK2d) | Thymidine kinase 2 (TK2) deficiency | Central Nervous System |  |  |  |  | 2018-08-15 |  | 2018-10-30 |  | 2019-03-25 |  | 2019-03-25 |  | 2019-07-15 |  |  |  | 2023-05-22 | Israel, Spain, United States of America | Israel (LPLV), Spain (LPLV), United States of America (LPLV) | Israel, Spain, United States of America | 8 | 0 | 8 | 38 | 38 | 38 | 38 | 0 | 0 | 38 | 0 | 0 | 38
Yes | NIS (Prospective and Retrospective) | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0110 | Study Archived | Non-Interventional Data Collection Study | Non Interventional Study - Retrospective | Not Applicable | RWE/GCSO | Neurology | UCB Pharma Global | Pifer C | Tillery N | Parexel |  | Yes | Yes | other | No | A Noninterventional Study to Collect Supplemental Information From Participants with Thymidine Kinase 2 Deficiency in the Doxecitine and Doxribtimine Clinical Studies. | Thymidine kinase 2 (TK2) deficiency | Central Nervous System | TK0110 is a "sister" study of TK0101, TK0102, TK0107 |  |  |  | 2023-03-13 |  | 2023-09-08 |  | 2024-04-05 |  | 2024-04-05 |  | 2024-04-16 |  | 2024-05-14 |  | 2024-07-15 | Israel, Italy, Russian Federation, Spain, Turkey, United States of America | Israel (LPLV), Italy (LPLV), Russian Federation (LPLV), Spain (LPLV), Turkey (LPLV), United States of America (LPLV) | Israel, Italy, Russian Federation, Spain, Turkey, United States of America | 18 | 10 | 10 | 47 | 47 | 47 | 43 | 0 | 0 | 43 | 0 | 0 | 43
Yes | NIS (Prospective and Retrospective) | Managing Type | 1 | Eloctate | Central Nervous System | HE0004 | Protoc. Summary Approved (Cancelled) | Eloctate Post Marketing Surveillance for Hemophilia A | Non Interventional Study - Prospective |  | Affiliates | Neurology | UCB Pharma Global | Namgoong K | Beinhauer-Zellenka U | Parexel |  | No | No | adults | No |  | Hemophilia A | Immunology |  | 2017-12-01 | 2017-11-28 | [14 empty] | South Korea | South Korea (Created) |  | 10 | 0 | 0 | 200 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | NIS (Prospective and Retrospective) | Managing Type | 1 | NEUPRO | Central Nervous System | PD0056 | Study Archived | Chinese Neupro non interventional study | Non Interventional Study - Prospective | Open | GCSO | Neurology | UCB Pharma Global |  |  | Parexel | PAREXEL | No | No | adults | No | Real-World Safety & Effectiveness of NEUPRO® in Mainland Chinese Patients with Idiopathic Parkinson’s Disease | Parkinson's disease | Central Nervous System |  | 2020-04-23 08:00 | 2020-04-23 |  | 2020-07-09 | 2021-03-11 | 2021-03-10 | 2022-01-11 | 2023-03-21 | 2022-02-10 | 2023-06-12 | 2022-04-07 | 2023-08-01 | 2022-06-02 | 2023-08-16 | 2022-10-11 | 2023-11-14 | China | China (LPLV) | China | 26 | 29 | 27 | 829 | 829 | 829 | 829 | 0 | 0 | 829 | 0 | 247 | 582
Yes | NIS (Prospective and Retrospective) | Managing Type | 1 | VIMPAT | Central Nervous System | EP0144 | Study Archived | Non-interventional study of VIMPAT in clinical practice | Non Interventional Study - Prospective | Open | RWE/GCSO | Neurology | UCB Pharma Global | Zhao H | Guo J | Parexel | PAREXEL | No | Yes | adults | No | POSTMARKETING SAFETY AND EFFECTIVENESS OF NOVEL ANTIEPILEPTIC DRUG VIMPAT® IN MAINLAND CHINESE PATIENT POPULATIONS A MULTICENTER PROSPECTIVE NONINTERVENTIONAL DRUG INTENSIVE MONITORING STUDY | Epilepsy | Central Nervous System |  | 2020-02-06 08:00 | 2020-02-06 |  | 2020-06-03 | 2020-10-19 | 2021-08-23 | 2022-07-29 | 2023-06-02 | 2023-01-19 | 2023-10-18 | 2023-04-10 | 2023-12-05 | 2023-06-05 | 2023-12-27 | 2023-10-12 | 2024-03-12 | China | China (LPLV) | China | 30 | 31 | 29 | 850 | 850 | 850 | 916 | 19 | 20 | 877 | 0 | 121 | 756
Yes | NIS (Prospective and Retrospective) | Managing Type | 1 | VIMPAT | Central Nervous System | EP0158 | Protocol Approved (Cancelled) | Extension LCM treatment of neonatal seizures | Non Interventional Study - Prospective | Not Applicable | GCSO | Neurology | UCB Pharma Global | Andrews J |  | Parexel | PAREXEL | No | Yes | paediatrics | No | A REMOTE FOLLOW-UP DEVELOPMENT ASSESSMENT STUDY OF NEONATES WHO PARTICIPATED IN SP0968 (LACOSAMIDE OR ACTIVE COMPARATOR TREATING REPEATED ELECTROENCEPHALOGRAPHIC NEONATAL SEIZURES) | Electroencephalographic neonatal seizure | Central Nervous System | EP0158 is an extension of SP0968 |  | 2020-07-07 | 2020-08-24 | 2020-09-29 | 2021-05-14 |  | 2022-03-01 |  | 2024-02-28 | [5 empty] | 2024-06-17 |  | Canada, United States of America | Canada (IRB / IEC Approval), United States of America (Created) | Canada | 3 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | NIS (Prospective and Retrospective) | Managing Type | 2 | VIMPAT | Central Nervous System | EP0076 | Study Archived | Patient Preference in AED Monotherapy/LCM-monotherapy launch | Non Interventional Study - Prospective | Open | GCSO | Neurology | UCB Pharma Global | Hoeckendorff J | Anderson K | Parexel | PAREXEL | No | Yes | adults | No | PATIENT PREFERENCE IN EPILEPSY MONOTHERAPY - A NONINTERVENTIONAL STUDY OF LACOSAMIDE AND OTHER ANTIEPILEPTIC DRUGS IN THE TREATMENT OF PARTIAL-ONSET SEIZURES, INCLUDING A DISCRETE-CHOICE EXPERIMENT | Epilepsy | Central Nervous System |  |  |  |  | 2017-03-24 | 2017-07-04 | 2017-08-29 | 2018-10-03 |  | 2019-10-31 |  | 2019-12-10 | 2019-10-29 | 2020-01-15 | 2019-11-25 | 2020-04-13 | 2020-04-15 | Denmark, France, Germany, Ireland, Italy, Netherlands, Spain, United Kingdom | Denmark (FPFV), France (FPFV), Germany (FPFV), Ireland (FPFV), Italy (FPFV), Netherlands (FPFV), Spain (FPFV), United Kingdom (FPFV) | Denmark, France, Germany, Ireland, Italy, Netherlands, Spain, United Kingdom | 91 | 91 | 63 | 301 | 301 | 270 | 311 | 0 | 7 | 304 | 0 | 18 | 286
Yes | NIS (Prospective and Retrospective) | Non-managing Type | 2 | KEPPRA | Central Nervous System | EP0076 | Study Archived | Patient Preference in AED Monotherapy/LCM-monotherapy launch | Non Interventional Study - Prospective | Open | GCSO | Neurology | UCB Pharma Global | Hoeckendorff J | Anderson K | Parexel | PAREXEL | No | Yes | adults | No | PATIENT PREFERENCE IN EPILEPSY MONOTHERAPY - A NONINTERVENTIONAL STUDY OF LACOSAMIDE AND OTHER ANTIEPILEPTIC DRUGS IN THE TREATMENT OF PARTIAL-ONSET SEIZURES, INCLUDING A DISCRETE-CHOICE EXPERIMENT | Epilepsy | Central Nervous System |  |  |  |  | 2017-03-24 | 2017-07-04 | 2017-08-29 | 2018-10-03 |  | 2019-10-31 |  | 2019-12-10 | 2019-10-29 | 2020-01-15 | 2019-11-25 | 2020-04-13 | 2020-04-15 | Denmark, France, Germany, Ireland, Italy, Netherlands, Spain, United Kingdom | Denmark (FPFV), France (FPFV), Germany (FPFV), Ireland (FPFV), Italy (FPFV), Netherlands (FPFV), Spain (FPFV), United Kingdom (FPFV) | Denmark, France, Germany, Ireland, Italy, Netherlands, Spain, United Kingdom | 91 | 91 | 63 | 301 | 301 | 270 | 311 | 0 | 7 | 304 | 0 | 18 | 286
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | C87041 | Created | C87041 Japan RA MTX Combination Domestic Study | Phase II |  | Affiliates |  | UCB Pharma Global | Sakamaki Y | [6 empty] | No |  | Indication for Rheumato GI | Immunology | C87041 is a parent study of C87071 | [16 empty] | Japan | Japan (Created) |  | 50 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | C87071 | CSR Approved | Japan RA MTX combintation extension study Domestic study B | Phase III | Open | Clinical Development Japan | Clinical Development Japan | R & D | [6 empty] | adults | No |  |  |  | C87071 is an extension of C87041 | [5 empty] | 2009-04-01 |  |  |  | 2013-06-06 | [5 empty] | 2014-05-12 | Japan | Japan (LPLV) | Japan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | RA0005 | CSR Approved | RA0005 - National DB for Rheumatic Diseases Cimzia Safety | Registry | Open | Affiliates | Immunology | UCB Pharma Global | Yates T | Bonny M | N/A | UCB |  |  | adults | No | National Databank for Rheumatic Diseases Registry Study of Safety in Patients Treated with Certolizumab Pegol and Non-biologic Disease-Modifying Antirheumatic Drug Therapies | [7 empty] | 2009-09-11 | 2009-09-01 |  |  |  | 2019-12-31 | [5 empty] | 2020-06-03 | United States of America | United States of America (LPLV) | United States of America | 1 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 1858 | 1858 | 0 | 0
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | RA0006 | Created | RA0006 - Monotherapy domestic Study A | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | RA0007 | Created | RA0007 - Monotherapy extension Study A | Phase III |  | UCB Pharma Global | Immunology | UCB Pharma Global | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2011-06-24
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | RA0020 | CSR Approved | RA0020- RABBIT (RA) Registry (Germany) | Registry | Open | GCSO | Immunology | UCB Pharma Global | Dombrowsky W, Yates T | Bonny M | N/A | UCB |  |  | adults | No | Long-term Observation of Treatment with Biologics in Rheumatoid Arthritis (RABBIT) This was the 4th amendment of the protocol but the first that we operated under and first to include UCB within the participating companies | [7 empty] | 2009-10-30 | 2009-10-30 |  |  |  | 2019-10-31 | [5 empty] | 2020-12-18 | Germany | Germany (LPLV) | Germany | 1 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 4932 | 0 | 0 | 4932
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | RA0021 | CSR Approved | RA0021- ARTIS (Swedish Safety Registry) | Registry | Open | UCB Pharma Global |  | UCB Pharma Global | Yates T | Bonny M | N/A | UCB |  |  | adults | No | NATION-WIDE SAFETY MONITORING OF BIOLOGICAL THERAPIES INCLUDING CERTOLIZUMAB PEGOL IN PATIENTS WITH RHEUMATIC DISEASE IN SWEDEN Registry | [7 empty] | 2010-01-15 | 2010-02-01 |  |  |  | 2017-11-30 | [5 empty] | 2018-01-01 | Sweden | Sweden (LPLV) | Sweden | 1 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 1947 | 0 | 0 | 1947
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | RA0022 | CSR Approved | RA0022 Particip. in British Society for Rheumat. Biologics r | Registry | Open | Affiliates | Immunology | Affiliates | Yates T | Bonny M | N/A |  |  |  | adults | No | A longitudinal observational study of patients with rheumatoid arthritis treated with biologic agents and prospective surveillance study for adverse events Certolizumab substudy Version 3 of the BSRBR protocol but the first the first protocol for our substudy | [7 empty] | 2011-01-29 | 2011-01-31 |  |  |  | 2019-12-31 | [5 empty] | 2020-06-26 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 6966 | 0 | 0 | 6966
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | RA0025 | CSR Approved | RA0025 - Korean CZP RA DBT | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | [6 empty] | adults | No | [9 empty] | 2009-12-04 |  |  |  | 2011-08-02 | [5 empty] | 2017-10-23 | South Korea | South Korea (LPLV) | South Korea | 15 | 0 | 0 | 127 | 127 | 127 | 0 | 0 | 0 | 121 | 0 | 43 | 78
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | RA0034 | CSR Approved | RA0034 (OTSUKA) Korean OL follow up to RA0025 | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | [6 empty] | adults | No | [9 empty] | 2010-04-13 |  |  |  | 2016-07-04 | [5 empty] | 2017-07-12 | South Korea | South Korea (LPLV) | South Korea | 15 | 0 | 0 | 127 | 127 | 127 | 0 | 0 | 0 | 106 | 0 | 42 | 64
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | RA0096 | CSR Approved | Efficacy Confirmation of CDP870 in Patients With Early RA | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Shoji T | Matsuoka K |  |  |  |  | adults | No | A Multicenter, Double-blind, Randomized, Placebo-controlled, Parallel-group Study to Assess the Efficacy and Safety in Patients With Early-stage RA who Are Naïve to Methotrexate and Have Poor Prognostic Factors | [8 empty] | 2011-10-17 |  |  |  | 2014-10-20 | [5 empty] | 2015-09-04 | Japan | Japan (LPLV) | Japan | 0 | 0 | 0 | 300 | 300 | 300 | 0 | 0 | 0 | 316 | 0 | 0 | 316
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | CIMZIA | Immunology | RA0119 | LPLV | DANBIO, a nationwide registry of biological therapies in DNK | Registry |  | Affiliates | Immunology | UCB Pharma Global | Sundman-Engberg B | [5 empty] | adults | No | DANBIO national clinical registry | [8 empty] | 2009-01-01 |  |  |  | 2019-12-01 | [6 empty] | Denmark | Denmark (LPLV) | Denmark | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2466 | 0 | 0 | 2466
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | NEUPRO | Central Nervous System | SP1016 | CSR Approved | Neuropsy. disturb. in PD. Epidemiological Prospective Study. | Non Interventional Study - Prospective |  | Affiliates - Spain |  | Affiliates - Spain | Ayuga A, Whitesides J | [6 empty] | No | [8 empty] | 2010-06-17 | 2010-05-15 |  |  |  | 2010-09-30 | [5 empty] | 2012-01-11 | Spain | Spain (LPLV) | Spain | 0 | 0 | 0 | 734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | Tozadenant | Central Nervous System | PD0020 | Created (Cancelled) | PD0020 - Phase 3 double-blind fluctuator study | Phase III |  | UCB Pharma Global | Neurology | UCB Pharma Global | [7 empty] | No |  | Parkinson's disease | Central Nervous System | PD0020 is a feeder study of PD0022 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | Tozadenant | Central Nervous System | PD0021 | Created (Cancelled) | PD0021 - Phase 3 double-blind non-fluctuator study | Phase III |  | UCB Pharma Global | Neurology | UCB Pharma Global | [7 empty] | No |  | Parkinson's disease | Central Nervous System | PD0021 is a feeder study of PD0022 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | Tozadenant | Central Nervous System | PD0022 | Created (Cancelled) | Phase 3 open label extension study | Phase III |  | UCB Pharma Global | Neurology | UCB Pharma Global | [7 empty] | No |  | Parkinson's disease | Central Nervous System | PD0022 is an extension of PD0020, PD0021 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | UCB5380 | Immunology | CL0441 | LPLV | Monitor III | Phase I | Not Applicable | Affiliates | Immunology | UCB Pharma Global | [6 empty] | adults | No | " Mono-pep data Analysis of the Phase 1b Study of Proinsulin (PI) Peptide Immunotherapy in New-Onset Type 1 Diabetes (MonoPepT1De-1b)" | [8 empty] | 2017-06-09 |  |  |  | 2018-05-16 | [6 empty] | United Kingdom | United Kingdom (LPLV) | United Kingdom | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | UCB6673 MultipepT1De | not defined | DB0001 | Created (Cancelled) | A multi-center, prospective, double-blind, placebo-controlle | Phase II | Double Blind | Affiliates | Immunology | UCB Pharma Global | [6 empty] | other | No | [20 empty] | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | Zilucoplan | Central Nervous System | ALS001 | CSR Approved | Healey ALS Platform trial | Phase II | Double Blind | GCSO | NewMeds | UCB Pharma Global | Harvey B | Russell R |  |  |  |  | adults | No | HEALEY ALS Platform Trial | Amyotrophic Lateral Sclerosis (ALS) | Central Nervous System | [6 empty] | 2020-07-14 |  |  |  | 2022-05-02 | [5 empty] | 2024-07-02 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 320 | 160 | 160 | 0 | 0 | 0 | 162 | 0 | 162 | 0
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | Zilucoplan | Central Nervous System | UP0107 | CSR Approved | Zilucoplan in COVID-19 patients with respiratory failure | Phase II | Not Applicable | GCSO | Neurology | UCB Pharma Global | Watanabe S | Cain D |  |  |  |  | adults | No |  | Covid-19 | Central Nervous System | [6 empty] | 2020-08-15 |  |  |  | 2021-05-27 | [5 empty] | 2022-05-12 | Belgium | Belgium (LPLV) | Belgium | 0 | 0 | 0 | 81 | 81 | 81 | 0 | 0 | 0 | 81 | 0 | 5 | 76
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | Zilucoplan | Central Nervous System | UP0108 | CSR Approved | Zilucoplan in hospitalized COVID-19 patients | Phase II | Not Applicable | GCSO | Neurology | UCB Pharma Global | Watanabe S | Cain D |  |  |  |  | adults | No |  | Covid-19 | Central Nervous System | [6 empty] | 2020-05-22 |  |  |  | 2021-08-02 | [5 empty] | 2024-03-11 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 0 | 0 | 0 | 120 | 120 | 120 | 0 | 0 | 0 | 76 | 0 | 6 | 70 | [22 empty] | yes
Yes | Non UCB Sponsored Co-Developed and Registry Studies | Managing Type | 1 | Zilucoplan | Central Nervous System | UP0109 | CSR Approved | COMMUNITY COV-01-005 Platform | Phase III | Not Applicable | GCSO | Neurology | UCB Pharma Global | Jabbarzadegan P | Cain D |  |  |  |  | adults | No | Industry Alliance Platform Trial to Assess the Efficacy and Safety of Multiple Candidate Agents for the Treatment of COVID-19 in Hospitalized Patients - Zilucoplan subprotocol | Covid-19 | Central Nervous System | [6 empty] | 2021-01-11 |  |  |  | 2021-08-03 | [5 empty] | 2022-01-18 | Argentina, Brazil, Chile, Russian Federation, South Africa, United States of America | Argentina (LPLV), Brazil (LPLV), Chile (LPLV), Russian Federation (LPLV), South Africa (LPLV), United States of America (LPLV) | Argentina, Brazil, Chile, Russian Federation, South Africa, United States of America | 0 | 0 | 0 | 520 | 350 | 350 | 0 | 0 | 0 | 108 | 0 | 34 | 74
Yes | Not assigned | Managing Type | 1 | Alfadex | not defined | SP0317 | Created | Drug Safety Trial Data. Study drug: ALPHA-CYCLODEXTRIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Scharfenecker U | [6 empty] | No | Drug Safety Trial Data. Study drug: ALPHA-CYCLODEXTRIN | [22 empty] | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Alfadex | not defined | SP0318 | Created | Drug Safety Trial Data. Study drug: ALPHA-CYCLODEXTRIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Scharfenecker U | [6 empty] | No | Drug Safety Trial Data. Study drug: ALPHA-CYCLODEXTRIN | [22 empty] | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Alfadex | not defined | SP0391 | Created | Drug Safety Trial Data. Study drug: A-CYCLODEXTRIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | Drug Safety Trial Data. Study drug: A-CYCLODEXTRIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ARTHROTEC, MISOFEN | not defined | SP0917 | Created | Pilot - Single dose bioequivalence of 75mg diclofenac and 20 | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | Long Title to be entered | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BACLOFEN, LIORESAL | not defined | SP0692 | Final TFLs released | Baclofen ODT single dose bioavailability | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Kastenholz K | [6 empty] | No | A pharmacokinetic study to compare the bioavailability of a unique new formulation (test), 20 mg orally disintegrating tablet (ODT) of baclofen to a marketed immediate release 20 mg tablet formulation (reference) |  |  |  | 2002-01-08 | 2002-01-08 |  | 2002-06-10 |  | 2002-06-23 |  | 2002-06-23 |  | 2002-07-15 |  |  |  | 2002-09-13 |  |  | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 28 | 28 | 24 | 0 | 0 | 0 | 25 | 0 | 0 | 25
Yes | Not assigned | Managing Type | 1 | BACLOFEN, LIORESAL | not defined | SP0741 | Final TFLs released | Baclofen ODT without water single dose bioavailability | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to evaluate the bioequivalence of a unique new formulation (test), orally disintegrating tablet (ODT), of baclofen 20 mg given without water, compared to a marketed immediate release baclofen 20 mg tablet formulation (reference) by Watson Laboratories, Inc. |  |  |  | 2003-02-26 | 2003-02-26 |  | 2003-04-03 |  | 2003-05-10 |  | 2003-05-10 |  | 2003-05-19 |  |  |  | 2003-06-20 |  |  | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 18 | 18 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BACLOFEN, LIORESAL | not defined | SP0760 | Protocol Approved | Baclofen ODT marketing study in MS patients | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A multicenter, open-label, randomized trial to assess subject preference of baclofen orally disintegrating tablets compared to conventional baclofen tablets in subjects with stable multiple sclerosis | Multiple sclerosis | Central Nervous System |  | 2003-06-23 | 2003-06-23 |  | 2003-08-13 | [12 empty] | United States of America | United States of America (Created) |  | 3 | 0 | 0 | 30 | 30 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BACLOFEN, LIORESAL | not defined | SP0785 | Created | Oral safety of multiple doses of Kemstro (Baclofen Orally Di | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | Oral safety of multiple doses of Kemstro (Baclofen Orally Disintegrating Tablet) in subjects with Multiple Sclerosis taking Baclofen | [22 empty] | 1 | 0 | 0 | 30 | 30 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BACLOFEN, LIORESAL | not defined | SP0798 | Study Archived | Pilot Phase 1 PK Trial with 3 different formulations of Bacl | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Goldammer N | Beinhauer-Zellenka U | [5 empty] | Yes | A single site, open label, randomized, pilot phase 1 trial in healthy young male subjects to characterize the pharmacokinetics of single doses of 3 different formulations of Baclofen Egalet 20 mg |  |  |  | 2004-03-08 | 2004-03-08 |  | 2004-03-19 |  | 2004-04-14 |  | 2004-04-21 |  | 2004-05-25 |  | 2004-07-05 |  | 2005-04-29 |  | 2006-01-05 | Germany | Germany (Created) |  | 1 | 0 | 0 | 8 | 8 | 8 | 12 | 4 | 0 | 8 | 0 | 0 | 8
Yes | Not assigned | Managing Type | 1 | BACLOFEN, LIORESAL | not defined | SP0843 | Created | Kemstro preference study in MS patients | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A multicenter, open-label, randomized crossover trial to assess subject preference for Kemstro compared to conventional Baclofen Tablets in subjects with stable Multiple Sclerosis | Multiple sclerosis | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BACLOFEN, LIORESAL | not defined | SP0853 | Study Archived | Baclofen pilot trial - Egalet formulation | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Goldammer N | Beinhauer-Zellenka U | [5 empty] | Yes | A single site, randomized, open label, cross-over pilot phase 1 trial in healthy young male subjects to investigate the pharmacokinetics of 3 different oral formulations of baclofen SR Egalet 20 mg compared to an immediate release formulation | Spasticity due to multiple sclerosis | Central Nervous System |  | 2005-01-13 | 2005-01-13 |  | 2005-02-15 |  | 2005-03-30 |  | 2005-03-30 |  | 2005-05-12 |  | 2005-06-27 |  | 2005-12-12 |  | 2006-07-07 | Germany | Germany (Created) |  | 1 | 0 | 0 | 8 | 8 | 8 | 15 | 7 | 0 | 8 | 0 | 0 | 8
Yes | Not assigned | Managing Type | 1 | BACLOFEN, LIORESAL | not defined | SP0855 | Study Archived | Baclofen pilot trial - in house formulation | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Goldammer N | Beinhauer-Zellenka U | [5 empty] | Yes | A single site, randomized, open-label, cross-over pilot phase 1 trial in healthy young male subjects to investigate the pharmacokinetics of 3 baclofen sustained release classical matrix tablets compared to an immediate release tablet | Spasticity due to multiple sclerosis | Central Nervous System |  | 2005-02-18 | 2005-02-18 |  | 2005-03-11 |  | 2005-05-09 |  | 2005-05-13 |  | 2005-06-14 |  | 2005-07-27 |  | 2006-01-19 |  | 2006-07-07 | Germany | Germany (Created) |  | 1 | 0 | 0 | 8 | 8 | 8 | 14 | 6 | 0 | 8 | 0 | 0 | 8
Yes | Not assigned | Managing Type | 1 | Bemetizide,Triamterene | not defined | SP0094 | Created | DIUCOMB - bei leichter und mittelschwerer Hypertonie | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Schmidt G | [6 empty] | No | DIUCOMB - bei leichter und mittelschwerer Hypertonie | Mild to Moderate Hypertension | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Bemetizide,Triamterene | not defined | SP0105 | Created | Pharmakokinetik von Bemetizid/Triamtereren - Einfluß der Nah |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Pharmakokinetik von Bemetizid und Triamteren nach peroraler Gabe von Diucomb mmidl an 18 gesunden Probanden, Teil 1: Einfluß der Nahrung auf die Bioverfügbarkeit. Teil 2: Pharmakokinetik und | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Bemetizide,Triamterene | not defined | SP0145 | Created | Drug Safety Trial Data. Study drug: DEHYDRO-TRI |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: DEHYDRO-TRI | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Bemetizide,Triamterene | not defined | SP0211 | Created | DIUCOMB-MILD - bei Patienten mit essentieller Hypertonie |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | DIUCOMB-MILD - bei Patienten mit essentieller Hypertonie | Mild to Moderate Hypertension | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Bemetizide,Triamterene | not defined | SP0214 | Created | Drug Safety Trial Data. Study drug: DEHYDRO-TRI-MITE |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: DEHYDRO-TRI-MITE | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Bemetizide,Triamterene | not defined | SP0215 | Created | Drug Safety Trial Data. Study drug: DEHYDRO-TRI |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: DEHYDRO-TRI | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Bemetizide,Triamterene | not defined | SP0216 | Created | DEHYDRO-TRI-MITE - bei Patienten mit chronischer Veneninsuff |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | DEHYDRO-TRI-MITE - bei Patienten mit chronischer Veneninsuffizienz und venös bedingten Ödemen | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Bemetizide,Triamterene | not defined | SP0217 | Created | Drug Safety Trial Data. Study drug: DEHYDOR-TRI |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: DEHYDOR-TRI | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Bemetizide,Triamterene | not defined | SP0218 | Created | Drug Safety Trial Data. Study drug: DEHYDRO-TRI |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: DEHYDRO-TRI | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BIMZELX | Immunology | AS0008 | Study Archived | BIMAB phase 2b, randomized, double-blind, placebo-controlled | Phase II | Double Blind | GCSO | Immunology | GCSO | Byerly R | Bonny M | PRA | PRA | Yes | Yes | adults | No | A MULTICENTER, PHASE 2B, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL-GROUP, DOSE-RANGING STUDY TO EVALUATE THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN SUBJECTS WITH ACTIVE ANKYLOSING SPONDYLITIS. | Ankylosing Spondylitis | Immunology | AS0008 is a "sister" study of PA0008 and is a parent study of AS0009 | 2016-01-29 | 2016-02-02 |  | 2016-08-01 | 2016-10-27 | 2016-10-27 05:00 | 2018-01-11 | 2017-07-11 05:00 | 2019-03-07 | 2018-08-29 22:00 | 2019-03-21 | 2019-02-12 | 2019-04-04 | 2019-02-27 | 2019-06-29 | 2019-06-04 | Bulgaria, Canada, Czech Republic, Germany, Hungary, Poland, Russian Federation, Spain, Ukraine, United States of America | Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), Germany (LPLV), Hungary (LPLV), Poland (LPLV), Russian Federation (LPLV), Spain (LPLV), Ukraine (LPLV), United States of America (LPLV) | Bulgaria, Canada, Czech Republic, Germany, Hungary, Poland, Russian Federation, Spain, Ukraine, United States of America | 86 | 89 | 74 | 407 | 303 | 303 | 601 | 0 | 298 | 303 | 0 | 40 | 263
Yes | Not assigned | Managing Type | 1 | BIMZELX | Immunology | PA0007 | Study Archived | MAD PsA | Phase I | Double Blind | GED |  | GED | Jones A | Driver D | Parexel | SPI PXL | No | No | adults | Yes | A subject-blind, investigator-blind, randomized, placebo-controlled study evaluating the safety, pharmacokinetics and pharmacodynamics of multiple doses of UCB4940 in subjects with psoriatic arthritis. | Psoriatic Arthritis | Immunology |  | 2013-10-30 | 2013-11-13 |  | 2014-01-20 | 2014-06-17 | 2014-06-17 | 2014-11-24 | 2015-03-13 |  | 2015-08-19 |  | 2015-09-18 |  | 2015-10-28 |  | 2015-12-18 | Bulgaria, Moldavia, United Kingdom | Bulgaria (LPLV), Moldavia (LPLV), United Kingdom (LPLV) | Bulgaria, Moldavia, United Kingdom | 3 | 3 | 3 | 84 | 50 | 50 | 80 | 0 | 27 | 53 | 0 | 3 | 50
Yes | Not assigned | Managing Type | 1 | BIMZELX | Immunology | PA0008 | Study Archived | BIMAB phase 2b, randomized, double-blind, placebo-contraolle | Phase II | Double Blind | GCSO | Immunology | GCSO |  |  | PRA | PRA | Yes | Yes | adults | No | A MULTICENTER, PHASE 2B, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL-GROUP, DOSE-RANGING STUDY TO EVALUATETHE EFFICACY AND SAFETY OF BIMEKIZUMAB IN ACTIVEPSORIATIC ARTHRITIS | Psoriatic Arthritis | Immunology | PA0008 is a "sister" study of AS0008 and is a parent study of PA0009 | 2016-02-01 | 2016-01-29 |  | 2016-07-31 | 2016-10-28 | 2016-10-27 05:00 | 2018-01-12 | 2017-07-21 05:00 | 2019-03-08 | 2018-07-16 05:00 | 2019-03-22 | 2018-12-06 | 2019-04-05 | 2018-12-21 | 2019-07-02 | 2019-04-04 | Czech Republic, Germany, Hungary, Poland, Russian Federation, United States of America | Czech Republic (LPLV), Germany (LPLV), Hungary (LPLV), Poland (LPLV), Russian Federation (LPLV), United States of America (LPLV) | Czech Republic, Germany, Hungary, Poland, Russian Federation, United States of America | 47 | 49 | 41 | 286 | 200 | 200 | 309 | 0 | 103 | 206 | 0 | 16 | 190
Yes | Not assigned | Managing Type | 1 | BIMZELX | Immunology | PS0010 | Study Archived | Dose ranging study of bimekizumab in Chronic Plaque PsO | Phase II | Double Blind | GCSO | Immunology | GCSO | Elyakhlifi S | Driver D | Parexel | SPI PXL | Yes | Yes | adults | No | A Multicenter, randomized, double-blind, placebo-controlled, parallel-group, dose ranging study to evaluate the safety, efficacy, pharmacokinetics, and pharmacodynamics of bimekizumab in adults subjects with moderate to severe chronic plaque psoriasis. | Psoriasis | Immunology | PS0010 is a parent study of PS0011 | 2015-11-06 | 2015-11-06 |  | 2016-06-02 | 2016-07-21 | 2016-08-25 | 2017-02-13 | 2017-03-01 | 2017-07-31 | 2017-07-10 | 2017-08-12 | 2017-11-21 | 2017-08-28 | 2018-03-08 | 2017-10-21 | 2018-05-30 | Canada, Czech Republic, Hungary, Japan, Poland, United States of America | Canada (LPLV), Czech Republic (LPLV), Hungary (LPLV), Japan (LPLV), Poland (LPLV), United States of America (LPLV) | Canada, Czech Republic, Hungary, Japan, Poland, United States of America | 30 | 43 | 40 | 300 | 245 | 200 | 355 | 0 | 105 | 250 | 0 | 17 | 233
Yes | Not assigned | Managing Type | 1 | BIMZELX | Immunology | PS0011 | Study Archived | BIMAB Phase 2 PsO Subjects | Phase II | Double Blind | GCSO | Immunology | UCB Pharma Global | Wall P | Beinhauer-Zellenka U | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, 48-WEEK, DOUBLE-BLIND, PLACEBO CONTROLLED, PARALLEL-GROUP EXTENSION STUDY TO ASSESS THE LONG-TERM SAFETY, TOLERABILITY, AND EFFICACY OF BIMEKIZUMAB IN ADULT SUBJECTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIASIS PHASE 2B | Psoriasis | Immunology | PS0011 is an extension of PS0010 | 2016-04-01 | 2016-03-29 |  | 2016-06-02 | 2016-11-11 | 2016-12-14 | 2017-08-15 | 2017-06-09 | 2018-09-25 | 2018-09-25 | 2018-11-09 | 2018-10-29 | 2018-12-03 | 2018-11-20 | 2019-02-15 | 2019-03-13 | Canada, Czech Republic, Hungary, Japan, Poland, United States of America | Canada (LPLV), Czech Republic (LPLV), Hungary (LPLV), Japan (LPLV), Poland (LPLV), United States of America (LPLV) | Canada, Czech Republic, Hungary, Japan, Poland, United States of America | 50 | 37 | 36 | 320 | 240 | 228 | 217 | 0 | 0 | 217 | 0 | 25 | 192
Yes | Not assigned | Managing Type | 1 | BIMZELX | Immunology | PS0016 | Study Archived | PD study in PSO to understand time to response/loss & conc. | Phase II | Double Blind | GED | Immunology | GED | Jones A | Driver D | Parexel | SPI PXL | Yes | Yes | adults | No | A MULTICENTER, RANDOMIZED, SUBJECT-BLIND, INVESTIGATOR-BLIND STUDY TO EVALUATE THE TIME COURSE OF PHARMACODYNAMIC RESPONSE, SAFETY AND PHARMACOKINETICS OF BIMEKIZUMAB IN ADULT SUBJECTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIASIS PHASE 2A | Psoriasis | Immunology | PS0016 is a parent study of PS0018 |  |  |  | 2016-06-06 | 2016-10-31 | 2016-12-27 | 2016-12-12 | 2017-03-06 | 2017-01-07 | 2017-12-11 | 2017-02-04 | 2018-04-16 | 2017-04-03 | 2018-06-09 | 2017-08-10 | 2018-07-18 | Australia, Canada, Moldavia, United States of America | Australia (LPLV), Canada (LPLV), Germany (1st Site Initiation (Cancelled)), Moldavia (LPLV), United States of America (LPLV) | Australia, Canada, Moldavia, United States of America | 10 | 12 | 10 | 45 | 45 | 45 | 73 | 0 | 24 | 49 | 0 | 2 | 47
Yes | Not assigned | Managing Type | 1 | BIMZELX | Immunology | RA0124 | Study Archived | UCB4940 BA Study | Phase I | Open | GED |  | Human Pharmacolgy (WHP) | Jones A | Driver D | PRA | SPI PRA | No | Yes | adults | Yes | AN OPEN-LABEL, PARALLEL-GROUP, SINGLE-DOSE STUDY TO EVALUATE THE ABSOLUTE BIOAVAILABILITY AND TOLERABILITY OF SUBCUTANEOUS UCB4940 IN HEALTHY SUBJECTS | Healthy Volunteers | Immunology |  | 2014-07-22 | 2014-07-29 |  | 2014-09-25 | 2014-11-20 | 2014-11-17 | 2014-12-11 | 2014-12-01 |  | 2015-04-26 |  | 2015-05-20 |  | 2015-07-15 |  | 2015-09-24 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 30 | 30 | 30 | 78 | 11 | 37 | 30 | 0 | 0 | 30
Yes | Not assigned | Managing Type | 1 | BIMZELX | Immunology | RA0134 | Protocol Approved (Cancelled) | OPEN-LABEL EXPLORATORY STUDY IN SUBJECTS WITH ACTIVATED PHOS | Phase II |  | GED | Immunology | GED | Jones A | Driver D | Parexel |  | Yes | Yes |  | No |  | Rheumatoid Arthritis | Immunology |  | 2016-02-01 | 2016-02-01 |  | 2016-04-04 | 2016-07-21 |  | 2017-02-02 | [9 empty] | Bulgaria, Georgia, Macedonia, Moldavia, Poland, Romania, Russian Federation, Serbia, United Kingdom | Bulgaria (1st Site Initiation), Georgia (Created), Macedonia (Created), Moldavia (1st Site Initiation), Poland (Created), Romania (Created), Russian Federation (Created), Serbia (Created), United Kingdom (Created) | Bulgaria, Moldavia | 4 | 2 | 0 | 80 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BIMZELX | Immunology | UC0011 | Study Archived | DB 2A EFFICACY, SAFETY, PK, BIMAB IN SUBJECTS WITH UC | Phase II | Double Blind | GCSO | Immunology | UCB Pharma Global | Esch M | Copetti C | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, SUBJECT-BLIND, INVESTIGATOR‑BLIND, RANDOMIZED, PLACEBO-CONTROLLED STUDY EVALUATING THE EFFICACY, SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF AN IV LOADING DOSE FOLLOWED BY SC ADMINISTRATION OF BIMEKIZUMAB (UCB4940) ADMINISTERED TO SUBJECTS WITH MODERATE TO SEVERE ACTIVE ULCERATIVE COLITIS | Colitis Ulcerative | Immunology |  | 2016-02-09 | 2016-02-09 |  | 2016-04-15 | 2016-08-12 | 2016-11-01 | 2017-08-31 | 2018-01-17 | 2018-03-01 | 2018-05-30 | 2018-03-15 | 2018-06-28 | 2018-03-29 | 2018-07-13 | 2018-05-29 | 2018-11-01 | Bulgaria, Czech Republic, Georgia, Italy, Moldavia, Poland, Romania, South Africa, Spain | Bulgaria (LPLV), Czech Republic (LPLV), Georgia (LPLV), Italy (LPLV), Moldavia (LPLV), Poland (LPLV), Romania (LPLV), South Africa (LPLV), Spain (LPLV), United Kingdom (1st Site Initiation (Cancelled)) | Bulgaria, Czech Republic, Georgia, Italy, Moldavia, Poland, Romania, South Africa, Spain | 25 | 23 | 13 | 90 | 60 | 55 | 52 | 0 | 29 | 23 | 0 | 4 | 19
Yes | Not assigned | Managing Type | 1 | BIMZELX | Immunology | UP0008 | Study Archived | To study the safety PK and PD of CDP4940 in mild psoriasis | Phase I | Double Blind | GED |  | GED | Valgaeren A | Mccabe S | Parexel | SPI PXL |  | No | adults | No | A RANDOMIZED, SUBJECT-BLIND, INVESTIGATOR-BLIND, PLACEBO-CONTROLLED, SINGLE-DOSE, DOSE ESCALATING STUDY EVALUATING THE SAFETY, PHARMACOKINETICS, AND PHARMACODYNAMICS OF UCB4940 IN PATIENTS WITH MILD TO MODERATE PSORIASIS | Psoriasis | Immunology |  | 2012-04-28 | 2012-08-01 |  | 2012-09-10 | 2012-11-22 | 2012-11-22 | 2013-02-19 | 2013-07-31 |  | 2014-01-13 |  | 2014-02-07 |  | 2014-04-25 |  | 2014-08-22 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 50 | 39 | 39 | 234 | 0 | 195 | 39 | 0 | 2 | 37
Yes | Not assigned | Managing Type | 1 | BIMZELX | Immunology | UP0031 | Study Archived | An Open-Label, Parallel-Group, Single-Dose Study to Evaluate | Phase I | Not Applicable | GED | Immunology | GED | Adriaens I |  | Parexel | SPI PXL | Yes | No | adults | Yes | An open-label, parallel-group, single dose study to evaluate the relative bioavailability and tolerability of 160mg subcutaneous bimekizumab in healthy subjects | Healthy Volunteers | Immunology |  | 2015-10-19 | 2015-11-24 |  | 2016-01-15 | 2016-03-04 | 2016-03-04 | 2016-03-18 | 2016-03-10 |  | 2016-06-17 |  | 2016-07-14 |  | 2016-08-08 |  | 2016-10-24 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 12 | 12 | 12 | 28 | 0 | 16 | 12 | 0 | 0 | 12
Yes | Not assigned | Managing Type | 1 | BIMZELX | Immunology | UP0042 | Study Archived | UP0042 BIMAB ethnic PK study | Phase I | Double Blind | GED | Immunology | UCB Pharma Global | Tatematsu S | Matsuoka K | Parexel | PAREXEL | No | Yes | adults | Yes | A RANDOMIZED DOUBLE-BLIND, PLACEBO-CONTROLLED, SINGLE-DOSE, PARALLEL-GROUP STUDY TO EVALUATE THE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF BIMEKIZUMAB ADMINISTERED AS SUBCUTANEOUS INJECTION TO JAPANESE AND CAUCASIAN HEALTHY SUBJECTS | Healthy Volunteers | Immunology |  |  |  |  | 2016-11-17 | 2017-02-07 | 2017-01-26 | 2017-02-24 | 2017-02-13 | 2017-07-14 | 2017-07-21 | 2017-08-10 | 2017-08-09 | 2017-09-04 | 2017-10-05 | 2017-11-17 | 2017-11-22 | Japan | Japan (LPLV) | Japan | 1 | 1 | 1 | 48 | 48 | 48 | 145 | 0 | 97 | 48 | 0 | 1 | 47
Yes | Not assigned | Managing Type | 1 | Bopindolol | not defined | SP0349 | Created | Drug Safety Trial Data. Study drug: BOPINDOLOL |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Drug Safety Trial Data. Study drug: BOPINDOLOL | [22 empty] | 0 | 0 | 0 | 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0007 | Study Archived | BE study for BRV oral tab. vs IV 100mg infusion | Phase I | Open | GED |  | R & D | Mollet M | Mccabe S | PRA | SPI PRA |  |  | adults | Yes | A RANDOMIZED, SINGLE-CENTER, OPEN-LABEL, 5-WAY CROSSOVER, SINGLE-DOSE BIOAVAILABILITY/BIOEQUIVALENCE COMPARISON OF BRIVARACETAM ORAL TABLETS (10MG, 50MG, 75MG, AND 100MG) AND BRIVARACETAM INTRAVENOUS BOLUS INJECTION (100MG) IN HEALTHY VOLUNTEERS | Epilepsy | Central Nervous System |  | 2012-07-27 | 2012-07-11 |  | 2012-11-27 |  | 2013-01-31 |  | 2013-02-25 |  | 2013-03-31 |  | 2013-04-26 |  | 2013-08-01 |  | 2013-10-02 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 25 | 25 | 25 | 47 | 0 | 22 | 25 | 0 | 0 | 25
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0039 | Protoc. Summary Approved (Cancelled) | PK stydy in end stage renal disease | Phase I |  | GED | Neurology | UCB Pharma Global |  |  | PRA | PRA |  |  | adults | No |  | Epilepsy | Central Nervous System |  | 2012-02-28 | 2012-07-26 | [17 empty] | 1 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0041 | Study Archived | BRV Ethanol interaction study | Phase I |  | R & D |  | UCB Pharma Global | Watanabe S | Cain D | N/A |  |  |  | adults | No | A DOUBLE-BLIND, RANDOMIZED, PLACEBO-CONTROLLED, THREE-WAY CROSSOVER STUDY TO INVESTIGATE THE DRUG-DRUG INTERACTIONS OF BRIVARACETAM AND ETHANOL IN HEALTHY MALE SUBJECTS | Epilepsy | Central Nervous System |  | 2012-06-26 | 2012-06-27 |  | 2012-08-20 | 2012-09-07 | 2012-09-24 | 2012-10-12 | 2012-10-01 |  | 2012-11-27 |  | 2013-04-05 |  | 2014-01-28 |  | 2014-02-27 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 25 | 18 | 18 | 31 | 0 | 13 | 18 | 1 | 0 | 17
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0066 | Created (Cancelled) | Epilepsy for Patients with Structural Brain Lesions | Registry |  | Clinical Development USA | CNS | Clinical Development USA | Melton K | Beaman M | [5 empty] | No |  | Epilepsy | Central Nervous System |  | 2014-06-16 | [18 empty] | 60 | 0 | 0 | 210 | 190 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0074 | Study Archived | PET study with BRV and LEV after intravenous admin in HVs | Phase I | Open | GED | Neurology | GED | Watanabe S | Cain D | PRA | PRA | No | Yes | adults | No | A SINGLE-CENTER, OPEN-LABEL POSITRON EMISSION TOMOGRAPHY STUDY TO EVALUATE THE TIMECOURSE OF DISPLACEMENT OF [11C]UCB-J BY BRIVARACETAM AND LEVETIRACETAM AFTER INTRAVENOUS ADMINISTRATION IN HEALTHY VOLUNTEERS | Epilepsy | Central Nervous System |  | 2015-04-15 | 2015-04-14 |  | 2015-06-09 | 2015-10-09 | 2015-11-02 | 2015-12-18 | 2017-06-01 | 2016-01-15 | 2017-09-01 | 2016-02-12 | 2017-10-26 | 2016-03-11 | 2017-12-08 | 2016-07-18 | 2018-03-07 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 26 | 13 | 13 | 11 | 0 | 2 | 9 | 0 | 1 | 8
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0077 | Study Archived | NIS study- BRV add-on | Non Interventional Study - Prospective | Open | GCSO | Neurology | UCB Pharma Global | Bollmann J, Joeres L | Beinhauer-Zellenka U | PRA | PRA | No | Yes | adults | No | A 12-MONTH NONINTERVENTIONAL, POSTMARKETING, MULTICENTER STUDY TO EVALUATE THE EFFECTIVENESS OF BRIVIACT® (BRIVARACETAM) AS ADJUNCTIVE THERAPY IN PATIENTS WITH EPILEPSY WITH PARTIAL-ONSET SEIZURES IN DAILY CLINICAL PRACTICE. | Epilepsy | Central Nervous System |  |  |  |  | 2015-11-04 | 2016-02-16 | 2016-02-16 | 2018-03-01 | 2019-06-27 11:00 | 2020-07-24 | 2020-07-15 10:00 | 2020-08-19 | 2020-08-25 | 2020-09-08 | 2020-09-23 | 2020-11-30 | 2020-12-07 | Denmark, Germany, Hungary, Ireland, Italy, Netherlands, Norway, Spain, United Kingdom | Denmark (LPLV), Germany (LPLV), Hungary (LPLV), Ireland (LPLV), Italy (LPLV), Netherlands (LPLV), Norway (LPLV), Spain (LPLV), United Kingdom (LPLV) | Denmark, Germany, Hungary, Ireland, Italy, Netherlands, Norway, Spain, United Kingdom | 100 | 48 | 43 | 530 | 530 | 530 | 548 | 0 | 0 | 548 | 0 | 216 | 332 |  |  |  | 2017-01-24
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0087 | Study Archived | BRV Epilepsy Monitoring Unit study | Phase II | Open | GCSO | Neurology | GCSO | Brown E | Tillery N | PRA | PRA | No | No | adults | No | A MULTICENTER, OPEN-LABEL, RANDOMIZED, PARALLEL-GROUP, ACTIVE-CONTROLLED STUDY TO ASSESS THE EFFICACY AND SAFETY OF BRIVARACETAM ADMINISTERED INTRAVENOUSLY AS TREATMENT FOR INCREASED SEIZURE ACTIVITY IN AN EPILEPSY MONITORING UNIT SETTING PHASE 2 | Epilepsy | Central Nervous System |  | 2016-05-28 | 2016-06-05 |  | 2016-07-28 | 2016-11-01 | 2017-02-07 05:00 | 2018-03-06 | 2018-04-25 12:12 | 2018-05-04 | 2018-04-27 12:12 | 2018-06-01 | 2018-06-06 | 2018-06-15 | 2018-08-23 | 2018-09-11 | 2018-12-03 | United States of America | United States of America (LPLV) | United States of America | 20 | 20 | 14 | 60 | 60 | 60 | 112 | 0 | 7 | 105 | 0 | 30 | 75
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01066 | Study Archived | 1st administration to men | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Pigeolet E |  |  | Medeval |  |  |  | Yes | Randomized, monocenter, double blind, placebo controlled, 3 alternating panel, 3-period rising single oral dose (10 to 1400mg), safety, tolerability, pharmacokinetic an pharmacodynamic study of ucb 34714 (capsule without exipient) in 27 healthy male volunteers. | Indication for Neuro Psychiatry; Indication for Phase I | Central Nervous System; Indication Group for Phase I |  |  |  | 2001-07-31 | 2001-08-10 | 2001-09-03 | 2001-09-03 |  |  | 2001-11-28 | 2001-12-12 | 2002-01-31 | 2002-03-19 |  |  | 2002-04-30 | 2002-10-16 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 0 | 1 | 43 | 27 | 27 | 43 | 0 | 16 | 27 | 0 | 0 | 27
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01067 | Study Archived | MTD multiple Dose | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Pigeolet E |  |  | A. Vranken (Quintiles) Medeval |  |  |  | Yes | Randomized, monocentre, double blind, placebo controlled, parallel group,2-weeks repeated oral dose, safety, tolerability, pharmacokinetic and pharmacodynamic study of ucb 34714 100 mg, 200 mg and 400 mg (capsule without excipient) twice daily in 36 healthy male volunteers. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 2002-04-22 | 2002-05-02 | 2002-05-09 |  |  | 2002-07-26 | 2002-08-09 | 2002-09-30 | 2002-10-18 |  | 2003-02-18 | 2002-12-30 | 2003-05-22 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 50 | 36 | 36 | 60 | 0 | 24 | 36 | 0 | 0 | 36
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01068 | Study Archived | C14 Oral | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | De Smedt F | [6 empty] | Yes | Open label, monocenter, excretion balance, pharmacokinetics and metabolism of 14C-labeled ucb 34714 after single 150mg oral dose administration in 6 healthy male volunteers. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 2002-04-10 |  | 2002-05-03 |  |  |  | 2002-05-28 |  | 2003-03-14 |  | 2003-03-21 |  | 2004-03-08 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 6 | 6 | 6 | 11 | 5 | 0 | 6 | 0 | 0 | 6
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01069 | Study Archived | Photosensitivity Study | Phase I | Single Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Pigeolet E, Riethuisen J | [6 empty] | No | A Placebo controlled, single blind, multi center study to explore the photoparoxysmal response in photosensitive epileptic subjects after one single oral dose(20 to 600 mg) of ucb 34714 in capsules. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2002-04-30 | 2002-05-16 | 2002-06-18 | 2002-09-13 |  | 2003-06-16 | 2002-11-15 | 2003-06-26 | 2003-01-15 | 2003-10-28 |  | 2003-12-09 | 2003-04-15 | 2004-03-31 | France, Germany | France (LPLV), Germany (LPLV), Netherlands (1st Site Initiation (Cancelled)) | France, Germany | 6 | 5 | 5 | 18 | 18 | 16 | 26 | 0 | 7 | 19 | 0 | 0 | 19
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01075 | Study Archived | Food Interaction | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Pigeolet E |  |  | Medeval |  |  |  | Yes | Randomized, monocenter, open label, two way cross-over, food interaction pilot study of a single dose (150mg) of ucb 34714 (oral capsule without excipient) in 8 healthy male volunteers | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2001-11-15 | 2001-11-19 | 2001-12-13 | 2001-12-17 |  |  | 2002-01-25 | 2002-01-23 | 2002-02-28 | 2002-06-12 |  |  | 2002-05-30 | 2002-11-26 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 8 | 8 | 8 | 10 | 0 | 2 | 8 | 0 | 0 | 8
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01079 | Study Archived | Median nerve | Phase I | Single Blind | Clinical Development Europe | Clinical Pharmaco | R & D | De Smedt F |  |  | CIC/UCB |  |  |  | Yes | Monocenter study of the hypoalgesic effect of venlafaxine 37.5 mg (part A, open) and of ucb 34714 200 mg and 400 mg (part B, placebo controlled, single-blind, randomized, three-way crossover), using electrical stimulation of the median nerve, in 24 healthy male volunteers. | Indication for Neuro Psychiatry | Central Nervous System |  | 2002-12-06 |  |  | 2003-01-14 |  | 2003-03-17 |  | 2003-04-07 |  | 2003-05-29 |  | 2003-10-14 |  | 2003-10-31 |  | 2004-05-19 | France | France (LPLV) | France | 1 | 1 | 1 | 24 | 24 | 24 | 25 | 0 | 9 | 16 | 0 | 3 | 13
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01080 | Study Archived | Drug- o.c. interaction study | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Moulaert B |  |  | Medeval / UCB |  |  |  | Yes | Randomized, monocenter, open label, two-way crossover, multiple oral dose interaction study between ucb 34714, 200 mg (oral capsule without excipient) twice daily and oral contraceptive (ethinylestradiol 30 mcg and levonorgestrel 150 mcg) once daily in 24 healthy female volunteers | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2002-04-30 | 2002-06-14 | 2002-07-19 | 2002-07-01 | 2002-08-09 |  | 2003-03-10 | 2002-12-15 | 2003-06-16 | 2003-03-01 | 2003-07-14 |  | 2003-10-15 | 2003-06-01 | 2004-04-19 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 24 | 24 | 24 | 35 | 0 | 11 | 24 | 0 | 1 | 23
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01081 | Study Archived | CBZ interaction study | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S, Mccabe S |  |  | Medeval/UCB |  |  |  | Yes | Monocenter, open label, bilateral pharmacokinetic interaction study of ucb 34714 (200 mg oral capsules bid) and carbamazepine (100 mg oral tablets/300 mg bid) during single and multiple oral administrations in 14 healthy male subjects | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2002-07-01 | 2002-08-19 | 2002-08-27 |  | 2002-09-12 |  |  |  | 2003-02-19 |  | 2003-04-16 |  | 2003-12-01 |  | 2004-06-21 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 30 | 14 | 14 | 19 | 0 | 5 | 14 | 0 | 1 | 13
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01082 | Study Archived | Phenytoin interaction | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S, Mccabe S |  |  | Medeval/UCB |  |  |  | Yes | Monocenter, open label, interaction study between ucb 34714 at steady state (200 mg oral capsules, twice daily) and single dose phenytoin 600 mg (2 x 300mg oral capsules) in 20 healthy male volunteers | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2002-07-01 | 2002-08-14 | 2002-08-19 | 2002-09-01 | 2002-09-06 | 2002-10-11 |  | 2002-11-15 | 2003-01-03 | 2003-01-15 | 2003-02-21 |  | 2004-03-05 | 2003-04-15 | 2004-05-18 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 20 | 20 | 20 | 27 | 0 | 7 | 20 | 0 | 1 | 19
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01097 | Created (Cancelled) | Bioequivalence polymorph I vs II | Phase I |  | Clinical Development Europe |  | R & D | De Smedt F | [6 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01104 | Protocol Approved (Cancelled) | Bioequivalence tablet vs capsule | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Mccabe S | [6 empty] | Yes | Monocenter, open label, randomized, four-way cross-over, oral single dose study to assess the relative bioavailability of brivaracetam capsules and tablets vs a reference oral solution, and to assess the influence of food on tablets in healthy male and female volunteers. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 2006-08-09 | [15 empty] | 1 | 0 | 0 | 56 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01109 | Study Archived | Renal insufficiency | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | De Smedt F |  |  | Pharmacon/UCB/independant monitor |  |  |  | No | Monocenter, open-label, parallel group, not randomized, pharmacokinetic study of a single oral administration of 200 mg capsule of ucb 34714, in subjects with normal renal function and with renal function impairment. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 2002-11-20 |  | 2003-03-20 |  |  |  | 2003-05-29 |  | 2003-08-20 |  | 2004-07-06 |  | 2004-08-30 | Poland | Poland (LPLV) | Poland | 1 | 1 | 1 | 18 | 18 | 18 | 22 | 0 | 4 | 18 | 0 | 0 | 18
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01111 | Study Archived | Hepatic insufficiency | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Perreaux A | [6 empty] | Yes | Open lable, parallel group, not randomized, pharmacikinetics study of a single oral administration of 100 mg ucb 34714 (50 mg capsules) in healthy subjects and patients with impaired liver function (Child-Pugh classes A, B and C). | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2004-02-16 | 2004-02-12 | 2004-08-18 | 2004-08-25 | 2005-11-02 | 2005-10-31 | 2005-11-30 | 2005-11-12 | 2006-01-03 | 2006-02-13 | 2006-02-28 | 2006-05-30 | 2006-04-30 | 2006-08-31 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 40 | 24 | 24 | 28 | 2 | 2 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01113 | Created (Cancelled) | POC | Phase II |  | Clinical Development Europe |  | R & D | Falter U | [6 empty] | No | [23 empty] | 6 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01114 | CSR Approved | ucb 34714 POC Epilepsy dose-ranging phase II | Phase II | Double Blind | Clinical Development Europe | CNS | R & D | Schelstraete I | Driver D |  | 100% PPD all countries |  |  |  | No | A multicenter, double-blind, randomized, placebo-controlled, 3 parallel groups, dose-ranging trial evaluating the efficacy and safety of ucb 34714 used as adjunctive treatment at doses of 50 and 150 mg/day in b.i.d. administration (oral capsules of 25 mg) for a maximum of 12 weeks in subjects from 16 to 65 years with refractory epilepsy suffering from partial onset seizures whether or not secondarily generalized | Indication for Neuro Psychiatry | Central Nervous System | N01114 is a feeder study of N01125 | 2004-07-12 | 2004-07-12 | 2004-09-30 | 2004-10-01 | 2005-01-15 | 2005-05-11 | 2005-10-15 | 2005-11-22 | 2006-03-15 | 2006-03-28 | 2006-05-15 | 2006-04-28 | 2006-06-30 | 2006-09-22 | 2006-09-15 | 2007-05-31 | Belgium, Czech Republic, Finland, France, Germany, Netherlands, Poland, Spain, United Kingdom | Belgium (LPLV), Czech Republic (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Netherlands (LPLV), Poland (LPLV), Spain (LPLV), United Kingdom (LPLV) | Belgium, Czech Republic, Finland, France, Germany, Netherlands, Poland, Spain, United Kingdom | 70 | 55 | 46 | 191 | 153 | 135 | 194 | 0 | 37 | 157 | 0 | 7 | 135
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01118 | Study Archived | PK elderly | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A, Riethuisen J |  |  | Biotrial |  |  |  | Yes | multicenter, open label, pharmacokinetic, safety and tolerability study of a single dose followed by a 10 day bid dosing regimen of ucb34714 administered twice a day orally as 200 mg capsules in healthy elderly volunteers | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2002-11-05 | 2002-12-15 | 2002-12-13 | 2003-02-20 | 2003-02-10 |  |  | 2003-03-04 | 2003-03-18 | 2003-04-30 | 2003-05-16 |  | 2003-07-18 | 2003-05-30 | 2004-09-01 | France | France (LPLV) | France | 2 | 2 | 2 | 16 | 16 | 15 | 33 | 17 | 0 | 16 | 0 | 1 | 15
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01124 | Protocol Approved (Cancelled) | ucb 34714: Post-herpetic neuralgia | Phase II | Double Blind | Clinical Development Europe |  | R & D | Falter U, Picciolato M | [6 empty] | No | An exploratory, double blind, randomized, placebo-controlled, parallel group, multicenter study, for the assessment of efficacy, safety and tolerability of ucb34714 50 mg oral caps. in b.i.d. administration at the dose of 400 mg/day (200 mg b.i.d.), in adults (more than 18 years) suffering from PHN. | Indication for Neuro Psychiatry | Central Nervous System |  | 2003-04-30 | 2003-03-20 | 2003-06-30 | 2003-07-17 | 2003-11-30 | [11 empty] | Belgium, France, Germany, United Kingdom | Belgium (Created), France (Created), Germany (Created), United Kingdom (Regulatory Approval) | United Kingdom | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01125 | Study Archived | ucb34714 - long term follow-up Epilepsy | Phase III | Open | GCSO | Neurology | GCSO | Reichel C | Anderson K | N/A | PPD | No | No | adults | No | An open-label, multi-center, follow-up trial to evaluate long-term safety and efficacy of brivaracetam (ucb 34714) used as adjunctive treatment at a flexible dose up to a maximum of 200 mg/day in subjects aged 16 years or older suffering from epilepsy | Epilepsy | Central Nervous System | N01125 is a follow up of N01114, N01187, N01236, N01252, N01254 | 2005-02-21 | 2001-01-01 | 2004-12-31 | 2005-01-21 | 2005-09-15 | 2005-09-08 | 2009-02-09 | 2009-02-09 | 2015-06-03 | 2019-05-28 | 2015-08-03 | 2019-07-15 | 2015-10-05 | 2019-09-25 | 2015-12-02 | 2019-10-17 | Austria, Belgium, Canada, Czech Republic, Finland, France, Germany, Hong Kong, Hungary, Israel, Italy, Netherlands, Norway, Poland, Russian Federation, Serbia, Singapore, South Africa, South Korea, Spain, Sweden, Switzerland, Taiwan, Tunisia, Ukraine, United States of America | Austria (LPLV), Belgium (LPLV), Canada (LPLV), Czech Republic (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Hong Kong (LPLV), Hungary (LPLV), Israel (LPLV), Italy (LPLV), Netherlands (LPLV), Norway (LPLV), Poland (LPLV), Russian Federation (LPLV), Serbia (LPLV), Singapore (LPLV), South Africa (LPLV), South Korea (LPLV), Spain (LPLV), Sweden (LPLV), Switzerland (LPLV), Taiwan (LPLV), Tunisia (LPLV), Ukraine (LPLV), United States of America (LPLV) | Austria, Belgium, Canada, Czech Republic, Finland, France, Germany, Hong Kong, Hungary, Israel, Italy, Netherlands, Norway, Poland, Russian Federation, Serbia, Singapore, South Africa, South Korea, Spain, Sweden, Switzerland, Taiwan, Tunisia, Ukraine, United States of America | 200 | 156 | 153 | 1000 | 1000 | 270 | 0 | 0 | 0 | 870 | 0 | 619 | 230
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01129 | Study Archived | Essential tremor explorative trial | Phase I | Single Blind | Clinical Development Europe | Clinical Pharmaco | R & D | De Smedt F |  |  | Monitoring Polish sites: CRA from Medisearch International Monitoring Hungarian site: CRA from Expert Select |  |  |  | No | A randomized placebo-controlled, 2-way crossover, monocenter, single-blind study to explore the efficacy of ucb 34714 in 32 subjects suffering from mild to moderate essential tremor after 14 days of multiple oral doses (up to 200 mg bid, 50 mg capsules). | Indication for Neuro Psychiatry | Central Nervous System |  | 2003-03-31 | 2003-03-31 | 2003-06-13 | 2003-06-12 | 2003-09-10 | 2004-02-16 |  | 2005-01-11 | 2004-03-31 | 2005-03-01 | 2004-05-31 | 2005-06-28 |  | 2005-08-09 | 2004-09-15 | 2006-09-25 | Belgium, France, Hungary, Poland | Belgium (LPLV), France (LPLV), Hungary (LPLV), Poland (LPLV) | Belgium, France, Hungary, Poland | 5 | 5 | 5 | 32 | 32 | 32 | 47 | 0 | 1 | 46 | 0 | 3 | 43
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01133 | Study Archived | CBZ interaction in patients | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S, Mccabe S | [6 empty] | No | Monocenter, open label, unilateral pharmacokinetic interaction study of ucb 34714 (100, 200 and 400 mg daily) on carbamazepine (³ 600 mg daily) during a four-week bid administration period in 9 adult male subjects suffering from epilepsy. | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2003-04-20 | 2003-05-30 | 2003-06-10 | 2003-08-01 | 2003-09-18 |  | 2003-10-30 | 2003-09-30 | 2003-12-18 | 2003-11-15 | 2004-03-11 |  | 2004-07-16 |  | 2006-07-06 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 16 | 9 | 9 | 9 | 0 | 0 | 9 | 0 | 0 | 9
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01135 | Study Archived | Interaction CBZ+valproate | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S, Mccabe S | [6 empty] | No | Multicenter, open label, unilateral metabolic interaction study of ucb 34714 (100, 200 and 400 mg daily) on carbamazepine (> 600 mg daily) during a four-week bid administration period in 9 adult male subjects suffering from epilepsy and treated with carbamazepine and valproate (> 500 mg daily). | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2003-06-04 | 2003-07-15 | 2003-07-17 | 2003-09-10 | 2004-03-29 |  | 2005-03-02 | 2003-11-30 | 2005-04-27 | 2004-01-20 | 2005-08-31 | 2004-05-30 | 2005-12-13 |  | 2006-09-14 | Poland, United Kingdom | Poland (LPLV), United Kingdom (LPLV) | Poland, United Kingdom | 4 | 3 | 2 | 18 | 9 | 9 | 10 | 0 | 1 | 9 | 0 | 0 | 9
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01147 | Created (Cancelled) | Presurgical design | Phase II |  | Clinical Development Europe |  | R & D | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01153 | Created (Cancelled) | NPP-PHN Pivotal EU | Phase III | Double Blind | Clinical Development Europe | CNS | R & D | Picciolato M | [6 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-04-07 | [18 empty] | 100 | 0 | 0 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01154 | Created (Cancelled) | NPP_Open-label follow-up study (EU) | Phase III | Open | UCB Pharma Global | Neurology | R & D | Falter U | [6 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-04-07 | [18 empty] | 100 | 0 | 0 | 650 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01155 | Created (Cancelled) | Ph II Comparison bid/od, titration/no titration | Phase II |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01156 | Created (Cancelled) | Essential Tremor Pivotal | Phase III |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01162 | CSR Approved | Post-herpetic Neuralgia (PHN) | Phase II | Double Blind | Clinical Development Europe | CNS | R & D | Picciolato M |  |  | UCB CRAs for UK, BE, FR and SP - Freelance CRA in Germany - CRO (Pharm-Olam) is responsible for the monitoring in CZ, SK, BG, CS and PL. |  |  |  | No | An exploratory, db, randomized, placebo-controlled, parallel group, multicenter study, for the assess. of efficacy, safety and tolerability of ucb 34714, 50 mg oral capsules in b.i.d. administration at the doses of 200 mg/day and 400 mg/day, in subjects (at least 18 y.) suffering from PHN. (as per Amendment 1) | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2003-11-20 | 2004-01-31 | 2004-01-23 | 2004-05-01 | 2004-10-11 | 2005-10-30 | 2005-11-17 | 2005-12-20 | 2006-01-05 | 2006-04-20 | 2006-03-02 | 2006-04-28 | 2006-04-07 | 2006-08-01 | 2006-12-19 | Belgium, Bulgaria, Czech Republic, France, Germany, Poland, Serbia, Slovakia, Spain, United Kingdom | Belgium (LPLV), Bulgaria (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Poland (LPLV), Serbia (LPLV), Slovakia (LPLV), Spain (LPLV), United Kingdom (LPLV) | Belgium, Bulgaria, Czech Republic, France, Germany, Poland, Serbia, Slovakia, Spain, United Kingdom | 30 | 53 | 41 | 200 | 150 | 150 | 214 | 0 | 44 | 152 | 0 | 13 | 139
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01163 | Protocol Approved (Cancelled) | Pharmaco EEG | Phase II | Open | Clinical Development Europe |  | R & D | Falter U | [6 empty] | No | An exploratory, open label, multicenter, pharmacodynamic study, evaluating the EEG under adjunctive treatment of ucb 34714 (50mg oral capsules in b.i.d. administration) during 5 to 8 days, in subjects 16 years and older suffering from Idiopathic Generalized Epilepsy. |  |  |  |  | 2004-01-09 |  | 2004-03-12 | [15 empty] | 7 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01169 | Study Archived | Population PK | Meta-analysis |  | UCB Pharma Global | Clinical Pharmaco | R & D | Falter U | [6 empty] | No | [19 empty] | 2005-11-18 |  |  |  | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01170 | Study Archived | Interaction 34714 - Topiramate | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Perreaux A | [6 empty] | Yes | Monocenter, open label, unilateral interaction study of brivaracetam at steady-state (200 mg twice daily) on topiramate (200 mg single dose) in 14 healthy male volunteers. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2004-11-30 | 2004-12-13 | 2005-05-05 | 2005-05-02 | 2005-05-13 | 2005-05-04 | 2005-06-20 | 2005-06-05 | 2005-07-15 | 2005-07-20 | 2005-08-16 | 2006-01-13 | 2005-11-07 | 2006-04-13 | Belgium | Belgium (LPLV) | Belgium | 1 | 0 | 1 | 21 | 14 | 14 | 24 | 0 | 10 | 14 | 0 | 0 | 14
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01171 | Study Archived | Interaction 34714 - Lamotrigine | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A | [6 empty] | Yes | Monocenter, open label, unilateral interaction study of ucb 34714 at steady-state (200 mg twice daily) on lamotrigine (25 mg single dose) in 14 healthy male volunteers. | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2005-01-18 | 2005-03-11 | 2005-03-18 | 2005-04-21 | 2005-04-22 | 2005-05-09 | 2005-05-31 | 2005-06-17 | 2005-06-25 | 2005-07-19 | 2005-07-26 | 2005-09-19 | 2005-10-04 | 2005-11-18 | 2006-06-29 | France | France (LPLV) | France | 0 | 1 | 1 | 23 | 14 | 14 | 23 | 0 | 9 | 14 | 0 | 0 | 14
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01172 | CSR Approved | Phenytoin interaction study | Phase I | Open | Clinical Development USA | Clinical Pharmaco | R & D | Salas V |  |  | Barbara Saiia (Contract Monitor) |  |  |  | No | A monocenter, open label, unilateral interaction study of ucb 34714 (400mg daily) on stable phenytoin monotherapy during a four-week bid administration period in 15 adult subjects suffering from epilepsy. | Indication for Neuro Psychiatry | Central Nervous System |  | 2004-04-16 | 2004-04-16 | 2004-06-18 | 2004-06-18 | 2004-09-03 | 2005-04-06 | 2005-01-31 | 2006-04-17 | 2005-04-05 | 2006-06-22 | 2005-05-06 | 2006-08-14 | 2005-07-22 | 2006-09-15 | 2005-11-04 | 2007-12-20 | United States of America | United States of America (LPLV) | United States of America | 3 | 3 | 3 | 17 | 15 | 15 | 27 | 0 | 8 | 19 | 0 | 0 | 19
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01178 | Created (Cancelled) | Essential Tremor dose ranging Phase lib | Phase II |  | UCB Pharma Global |  | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01185 | Study Archived | Intellisite 34714 | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | Global Medical Affairs | Bendahmane S |  |  | UCB/PP |  |  |  | Yes | Pharmacoscintigraphic investigation of the regional drug absorption of ucb 34714 (200 mg) delivered using the EnterionTM capsule in 3 different sites of the GI tract in comparison with the 200 mg immediate release oral capsule: open-label, randomized, four-way cross-over, single dose study, in 9 healthy adult male volunteers. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2004-09-03 | 2004-09-07 | 2004-10-12 | 2004-10-22 | 2004-11-16 | 2004-11-16 | 2004-12-15 | 2005-01-14 | 2005-02-18 | 2005-02-22 | 2005-07-15 | 2005-08-17 | 2005-09-12 | 2006-04-18 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 18 | 9 | 6 | 29 | 0 | 21 | 8 | 0 | 2 | 6
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01187 | CSR Approved | PME - ULD (Europe) | Phase III | Double Blind | Clinical Development Europe | CNS | R & D | Gerard D | [6 empty] | No | A multicenter, randomized, double-blind, placebo-controlled, parallel study to evaluate the efficacy and safety of brivaracetam used as adjunctive treatment for 12 weeks in adolescent and adult patients (=16 years) with genetically ascertained Unverricht-Lundborg disease. | Indication for Neuro Psychiatry | Central Nervous System | N01187 is a feeder study of N01125 | 2006-03-15 | 2006-03-14 | 2006-04-28 | 2006-05-05 | 2006-09-25 | 2006-11-21 | 2007-03-26 | 2007-05-24 | 2007-08-13 | 2007-10-15 | 2007-09-03 | 2007-11-19 | 2007-12-14 | 2007-12-21 | 2008-01-15 | 2009-05-13 | Finland, France, Italy, Netherlands, Reunion, Sweden, Tunisia | Finland (LPLV), France (LPLV), Italy (LPLV), Netherlands (LPLV), Reunion (LPLV), Sweden (LPLV), Tunisia (LPLV) | Finland, France, Italy, Netherlands, Reunion, Sweden, Tunisia | 15 | 13 | 13 | 55 | 45 | 39 | 56 | 0 | 6 | 50 | 0 | 3 | 47
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01188 | Created (Cancelled) | Essential Tremor F-U | Phase III |  | UCB Pharma Global |  | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01193 | CSR Approved | Low dose ranging trial with Brivaracetam | Phase II | Double Blind | Clinical Development USA | CNS | R & D |  |  |  | PPD |  |  |  | No | A multicenter, double-blind, randomized, placebo-controlled, 4 parallel groups, dose-ranging trial evaluating the efficacy and safety of brivaracetam used as adjunctive treatment at doses of 5, 20 and 50 mg/day in b.i.d. administration (oral tablets of 2.5 or 10 mg) for a maxiumem of 7 weeks in subjects from 16-65 years with refractory epilepsy suffering from partial onsent seizures whether or not secondarily generalized | Indication for Neuro Psychiatry | Central Nervous System | N01193 is a feeder study of N01199 | 2005-01-07 | 2005-02-04 | 2005-05-06 | 2005-05-09 | 2005-09-30 | 2005-11-07 | 2006-03-01 | 2006-03-30 | 2006-05-31 | 2006-06-29 | 2006-07-03 | 2006-08-02 | 2006-08-10 | 2006-09-28 | 2006-10-18 | 2008-07-17 | Brazil, India, Mexico, United States of America | Brazil (LPLV), India (LPLV), Mexico (LPLV), United States of America (LPLV) | Brazil, India, Mexico, United States of America | 65 | 53 | 43 | 255 | 204 | 184 | 265 | 0 | 55 | 210 | 0 | 13 | 197
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01199 | Study Archived | POS_Open label Follow-up - POS epilepsy | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Bullock E | Grose-Hodge R | N/A | PPD | No | No | other | No | An open-label, multicenter, follow-up trial to evaluate the long-term safety and efficacy of brivaracetam used as adjunctive treatment at a flexible dose up to a maximum of 200 mg/day in subjects aged 16 years or older suffering from epilepsy. | Epilepsy | Central Nervous System | N01199 is a follow up of N01193, N01253 | 2005-05-09 | 2005-05-09 | 2005-07-31 | 2005-08-30 | 2005-12-12 | 2006-01-23 | 2006-05-01 | 2009-02-06 | 2009-11-01 | 2017-09-18 | 2010-01-27 | 2017-11-02 | 2010-03-09 | 2017-12-21 | 2010-06-23 | 2018-03-09 | Australia, Brazil, Canada, India, Mexico, United States of America | Australia (LPLV), Brazil (LPLV), Canada (LPLV), India (LPLV), Mexico (LPLV), United States of America (LPLV) | Australia, Brazil, Canada, India, Mexico, United States of America | 200 | 99 | 99 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 672 | 0 | 549 | 120
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01202 | Created (Cancelled) | DN_Phase II b study - diabetic Neuropathy (dose raging) | Phase II |  | UCB Pharma Global |  | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01203 | Created (Cancelled) | DPN pivotal (US) | Phase III | Double Blind | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2008-09-01 |  |  |  | 100 | 0 | 0 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01204 | Created (Cancelled) | PHN Pivotal (US) | Phase III | Double Blind | UCB Pharma Global | Neurology | R & D | Falter U | [6 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2006-04-07 |  |  |  | 120 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01206 | Created (Cancelled) | OD PK | Phase I |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01207 | Created (Cancelled) | NPP Phase 2 in GBP refractory cases | Phase II |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01208 | Created (Cancelled) | POC Super efficacy in refractory epilepsy | Phase II |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01209 | CSR Approved | Phase I single dose (34714-JAP) | Phase I | Double Blind | Clinical Development Japan | Clinical Development Japan | R & D | Suzuki H | [6 empty] | Yes | A double-blind, randomized, placebo-controlled study to evaluate the saftey and pharmacokinetics of single oral dose of ucb 34714 in Japanese healthy adult male subjects. | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2007-10-30; 2005-02-04: 2007-10-25; 2005-05-09: 2007-12-19; 2005-11-07: 2008-02-25; 2006-03-30: 2008-09-02; 2006-06-29: 2008-10-04; 2006-08-02: 2008-12-16; 2006-09-28: 2009-07-31; 2008-07-17: 2009-12-10 | Japan | Japan (LPLV) | Japan | 1 | 0 | 1 | 80 | 80 | 80 | 82 | 0 | 32 | 50 | 0 | 0 | 50
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01210 | Created (Cancelled) | 34714-NI-A-POC | Phase II | Double Blind | Clinical Development Europe | CNS | R & D | [7 empty] | Yes |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2009-12-10 |  |  |  | 40 | 0 | 0 | 200 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01233 | CSR Approved | Thorough QT study | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S | [6 empty] | Yes | Randomized, placebo- and moxifloxacin-controlled study of the effect of brivaracetam on cardiac repolarization in four parallel groups of healthy male and female subjects. | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-01-18 | 2006-01-23 | 2006-02-14 | 2006-02-14 | 2006-04-03 | 2006-03-22 | 2006-07-05 | 2006-07-03 | 2006-07-31 | 2006-07-25 |  | 2006-10-19 | 2006-11-11 | 2006-12-19 | 2007-02-28 | 2007-02-14 | France | France (LPLV) | France | 0 | 2 | 2 | 300 | 182 | 182 | 292 | 0 | 108 | 184 | 0 | 2 | 182
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01236 | CSR Approved | PME - ULD (Global) | Phase III | Double Blind | Clinical Development Europe | CNS | R & D | Gerard D | [6 empty] | No | A multicenter, randomized, double-blind, placebo-controlled, parallel study to evaluate the efficacy and safety of brivaracetam used as adjunctive treatment for 12 weeks in adolescent and adult patients (=16 years) with genetically ascertained Unverricht-Lundborg disease. | Indication for Neuro Psychiatry | Central Nervous System | N01236 is a feeder study of N01125 | 2006-03-15 | 2006-03-14 | 2006-04-28 | 2006-05-05 | 2006-09-29 | 2006-11-07 | 2007-03-30 | 2007-08-03 | 2007-08-17 | 2008-01-08 | 2007-09-14 | 2008-03-12 |  | 2008-04-10 |  | 2008-10-07 | Canada, Finland, France, Israel, Russian Federation, Serbia, Tunisia, United States of America | Canada (LPLV), Finland (LPLV), France (LPLV), Israel (LPLV), Russian Federation (LPLV), Serbia (LPLV), Tunisia (LPLV), United States of America (LPLV) | Canada, Finland, France, Israel, Russian Federation, Serbia, Tunisia, United States of America | 0 | 19 | 18 | 55 | 45 | 39 | 72 | 1 | 15 | 56 | 0 | 2 | 54
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01238 | Created (Cancelled) | Ph IIb DPN (EU) | Phase II |  | Clinical Development Europe | CNS | R & D | Bare S | Baukens C | [5 empty] | No |  |  |  |  | 2005-01-07: 2006-04-07 |  |  |  | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01249 | CSR Approved | Dose-response refractory patients in POS | Meta-analysis |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  |  |  |  | 2008-07-17: 2007-06-01 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01250 | CSR Approved | Pop PK Ph II | Meta-analysis |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No |  |  |  |  | 2008-07-17: 2008-07-11 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01252 | Study Archived | POS_Pivotal study 1 - POS epilepsy (EUR) | Phase III | Double Blind | Clinical Development Europe | CNS | R & D | Schelstraete I | Driver D | [5 empty] | No | A multi-center, double-blind, parallel-group, placebo-controlled, randomized study: evaluation of the efficacy and safety of brivaracetam in subjects ( 16 to 70 years old) with Partial Onset Seizures. | Indication for Neuro Psychiatry | Central Nervous System | N01252 is a "sister" study of N01253 and is a feeder study of N01125 | 2006-09-01 | 2006-10-12 | 2007-01-16 | 2007-01-16 | 2007-06-01 | 2007-09-10 | 2008-02-29 | 2008-09-19 | 2008-08-14 | 2009-02-09 | 2008-09-12 | 2009-04-16 | 2008-10-13 | 2009-07-31 | 2008-12-17 | 2010-09-30 | Belgium, Finland, France, Germany, Hungary, India, Italy, Netherlands, Poland, Spain, Switzerland, United Kingdom | Belgium (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), India (LPLV), Italy (LPLV), Netherlands (LPLV), Poland (LPLV), Spain (LPLV), Switzerland (LPLV), United Kingdom (LPLV) | Belgium, Finland, France, Germany, Hungary, India, Italy, Netherlands, Poland, Spain, Switzerland, United Kingdom | 100 | 84 | 76 | 500 | 400 | 0 | 486 | 0 | 90 | 396 | 0 | 24 | 372
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01253 | Study Archived | POS_Pivotal study 2 - POS epilepsy (US) | Phase III | Double Blind | Clinical Development USA | CNS | R & D | Stalvey T | Edwards M | [5 empty] | No | An international, double-blind, parallel-group, placebo-controlled, randomized study: evaluation of the efficacy and safety of brivaracetam in subjects ( 16 to 70 years old) with Partial Onset Seizures | Indication for Neuro Psychiatry | Central Nervous System | N01253 is a "sister" study of N01252 and is a feeder study of N01199 | 2006-10-12 | 2006-10-12 | 2006-12-17 | 2007-02-05 | 2007-09-03 | 2007-09-07 | 2008-05-30 | 2008-07-23 | 2008-11-07 | 2009-01-02 | 2008-12-05 | 2009-03-17 | 2009-01-09 | 2009-07-31 | 2009-03-11 | 2011-08-17 | Australia, Brazil, Canada, Mexico, United States of America | Australia (LPLV), Brazil (LPLV), Canada (LPLV), Mexico (LPLV), United States of America (LPLV) | Australia, Brazil, Canada, Mexico, United States of America | 100 | 85 | 74 | 500 | 400 | 0 | 509 | 0 | 109 | 400 | 0 | 22 | 378
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01254 | Study Archived | POS global exposure study | Phase III | Double Blind | Clinical Development Europe | CNS | R & D | Pietteur V | [6 empty] | No | An international, randomized, double-blind, parrallel-group, placebo-controlled, flexible dose study : evaluation of the safety and efficacy of brivaracetam in subjects (>= 16 to 70 years old) suffering from localized-related or generalized epilepsy |  |  | N01254 is a feeder study of N01125 | 2006-09-04 | 2006-10-12 | 2006-12-22 | 2007-02-06 | 2007-06-01 | 2007-10-15 | 2008-02-29 | 2008-07-11 | 2008-08-29 | 2008-11-28 | 2008-09-29 |  | 2008-11-06 | 2009-07-31 | 2009-01-05 | 2010-12-16 | Austria, Belgium, Czech Republic, Germany, Hong Kong, India, Italy, Norway, Russian Federation, Singapore, South Africa, South Korea, Sweden, Taiwan, Ukraine | Austria (LPLV), Belgium (LPLV), Czech Republic (LPLV), Germany (LPLV), Hong Kong (LPLV), India (LPLV), Italy (LPLV), Norway (LPLV), Russian Federation (LPLV), Singapore (LPLV), South Africa (LPLV), South Korea (LPLV), Sweden (LPLV), Taiwan (LPLV), Ukraine (LPLV) | Austria, Belgium, Czech Republic, Germany, Hong Kong, India, Italy, Norway, Russian Federation, Singapore, South Africa, South Korea, Sweden, Taiwan, Ukraine | 110 | 85 | 74 | 588 | 470 | 470 | 541 | 0 | 62 | 479 | 0 | 33 | 446
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01256 | CSR Approved | iv PK 1 BE | Phase I | Open | UCB Pharma Global | Clinical Pharmaco | R & D | Valgaeren A | Mccabe S | [5 empty] | Yes | A randomized, monocenter, open-label, three-way cross-over, dose availability study of three different formulations of brivaracetam, followed by a non-randomized, monocenter, open label safety assessment study of four escalating doses of brivaracetam (BRV) administered via two formulations, on healthy volunteers | Indication for Neuro Psychiatry | Central Nervous System |  | 2007-03-16 | 2007-03-16 | 2007-06-01 | 2007-06-15 | 2007-08-14 | 2007-08-09 | 2007-10-31 | 2007-11-05 | 2007-11-29 | 2007-11-29 | 2008-01-07 | 2008-01-15 | 2008-02-29 | 2008-03-14 | 2008-04-30 | 2008-10-22 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 16 | 16 | 0 | 88 | 40 | 0 | 48 | 0 | 0 | 48 | 2007-12-05 | 2007-12-05 | 2008-02-29
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01257 | Created (Cancelled) | iv PK 2 Rapid infusion /high dose | Phase I | Open | UCB Pharma Global | Clinical Pharmaco | R & D | Falter U | [6 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2008-12-12 |  |  |  | 1 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01258 | Study Archived | iv patients safety | Phase III | Double Blind | Clinical Development USA | CNS | R & D | Barnes M | Kenney P | N/A | PRA is the selected CRO |  |  | adults | No | A MULTICENTER, OPEN-LABEL, FOUR-ARM, RANDOMIZED TRIAL EVALUATING THE SAFETY AND TOLERABILITY OF BRIVARACETAM INTRAVENOUS INFUSION AND BOLUS, ADMINISTERED IN BID REGIMEN AS AN ADJUNCTIVE ANTIEPILEPTIC TREATMENT IN SUBJECTS FROM 16 TO 70 YEARS SUFFERING FROM EPILEPSY | Indication for Neuro Psychiatry | Central Nervous System | N01258 is a feeder study of N01379 | 2007-06-18 | 2008-05-05 |  | 2008-10-20 |  | 2011-08-09 | 2012-05-10 | 2012-05-16 |  | 2012-07-20 |  | 2012-09-26 |  | 2012-11-27 |  | 2013-04-04 | Czech Republic, Germany, Poland, United States of America | Czech Republic (LPLV), Germany (LPLV), Poland (LPLV), United States of America (LPLV) | Czech Republic, Germany, Poland, United States of America | 35 | 24 | 17 | 125 | 100 | 0 | 114 | 0 | 9 | 105 | 2 | 2 | 101
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01259 | CSR Approved | Interaction with inhibitor/inducer CYP2C8 | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Valgaeren A | Mccabe S |  | ATC |  |  |  | Yes | Monocenter, open-label, randomized, 2x2-way cross-over study to assess the effects of gemfibrozil and rifampicin on the pharmacokinetics of brivaracetam, a CYP2C8 substrate, in healthy male subjects. | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-12-01 | 2006-12-01 | 2006-12-22 | 2007-01-12 | 2007-02-12 | 2007-02-26 | 2007-03-02 | 2007-03-08 | 2007-05-04 | 2007-05-03 | 2007-06-07 | 2007-06-22 | 2007-08-30 | 2007-10-02 | 2007-09-30 | 2008-04-07 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 70 | 52 | 52 | 81 | 0 | 29 | 52 | 0 | 1 | 51
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01261 | CSR Approved | Effect of Brivaracetam on midazolam | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Achour M, Mccabe S | [6 empty] | Yes | Single-centre, open-label Phase I study to assess the effects of a repeated administration of brivaracetam on CYP3A4 activity in human healthy male volunteers using midazolam as a probe | Indication for Neuro Psychiatry | Central Nervous System |  | 2007-01-01 |  | 2006-09-08 | 2006-09-11 | 2007-01-10 | 2007-01-10 | 2007-01-31 | 2007-01-29 | 2007-03-12 | 2007-03-07 | 2007-04-12 | 2007-05-03 | 2007-06-22 | 2007-06-20 | 2007-08-10 | 2008-01-08 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 60 | 42 | 42 | 60 | 0 | 18 | 42 | 0 | 1 | 41
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01263 | Study Archived | Phase IIa PK study in pediatric patients - Epilepsy | Phase II | Open | Clinical Development Europe | CNS | R & D | Martens A | Wajskop M | N/A | PRA |  |  | paediatrics | No | Open-label, single-arm, multi-center, pharmacokinetic, safety and efficacy study of adjunctive administration of brivaracetam in children (1 month - < 16 years) with epilepsy | Indication for Neuro Psychiatry | Central Nervous System | N01263 is a feeder study of N01266 | 2006-10-06 | 2006-10-12 | 2008-02-28 | 2010-11-10 | 2009-11-16 | 2011-07-05 | 2010-07-16 | 2013-02-11 | 2010-09-12 | 2013-03-13 | 2010-10-01 | 2013-05-08 | 2011-02-21 | 2013-06-06 | 2011-05-02 | 2013-08-22 | Belgium, Czech Republic, Mexico, Poland, Spain, United States of America | Belgium (LPLV), Czech Republic (LPLV), Mexico (LPLV), Poland (LPLV), Spain (LPLV), United States of America (LPLV) | Belgium, Czech Republic, Mexico, Poland, Spain, United States of America | 50 | 41 | 29 | 100 | 100 | 0 | 110 | 0 | 10 | 100 | 0 | 10 | 90
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01264 | Created (Cancelled) | Dose ranging POS Pediatric Phase IIB | Phase II |  | Clinical Development Europe | CNS | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2008-04-18 |  |  |  | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01265 | Created (Cancelled) | POS_Phase III study in pediatric patients - POS Epilepsy | Phase III | Double Blind | GCSO | Neurology | GCSO |  |  | PRA | SPI PRA |  |  |  | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2017-01-16 |  |  |  | 70 | 0 | 0 | 250 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01266 | Study Archived | Epilepsy - Pediatric FU open-label extension | Phase III | Open | GCSO | Neurology | GCSO | Reichel C | Anderson K | PRA | PRA | Yes | Yes | paediatrics | No | OPEN-LABEL, SINGLE-ARM, MULTICENTER, LONG-TERM STUDY TO EVALUATE SAFETY AND EFFICACY OF BRIVARACETAM USED AS ADJUNCTIVE TREATMENT IN PEDIATRIC SUBJECTS WITH EPILEPSY PHASE 3 | Epilepsy | Central Nervous System | N01266 is an extension of EP0065, N01263, N01349 and is a feeder study of EP0156 | 2007-09-07 08:00 | 2007-09-07 | 2008-02-28 | 2011-03-10 | 2009-12-29 | 2011-08-01 | 2013-03-01 | 2020-11-02 | 2017-09-04 | 2022-02-03 | 2017-10-05 | 2022-03-09 | 2017-12-04 | 2022-04-05 | 2018-03-20 | 2022-06-09 | Belgium, Czech Republic, Germany, Hungary, Italy, Mexico, Poland, Spain, United States of America | Belgium (LPLV), Czech Republic (LPLV), France (1st Site Initiation (Cancelled)), Germany (LPLV), Hungary (LPLV), Ireland (1st Site Initiation (Cancelled)), Italy (LPLV), Mexico (LPLV), Netherlands (1st Site Initiation (Cancelled)), Poland (LPLV), Spain (LPLV), United Kingdom (1st Site Initiation (Cancelled)), United States of America (LPLV) | Belgium, Czech Republic, Germany, Hungary, Italy, Mexico, Poland, Spain, United States of America | 150 | 89 | 46 | 600 | 600 | 420 | 264 | 0 | 7 | 257 | 0 | 137 | 120
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01267 | Created (Cancelled) | Peds PK1 month-4Y | Phase I | Double Blind | UCB Pharma Global | Clinical Pharmaco | R & D | Falter U | [6 empty] | Yes |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01276 | Study Archived | Conversion to monotherapy US | Phase III | Double Blind | Clinical Development USA | CNS | R & D | Jensen L | Driver D |  | - EU sites: PPD Belgium - US sites: PPD Development LP (Austin, TX - USA) |  |  |  | No | An international, double-blind, randomized, multi-center, parallel group, historical-control conversion to monotherapy study to evaluate the efficacy and safety of brivaracetam in subjects (= 16 to 75 years old) with partial onset seizures with or without secondary generalization. | Indication for Neuro Psychiatry | Central Nervous System | N01276 is a follow up of N01315 | 2007-09-27 | 2007-08-03 | 2007-11-20 | 2008-01-16 | 2008-05-31 | 2008-08-25 | 2009-12-01 | 2009-10-22 | 2010-07-30 | 2010-02-15 | 2010-09-14 | 2010-10-05 | 2010-10-21 | 2010-12-01 | 2011-01-13 | 2011-05-03 | Australia, Belgium, Canada, Czech Republic, Germany, Sweden, United States of America | Australia (LPLV), Belgium (LPLV), Canada (LPLV), Czech Republic (LPLV), Germany (LPLV), Sweden (LPLV), United States of America (LPLV) | Australia, Belgium, Canada, Czech Republic, Germany, Sweden, United States of America | 80 | 79 | 56 | 223 | 178 | 0 | 164 | 0 | 76 | 88 | 0 | 56 | 32 |  |  | 2010-03-15 | 2010-04-06
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01282 | CSR Approved | Briva 50 mg Interaction OC | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Stockis A |  |  | Biotrial |  |  |  | Yes | Interaction study between brivaracetam 50 mg twice daily and a combined oral contraceptive containing 30 µg ethinylestradiol and 150 µg levonorgestrel in healthy female subjects | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-12-15 | 2007-03-02 | 2007-04-02 | 2007-06-11 | 2007-05-10 | 2007-08-24 | 2007-07-06 | 2007-10-15 | 2007-11-30 | 2008-04-07 | 2008-01-04 | 2008-05-05 | 2008-02-15 | 2008-09-23 | 2008-04-13 | 2010-04-21 | France | France (LPLV) | France | 0 | 2 | 2 | 48 | 24 | 0 | 38 | 0 | 10 | 28 | 0 | 5 | 23
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01284 | Created (Cancelled) | Mono newly diagnosed EU | Phase III |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2010-11-17 |  |  |  | 100 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01285 | Created (Cancelled) | POS MONO LTFU | Phase III | Double Blind | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2009-11-14 |  |  |  | 70 | 0 | 0 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01287 | Study Archived | BioEquiv tablets vs capsules 25 & 50 | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Mccabe S | [6 empty] | Yes | Monocenter, open label, randomized, five-way cross-over relative bioavailability/bioequivalence study of brivaracetam solid oral formulations (capsule and tablet) using as reference brivaracetam oral solution with assessment of food effect on brivaracetam oral tablet formulation. | Indication for Neuro Psychiatry | Central Nervous System |  | 2007-06-22 |  | 2007-03-06 | 2007-03-02 | 2007-04-23 | 2007-05-10 | 2007-05-14 | 2007-05-21 | 2007-06-22 | 2007-06-29 | 2007-08-10 | 2007-08-07 | 2007-10-10 | 2007-10-08 | 2007-11-08 | 2007-12-07 | France | France (LPLV) | France | 0 | 0 | 1 | 25 | 25 | 25 | 33 | 0 | 8 | 25 | 25 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01294 | Created (Cancelled) | Phase I multiple dose | Phase I |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2012-01-14 |  |  |  | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01295 | Study Archived | Drug Abuse Potential | Phase I | Double Blind | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | Yes | A Mono-center, Randomized, Double-blind, Triple-dummy Placebo, Unscheduled and Scheduled Comparators Controlled, Single-dose Crossover Trial to Evaluate the Abuse Potential of Brivaracetam in Subjects with a History of Recreational CNS Depressant Use | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2008-01-25; 2005-05-09: 2008-02-01; 2005-11-07: 2008-11-17; 2006-03-30: 2008-12-22; 2006-06-29: 2009-03-03; 2006-08-02: 2009-04-23; 2006-09-28: 2009-07-03; 2008-07-17: 2011-04-21 | Canada | Canada (LPLV) | Canada | 1 | 1 | 1 | 36 | 36 | 0 | 192 | 0 | 112 | 44 | 0 | 8 | 36
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01296 | CSR Approved | Oral solution | Phase I | Open | UCB Pharma Global | Clinical Pharmaco | R & D | Mccabe S | [6 empty] | Yes | Randomized, monocenter, open label, two-way crossover, single dose bioequivalence study of two different formulations of brivaracetam in healthy fasting subjects. | Indication for Neuro Psychiatry | Central Nervous System |  | 2007-10-24 |  | 2007-08-24 | 2007-08-24 | 2008-01-07 | 2008-01-07 | 2008-01-23 | 2008-02-04 | 2008-02-11 | 2008-02-15 | 2008-03-18 | 2008-03-14 | 2008-05-05 | 2008-05-23 | 2008-05-29 | 2008-08-05 | France | France (LPLV) | France | 1 | 1 | 1 | 37 | 24 | 24 | 37 | 0 | 13 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01297 | CSR Approved | BRV neurocognitive effects in health volunteers | Phase I | Double Blind | UCB Pharma Global | Neurology | R & D | Hoeckendorff J | Anderson K | [5 empty] | Yes | Randomized, comparative, double-blind, placebo-controlled four-way cross-over study to investigate neurocognitive effects of brivaracetam in healthy subjects |  |  |  | 2005-01-07: 2008-01-19; 2005-02-04: 2008-02-01; 2005-05-09: 2008-05-21; 2005-11-07: 2008-07-14; 2006-03-30: 2008-08-21; 2006-06-29: 2008-10-13; 2006-08-02: 2009-01-07; 2006-09-28: 2009-04-16; 2008-07-17: 2010-08-09 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 60 | 20 | 16 | 77 | 0 | 57 | 20 | 0 | 4 | 16
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01298 | Created (Cancelled) | LEV non-responders switch study | Phase II |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  |  |  |  | 2005-01-07: 2010-06-16 |  |  |  | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01299 | Created (Cancelled) | CAE/JAE Video-EEG monotherapy | Phase II |  | UCB Pharma Global | Neurology | R & D |  |  | PRA | SPI PRA |  |  |  | No |  |  |  |  | 2005-01-07: 2013-12-27 |  |  |  | 20 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01300 | Created (Cancelled) | BRV Ph III/IV a | Phase IV |  | UCB Pharma Global | GMA Neurology / Psychiatry | Global Medical Affairs | [7 empty] | No |  |  |  |  | 2005-01-07: 2011-03-03 |  |  |  | 40 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01301 | Created (Cancelled) | BRV Ph III/IV b | Phase IV |  | UCB Pharma Global | GMA Neurology / Psychiatry | Global Medical Affairs | [7 empty] | No |  |  |  |  | 2005-01-07: 2011-10-31 |  |  |  | 40 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01302 | Created (Cancelled) | BRV Ph III/IV c | Phase IV |  | UCB Pharma Global | GMA Neurology / Psychiatry | Global Medical Affairs | [7 empty] | No |  |  |  |  | 2005-01-07: 2012-01-23 |  |  |  | 40 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01303 | Created (Cancelled) | BRV Ph III/IV d | Phase IV |  | UCB Pharma Global | GMA Neurology / Psychiatry | Global Medical Affairs | [7 empty] | No |  |  |  |  | 2005-01-07: 2011-03-03 |  |  |  | 40 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01306 | Study Archived | Conversion to Monotherapy EU | Phase III | Double Blind | Clinical Development Europe | CNS | R & D | Heidbrede T, Hufkens V, Jensen L | Driver D |  | - EU sites: PPD Belgium - US sites: PPD Development LP (Austin, TX - USA) |  |  |  | No | An international, double-blind, randomized, multi-center, parallel group, historical-control conversion to monotherapy study to evaluate the efficacy and safety of brivaracetam in subjects (= 16 to 75 years old) with partial onset seizures with or without | Indication for Neuro Psychiatry | Central Nervous System | N01306 is a parent study of N01315 | 2007-09-27 | 2007-08-03 | 2007-11-20 | 2008-01-16 | 2008-05-30 | 2008-08-06 | 2009-11-30 | 2009-11-05 | 2010-08-01 | 2010-03-09 | 2010-09-14 | 2010-10-15 | 2010-10-20 | 2010-12-09 | 2011-01-12 | 2011-05-04 | France, Germany, Hungary, Italy, Spain, United States of America | Finland (1st Site Initiation (Cancelled)), France (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Spain (LPLV), United States of America (LPLV) | France, Germany, Hungary, Italy, Spain, United States of America | 68 | 75 | 37 | 223 | 178 | 178 | 106 | 0 | 44 | 62 | 0 | 39 | 23 |  |  | 2010-03-30 | 2010-04-06
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01315 | Study Archived | Monotherapy LTFU | Phase III | Open | GCSO | Neurology | R & D | Wheeler L | Smit R | N/A | PPD | No | No | other | No | An open-label, multinational, multicenter, follow-up study to evaluate the long-term safety and efficacy of brivaracetam, used at a flexible dose up to a maximum of 200 mg/day, in subjects aged 16 years or older suffering from epilepsy. | Epilepsy | Central Nervous System | N01315 is a follow up of N01306 and is a parent study of N01276 |  | 2008-04-18 |  | 2008-04-18 | 2008-10-08 | 2008-11-19 | 2009-04-20 | 2010-02-09 | 2012-07-10 | 2017-03-20 | 2012-07-30 | 2017-07-10 | 2012-08-28 | 2017-08-31 | 2012-11-19 | 2017-11-29 | Australia, Belgium, Canada, Czech Republic, France, Germany, Hungary, Italy, Spain, Sweden, United States of America | Australia (LPLV), Belgium (LPLV), Canada (LPLV), Czech Republic (LPLV), Finland (1st Site Initiation (Cancelled)), France (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Spain (LPLV), Sweden (LPLV), United States of America (LPLV) | Australia, Belgium, Canada, Czech Republic, France, Germany, Hungary, Italy, Spain, Sweden, United States of America | 160 | 141 | 58 | 600 | 600 | 150 | 0 | 0 | 0 | 109 | 0 | 85 | 23
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01358 | Study Archived | Therapeutic Confirmatory Study | Phase III | Double Blind | GCSO |  |  | Copetti C, Kimbara A, Suzuki A | Beinhauer-Zellenka U, Grose-Hodge R | N/A | PRA | Yes | No | adults | No | A RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER, PARALLEL-GROUP STUDY TO EVALUATE THE EFFICACY AND SAFETY OF BRIVARACETAM IN SUBJECTS (>=16 TO 80 YEARS OLD) WITH PARTIAL ONSET SEIZURES | Epilepsy | Central Nervous System | N01358 is a feeder study of N01379 |  | 2010-09-27 |  | 2010-09-15 | 2011-01-14 | 2010-12-10 | 2012-06-12 | 2013-12-20 |  | 2014-05-22 |  | 2014-06-30 |  | 2014-07-21 |  | 2014-11-06 | Austria, Belgium, Brazil, Bulgaria, Canada, Czech Republic, Estonia, Finland, France, Germany, Hong Kong, Hungary, India, Italy, Japan, Latvia, Lithuania, Mexico, Netherlands, Poland, Russian Federation, South Korea, Spain, Sweden, Taiwan, United Kingdom, United States of America | Austria (LPLV), Belgium (LPLV), Brazil (LPLV), Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), Estonia (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Hong Kong (LPLV), Hungary (LPLV), India (LPLV), Italy (LPLV), Japan (LPLV), Latvia (LPLV), Lithuania (LPLV), Mexico (LPLV), Netherlands (LPLV), Poland (LPLV), Russian Federation (LPLV), South Korea (LPLV), Spain (LPLV), Sweden (LPLV), Taiwan (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Austria, Belgium, Brazil, Bulgaria, Canada, Czech Republic, Estonia, Finland, France, Germany, Hong Kong, Hungary, India, Italy, Japan, Latvia, Lithuania, Mexico, Netherlands, Poland, Russian Federation, South Korea, Spain, Sweden, Taiwan, United Kingdom, United States of America | 133 | 257 | 208 | 950 | 720 | 720 | 1045 | 0 | 277 | 768 | 0 | 72 | 696
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01372 | Study Archived | N01372 Ph IIIb_IV Long Term Follow up | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Howerton C | Smit R | PRA | SPI PRA | No | No | other | No | AN OPEN-LABEL, MULTICENTER, FOLLOW-UP STUDY TO EVALUATE THE LONG-TERM SAFETY AND EFFICACY OF BRIVARACETAM USED AS ADJUNCTIVE TREATMENT IN SUBJECTS AGED 16 YEARS OR OLDER WITH EPILEPSY PHASE 3b | Epilepsy | Central Nervous System | N01372 is a follow up of N01395 | 2011-11-18 | 2011-12-12 |  | 2012-03-27 | 2012-09-19 | 2012-10-17 | 2016-04-30 | 2013-11-15 |  | 2016-08-09 |  | 2016-10-18 |  | 2016-11-10 |  | 2017-03-31 | France, Germany, Spain, United States of America | France (LPLV), Germany (LPLV), Spain (LPLV), United States of America (LPLV) | France, Germany, Spain, United States of America | 30 | 10 | 10 | 100 | 100 | 0 | 26 | 0 | 0 | 26 | 0 | 13 | 13
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01379 | Study Archived | POS Open Label Follow-up Study | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Reichel C | Anderson K | PRA | PRA | No | No | adults | No | AN OPEN-LABEL, MULTICENTER, FOLLOW-UP STUDY TO EVALUATE THE LONG-TERM SAFETY AND EFFICACY OF BRIVARACETAM USED AS ADJUNCTIVE TREATMENT IN SUBJECTS AGED 16 YEARS OR OLDER WITH EPILEPSY | Epilepsy | Central Nervous System | N01379 is an extension of N01358 and is a follow up of N01258 |  | 2010-04-30 |  | 2010-09-15 | 2011-06-07 | 2011-05-10 | 2013-01-01 | 2014-05-12 | 2019-04-30 | 2019-04-18 | 2019-05-30 | 2019-06-11 | 2019-07-11 | 2019-07-23 | 2019-09-18 | 2019-09-23 | Austria, Belgium, Brazil, Bulgaria, Canada, Czech Republic, Estonia, Finland, France, Germany, Hong Kong, Hungary, India, Italy, Japan, Latvia, Lithuania, Mexico, Netherlands, Poland, Russian Federation, South Korea, Spain, Sweden, Taiwan, United Kingdom, United States of America | Austria (LPLV), Belgium (LPLV), Brazil (LPLV), Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), Estonia (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Hong Kong (LPLV), Hungary (LPLV), India (LPLV), Italy (LPLV), Japan (LPLV), Latvia (LPLV), Lithuania (LPLV), Mexico (LPLV), Netherlands (LPLV), Poland (LPLV), Russian Federation (LPLV), South Korea (LPLV), Spain (LPLV), Sweden (LPLV), Taiwan (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Austria, Belgium, Brazil, Bulgaria, Canada, Czech Republic, Estonia, Finland, France, Germany, Hong Kong, Hungary, India, Italy, Japan, Latvia, Lithuania, Mexico, Netherlands, Poland, Russian Federation, South Korea, Spain, Sweden, Taiwan, United Kingdom, United States of America | 170 | 195 | 184 | 720 | 720 | 650 | 768 | 0 | 0 | 768 | 0 | 467 | 300
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01391 | Created (Cancelled) | OL study to show that BRV and LCM are an ideal combination t |  |  | Clinical Development Europe | CNS | Global Medical Affairs Europe | Vandendriessche A | Beaman M | PRA | PRA |  |  |  | No |  | Epilepsy | Central Nervous System |  | 2005-01-07: 2014-04-05 |  |  |  | 30 | 0 | 0 | 140 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01394 | Study Archived | BRIV IV in NICU | Phase II | Open | GCSO | Neurology |  | Heinzen L | Smit R | PRA | SPI PRA | No | No | adults | No | A RANDOMIZED, OPEN-LABEL, MULTICENTER, PARALLEL-GROUP, EXPLORATORY STUDY TO EVALUATE THE EFFICACY OF INTRAVENOUS BRIVARACETAM AND INTRAVENOUS PHENYTOIN IN SUBJECTS EXPERIENCING NONCONVULSIVE ELECTROGRAPHIC SEIZURES | Indication for Neuro Psychiatry | Central Nervous System |  | 2012-04-10 | 2012-07-19 |  | 2012-12-06 | 2013-05-03 | 2014-03-24 | 2015-05-05 | 2014-08-08 |  | 2014-10-21 |  | 2015-02-26 |  | 2015-04-07 |  | 2015-04-07 | United States of America | United States of America (LPLV) | United States of America | 15 | 7 | 2 | 60 | 50 | 46 | 2 | 0 | 1 | 1 | 0 | 1 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | Central Nervous System | N01395 | Study Archived | BRV differentation from LEV | Phase III | Open | Clinical Development Europe | GMA Neurology / Psychiatry | Global Medical Affairs | Van Den Steen B | Cain D | PRA | SPI PRA |  |  | other | No | AN OPEN-LABEL, MULTICENTER, SINGLE-ARM STUDY TO EVALUATE THE REDUCTION IN NONPSYCHOTIC BEHAVIORAL SIDE EFFECTS IN SUBJECTS WITH EPILEPSY SWITCHING FROM LEVETIRACETAM TO BRIVARACETAM DUE TO NONPSYCHOTIC BEHAVIORAL SIDE EFFECTS PHASE 3b | Epilepsy | Central Nervous System | N01395 is a parent study of N01372 | 2011-09-16 | 2011-10-03 |  | 2012-01-12 | 2012-05-30 | 2012-07-24 | 2014-05-29 | 2013-08-21 |  | 2013-11-15 |  | 2014-01-26 |  | 2014-06-25 |  | 2014-09-05 | France, Germany, Spain, United Kingdom, United States of America | France (LPLV), Germany (LPLV), Italy (1st Site Initiation (Cancelled)), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | France, Germany, Spain, United Kingdom, United States of America | 31 | 31 | 12 | 35 | 32 | 30 | 32 | 0 | 3 | 29 | 0 | 3 | 26
Yes | Not assigned | Managing Type | 1 | BRIVIACT | not defined | N01277 | Protoc. Summary Approved (Cancelled) | Phase III Pivotal PGTCS | Phase III | Double Blind | Clinical Development USA | CNS | Clinical Development USA | Jensen L | Driver D | PRA | PRA |  |  | other | No |  | Indication for Neuro Psychiatry | Central Nervous System | N01277 is a follow up of N01279 and is a parent study of N01279 | 2005-01-07: 2011-06-24; 2005-02-04: 2011-06-22 | Australia, Austria, Belgium, Canada, China, Czech Republic, France, Germany, Greece, Hungary, India, Israel, Italy, Mexico, Poland, Romania, Russian Federation, Serbia, Slovakia, South Africa, South Korea, Spain, Sweden, Taiwan, Ukraine, United Kingdom, United States of America | Australia (Created), Austria (Created (Held)), Belgium (Created), Canada (Created), China (Created), Czech Republic (Created), France (Created), Germany (Created), Greece (Created), Hungary (Created), India (Created), Israel (Created), Italy (Created), Mexico (Created), Poland (Created), Romania (Created), Russian Federation (Created), Serbia (Created), Slovakia (Created), South Africa (Created), South Korea (Created), Spain (Created), Sweden (Created), Taiwan (Created), Ukraine (Created), United Kingdom (Created), United States of America (Created) |  | 225 | 0 | 0 | 785 | 550 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2016-01-11
Yes | Not assigned | Managing Type | 1 | BRIVIACT | not defined | N01278 | Protoc. Summary Approved (Cancelled) | Phase III Pivotal JME | Phase III | Double Blind | UCB Pharma Global | Neurology | R & D |  |  | PRA | PRA |  |  |  | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2011-07-29; 2005-02-04: 2011-10-24 |  |  |  | 40 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | BRIVIACT | not defined | N01279 | Protoc. Summary Approved (Cancelled) | PGS LTFU | Phase III | Double Blind | Clinical Development USA | CNS | R & D | Jensen L | Driver D | PRA | SPI PRA |  |  |  | No |  | Indication for Neuro Psychiatry | Central Nervous System | N01279 is a follow up of N01277 and is a parent study of N01277 | 2005-01-07: 2011-08-03; 2005-02-04: 2011-08-12 | Australia, Belgium, Canada, China, Czech Republic, France, Germany, Greece, Hungary, India, Israel, Italy, Mexico, Poland, Romania, Russian Federation, Serbia, Slovakia, South Africa, South Korea, Spain, Sweden, Taiwan, Ukraine, United Kingdom, United States of America | Australia (Created), Belgium (Created), Canada (Created), China (Created), Czech Republic (Created), France (Created), Germany (Created), Greece (Created), Hungary (Created), India (Created), Israel (Created), Italy (Created), Mexico (Created), Poland (Created), Romania (Created), Russian Federation (Created), Serbia (Created), Slovakia (Created), South Africa (Created), South Korea (Created), Spain (Created), Sweden (Created), Taiwan (Created), Ukraine (Created), United Kingdom (Created), United States of America (Created) |  | 80 | 0 | 0 | 200 | 200 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2020-11-03
Yes | Not assigned | Managing Type | 1 | Bupranolol | not defined | SP0234 | Created | BUPRANOLOL - bei Patienten mit primärer Hypertonie im WHO-St |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | BUPRANOLOL - bei Patienten mit primärer Hypertonie im WHO-Stadium I-III | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Bupranolol | not defined | SP0357 | Created | Bupranolol - Betadrenol 100 - Patch - Tablets - Patients wit |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Bioavailability and pharmacokinetics of bupranolol after single dose aministration of bupranolol-TTS or betadrenol 100 tablets in patients with impaired liver function compared to healthy controls | [22 empty] | 0 | 0 | 0 | 23 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Bupranolol | not defined | SP0499 | Created | Bupranolol |  | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Einfluß einer chronischen Betarezeptorenblockade bei koronarkranken Pat. auf psychomentalen Streß und körperliche Belastung bezüglich Kreislaufverhalten | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0103 | Created | ASS / CAPTOPRIL - bei Patienten mit leichter bis mittelschwe |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | ASS / CAPTOPRIL - bei Patienten mit leichter bis mittelschwerer Hypertonie | Mild to Moderate Hypertension | Immunology | [20 empty] | 0 | 0 | 0 | 36 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0104 | Created | CAPTOPRIL - bei Patienten mit essentieller Hypertonie und li |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | CAPTOPRIL - bei Patienten mit essentieller Hypertonie und linksventrikulärer Hypertrophie | [22 empty] | 0 | 0 | 0 | 92 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0119 | Created | COR-TENSOBON - bei Patienten mit chronischer Linksherzinsuff |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | COR-TENSOBON - bei Patienten mit chronischer Linksherzinsuffizienz | [22 empty] | 0 | 0 | 0 | 142 | 140 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0121 | Created | TENSOBON-COMP - Überprüfung der Wirksamkeit, Verträglichkeit |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | TENSOBON-COMP - Überprüfung der Wirksamkeit, Verträglichkeit, Lebenszufriedenheit | [22 empty] | 0 | 0 | 0 | 592 | 562 | 562 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0157 | Created | TENSOBON-25 - bei Patienten mit akutem Myokardinfarkt |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | TENSOBON-25 - bei Patienten mit akutem Myokardinfarkt | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0158 | Created (Cancelled) | CAPTOPRIL - bei Patienten mit unbehandelter leichter bis mit |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | CAPTOPRIL - bei Patienten mit unbehandelter leichter bis mittelschwerer Hypertonie | Mild to Moderate Hypertension | Immunology | [20 empty] | 0 | 0 | 0 | 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0219 | Created (Cancelled) | TENSOBON - bei Nonrespondern mit leichter bis mittelschwerer |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | TENSOBON - bei Nonrespondern mit leichter bis mittelschwerer Hypertonie | Mild to Moderate Hypertension | Immunology | [20 empty] | 0 | 0 | 0 | 207 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0220 | Created | Drug Safety Trial Data. Study drug: TENSOBON |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: TENSOBON | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0221 | Created (Cancelled) | TENSOBON-25 Prüfung zur Prävention einer Rezidivstenose pos |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | TENSOBON-25 Prüfung zur Prävention einer Rezidivstenose post PTCA | [22 empty] | 0 | 0 | 0 | 239 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0226 | Created | TENSOBON - bei herzinsuffizienten Patienten mit und ohne Nit |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | TENSOBON - bei herzinsuffizienten Patienten mit und ohne Nitrattoleranz | [22 empty] | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0232 | Created | TENSOBON/TENSOBON-COMP - in patients with mild to moderate h |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | TENSOBON/TENSOBON-COMP - in patients with mild to moderate hypertension | Mild to Moderate Hypertension | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0236 | Created | TENSOBON - bei progressiver systemischer Sklerodermie |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | TENSOBON - bei progressiver systemischer Sklerodermie | [22 empty] | 0 | 0 | 0 | 36 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0237 | Created | TENSOBON - bei Patienten mit chronischer Herzinsuffizienz |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | TENSOBON - bei Patienten mit chronischer Herzinsuffizienz | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0238 | Created | TENSOBON - bei Patienten mit Belastungskoronarinsuffizienz |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | TENSOBON - bei Patienten mit Belastungskoronarinsuffizienz | [22 empty] | 0 | 0 | 0 | 43 | 43 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0261 | Created | TENSOBON-25 - bei Patienten mit chronischer Linksherzinsuffi | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | TENSOBON-25 - bei Patienten mit chronischer Linksherzinsuffizienz | [22 empty] | 0 | 0 | 0 | 551 | 535 | 535 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0268 | Created (Cancelled) | TENSOBON-25 - bei normotonen Diabetikern |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | TENSOBON-25 - bei normotonen Diabetikern | [22 empty] | 0 | 0 | 0 | 14 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0273 | Created | COR-TENSOBON - bei Patienten mit chronischer Herzinsuffizien |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | COR-TENSOBON - bei Patienten mit chronischer Herzinsuffizienz | [22 empty] | 0 | 0 | 0 | 1606 | 1236 | 1236 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0352 | Created | TENSOBON-not available (DMCD) |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | not available (DMCD) | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0353 | Created | TENSOBON - bei Patienten mit chronischer Herzinsuffizienz |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | TENSOBON - bei Patienten mit chronischer Herzinsuffizienz | [22 empty] | 0 | 0 | 0 | 54 | 46 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0402 | Created | TENSOBON - bei Patienten mit chronischer Linksherzinsuffizie | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | TENSOBON - bei Patienten mit chronischer Linksherzinsuffiziens | [22 empty] | 0 | 0 | 0 | 525 | 525 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0450 | Created | Oral, single-dose, open, randomised, relative bv, CAPTOPRIL |  |  | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | Relative Bioavailability of Two Different Formulations of captropril in Healthy Male Volunteers | [22 empty] | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0508 | Created | Tensobon/Tensobon-Comp - Erhaltung der guten Blutdruckeinste | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | Tensobon/Tensobon-Comp - Erhaltung der guten Blutdruckeinstellung | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CAPOTEN, ECOPACE, NOYADA | not defined | SP0509 | Created | Tensobon / Tensobon comp - Erhaltung der guten Blutdruckeins | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | Tensobon / Tensobon comp - Erhaltung der guten Blutdruckeinstellung | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Captopril,Isosorbide Dinitrate | not defined | SP0154 | Created | ISOKET UND TENSOBON - in patients with chronic heart failure |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | The effect of isosorbide dinitrate and captopril, singly and together, in patients with chronic heart failure | [22 empty] | 0 | 0 | 0 | 40 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Captopril,Isosorbide Dinitrate | not defined | SP0213 | Created | ISOKET/COR-TENSOBON - bei Patienten mit KHK |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | ISOKET/COR-TENSOBON - bei Patienten mit KHK | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 37 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Captopril,Isradipine | not defined | SP0122 | Created (Cancelled) | TENSOBON/ISRADIPIN - bei Patienten mit Aortenklappeninsuffiz |  |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | TENSOBON/ISRADIPIN - bei Patienten mit Aortenklappeninsuffizienz | [22 empty] | 0 | 0 | 0 | 8 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CARAMET, SINEMET, DUODOPA | not defined | SP0694 | LPLV | Carbidopa/levodopa ODT single dose bioavailability | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Kastenholz K | [6 empty] | No | A pharmacokinetic study to compare the bioavailability of a unique new formulation (test), orally disintegrating tablet (ODT) of carbidopa 25mg /levodopa 250 mg to a marketed immediate release carbidopa 25 mg / levodopa 250 mg tablet formulation (reference), Sinemet by DuPont Pharmaceuticals, Inc |  |  |  | 2005-01-07: 2002-01-28; 2005-02-04: 2002-01-28; 2005-05-09: 2002-04-04; 2005-11-07: 2002-09-01; 2006-03-30: 2002-09-01; 2006-06-29: 2002-09-23 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 36 | 36 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CARAMET, SINEMET, DUODOPA | not defined | SP0722 | Final TFLs released | Carbidopa/levodopa ODT single dose bioequivalence | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Kastenholz K | [6 empty] | No | A PK Study to Compare the BE of a New Formulation (Test) Orally Disintegrating Tablet (ODT) of Carbidopa 25 mg/Levodopa 250 mg to a Marketed Immediate Release Carbidopa 25 mg/Levodopa 250 mg (Reference) Sinemet, DuPont Pharmaceuticals, Inc. |  |  |  | 2005-01-07: 2002-10-16; 2005-02-04: 2002-10-16; 2005-05-09: 2002-10-22; 2005-11-07: 2002-11-09; 2006-03-30: 2002-11-10; 2006-06-29: 2002-12-02; 2006-09-28: 2003-02-06 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 50 | 50 | 32 | 0 | 0 | 0 | 49 | 0 | 0 | 49
Yes | Not assigned | Managing Type | 1 | CARAMET, SINEMET, DUODOPA | not defined | SP0780 | Created | Carbidopa/Levodopa ODT marketing study in Parkinson's patien | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A multicenter, open-label trial to assess subject preference of PARCOPA, Carbidopa/Levodopa Orally Disintegrating Tablets, compared to conventional Carbidopa/Levodopa Tablets in subjects with stable Parkinson's Disease | Parkinson's disease | Central Nervous System | [20 empty] | 8 | 0 | 0 | 54 | 54 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CARAMET, SINEMET, DUODOPA | not defined | SP0782 | Created | A pilot trial to compare pharmacokinetics in subjects with P | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to compare a new orally disintegrating tablet (ODT) formulation of carbidopa/levodopa to a marketed immediate release carbidopa/levodopa formulation (Sinemet (R), Merck & Co., Inc.) in subjects with Parkinsons disease | Parkinson's disease | Central Nervous System | [20 empty] | 1 | 0 | 0 | 10 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CARAMET, SINEMET, DUODOPA | not defined | SP0837 | Created (Cancelled) | PARCOPA Phase 4 subject preference study in Parkinsons dise | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A Phase 4 multicenter, open-label trial to assess subject preference for PARCOPA, Carbidopa/Levodopa Orally Disintegrating Tablets, compared to conventional Carbidopa/Levodopa Tablets in subjects with Parkinson's Disease | Parkinson's disease | Central Nervous System | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CARAMET, SINEMET, DUODOPA | not defined | SP0867 | Created | Pilot trial to compare onset of action of Parcopa with conve | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A single center, randomized, double-blind, crossover pilot trial comparing the onset of action of Parcopa® with Sinemet® in subjects with stable Parkinson's disease | Parkinson's disease | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32301 | CSR Approved | First in man | Phase I | Double Blind | Clinical Development GB | Clinical Pharmaco | R & D | Richardson A | [6 empty] | Yes | A Phase I double-blind, randomised, placebo-controlled, dose escalating study to assess the safety, tolerability and pharmacokinetics of single oral doses of CDP323 in the fed (500 mg) and fasted (50, 100, 300, 500, 800 and 1000 mg) state in healthy male volunteers | Indication for Rheumato GI | Immunology |  | 2005-05-09: 2003-09-20; 2005-11-07: 2003-11-03; 2006-03-30: 2003-12-15; 2006-06-29: 2003-12-19; 2006-08-02: 2004-01-23; 2006-09-28: 2004-02-06; 2008-07-17: 2004-10-08 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 0 | 1 | 24 | 24 | 24 | 24 | 0 | 0 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32302 | CSR Approved | Multiple Dose HV | Phase I | Double Blind | Clinical Development GB | Clinical Pharmaco | R & D | Richardson A | [6 empty] | Yes | A randomized double blind, placebo controlled, escalating dose study to investigate the safety, tolerability, pharmacokinetics and pharmacodynamics of CDP323 in healthy adult males | Indication for Rheumato GI | Immunology |  | 2005-02-04: 2004-01-08; 2005-05-09: 2004-01-13; 2005-11-07: 2004-02-24; 2006-03-30: 2004-03-30; 2006-06-29: 2004-04-13; 2006-08-02: 2004-06-14; 2006-09-28: 2004-07-12; 2008-07-17: 2005-05-13 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 0 | 1 | 27 | 27 | 27 | 27 | 0 | 0 | 27 | 0 | 0 | 27
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32303 | CSR Approved | Gender comparison in HV | Phase I | Double Blind | Clinical Development GB | Clinical Pharmaco | R & D | Richardson A | [6 empty] | Yes | A Phase 1 Double Blind, Randomised, Placebo Controlled, Single Dose Study to Compare the Safety, Tolerability, Pharmacokinetics and Pharmacodynamics of Oral CDP323 (500 mg), an Alpha-4 Integrin Antagonist, in 24 Healthy Volunteers; Male and Female of Non-child Bearing Potential | Indication for Rheumato GI | Immunology |  | 2005-05-09: 2004-02-06; 2005-11-07: 2004-02-27; 2006-03-30: 2004-02-27; 2006-06-29: 2004-02-27; 2006-08-02: 2004-04-05; 2006-09-28: 2004-05-10; 2008-07-17: 2004-05-20 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 0 | 1 | 24 | 24 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32305 | Created (Cancelled) | RA: PoC Study | Phase II |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | [20 empty] | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32306 | Created (Cancelled) | RA-Dose finding Study | Phase II |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | [20 empty] | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32307 | Created (Cancelled) | Pivotal 1 | Phase III |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | [20 empty] | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32308 | Created (Cancelled) | Pivotal 2 | Phase III |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | [20 empty] | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32309 | Created (Cancelled) | Juvenile RA | Phase III |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | [20 empty] | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32310 | Protocol Approved (Cancelled) | Allergen challenge study | Phase II | Double Blind / Double Dummy | Clinical Development Europe | TA Allergology / Respiratory | R & D | Martin L | [6 empty] | No | A Double Blind Randomized Four-Way Crossover, Placebo-Controlled study to Assess the Efficacy of ThreeOral Doses of CDP323 (100mg, 250mg, 1000 mg bid capsules) at steady state, on Eosinophils Trafficking after a Nasal Allergen Challenge (NAC) in Seasonal Allergic Patients Sensitized to Grass Pollen Open Comparison with Topical Budesonide (256 mcg), as Active Control | Indication for Dermato Allergo | Immunology |  | 2005-01-07: 2005-03-04; 2005-02-04: 2005-03-18; 2005-05-09: 2005-06-24 |  |  |  | 1 | 0 | 0 | 25 | 18 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32311 | Created (Cancelled) | Formulation and absorption sites | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S, Perreaux A |  |  | Pharmaceutical Profile |  |  |  | No | A phase I, randomised, open label, cross-over design, pharmaco-scintigraphic study in healthy volunteers to investigate the comparative bioavailability of 3 formulations of CDP-323 (via an enterion capsule) and to determine the regional absorption characteristics | Indication for Rheumato GI | Immunology |  | 2005-01-07: 2005-03-04 |  |  |  | 1 | 0 | 0 | 30 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32312 | Created (Cancelled) | Absolute bioavailability | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S, Valgaeren A | Mccabe S | [5 empty] | Yes |  | Indication for Rheumato GI | Immunology |  | 2005-01-07: 2005-10-01 |  |  |  | 0 | 0 | 0 | 24 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32313 | Created (Cancelled) | Mass Balance (C14) | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Salas V | [6 empty] | No |  | Indication for Rheumato GI | Immunology |  | 2005-01-07: 2009-05-11; 2005-05-06: 2005-07-07; 2005-09-30: 2009-01-23; 2006-03-01: 2009-01-22; 2006-05-31: 2009-03-04; 2006-07-03: 2009-03-24; 2006-08-10: 2009-05-20; 2006-10-18: 2009-07-30 |  |  |  | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32314 | Study Archived | Drug Interaction Cocktail Study | Phase I |  | UCB Pharma Global | Immunology | R & D | Valgaeren A | Mccabe S | [5 empty] | Yes | An Open-Label Study of the Effects of Repeated CDP323 Dosing on Cytochrome P450 1A2, 3A4, 2C8, 2C9 and 2D6 Activity in Healthy Male Subjects | Indication for Rheumato GI | Immunology |  | 2005-01-07: 2008-10-13; 2005-05-06: 2008-12-15; 2005-05-09: 2008-12-03; 2005-11-07: 2009-01-28; 2006-03-30: 2009-03-04; 2006-06-29: 2009-06-10; 2006-08-02: 2009-06-26; 2006-09-28: 2009-10-26; 2008-07-17: 2010-04-07 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 16 | 16 | 16 | 36 | 0 | 20 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32320 | Created (Cancelled) | Study 006 Open Label | Phase II |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | [20 empty] | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32321 | Created (Cancelled) | Pivotal Open Label | Phase III |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | [20 empty] | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32322 | Study Archived | MS - Serial MRI 6 months | Phase II | Double Blind | Clinical Development Europe | CNS | R & D | Hernandez D, Vandendriessche A | Beaman M, Smit R | [5 empty] | No | Double-blind, placebo-controlled, randomized, parallel-group Phase II study in subjects with relapsing forms of multiple sclerosis (MS) to evaluate the safety, tolerability, and effects of two doses of CDP323 over 24 weeks with a rater-blind MRI follow-up over 12 weeks. | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-03-03 | 2006-03-03 | 2006-04-20 | 2007-01-11 | 2006-09-15 | 2007-05-04 | 2007-04-16 | 2009-04-06 | 2008-01-15 | 2010-07-28 | 2008-02-04 | 2010-09-13 | 2009-03-20 | 2010-10-19 | 2008-04-24 | 2011-01-18 | Belgium, Canada, Finland, France, Germany, Hungary, Netherlands, Spain, Sweden, United Kingdom, United States of America | Belgium (LPLV), Canada (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Netherlands (LPLV), Spain (LPLV), Sweden (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Canada, Finland, France, Germany, Hungary, Netherlands, Spain, Sweden, United Kingdom, United States of America | 39 | 80 | 70 | 250 | 201 | 201 | 335 | 0 | 103 | 232 | 0 | 2 | 213 | 2009-01-02 | 2009-01-02 | 2009-04-03 |  |  |  | 2011-01-06 |  |  |  | 2011-07-27
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32323 | Protoc. Summary Approved (Cancelled) | Clinical pharmacokinetic study to assess new salt form | Phase I | Open | Clinical Development USA | Clinical Pharmaco | R & D | Salas V | [6 empty] | Yes |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2007-06-01; 2005-02-04: 2007-06-01 |  |  |  | 1 | 0 | 0 | 64 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32324 | Created (Cancelled) | Hepatic Impairment | Phase I |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No |  |  |  |  | 2005-01-07: 2012-01-27 |  |  |  | 1 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32325 | CSR Approved | MS - Dose ranging Surrogate marker | Phase II | Double Blind | UCB Pharma Global | Neurology | R & D | Valgaeren A | Mccabe S | [5 empty] | No | Double-blind, placebo-controlled, randomized, parallel-group study in subjects with relapsing forms of multiple sclerosis to evaluate the effects of different CDP323 doses on biomarker patterns as well as on safety and tolerability. | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2007-08-17; 2005-02-04: 2007-12-07; 2005-05-09: 2008-05-14; 2005-11-07: 2008-07-10; 2006-03-30: 2009-01-21; 2006-06-29: 2009-03-08; 2006-08-02: 2009-05-08; 2006-09-28: 2009-07-17; 2008-07-17: 2010-04-06 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 0 | 2 | 1 | 130 | 105 | 105 | 106 | 0 | 35 | 71 | 0 | 1 | 70
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32326 | Created (Cancelled) | Open label long term safety | Phase II |  | Clinical Development USA | CNS | R & D | Raetz M | Bonny M | [5 empty] | No |  |  |  |  | 2005-01-07: 2009-09-28 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32328 | Study Archived | Formulation PK & Safety - new salt | Phase I |  | UCB Pharma Global | Clinical Pharmaco | UCB Pharma Global | Hernandez D, Salas V | Smit R | [5 empty] | Yes | A Three-Part Study in Healthy Males and Females Assessing the Relative Bioavailability (to CDP323 Free Base Capsules) and Food Effect of Two Formulations of UCBD3232, the Estimated Bioavailability of CT7758, the Single and Repeat Dose Safety, Tolerability and Pharmacokinetics of Escalating Doses of UCBD3232, the Chronopharmacokineticcs of UCBD3232, and the Potential Effects of UCBD3232 on the Cytochrome P450 1A2 and 3A4. | Indication for Rheumato GI | Immunology |  | 2008-09-05 |  |  | 2008-02-01 | 2008-10-01 | 2008-10-22 | 2008-11-26 | 2009-05-27 | 2009-01-14 | 2009-07-22 | 2009-01-28 | 2009-09-25 | 2010-01-27 | 2009-07-16 | 2010-03-16 | 2010-03-22 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 68 | 68 | 68 | 65 | 0 | 45 | 20 | 0 | 0 | 20
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32328B | Final TFLs released | Formulation PK & Safety - new salt | Phase I |  | UCB Pharma Global | Clinical Pharmaco | UCB Pharma Global | [7 empty] | No |  |  |  |  | 2005-01-07: 2008-11-03; 2006-08-02: 2009-07-29; 2006-09-28: 2009-10-26 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP323 | Central Nervous System | C32328C | Created (Cancelled) | Formulation PK & Safety - new salt | Phase I |  | UCB Pharma Global | Clinical Pharmaco | UCB Pharma Global | [7 empty] | No |  |  |  |  | 2005-01-07: 2008-09-05 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP435 (Anti IL 17) | Central Nervous System | C43501 | Protoc. Summary Approved (Cancelled) | 1st administration to human subjects | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A | [6 empty] | Yes | A phase I, double blind, randomized, placebo controlled, dose escalating study to assess the safety, tolerability and pharmacokinetics of single subcutaneous doses of CDP435 in healthy male subjects | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2005-09-01; 2005-02-04: 2005-09-02 |  |  |  | 1 | 0 | 0 | 90 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP435 (Anti IL 17) | Central Nervous System | C43502 | Created (Cancelled) | Phase II (POC) | Phase II |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07: 2007-06-26 |  |  |  | 40 | 0 | 0 | 120 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP435 (Anti IL 17) | Central Nervous System | C43503 | Created (Cancelled) | PhaseIIB | Phase II |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 200 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP435 (Anti IL 17) | Central Nervous System | C43504 | Created (Cancelled) | Phase II open label | Phase II |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 300 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP435 (Anti IL 17) | Central Nervous System | C43505 | Created (Cancelled) | Phase III study | Phase III |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP435 (Anti IL 17) | Central Nervous System | C43506 | Created (Cancelled) | Phase III study | Phase III |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP435 (Anti IL 17) | Central Nervous System | C43507 | Created (Cancelled) | Open label (Phase III Rollovers) | Phase III |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP435 (Anti IL 17) | Central Nervous System | MSD035 | Created (Cancelled) | 435 not yet fully adopted, No ECDP available, figures | Phase I |  | UCB Pharma Global |  | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP484 | Immunology | C48401 | CSR Approved | DB single ascending dose safety study | Phase I | Double Blind | Clinical Development GB | Immunology | R & D | Soranson J | Grose-Hodge R |  | KENDLE and PHARM-OLAM |  |  |  | No | A double-blind, placebo-controlled, randomised, single ascending dose (100, 200, 400 & 800 mg s.c.), multi-centre study, to evaluate the safety and tolerability of CDP484 (humanised anti-IL-1b Fab conjugated with PEG), to characterise the PK profile and to investigate the effects of CDP484 on measures of disease activity in subjects with active rheumatoid arthritis | Indication for Rheumato GI | Immunology |  | 2005-01-07: 2003-10-06; 2005-05-09: 2003-06-15; 2005-11-07: 2004-01-08; 2006-03-30: 2004-08-17; 2006-06-29: 2004-10-15; 2006-08-02: 2004-11-03; 2006-09-28: 2004-12-06; 2008-07-17: 2005-04-27 | Bulgaria, Hungary, Serbia, United Kingdom | Bulgaria (LPLV), Hungary (LPLV), Serbia (LPLV), United Kingdom (LPLV) | Bulgaria, Hungary, Serbia, United Kingdom | 0 | 0 | 18 | 0 | 0 | 0 | 139 | 0 | 19 | 120 | 0 | 0 | 120
Yes | Not assigned | Managing Type | 1 | CDP484 | Immunology | C48402 | Created (Cancelled) | Treat.signs+symptoms in active RA | Phase II |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP484 | Immunology | C48403 | Created (Cancelled) | Anti-TNF non-responders PoC in RA | Phase II |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP484 | Immunology | C48404 | Created (Cancelled) | Phase II open-label in RA | Phase II |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP484 | Immunology | C48405 | Created (Cancelled) | MTX Interaction Study | Phase II |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP484 | Immunology | C48406 | Created (Cancelled) | RA Pivotal 1 |  |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP484 | Immunology | C48407 | Created (Cancelled) | RA Pivotal 2 |  |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP484 | Immunology | C48409 | Created (Cancelled) | Phase III open label in RA |  |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP7524 | Immunology | HP0001 | Created | TH17 Cells Role | Phase I |  | UCB Pharma Global | Immunology | R & D | Daoust A | [6 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP791 | Oncology | C79101 | CSR Approved | PKPD in Subjects with Advanced Solid Tumours | Phase I | Open | Clinical Development GB | Oncology | R & D | Soranson J | Grose-Hodge R |  | CAMPBELL CHARLES ASSOCIATE |  |  |  | No | A Phase I, Open Label Study to Assess the Safety and Tolerability, Pharmacokinetic Profile, and Pharmacodynamic Effects of 0.3, 1, 3, 10, 20, 30mg/kg CDP791 (an anti KDR humanised di- Fab' Conjugated with PEG) in Subjects with Advanced Solid Tumours, for Whom no Standard Anti-Cancer Treatment Exists | Indication for Oncology | Oncology |  | 2005-05-09: 2003-04-09; 2005-11-07: 2003-09-05; 2006-03-30: 2005-02-02; 2006-06-29: 2005-06-01; 2006-08-02: 2005-06-23; 2006-09-28: 2005-07-07; 2008-07-17: 2006-05-11 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 0 | 1 | 28 | 28 | 28 | 53 | 0 | 22 | 31 | 3 | 4 | 24
Yes | Not assigned | Managing Type | 1 | CDP791 | Oncology | C79102 | CSR Approved | Non-small cell lung.combin.chemot | Phase II | Open | Clinical Development GB | Oncology | R & D | Soranson J | Grose-Hodge R |  | PRA |  |  |  | No | A Two-Part, Open Label Phase II Trial: Part One, Dose Escalation Safety; Part Two, Randomized/Comparing CDP791 (10 or 20 mg/kg) Plus Carboplatin/Paclitaxel With Carboplatin/Paclitaxel Alone in Subjects With Locally Advanced or Metastatic (Stage IIIb With Pleural Effusion or Stage IV) Non-Squamous Non-Small-Cell Lung Cancer | Indication for Oncology | Oncology | C79102 is a parent study of C79114 |  | 2005-04-25 | 2005-04-29 | 2005-04-26 | 2005-08-17 | 2005-08-15 | 2006-03-27 | 2006-09-13 | 2007-06-20 | 2009-06-25 | 2007-07-03 | 2010-04-23 | 2010-05-21 |  | 2007-10-08 | 2010-06-18 | Hungary, Poland, Russian Federation | Hungary (LPLV), Poland (LPLV), Russian Federation (LPLV) | Hungary, Poland, Russian Federation | 20 | 28 | 26 | 200 | 165 | 0 | 166 | 0 | 1 | 165 | 0 | 165 | 0 |  |  | 2006-10-11 |  |  |  | 2007-05-01 |  |  |  | 2008-04-14
Yes | Not assigned | Managing Type | 1 | CDP791 | Oncology | C79103 | Created | NSCLC Phase 3 | Phase III | Open | Clinical Development GB | Oncology | R & D | [7 empty] | No |  | Indication for Oncology | Oncology |  | 2005-01-07: 2008-09-10 |  |  |  | 150 | 0 | 0 | 900 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP791 | Oncology | C79104 | Created | NSCLC P3 Gem/Cis |  |  | UCB Pharma Global | Oncology | UCB Pharma Global | [7 empty] | No |  |  |  |  | 2005-01-07: 2009-01-21 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP791 | Oncology | C79105 | Created (Cancelled) | Non-small cell lung,squamous safe | Phase I |  | UCB Pharma Global | Oncology | R & D | [7 empty] | No |  | Indication for Oncology | Oncology | [20 empty] | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP791 | Oncology | C79109 | Created (Held) | Ovarian, combination chemotherapy study | Phase II | Open | Clinical Development GB | Oncology | R & D | [7 empty] | No |  | Indication for Oncology | Oncology |  | 2005-01-07: 2006-09-29 |  |  |  | 4 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP791 | Oncology | C79110 | Created (Held) | Ovarian Phase 3 | Phase III | Open | Clinical Development GB | Oncology | R & D | [7 empty] | No |  | Indication for Oncology | Oncology |  | 2005-01-07: 2007-07-23 |  |  |  | 150 | 0 | 0 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP791 | Oncology | C79113 | Created (Cancelled) | Renal Phase II | Phase II | Open | Clinical Development GB | Oncology | R & D | [7 empty] | No |  | Indication for Oncology | Oncology |  | 2005-01-07: 2006-10-06 |  |  |  | 40 | 0 | 0 | 130 | 130 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP791 | Oncology | C79114 | Created (Cancelled) | Open Follow Up Study | Phase III | Open | Clinical Development GB | Oncology | R & D | [7 empty] | No |  | Indication for Oncology | Oncology | C79114 is a follow up of C79102 | 2005-01-07: 2008-05-23 |  |  |  | 70 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP791 | Oncology | C79115 | Protoc. Summary Approved (Held) | Japanese Phase I | Phase I |  | Clinical Development Japan | Clinical Development Japan | R & D | Sakai A | [6 empty] | No |  |  |  |  | 2005-01-07: 2007-02-01; 2005-02-04: 2007-02-02 | Japan | Japan (Created (Held)) |  | 1 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP791 | Oncology | C79116 | Created (Cancelled) | SCLC Phase 3 | Phase III |  | Clinical Development GB | Oncology | R & D | [7 empty] | No |  |  |  |  | 2005-01-07: 2009-01-15 |  |  |  | 150 | 0 | 0 | 900 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP791 | Oncology | C79117 | Created (Cancelled) | Phase I CDP791 NSCLC Squamous safety study | Phase I |  | UCB Pharma Global | Oncology | R & D | [7 empty] | No |  | Indication for Oncology | Oncology |  | 2005-01-07: 2007-09-24 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP791 | Oncology | C79118 | Created (Cancelled) | Phase I CDP791 NSCLC Gem Cis safety study | Phase I |  | UCB Pharma Global | Oncology | R & D | [7 empty] | No |  |  |  |  | 2005-01-07: 2007-09-24 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CDP791 | Oncology | C79120 | Created | C79120 Indication 3 Ph II | Phase II |  | UCB Pharma Global |  | UCB Pharma Global | [7 empty] | No |  |  |  |  | 2005-01-07: 2009-09-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CILOSTAZOL/PLETAL | not defined | SP0922 | Created | Pletal® in der Therapie bei Claudicatio intermittens in der | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Ney U | [6 empty] | No | PLETAL® in the therapy of peripheral arterial occlusive disease (PAOD) of Fontaine class II (intermittent claudication in daily practice) | Claudicatio Intermittens | Immunology | [20 empty] | 253 | 0 | 0 | 1310 | 1310 | 1310 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Central Nervous System | AH0001 | Created (Cancelled) | A phase 2 study of certolizumab pegol in Ahzehimer’s disease | Phase II |  | Clinical Development USA | CNS | Clinical Development USA | Simpson J | Driver D | PRA | PRA |  |  |  | No |  |  |  |  | 2005-01-07: 2012-07-31 |  |  |  | 50 | 0 | 0 | 750 | 400 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Central Nervous System | AH0002 | Created (Cancelled) | Open-Label extension of study AH0001 in Alzheimer' s disease | Phase II |  | Clinical Development USA | CNS | Clinical Development USA | Simpson J | Driver D | PRA | PRA |  |  |  | No |  |  |  |  | 2005-01-07: 2013-02-13 |  |  |  | 50 | 0 | 0 | 300 | 300 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | AKS001 | Study Archived | Axial SpA | Phase III | Open | GCSO | Immunology | UCB Pharma Global | Teichmann R | Tillery N | N/A | PRA | No | Hybrid | adults | No | PHASE 3, MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED STUDY TO EVALUATE EFFICACY AND SAFETY OF CERTOLIZUMAB PEGOL IN SUBJECTS WITH ACTIVE AXIAL SPONDYLOARTHRITIS (AXIAL SPA) | Axial Spondyloarthritis (axSpA) | Immunology |  | 2009-05-28 | 2009-05-28 |  | 2009-09-23 | 2010-03-11 | 2010-03-11 | 2011-03-11 | 2011-07-06 |  | 2015-08-18 |  | 2016-04-12 |  | 2016-05-04 |  | 2016-07-20 | Argentina, Belgium, Brazil, Canada, Czech Republic, France, Germany, Hungary, Italy, Mexico, Netherlands, Poland, Spain, United Kingdom, United States of America | Argentina (LPLV), Belgium (LPLV), Brazil (LPLV), Canada (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Mexico (LPLV), Netherlands (LPLV), Poland (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Argentina, Belgium, Brazil, Canada, Czech Republic, France, Germany, Hungary, Italy, Mexico, Netherlands, Poland, Spain, United Kingdom, United States of America | 150 | 125 | 104 | 600 | 315 | 315 | 592 | 0 | 265 | 327 | 0 | 126 | 201 |  |  | 2012-05-08 | 2012-07-27 |  |  | 2012-10-26 | 2013-03-29
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | AS0002 | Study Archived | NIS on pts with axial spondyloarthritis treated w/ Cimzia | Non Interventional Study - Prospective | Open | GCSO | Immunology | UCB Pharma Global | Kleine E | Bonny M | Parexel | SPI PXL | No | No | adults | No | A NONINTERVENTIONAL STUDY TO ASSESS THE EFFECTIVENESS OF CERTOLIZUMAB PEGOL IN PATIENTS WITH AXIAL SPONDYLOARTHRITIS IN DAILY PRACTICE | Axial Spondyloarthritis (axSpA) | Immunology |  | 2014-04-25 | 2014-07-17 |  | 2014-07-17 | 2015-02-11 | 2015-01-12 | 2017-02-10 | 2017-03-29 |  | 2018-03-09 |  | 2018-04-09 |  | 2018-05-09 |  | 2018-07-27 | Belgium, Germany, Greece, Italy, Spain, United Kingdom | Belgium (LPLV), Germany (LPLV), Greece (LPLV), Italy (LPLV), Spain (LPLV), United Kingdom (LPLV) | Belgium, Germany, Greece, Italy, Spain, United Kingdom | 127 | 112 | 101 | 678 | 678 | 508 | 684 | 0 | 0 | 684 | 0 | 186 | 498 |  |  |  | 2017-05-29
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | AS0005 | Study Archived | Remission and dose down | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Hoeckendorff J | Anderson K | Parexel | PAREXEL | Yes | Yes | adults | No | MULTICENTER, OPEN-LABEL (PART A) FOLLOWED BY A RANDOMIZED, DOUBLE-BLIND, PARALLEL-GROUP, PLACEBO-CONTROLLED STUDY (PART B) TO EVALUATE MAINTENANCE OF REMISSION IN SUBJECTS WITH ACTIVE AXIAL SPONDYLOARTHRITIS (AXSPA) RECEIVING EITHER CERTOLIZUMAB PEGOL 200MG Q2W OR 200MG Q4W AS COMPARED TO PLACEBO. | Axial Spondyloarthritis (axSpA) | Immunology |  | 2014-05-21 | 2014-09-26 |  | 2015-03-27 | 2015-07-03 | 2015-07-31 | 2017-02-02 | 2017-03-24 | 2019-03-07 | 2019-04-23 | 2019-03-26 | 2019-05-09 | 2019-04-08 | 2019-09-27 | 2019-07-11 | 2019-11-19 | Belgium, Bulgaria, Czech Republic, France, Germany, Hungary, Netherlands, Poland, Romania, Spain, Taiwan, Turkey, United Kingdom, United States of America | Belgium (LPLV), Bulgaria (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Netherlands (LPLV), Poland (LPLV), Romania (LPLV), Spain (LPLV), Taiwan (LPLV), Turkey (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Bulgaria, Czech Republic, France, Germany, Hungary, Netherlands, Poland, Romania, Spain, Taiwan, Turkey, United Kingdom, United States of America | 95 | 118 | 108 | 1250 | 750 | 185 | 1253 | 0 | 517 | 736 | 0 | 521 | 215
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | AS0006 | Study Archived | Assessment of CZP in nr-axSpA with objective signs of inflam | Phase III | Double Blind | GCSO | Immunology | GCSO | Teichmann R | Tillery N | PRA | PRA | Yes | Yes | adults | No | Phase 3, Multicenter, Randomized, Placebo-controlled, Double-Blind Study to Evaluate Efficacy and Safety of Certolizumab Pegol in Subjects with Active Axial Spondyloarthritis (AXSPA) without x-ray evidence of Ankylosing Spondylitis (AS) and Objective Signs of Inflammation. | Axial Spondyloarthritis (axSpA) | Immunology |  | 2014-04-18 | 2014-04-28 |  | 2015-06-01 | 2015-08-31 | 2015-09-03 | 2016-12-16 | 2017-03-02 06:00 | 2018-03-23 | 2020-05-14 10:00 | 2018-04-06 | 2020-10-09 | 2018-04-18 | 2021-01-25 | 2018-06-18 | 2021-04-19 | Australia, Bulgaria, Canada, Czech Republic, Hungary, Poland, Russian Federation, Taiwan, United States of America | Australia (LPLV), Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), Hungary (LPLV), Poland (LPLV), Russian Federation (LPLV), Taiwan (LPLV), United States of America (LPLV) | Australia, Bulgaria, Canada, Czech Republic, Hungary, Poland, Russian Federation, Taiwan, United States of America | 122 | 122 | 104 | 955 | 317 | 317 | 952 | 0 | 635 | 317 | 0 | 71 | 246
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | AS0007 | Study Archived | MULTICENTER, OPEN-LABEL study to assess to Effect of CZP 200 | Phase IV | Open | GCSO | Immunology | UCB Pharma Global | Conrath P | Copetti C | PRA | PRA | No | No | adults | No | MULTICENTER, OPEN-LABEL STUDY TO ASSESS THE EFFECTS OF CERTOLIZUMAB PEGOL ON THE REDUCTION OF ANTERIOR UVEITIS FLARES IN AXIAL SPONDYLOARTHRITIS SUBJECTS WITH A HISTORY OF ANTERIOR UVEITIS (C-VIEW) | Axial Spondyloarthritis (axSpA) | Immunology |  | 2016-01-15 | 2016-01-19 |  | 2016-04-14 | 2016-10-13 | 2016-12-21 23:00 | 2018-01-11 | 2017-12-12 23:00 | 2020-01-29 | 2020-01-23 23:00 | 2020-02-26 | 2020-02-26 | 2020-03-25 | 2020-03-13 | 2020-06-19 | 2020-08-10 | Czech Republic, Germany, Netherlands, Poland, Spain | Czech Republic (LPLV), Germany (LPLV), Netherlands (LPLV), Poland (LPLV), Spain (LPLV) | Czech Republic, Germany, Netherlands, Poland, Spain | 26 | 26 | 23 | 130 | 86 | 86 | 117 | 0 | 28 | 89 | 0 | 6 | 83 |  |  | 2019-02-15 08:00
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87011 | CSR Approved | Efficacy and safety of CDP870 400mg vs placebo | Phase III | Double Blind | Clinical Development USA | Immunology | R & D | [7 empty] | No | Efficacy and Safety of CDP870 400 mg subcutaneously versus placebo in the treatment of the signs and symptoms of patients with rheumatoid arthritis who have previously failed at least one DMARD. | Indication for Rheumato GI | Immunology | C87011 is a feeder study of C87015 | 2005-05-09: 2003-02-03; 2005-11-07: 2003-06-13; 2006-03-30: 2003-11-03; 2006-06-29: 2004-06-01; 2006-08-02: 2004-07-29; 2006-10-18: 2005-05-23; 2008-07-17: 2006-07-26 | United States of America | United States of America (LPLV) | United States of America | 36 | 0 | 1 | 520 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87014 | CSR Approved | Efficacy ans safety of CDP870 in Comb with MTX vs MTX alone | Phase III | Double Blind | Clinical Development USA | Immunology | R & D | [7 empty] | No | Efficacy and Safety of CDP-870 400 mg Subcutaneously in Combination with Methotrexate Compared to Methotrexate Alone in the Treatment of the Signs and Symptoms of Patients with Rheumatoid Arthritis who are Partial Responders to Methotrexate | Indication for Rheumato GI | Immunology | C87014 is a feeder study of C87015 | 2005-05-09: 2002-08-19; 2006-08-02: 2004-03-12; 2006-10-18: 2005-03-30; 2008-07-17: 2006-08-30 | Austria, Belgium, Czech Republic, Germany, Ireland, United Kingdom, United States of America | Austria (Created), Belgium (Created), Czech Republic (Created), Germany (Created), Ireland (Created), United Kingdom (Created), United States of America (Created) |  | 43 | 0 | 0 | 270 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87015 | CSR Approved | Open label long-term safety study | Phase III | Open | Clinical Development USA | Immunology | R & D | Goldammer N | Beinhauer-Zellenka U | N/A | Kendle |  |  |  | No | A Phase III, Multicenter, Open-label, long term study to assess the safety and tolerability of CDP870 400 mg subcutaneously every 4 weeks in patients with Rheumatoid Arthritis. (Incorporating amendments 1,2,3,4,5,and 6) | Indication for Rheumato GI | Immunology | C87015 is a follow up of C87011, C87014 | 2002-08-21 |  | 2002-10-18 | 2002-10-18 | 2003-03-15 | 2003-03-12 |  | 2004-06-30 | 2006-06-15 | 2011-02-18 | 2007-02-19 | 2011-06-03 | 2008-03-25 | 2012-05-30 | 2009-10-31 | 2012-06-27 | Austria, Belgium, Czech Republic, Germany, Ireland, United Kingdom, United States of America | Austria (LPLV), Belgium (LPLV), Czech Republic (LPLV), Germany (LPLV), Ireland (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Austria, Belgium, Czech Republic, Germany, Ireland, United Kingdom, United States of America | 71 | 71 | 71 | 467 | 402 | 188 | 0 | 0 | 0 | 402 | 0 | 232 | 170
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87027 | CSR Approved | Efficacy of CDP870 400mg/MTX | Phase III | Double Blind | Clinical Development USA | Immunology | R & D | Collini E | Beaman M |  | Quintiles |  |  |  | No | Protocol #CDP870-027 A phase III multicentre, double blind, placebo-controlled, parallel group 52 week study to assess the effi9ccay and safety of 2 dose regimens of lyophilized CDP870 given sbucutaneously as additional medication to methotrexate in the treatement of signs and symptoms and preventing structural damage in patients with active rheumatoid arthritis who have an imcomplete response to methotrexate. | Indication for Rheumato GI | Immunology | C87027 is a parent study of C87028 | 2005-03-09 08:00 |  | 2004-11-17 | 2004-11-17 | 2005-02-11 | 2005-02-18 | 2005-08-26 | 2005-09-21 | 2006-11-26 | 2006-10-23 | 2006-12-22 | 2007-02-12 | 2007-01-12 | 2007-02-26 | 2007-03-13 | 2007-10-05 | Argentina, Australia, Belgium, Bulgaria, Canada, Chile, Croatia, Czech Republic, Estonia, Finland, France, Hungary, Israel, Latvia, Lithuania, Mexico, New Zealand, Russian Federation, Serbia, Slovakia, Ukraine, United States of America | Argentina (LPLV), Australia (LPLV), Belgium (LPLV), Bulgaria (LPLV), Canada (LPLV), Chile (LPLV), Croatia (LPLV), Czech Republic (LPLV), Estonia (LPLV), Finland (LPLV), France (LPLV), Hungary (LPLV), Israel (LPLV), Latvia (LPLV), Lithuania (LPLV), Mexico (LPLV), New Zealand (LPLV), Russian Federation (LPLV), Serbia (LPLV), Slovakia (LPLV), Ukraine (LPLV), United States of America (LPLV) | Argentina, Australia, Belgium, Bulgaria, Canada, Chile, Croatia, Czech Republic, Estonia, Finland, France, Hungary, Israel, Latvia, Lithuania, Mexico, New Zealand, Russian Federation, Serbia, Slovakia, Ukraine, United States of America | 190 | 163 | 147 | 1300 | 950 | 950 | 1274 | 0 | 282 | 992 | 0 | 415 | 577
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87028 | Study Archived | Open label long term extension | Phase III | Open | Clinical Development Europe | Immunology | R & D | Bretschneider M | Tillery N | N/A | UCB |  |  |  | No | Protocol #CDP870-028 A Phase III multi-centre, open label , follow-up study to CDP870-027, to assess the efficacy and safety of lyophilized CDP870 an engineered human anti-TNF PEG conjugate, dosed subcutaneously at 400mg every two weeks as additional medication to methotrexate, in the treatement of signs and symptoms and preventing structural damage in patients with active rheumatoid arthritis. | Indication for Rheumato GI | Immunology | C87028 is an extension of C87027 | 2005-01-10 | 2005-02-04 | 2005-04-04 | 2005-04-04 | 2005-06-15 | 2005-06-21 | 2006-08-26 | 2006-09-15 | 2007-10-12 | 2012-02-06 | 2008-06-26 | 2012-08-11 | 2008-10-31 | 2012-09-15 | 2008-12-19 | 2013-02-06 | Argentina, Australia, Belgium, Bulgaria, Canada, Chile, Croatia, Czech Republic, Estonia, Finland, France, Hungary, Israel, Latvia, Lithuania, Mexico, New Zealand, Russian Federation, Serbia, Slovakia, Ukraine, United States of America | Argentina (LPLV), Australia (LPLV), Belgium (LPLV), Bulgaria (LPLV), Canada (LPLV), Chile (LPLV), Croatia (LPLV), Czech Republic (LPLV), Estonia (LPLV), Finland (LPLV), France (LPLV), Hungary (LPLV), Israel (LPLV), Latvia (LPLV), Lithuania (LPLV), Mexico (LPLV), New Zealand (LPLV), Russian Federation (LPLV), Serbia (LPLV), Slovakia (LPLV), Ukraine (LPLV), United States of America (LPLV) | Argentina, Australia, Belgium, Bulgaria, Canada, Chile, Croatia, Czech Republic, Estonia, Finland, France, Hungary, Israel, Latvia, Lithuania, Mexico, New Zealand, Russian Federation, Serbia, Slovakia, Ukraine, United States of America | 190 | 127 | 121 | 800 | 800 | 560 | 0 | 0 | 0 | 857 | 0 | 332 | 525
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87029 | Created (Cancelled) | High dose study |  |  | UCB Pharma Global |  | R & D | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87031 | CSR Approved | Safety and efficacy CDP870 400 mg sc in active CD | Phase III | Double Blind | Clinical Development GB | Immunology | R & D | O'Neil G, Payne (Contractor) N |  |  | ICON/POI |  |  |  | No | A Phase III multi-national, multi-centre, double-blind placebo-controlled parallel group, 26 week study to assess the safety and efficacy of the humanised anti-TNF PEG conjugate, CDP870 400 mg sc, (dosed at Weeks 0, 2, 4 then 4-weekly to Week 24), in the treatment of patients with active Crohn's dis | Indication for Rheumato GI | Immunology | C87031 is a feeder study of C87034 and is a parent study of C87033 |  |  |  | 2003-07-04 |  | 2003-12-10 | 2004-10-29 | 2004-11-04 | 2005-06-01 | 2005-05-31 | 2005-06-29 | 2005-07-07 | 2005-07-29 | 2005-09-16 | 2005-09-23 | 2005-12-16 | Australia, Austria, Belarus, Belgium, Bulgaria, Canada, Czech Republic, Estonia, Georgia, Germany, Hong Kong, Hungary, Italy, Latvia, Norway, Poland, Russian Federation, Slovenia, South Africa, Sweden, Ukraine, United States of America | Australia (LPLV), Austria (LPLV), Belarus (LPLV), Belgium (LPLV), Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), Estonia (LPLV), Georgia (LPLV), Germany (LPLV), Hong Kong (LPLV), Hungary (LPLV), Italy (LPLV), Latvia (LPLV), Norway (LPLV), Poland (LPLV), Russian Federation (LPLV), Slovenia (LPLV), South Africa (LPLV), Sweden (LPLV), Ukraine (LPLV), United States of America (LPLV) | Australia, Austria, Belarus, Belgium, Bulgaria, Canada, Czech Republic, Estonia, Georgia, Germany, Hong Kong, Hungary, Italy, Latvia, Norway, Poland, Russian Federation, Slovenia, South Africa, Sweden, Ukraine, United States of America | 175 | 0 | 171 | 1006 | 602 | 400 | 982 | 0 | 320 | 662 | 0 | 279 | 383
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87032 | CSR Approved | Maintenance of clinical response | Phase III | Double Blind | Clinical Development GB | Immunology | R & D | O'Neil G, Payne (Contractor) N |  |  | ICON/POI |  |  |  | No | A Phase III multi-national, multi-centre, double-blind placebo-controlled parallel group, 26 week study to assess the maintenance of clinical response to humanised anti-TNF PEG conjugate, CDP870 400 mg sc, (dosed 4-weekly from Weeks 8 to 24), in the treatment of patients with active Crohn's disease | Indication for Rheumato GI | Immunology | C87032 is a feeder study of C87034 |  |  |  | 2003-07-04 |  | 2004-02-18 | 2004-10-29 | 2004-10-15 | 2005-05-10 | 2005-05-06 | 2005-06-07 | 2005-06-29 | 2005-07-08 | 2005-09-16 | 2005-09-02 | 2005-12-14 | Australia, Canada, Denmark, Germany, Hungary, Ireland, Israel, Lithuania, New Zealand, Norway, Poland, Serbia, Singapore, South Africa, Spain, Ukraine, United States of America | Australia (LPLV), Canada (LPLV), Denmark (LPLV), Germany (LPLV), Hungary (LPLV), Ireland (LPLV), Israel (LPLV), Lithuania (LPLV), New Zealand (LPLV), Norway (LPLV), Poland (LPLV), Serbia (LPLV), Singapore (LPLV), South Africa (LPLV), Spain (LPLV), Ukraine (LPLV), United States of America (LPLV) | Australia, Canada, Denmark, Germany, Hungary, Ireland, Israel, Lithuania, New Zealand, Norway, Poland, Serbia, Singapore, South Africa, Spain, Ukraine, United States of America | 175 | 0 | 147 | 1186 | 712 | 300 | 938 | 0 | 263 | 675 | 1 | 413 | 261
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87033 | Study Archived | OL 206 week safety study, patient completed precise | Phase III | Open | Clinical Development Europe | Immunology | R & D | Ambarkhane S | Weinsberg F | N/A | ICON/POI |  |  |  | No | A Phase III multi-national, multi-centre, open label, safety study to assess the safety of chronic therapy with the humanised anti-TNF PEG conjugate CDP870 400 mg sc,(dosed 4-weekly),in the treatment of patients with active Crohn's disease who have previously completed studies CDP870-031 or CDP870-032 | Indication for Rheumato GI | Immunology | C87033 is an extension of C87031 | 2003-12-24 | 2003-07-10 |  | 2003-07-10 |  | 2004-07-05 | 2005-05-13 | 2005-06-08 | 2007-08-22 | 2012-08-16 | 2007-10-19 | 2012-10-18 |  | 2012-12-12 | 2008-01-14 | 2013-05-23 | Australia, Austria, Belarus, Belgium, Bulgaria, Canada, Czech Republic, Denmark, Estonia, Georgia, Germany, Hong Kong, Hungary, Israel, Italy, Latvia, Lithuania, New Zealand, Norway, Poland, Russian Federation, Serbia, Singapore, Slovenia, South Africa, Spain, Sweden, Ukraine, United States of America | Australia (LPLV), Austria (LPLV), Belarus (LPLV), Belgium (LPLV), Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), Denmark (LPLV), Estonia (LPLV), Georgia (LPLV), Germany (LPLV), Hong Kong (LPLV), Hungary (LPLV), Israel (LPLV), Italy (LPLV), Latvia (LPLV), Lithuania (LPLV), New Zealand (LPLV), Norway (LPLV), Poland (LPLV), Russian Federation (LPLV), Serbia (LPLV), Singapore (LPLV), Slovenia (LPLV), South Africa (LPLV), Spain (LPLV), Sweden (LPLV), Ukraine (LPLV), United States of America (LPLV) | Australia, Austria, Belarus, Belgium, Bulgaria, Canada, Czech Republic, Denmark, Estonia, Georgia, Germany, Hong Kong, Hungary, Israel, Italy, Latvia, Lithuania, New Zealand, Norway, Poland, Russian Federation, Serbia, Singapore, Slovenia, South Africa, Spain, Sweden, Ukraine, United States of America | 135 | 198 | 206 | 280 | 280 | 280 | 0 | 0 | 0 | 596 | 0 | 477 | 119 |  |  | 2006-06-29 | 2006-06-29 | [6 empty] | 2009-10-09 | 2009-10-09 |  |  | 2010-11-25 | 2010-11-29 |  |  | 2012-02-02 | 2011-12-16
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87034 | Study Archived | OL 204 week safety study, patients withdraw Precise | Phase III | Open | Clinical Development Europe | Immunology | R & D | Ambarkhane S | Weinsberg F | N/A | ICON/POI/UCB |  |  |  | No | A Phase III multi-national, multi-centre, open label, safety study to assess the safety of re-exposure after a variable interval and subsequent chronic therapy with the humanised anti-TNF PEG conjugate CDP870 400 mg sc, (dosed at Weeks 0, 2 and 4 then every 4 weeks), in the treatment of patients with active Crohn's disease who have previously been withdrawn from studies CDP870-031 or CDP870-032 due to an exacerbation of Crohn's disease | Indication for Rheumato GI | Immunology | C87034 is an extension of C87031, C87032 | 2003-07-10 | 2003-07-10 |  | 2003-07-10 |  | 2004-02-13 | 2005-05-13 | 2005-04-27 | 2007-07-25 | 2012-05-17 | 2007-09-21 | 2012-10-26 |  | 2012-11-12 | 2007-12-19 | 2013-05-17 | Australia, Austria, Belarus, Belgium, Bulgaria, Canada, Czech Republic, Denmark, Estonia, Germany, Hungary, Israel, Italy, New Zealand, Norway, Poland, Russian Federation, Serbia, Singapore, Slovenia, South Africa, Spain, Ukraine, United States of America | Australia (LPLV), Austria (LPLV), Belarus (LPLV), Belgium (LPLV), Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), Denmark (LPLV), Estonia (LPLV), Germany (LPLV), Hungary (LPLV), Israel (LPLV), Italy (LPLV), New Zealand (LPLV), Norway (LPLV), Poland (LPLV), Russian Federation (LPLV), Serbia (LPLV), Singapore (LPLV), Slovenia (LPLV), South Africa (LPLV), Spain (LPLV), Ukraine (LPLV), United States of America (LPLV) | Australia, Austria, Belarus, Belgium, Bulgaria, Canada, Czech Republic, Denmark, Estonia, Germany, Hungary, Israel, Italy, New Zealand, Norway, Poland, Russian Federation, Serbia, Singapore, Slovenia, South Africa, Spain, Ukraine, United States of America | 135 | 133 | 141 | 620 | 620 | 620 | 0 | 0 | 0 | 311 | 0 | 288 | 23 | [14 empty] | 2010-12-02 |  |  |  | 2012-01-10
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87035 | Study Archived | C87035-Open label stu.to assess saf,plas | Phase II | Open | Clinical Development USA | Immunology | Clinical Development USA |  |  | N/A | Kendle was responsible from study start to January 2011. UCB Internal CSM team was responbilbe from January 2011 to August 2011. PRA International is responsible as of August 2011. |  |  | paediatrics | No | A Phase 2, open-label, multicenter study to assess the safety and efficacy of certolizumab pegol in children and adolescents with active Crohn's disease (NURTURE Study) | Indication for Rheumato GI | Immunology | C87035 is a parent study of CR0012 | 2008-10-15 | 2008-07-01 |  | 2009-02-12 | 2009-04-17 | 2009-04-17 | 2011-10-31 | 2011-05-26 |  | 2012-07-02 |  | 2012-10-08 |  | 2012-11-27 |  | 2013-05-31 | Australia, Canada, New Zealand, United States of America | Australia (LPLV), Canada (LPLV), New Zealand (LPLV), United States of America (LPLV) | Australia, Canada, New Zealand, United States of America | 40 | 40 | 33 | 160 | 160 | 70 | 157 | 7 | 51 | 99 | 1 | 80 | 18 |  |  | 2010-06-16 |  |  |  | 2010-07-27
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87036 | Created (Cancelled) | Alternate Dosing Regimen Study | Phase III | Double Blind | Clinical Development GB | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology |  | 2005-01-07: 2006-09-01 |  |  |  | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87037 | Study Archived | Japan-Crohn study | Phase II | Double Blind | Clinical Development Japan | Clinical Development Japan | R & D | Okayasu M | [6 empty] | No | A Phase II, multi-centre, double-blind, placebo-controlled parallel group, dose-response study to assess the efficacy and safety of CDP870 / certolizumab pegol dosed subcutaneously in patients with active Crohn's disease. | Indication for Rheumato GI | Immunology | C87037 is a parent study of C87047, C87048 | 2005-11-10 | 2005-11-07 | 2005-11-10 | 2006-03-01 | 2006-01-31 | 2006-03-02 | 2007-02-05 |  | 2007-05-28 |  | 2007-07-30 | 2008-08-26 |  | 2008-09-26 | 2007-11-15 | 2008-10-28 | Japan | Japan (FPFV) | Japan | 26 | 26 | 21 | 100 | 100 | 0 | 128 | 0 | 34 | 94 | 0 | 6 | 88
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87038 | CSR Approved | Bioequivalence solution verus lyophilized | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | De Smedt F | [6 empty] | Yes | Open label randomized, parallel group, single dose, comparative bioavailability study of Certolizumab pegol given as a 400 mg single subcutaneous injection of either the reconstituted lyophilized formulation or, a solution formulation, in healthy male volunteers | Indication for Rheumato GI | Immunology |  | 2005-04-15 | 2005-04-18 | 2005-04-22 | 2005-04-28 | 2005-07-01 | 2005-06-21 | 2005-10-17 | 2005-10-23 | 2005-12-16 | 2006-01-16 | 2006-02-03 | 2006-02-28 | 2006-02-28 | 2006-05-03 | 2006-04-28 | 2007-03-06 | France | France (LPLV) | France | 1 | 1 | 1 | 80 | 48 | 48 | 6 | 6 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87039 | Study Archived | Population PK Phase 3 | Meta-analysis |  | Clinical Development Europe | Clinical Pharmaco | R & D | [7 empty] | No |  |  |  |  | 2008-07-17: 2005-12-21 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87040 | CSR Approved | Psoriasis dose-response study | Phase II | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | R & D | Wajskop M | [6 empty] | No | Multicenter, dose response, randomized, double blind, parallel, 3 arms, placebo controlled clinical trial to evaluate the efficacy and the safety of subcutaneous CDP870 (certolizumab pegol) at 2 different dose regimens (200 mg weekly for 3 weeks (loading dose) followed by 200mg/2 weeks and 400 mg weekly for 3 weeks (loading dose) followed by 400 mg/2 weeks) during 12 weeks, followed by a minimum of 12 weeks of follow-up without treatment (or until relapse) in subjects suffering from moderate-to-severe chronic plaque psoriasis who are candidates for systemic therapy and/or phototherapy and/or | Indication for Dermato Allergo | Immunology |  | 2005-04-01 | 2005-04-29 | 2005-05-01 | 2005-05-12 | 2005-10-03 | 2005-10-17 | 2006-02-10 | 2006-02-22 | 2006-11-10 | 2006-11-14 | 2006-12-08 | 2007-01-11 | 2007-01-12 | 2007-06-14 | 2007-02-26 | 2008-04-22 | France, Germany | France (LPLV), Germany (LPLV) | France, Germany | 17 | 17 | 16 | 180 | 150 | 0 | 215 | 0 | 39 | 176 | 0 | 20 | 148 |  |  | 2006-07-17
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87042 | CSR Approved | Refractory to infliximab therapy (blinded) | Phase III | Double Blind | Clinical Development Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Vanden Eynde L |  |  | Kendle |  |  |  | No | A Phase IIIb multicentre, open label induction and double blind comparison of two maintenance schedules clinical trial evaluating clinical benefit and tolerability of certolizumab pegol, a pegylated Fab fragment of humanized antibody to tumor necrosis factor (TNF) over 26 weeks in patient suffering from Crohn's Disease with prior loss of response or intolerance to infliximab | Crohn's disease | Immunology | C87042 is a parent study of C87046 |  | 2005-06-24 | 2005-07-29 | 2005-11-18 | 2005-12-01 | 2006-04-05 | 2006-06-30 | 2007-07-18 | 2006-12-01 | 2008-04-02 |  | 2008-08-07 |  | 2008-12-02 |  | 2008-12-02 | Austria, Belgium, Canada, Denmark, France, Germany, Italy, Netherlands, Norway, Spain, Sweden, Switzerland, United Kingdom, United States of America | Austria (LPLV), Belgium (LPLV), Canada (LPLV), Denmark (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Netherlands (LPLV), Norway (LPLV), Spain (LPLV), Sweden (LPLV), Switzerland (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Austria, Belgium, Canada, Denmark, France, Germany, Italy, Netherlands, Norway, Spain, Sweden, Switzerland, United Kingdom, United States of America | 121 | 126 | 113 | 600 | 600 | 270 | 681 | 11 | 130 | 380 | 1 | 107 | 272 |  |  | 2008-02-01
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87043 | Study Archived | Endoscopy Histology healing | Phase III | Open | Clinical Development Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Hermans S | [6 empty] | No | A Phase IIIB multicentre open label 54 weeks clinical trial evaluating certolizumab pegol, a PEGylated Fab fragment of humanized antibody to tumor necrosis factor alpha (TNF) on endoscopic and mucosal healing in patients suffering from active Crohn's disease | Indication for Rheumato GI | Immunology |  | 2005-08-10 | 2005-07-29 | 2005-09-16 | 2005-10-16 | 2005-12-15 | 2006-02-13 | 2006-09-30 | 2007-10-25 | 2007-09-30 | 2009-12-31 | 2007-11-30 | 2010-04-02 | 2008-02-28 | 2010-06-16 | 2008-02-28 | 2011-01-13 | Belgium, France, Germany | Belgium (LPLV), France (LPLV), Germany (LPLV) | Belgium, France, Germany | 15 | 25 | 20 | 85 | 85 | 0 | 118 | 0 | 29 | 89 | 63 | 25 | 1 |  |  | 2007-11-22
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87044 | CSR Approved | Psoriasis Phase II study extension | Phase II | Single Blind | Clinical Development Europe | TA Allergology / Respiratory | R & D | Wajskop M |  |  | CSM Group-UCB |  |  |  | No | Follow-up of study C87040 : Multicenter, single blind study to describe the efficacy and safety of re-treatment with CDP870 (certolizumab pegol) subcutaneous at 2 different dose regimens (400 mg initial dose at week 0 with 200 mg every 2 weeks thereafter and 400 mg every 2 weeks) or placebo for 12 weeks, in subjects suffering from moderate-to-severe chronic plaque psoriasis who are candidates for systemic therapy and/or phototherapy and/or photochemotherapy, having responded to treatment in study C87040 and having subsequently relapsed | Indication for Dermato Allergo | Immunology |  | 2005-10-07 | 2005-11-07 | 2005-08-29 | 2005-12-01 | 2006-03-31 | 2006-04-19 | 2006-11-10 | 2006-11-14 | 2007-05-09 | 2007-05-09 | 2007-05-31 | 2007-06-11 | 2007-07-05 | 2007-08-31 | 2007-12-31 | 2008-06-16 | France, Germany | France (LPLV), Germany (LPLV) | France, Germany | 17 | 13 | 13 | 100 | 75 | 90 | 73 | 0 | 2 | 71 | 0 | 3 | 67
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87045 | Study Archived | Comparative Bioavailability - Auto Injector Device | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Valgaeren A | Mccabe S | [5 empty] | Yes | Open label, randomized, parallel group, single dose, 2-way comparison bioequivalence study of Certolizumab pegol solution (2 subcutaneous injections) injected either by a pre-filled syringe (reference) or by an auto injection device (test) to healthy volunteers. | Indication for Rheumato GI | Immunology |  | 2005-01-07: 2007-06-01; 2005-05-09: 2007-07-02; 2005-11-07: 2007-10-12; 2006-03-30: 2008-01-07; 2006-06-29: 2008-04-07; 2006-08-02: 2008-06-03; 2006-09-28: 2008-09-17; 2008-07-17: 2008-12-19 | France | France (LPLV) | France | 1 | 1 | 1 | 200 | 100 | 100 | 118 | 0 | 20 | 98 | 98 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87046 | Study Archived | Open label extention for infliwimab failure | Phase III | Open | Global Medical Affairs Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Vanden Eynde L | [6 empty] | No | Open label long term Clinical Trial Evaluating Efficacy and Safety of Chronic Therapy with certolizumab pegol, a PEGylated Fab fragment of humanized antibody to tumor necrosis factor alpha (TNF) in patients suffering from Crohn's disease and having completed C87042 study. | Indication for Rheumato GI | Immunology | C87046 is an extension of C87042 | 2006-03-31 | 2006-04-21 | 2006-06-30 | 2006-08-11 | 2006-10-05 | 2006-10-18 | 2007-08-31 | 2008-01-29 | 2007-12-28 | 2010-04-14 | 2010-10-29 | 2010-11-02 | 2010-12-20 | 2011-01-06 | 2011-04-18 | 2011-11-03 | Austria, Belgium, Canada, France, Germany, Italy, Netherlands, Spain, Sweden, Switzerland, United Kingdom, United States of America | Austria (LPLV), Belgium (LPLV), Canada (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Netherlands (LPLV), Spain (LPLV), Sweden (LPLV), Switzerland (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Austria, Belgium, Canada, France, Germany, Italy, Netherlands, Spain, Sweden, Switzerland, United Kingdom, United States of America | 100 | 74 | 72 | 250 | 0 | 0 | 4 | 0 | 0 | 233 | 0 | 143 | 90
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87047 | Study Archived | Japanese CD Maintenance responders study | Phase II | Double Blind | Clinical Development Japan | Clinical Development Japan | R & D | Okayasu M | [6 empty] | No | A 26-week, multi-center, open-label study to investigate the efficacy and safety of CDP870 in active Crohn's disease patients, who showed clinical efficacy in a remission induction study (Study CDP870-037), at Week 26 after subcutaneous administration of CDP870 400 mg from Week 8 until Week 24 at 4- week intervals - Remission maintenance study of CDP870/certolizumab pegol in active Crohn's disease patients. | Indication for Rheumato GI | Immunology | C87047 is an extension of C87037 | 2006-01-13 | 2006-02-03 | 2006-01-31 | 2006-03-01 | 2006-04-03 | 2006-05-10 | 2007-04-09 |  | 2007-10-22 |  |  | 2008-06-26 |  | 2008-09-13 | 2008-04-24 | 2009-01-09 | Japan | Japan (FPFV) | Japan | 26 | 26 | 16 | 30 | 30 | 30 | 0 | 0 | 0 | 40 | 0 | 12 | 28
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87048 | CSR Approved | Japanese CD Maintenance non-responders study | Phase II | Double Blind | Clinical Development Japan | Clinical Development Japan | R & D | Okayasu M | [6 empty] | No | A multi-center, open-label study to investigate the efficacy and safety of CDP870 in active Crohn's disease patients, who showed no clinical efficacy in a remission induction study (Study CDP870-037) but showed clinical efficacy after additional remission induction therapy was applied, at Week 26 after subcutaneous administration of CDP870 400 mg from Week 8 until Week 24 at 4-week intervals - Remission maintenance study, including additional remission induction therapy, of CDP870/certolizumab pegol in active Crohn's disease patients showing no clinical efficacy in Study CDP870-037. | Indication for Rheumato GI | Immunology | C87048 is a follow up of C87037 | 2006-01-13 | 2006-02-03 | 2006-01-31 | 2006-03-01 | 2006-04-03 | 2006-05-02 | 2007-04-09 |  | 2007-12-17 |  |  | 2008-06-26 |  | 2008-09-13 | 2008-06-19 | 2008-11-14 | Japan | Japan (FPFV) | Japan | 26 | 26 | 16 | 30 | 30 | 30 | 0 | 0 | 0 | 46 | 0 | 15 | 31
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87049 | Created (Cancelled) | Disease Modification | Phase IV |  | Global Medical Affairs Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | [7 empty] | No |  |  |  |  | 2005-01-07: 2008-04-22 |  |  |  | 0 | 0 | 0 | 600 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87050 | CSR Approved | Phase III 24 wk study to asses Efficacy and Safety of CDP870 | Phase III | Double Blind | Clinical Development USA | Immunology | R & D | Phillips T |  |  | Quintiles |  |  |  | No | Protocol #RPCE05A1002 A Phase III Multi-Center, double-Blind, Placebo-controlled, Parallel Group 24-Week Study to Assess the Efficacy and Safety of 2 Dose Regimens of Liquid CDP870 Dosed at 200 mg or 400 mg Every two weeks given subcutaneously as additional medication to Methotrexate in the treatmen t of signs and symptoms of Rheumatoid Arthritis and in preventing joint damage in patients with active Rheumatoid Arthritis and in preventing joint damage in patients with active Rheumatoid Arthritis who have an incomplete response to Methotrexate. | Indication for Rheumato GI | Immunology | C87050 is a parent study of C87051 | 2005-02-04 | 2005-02-04 | 2005-05-05 | 2005-05-05 | 2005-06-30 | 2005-06-30 | 2006-02-28 | 2006-01-06 | 2006-08-29 | 2006-09-19 | 2006-09-25 | 2007-02-14 | 2006-10-03 | 2007-02-26 | 2007-01-29 | 2007-10-16 | Bulgaria, Croatia, Czech Republic, Estonia, Israel, Latvia, Lithuania, Poland, Russian Federation, Serbia, Slovakia, Ukraine, United States of America | Argentina (1st Site Initiation (Cancelled)), Bulgaria (LPLV), Croatia (LPLV (Stopped)), Czech Republic (LPLV), Estonia (LPLV), Israel (LPLV), Latvia (LPLV), Lithuania (LPLV), Mexico (1st Site Initiation (Cancelled)), Poland (LPLV), Russian Federation (LPLV), Serbia (LPLV), Slovakia (LPLV), Ukraine (LPLV), United States of America (LPLV) | Bulgaria, Croatia, Czech Republic, Estonia, Israel, Latvia, Lithuania, Poland, Russian Federation, Serbia, Slovakia, Ukraine, United States of America | 100 | 95 | 77 | 720 | 590 | 472 | 0 | 0 | 0 | 634 | 0 | 253 | 381
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87051 | Study Archived | Phase III Open Label Long Term F/U Liquid Certolizumab | Phase III | Open | Clinical Development USA | Immunology | R & D | Thierfelder S | Driver D | N/A | UCB |  |  |  | No | A Phase III Multi-center, Open-label, Follow-up Study, to Assess the Safety and Efficacy of Liquid Certolizumab Pegol as Additional Medication to Methotrexate, in the Treatment of Signs and Symptoms and in the Prevention of Joint Damage in Patients with Active Rheumatoid Arthritis who participated in Study CDP870-050. | Indication for Rheumato GI | Immunology | C87051 is a follow up of C87050 | 2005-04-01 | 2005-06-03 | 2005-07-06 | 2005-09-29 | 2005-12-12 | 2005-12-07 | 2006-11-08 | 2006-08-04 | 2008-03-31 | 2012-02-08 | 2008-06-26 | 2012-06-16 | 2008-10-31 | 2012-09-22 | 2008-12-19 | 2013-02-21 | Bulgaria, Croatia, Czech Republic, Estonia, Israel, Latvia, Lithuania, Poland, Russian Federation, Serbia, Slovakia, Ukraine, United States of America | Bulgaria (LPLV), Croatia (LPLV), Czech Republic (LPLV), Estonia (LPLV), Israel (LPLV), Latvia (LPLV), Lithuania (LPLV), Poland (LPLV), Russian Federation (LPLV), Serbia (LPLV), Slovakia (LPLV), Ukraine (LPLV), United States of America (LPLV) | Bulgaria, Croatia, Czech Republic, Estonia, Israel, Latvia, Lithuania, Poland, Russian Federation, Serbia, Slovakia, Ukraine, United States of America | 75 | 69 | 68 | 480 | 472 | 472 | 0 | 0 | 0 | 582 | 0 | 221 | 361
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87052 | Created (Held) | Open Label Extension study | Phase III | Open | Clinical Development Europe | TA Allergology / Respiratory | R & D | [7 empty] | No | Multicenter, open label long term safety study to assess the safety of certolizumab in the treatment of subjects with moderate to severe psoriasis, previously treated with certolizumab pegol. |  |  |  | 2005-01-07: 2008-08-28 |  |  |  | 100 | 0 | 0 | 900 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87053 | Protoc. Summary Approved (Held) | Induction of Response | Phase III | Double Blind | Clinical Development GB | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | C87053 is a feeder study of C87057 | 2005-01-07: 2006-04-26; 2005-02-04: 2006-05-05; 2005-05-06: 2006-06-14; 2005-09-30: 2006-09-29; 2006-03-01: 2007-04-27; 2006-05-31: 2007-09-25; 2006-10-18: 2008-01-01 |  |  |  | 70 | 0 | 0 | 416 | 312 | 249 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87054 | Protoc. Summary Approved (Held) | Maintenance of Remission | Phase III | Double Blind | Clinical Development GB | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | C87054 is a feeder study of C87057 | 2005-01-07: 2006-05-05; 2005-02-04: 2006-05-22; 2005-05-06: 2006-06-14; 2005-09-30: 2006-09-29; 2006-03-01: 2007-03-29; 2006-05-31: 2008-08-07; 2006-10-18: 2008-11-12 |  |  |  | 110 | 0 | 0 | 735 | 551 | 303 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87055 | CSR Approved | CDP870-CR Greek Affiliate -Open label, multi-center study | Phase III | Open | Affiliates |  | Affiliates | Liakou K |  |  | Zeincro Hellas SA |  |  |  | No | Certolizumab pegol in the treatment of adult Greek patients with moderate to severe Crohn's Disease, who have been previously treated successfully with infliximab but who have subsequently lost the response or have developed intolerance to infliximab an open-label, multi-center, single-cohort study to evaluate efficacy, safety and onset of action. | Indication for Rheumato GI | Immunology | C87055 is a parent study of C87069 | 2006-03-10 | 2006-03-14 |  | 2006-06-07 | 2006-09-05 | 2007-04-13 | 2007-05-31 | 2008-02-04 | 2007-09-15 | 2008-08-06 | 2007-11-01 | 2009-03-31 | 2008-02-05 |  | 2008-04-10 | 2010-04-12 | Greece | Greece (LPLV) | Greece | 11 | 11 | 7 | 50 | 50 | 35 | 15 | 0 | 1 | 14 | 2 | 1 | 11
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87056 | CSR Approved | Bioequivalence study comparing 1st and 2nd generation drug | Phase I | Double Blind | Clinical Development USA | Clinical Pharmaco | R & D | Salas V | [6 empty] | Yes | Open label, parallel group, single dose, comparative bioavailability study of certolizumab pegol given as subcutaneous injections of either first generation or second generation in healthy male volunteers. | Indication for Rheumato GI | Immunology |  | 2007-05-17 |  | 2006-11-30 | 2007-03-06 | 2007-05-02 | 2007-09-26 | 2007-11-26 | 2007-12-27 | 2007-11-26 | 2008-03-28 | 2008-01-15 | 2008-05-09 | 2008-02-19 | 2008-06-27 | 2008-05-26 | 2008-11-04 | United States of America | United States of America (LPLV) | United States of America | 1 | 2 | 2 | 96 | 96 | 96 | 156 | 0 | 66 | 90 | 0 | 0 | 90
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87057 | Protoc. Summary Approved (Held) | Open Label FU to C87053 & C87054 | Phase III | Open | Clinical Development GB | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology | C87057 is a follow up of C87053, C87054 | 2005-01-07: 2006-04-26; 2005-02-04: 2006-05-05; 2005-05-06: 2006-06-14; 2005-09-30: 2006-10-27; 2006-03-01: 2008-05-14; 2006-05-31: 2009-12-09; 2006-10-18: 2010-05-04 |  |  |  | 110 | 0 | 0 | 475 | 475 | 316 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87058 | Protoc. Summary Approved (Cancelled) | Fistulas Healing | Phase IV |  | Global Medical Affairs Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Roobaert S | [6 empty] | No |  |  |  |  | 2005-02-04: 2006-06-02 |  |  |  | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87059 | Study Archived | COSPAR I - Steroid sparing | Phase III | Double Blind | Global Medical Affairs US | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Vanden Eynde L |  |  | PPD |  |  |  | No | A Phase IIIb multi-center, double-blind, placebo-controlled, randomized trial to examine the corticosteroid-sparing effect of certolizumab pegol in patients with moderate to severe Crohn's disease | Indication for Rheumato GI | Immunology | C87059 is a parent study of C87065 | 2006-05-19 | 2006-05-19 | 2006-07-07 | 2006-05-19 | 2006-09-19 | 2006-11-01 | 2008-09-16 | 2008-09-16 | 2009-07-06 | 2009-07-06 | 2009-10-30 | 2009-10-30 | 2010-01-27 | 2010-03-05 | 2010-03-31 | 2011-03-03 | Canada, Germany, United States of America | Canada (LPLV), Germany (LPLV), United States of America (LPLV) | Canada, Germany, United States of America | 100 | 113 | 75 | 440 | 352 | 352 | 281 | 0 | 104 | 177 | 0 | 120 | 57
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87060 | Created (Held) | 2nd Pivotal study | Phase III | Double Blind | Clinical Development USA | TA Allergology / Respiratory | R & D | Edeline M | [6 empty] | No | Multicenter, randomized, double blind, placebo controlled study to evaluate the efficacy and the safety of subcutaneous Certolizumab pegol in subjects suffering from moderate to severe chronic plaque psoriasis | Indication for Dermato Allergo | Immunology |  | 2005-01-07: 2008-02-13; 2005-05-06: 2007-01-30 | Canada, United States of America | Canada (Created), United States of America (Created) |  | 60 | 0 | 0 | 550 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009-08-26
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87061 | Created (Cancelled) | Open label Safety | Phase III | Double Blind | UCB Pharma Global | TA Allergology / Respiratory | R & D | [7 empty] | No |  | Indication for Dermato Allergo | Immunology |  | 2005-01-07: 2006-10-01 |  |  |  | 30 | 0 | 0 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87062 | Created (Cancelled) | CERTAIN I | Phase III |  | UCB Pharma Global | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87063 | Created (Cancelled) | CERTAIN II | Phase III |  | UCB Pharma Global | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87064 | Protoc. Summary Approved (Held) | Severe Asthma Phase II Dose Ranging | Phase II | Double Blind | UCB Pharma Global | TA Allergology / Respiratory | R & D | [7 empty] | No | Multicenter, Randomized, Placebo-controlled, Double Blind Efficacy and Safety Study of certolizumab pegol as Add-on Treatment in Subjects Suffering from Severe Persistent Asthma Despite Optimal Treatment. | Indication for Dermato Allergo | Immunology |  | 2005-01-07: 2006-07-31; 2005-02-04: 2006-10-24; 2005-05-06: 2006-08-31; 2005-09-30: 2007-01-10; 2006-03-01: 2007-03-07; 2006-05-31: 2008-03-18; 2006-07-03: 2008-04-05; 2006-08-10: 2008-07-05; 2006-10-18: 2008-07-24 |  |  |  | 50 | 0 | 0 | 400 | 228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2009-04-08
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87065 | Study Archived | COSPAR II - extension for COSPAR I | Phase III | Open | Global Medical Affairs US | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Vanden Eynde L |  |  | PPD |  |  |  | No | An open-label, multi-center trial to examine the long term safety, efficacy, and corticosteroid-sparing effect of certolizumab pegol in patients with moderate to severe Crohn's disease who have failed tapering of corticosteroids, needed corticosteroids after completion of tapering, or have successfu | Indication for Rheumato GI | Immunology | C87065 is an extension of C87059 | 2006-06-30 | 2006-07-14 | 2006-09-01 | 2006-09-01 | 2006-10-11 | 2007-01-04 | 2008-05-30 | 2009-04-15 | 2010-08-02 | 2010-02-23 | 2010-08-18 | 2010-05-19 | 2010-09-10 | 2011-02-04 | 2010-12-08 | 2011-03-03 | Canada, Germany, United States of America | Canada (LPLV), Germany (LPLV), United States of America (LPLV) | Canada, Germany, United States of America | 100 | 113 | 49 | 352 | 352 | 352 | 107 | 0 | 1 | 106 | 2 | 53 | 51
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87066 | Created (Held) | Severe Asthma Phase III study 1 | Phase III | Double Blind | UCB Pharma Global | TA Allergology / Respiratory | R & D | [7 empty] | No |  | Indication for Dermato Allergo | Immunology |  | 2005-01-07: 2009-05-18 |  |  |  | 110 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2010-12-07
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87067 | Created (Held) | Severe Asthma Phase III Study 2 | Phase III |  | UCB Pharma Global | TA Allergology / Respiratory | R & D | [7 empty] | No |  | Indication for Dermato Allergo | Immunology |  | 2005-01-07: 2009-05-18 |  |  |  | 130 | 0 | 0 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2011-04-20
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87068 | Created | Population PK - Phase III CDP870-RA | Meta-analysis |  | Clinical Development Europe | Clinical Pharmaco | R & D | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87069 | Protocol Approved (Cancelled) | CDP870-CR Greek Affiliate - Follow Up | Phase IV | Open | Affiliate Greece |  | Affiliate Greece | Liakou K | [6 empty] | No | Open label long term Clinical Trial Evaluating Safety of Chronic Therapy with certolizumab pegol, a PEGylated Fab fragment of humanized antibody to tumor necrosis factor alpha (TNF) in patients suffering from Crohn's disease and having completed C87055 study |  |  | C87069 is a follow up of C87055 | 2005-02-04: 2006-07-14; 2005-05-06: 2006-10-15; 2005-05-09: 2006-12-15; 2005-09-30: 2007-01-01; 2006-03-01: 2007-09-03; 2006-05-31: 2007-10-01; 2006-07-03: 2008-01-21; 2006-08-10: 2008-03-25; 2006-10-18: 2008-05-20 | Greece | Greece (IRB / IEC Submission) |  | 11 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87070 | Created (Held) | Comparison versus active comparator | Phase II | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | R & D | [7 empty] | No | Multicenter, randomized, double blind, double-dummy controlled study to compare the efficacy and the safety of subcutaneous Certolizumab pegol with etanercept in subjects suffering from moderate to severe chronic plaque psoriasis | Indication for Dermato Allergo | Immunology |  | 2005-01-07: 2009-10-30 |  |  |  | 70 | 0 | 0 | 700 | 605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87072 | Created (Held) | Phase II Study | Phase II |  | Clinical Development GB | Immunology | R & D | [7 empty] | No |  |  |  |  | 2005-01-07: 2007-02-16 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87074 | Created (Cancelled) | Safety Study (GMA Infl) | Phase III | Open | Global Medical Affairs Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Roobaert S | [6 empty] | No |  | Indication for Rheumato GI | Immunology |  | 2005-01-07: 2006-12-18 |  |  |  | 300 | 0 | 0 | 1800 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87075 | Study Archived | Registry (Clinical) | Registry | Open | GCSO | Immunology | UCB Pharma Global | Tillery N | Beinhauer-Zellenka U | N/A | PRA | No | Hybrid | adults | No | A Non-Interventional, Long term, Post-Marketing Registry of Patients Treated with Certolizumab Pegol (CIMZIA) For Crohn's Disease | Crohn's disease | Immunology |  | 2008-06-19 | 2008-07-17 |  | 2009-01-06 | 2009-01-06 | 2009-01-30 | 2012-02-06 | 2017-10-07 | 2025-09-09 | 2020-08-28 | 2025-09-30 | 2021-01-13 | 2025-10-15 | 2021-01-22 | 2025-09-19 | 2021-04-21 | United States of America | United States of America (LPLV) | United States of America | 300 | 280 | 197 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 3122 | 0 | 2669 | 449
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87076 | Study Archived | Moderate to Low Disease activity study | Phase III | Double Blind | Clinical Development Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Elyakhlifi S | Driver D | [5 empty] | No | A Phase IIIB, multi-centre, double-blind randomized, placebo-controlled, parallel group 52-week study to evaluate safety and efficacy of the PEGylated anti-TNF Fab fragment, certolizumab pegol, administered concomitantly with stable-dose DMARDs in patients with moderate to low disease activity rheumatoid arthritis |  |  | C87076 is a follow up of C87080 and is a parent study of C87080 | 2007-04-04 | 2007-07-19 | 2007-10-11 | 2007-10-29 | 2008-03-03 | 2008-06-03 | 2008-08-15 | 2009-10-29 | 2009-10-01 | 2010-12-10 | 2009-10-12 | 2011-04-18 | 2009-11-10 | 2011-08-22 | 2010-02-01 | 2011-12-08 | Austria, France, Germany, Italy, Poland | Austria (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Poland (LPLV) | Austria, France, Germany, Italy, Poland | 54 | 55 | 37 | 230 | 170 | 0 | 271 | 0 | 77 | 194 | 0 | 35 | 159 | 2010-10-30 | 2010-10-30 | 2010-10-30 | 2010-12-17
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87077 | Study Archived | Dosing Flexibility | Phase III | Double Blind | Global Medical Affairs US | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Collini E | Beaman M | [5 empty] | No | A Phase IIIb open-label run-in and double-blind randomized study to evaluate the safety and efficacy of certolizumab pegol administered concomitantly with stable-dose methotrexate in patients with active rheumatoid arthritis |  |  | C87077 is a parent study of C87084 | 2006-11-16 | 2007-02-09 |  | 2007-05-08 | 2007-11-03 | 2007-12-03 | 2010-05-31 | 2010-04-16 | 2011-01-14 | 2011-03-01 | 2011-05-16 | 2011-04-12 | 2011-07-14 | 2011-07-06 | 2011-10-14 | 2011-10-06 | Canada, France, United States of America | Canada (LPLV), France (LPLV), United States of America (LPLV) | Canada, France, United States of America | 70 | 76 | 61 | 447 | 335 | 201 | 620 | 0 | 287 | 209 | 0 | 34 | 175
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87078 | CSR Approved | Meta pop PK/PD | Meta-analysis |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No |  |  |  |  | 2008-07-17: 2007-03-23 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87079 | Database Locked | Meta pop PK/PD | Meta-analysis |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No |  |  |  |  | 2006-08-02: 2007-05-24 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87080 | Study Archived | Follow-up of the C87076 | Phase III | Open | Clinical Development Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Elyakhlifi S | Driver D | N/A |  |  |  | adults | No | A Phase IIIB, multi-centre open label, follow-up study to evaluate the safety and efficacy of certolizumab pegol administered concomitantly with DMARDs in subjects with active rheumatoid arthritis who participated in the study C87076. | Indication for Rheumato GI | Immunology | C87080 is a follow up of C87076 and is a parent study of C87076 | 2007-10-10 | 2007-03-01 |  | 2008-02-20 | 2008-12-31 | 2009-01-26 | 2010-12-06 | 2010-11-17 | 2012-08-03 | 2012-12-14 | 2012-11-02 | 2013-01-31 | 2012-12-03 | 2013-03-28 | 2013-06-19 | 2013-08-05 | Austria, France, Germany, Italy, Poland | Austria (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Poland (LPLV) | Austria, France, Germany, Italy, Poland | 40 | 26 | 25 | 132 | 132 | 0 | 0 | 0 | 0 | 131 | 0 | 9 | 98
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87081 | Created (Held) | Phase III Pivotal study | Phase III |  | UCB Pharma Global | TA Allergology / Respiratory | R & D | [7 empty] | No |  | Indication for Dermato Allergo | Immunology |  | 2005-01-07: 2010-01-26 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2010-11-23 |  |  |  | 2011-04-22
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87083 | Created (Cancelled) | Cimzia vs Enbrel PFS | Phase IV | Double Blind | Global Medical Affairs US | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Russell G | [6 empty] | No |  | Indication for Rheumato GI | Immunology |  | 2005-01-07: 2007-08-19; 2005-05-06: 2007-05-06; 2005-09-30: 2007-07-27; 2006-03-01: 2007-10-31; 2006-05-31: 2008-07-23 |  |  |  | 20 | 0 | 0 | 125 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87084 | Study Archived | Open label extension study for C87077 | Phase III | Open | Global Medical Affairs US | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Collini E | Beaman M | [5 empty] | No | A Phase IIIb, multicenter open-label, follow-up study to evaluate the safety and efficacy of certolizumab pegol administered concomitantly with methotrexate in patients with active rheumatoid arthritis who participated in C87077 |  |  | C87084 is an extension of C87077 | 2007-08-08 | 2007-03-23 |  | 2007-05-18 | 2007-12-26 | 2008-09-02 | 2009-11-16 | 2010-12-22 | 2012-06-12 | 2011-05-19 | 2012-09-10 | 2011-12-12 | 2012-11-19 | 2012-02-13 | 2013-03-07 | 2012-07-27 | Canada, United States of America | Canada (LPLV), United States of America (LPLV) | Canada, United States of America | 70 | 42 | 42 | 201 | 201 | 201 | 0 | 0 | 0 | 168 | 0 | 10 | 158
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87085 | Study Archived | Efficacy and Safety study | Phase III | Double Blind | Clinical Development Europe | Immunology | R & D | Schmid M |  |  | PPD |  |  |  | No | A phase IIIb, multinational, randomized, double-blind, placebo-controlled trial to assess the efficacy and safety of certolizumab pegol, a pegylated Fab' fragment of a humanized anti-TNF-alpha monoclonal antibody,... ...administered subcutaneously at weeks 0, 2 and 4 in subjects with moderately to severely active Crohn's disease | Indication for Rheumato GI | Immunology | C87085 is a parent study of C87088 | 2007-04-09 | 2007-04-10 | 2007-12-06 | 2007-09-24 | 2008-01-18 | 2008-03-18 | 2008-07-17 | 2009-08-14 | 2008-09-09 | 2009-11-25 | 2008-10-07 | 2009-12-23 | 2008-11-05 | 2010-03-17 | 2008-12-05 | 2010-06-30 | Australia, Austria, Belgium, Brazil, Canada, Chile, Czech Republic, Estonia, Finland, Germany, Hungary, Israel, Italy, Latvia, New Zealand, Poland, Romania, Russian Federation, Ukraine, United States of America | Australia (LPLV), Austria (LPLV), Belgium (LPLV), Brazil (LPLV), Canada (LPLV), Chile (LPLV), Czech Republic (LPLV), Estonia (LPLV), Finland (LPLV), Germany (LPLV), Hungary (LPLV), Israel (LPLV), Italy (LPLV), Latvia (LPLV), New Zealand (LPLV), Poland (LPLV), Romania (LPLV), Russian Federation (LPLV), Ukraine (LPLV), United States of America (LPLV) | Australia, Austria, Belgium, Brazil, Canada, Chile, Czech Republic, Estonia, Finland, Germany, Hungary, Israel, Italy, Latvia, New Zealand, Poland, Romania, Russian Federation, Ukraine, United States of America | 150 | 154 | 120 | 374 | 374 | 0 | 636 | 1 | 188 | 447 | 4 | 46 | 396
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87088 | Study Archived | Follow-on extension to C87085 | Phase III | Open | GCSO | Immunology |  | Kleine E | Bonny M | N/A | PPD |  |  | adults | No | A phase IIIb, multinational, open-label, follow-on trial to C87085 designed to assess the long-term safety of certolizumab pegol, a pegylated Fab' fragment of a humanized anti TNF alpha monoclonal antibody,... ...administered at weeks 0, 2 and 4, and then every 4 weeks thereafter, in subjects with moderately to severely active Crohn’s disease who have participated in study C87085 | Indication for Rheumato GI | Immunology | C87088 is a follow up of C87085 | 2007-06-13 | 2007-05-14 | 2007-09-24 | 2007-09-24 | 2008-02-18 | 2008-05-19 | 2008-09-10 | 2009-10-14 | 2009-11-04 | 2014-12-22 | 2009-11-24 | 2015-02-24 | 2009-12-23 | 2015-04-02 | 2010-01-05 | 2015-05-22 | Australia, Austria, Belgium, Brazil, Canada, Czech Republic, Estonia, Germany, Hungary, Israel, Italy, Latvia, New Zealand, Poland, Romania, Russian Federation, Ukraine, United States of America | Australia (LPLV), Austria (LPLV), Belgium (LPLV), Brazil (LPLV), Canada (LPLV), Chile (1st Site Initiation (Cancelled)), Czech Republic (LPLV), Estonia (LPLV), Finland (1st Site Initiation (Cancelled)), Germany (LPLV), Hungary (LPLV), Israel (LPLV), Italy (LPLV), Latvia (LPLV), New Zealand (LPLV), Poland (LPLV), Romania (LPLV), Russian Federation (LPLV), Ukraine (LPLV), United States of America (LPLV) | Australia, Austria, Belgium, Brazil, Canada, Czech Republic, Estonia, Germany, Hungary, Israel, Italy, Latvia, New Zealand, Poland, Romania, Russian Federation, Ukraine, United States of America | 160 | 151 | 100 | 402 | 402 | 0 | 0 | 0 | 0 | 408 | 0 | 319 | 87 |  |  | 2010-09-01 | 2010-11-10 |  |  | 2011-10-18 | 2012-02-03 |  |  | 2012-09-24 | 2012-09-24 |  |  | 2013-08-03 | 2013-08-01 |  |  | 2014-08-11 | 2014-08-11
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87089 | Created (Held) | Rescue Study | Phase III |  | Global Medical Affairs Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Roobaert S | [6 empty] | No |  |  |  |  | 2005-01-07: 2008-01-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87091 | Protocol Approved (Cancelled) | Perfect | Phase III |  | Global Medical Affairs Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Conrath P | Copetti C | [5 empty] | No |  |  |  |  | 2007-09-12 | 2007-09-12 | 2007-09-13 | 2007-09-13 | 2008-04-01 |  | 2008-09-30 |  | 2009-03-10 |  | 2009-05-01 |  | 2009-06-24 |  | 2009-09-25 |  | France | France (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87093 | Created (Held) | Crohn's Genomics study (in addition to C87085)reuse # | Meta-analysis |  | UCB Pharma Global | Immunology | R & D | Steinert A | [6 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87094 | CSR Approved | Real life | Phase III | Double Blind | Global Medical Affairs US | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Schelstraete I | Driver D |  | PPD |  |  |  | No | A Phase IIIb, multicenter study with a 12-week double-blind, placebo-controlled, randomized period followed by an open-label, extension phase to evaluate the safety and efficacy of certolizumab pegol administered to patients with active rheumatoid arthritis | Indication for Rheumato GI | Immunology |  | 2008-03-04 | 2008-01-14 |  | 2008-04-23 | 2008-07-17 | 2008-07-23 | 2009-12-04 | 2009-11-26 | 2011-02-18 | 2011-03-08 | 2011-05-05 | 2011-05-06 | 2011-06-10 | 2012-01-05 | 2011-12-12 | 2012-04-27 | Canada, France, Germany, Italy, Netherlands, Spain, United States of America | Canada (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Netherlands (LPLV), Spain (LPLV), United States of America (LPLV) | Canada, France, Germany, Italy, Netherlands, Spain, United States of America | 220 | 212 | 179 | 1310 | 1048 | 0 | 1648 | 0 | 583 | 1065 | 0 | 229 | 836 |  |  | 2010-09-01
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87095 | Created (Cancelled) | Head to Head | Phase III |  | UCB Pharma Global | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | [7 empty] | No |  |  |  |  | 2005-01-07: 2008-01-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87096 | Created (Cancelled) | Switch study | Phase III |  | UCB Pharma Global | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | [7 empty] | No |  |  |  |  | 2005-01-07: 2008-01-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87097 | Created (Cancelled) | Clinical Evaluation of cimzia 2G Formula in patients | Phase II |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology |  | 2005-01-07: 2007-08-29 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87098 | Created (Cancelled) | CertolizumabPegol;NIS evaluates efficacy/safety tr. w/Cimzia | Non Interventional Study - Prospective |  | Affiliates |  | Affiliates | [7 empty] | No |  |  |  |  | 2005-01-07: 2007-08-21 | Switzerland | Switzerland (Created) |  | 10 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | C87099 | Created (Cancelled) | NIS OBS real life AFF | Non Interventional Study - Prospective |  | UCB Pharma Global | GMA Allergy/Respiratory/Inflam | Affiliates - France | [7 empty] | No |  |  |  |  | 2005-01-07: 2007-10-20 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | CR0001 | CSR Approved | Sperm Quality Study | Phase I | Double Blind | UCB Pharma Global | Clinical Pharmaco | UCB Pharma Global | Soranson J | Grose-Hodge R | [5 empty] | Yes | Randomized, single-center, double-blind, placebo-controlled study to explore the effect of a single dose of certolizumab pegol 400mg on semen quality in healthy male volunteers. |  |  |  | 2009-09-07 | 2009-09-25 |  | 2010-01-11 | 2010-04-14 | 2010-04-08 | 2011-01-31 | 2010-11-29 | 2011-03-29 | 2011-03-29 | 2011-05-25 | 2011-08-30 | 2011-07-20 | 2011-07-06 | 2011-11-15 | 2011-10-24 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 23 | 20 | 20 | 81 | 0 | 61 | 20 | 0 | 0 | 20
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | CR0002 | Created (Cancelled) | CONCERT | Non Interventional Study - Prospective |  | UCB Pharma Global | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | [7 empty] | No |  |  |  |  | 2005-01-07: 2007-10-22 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | CR0004 | Created (Cancelled) | CD Peadiatric Efficacy Study | Phase II |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  |  |  |  | 2005-01-07: 2008-10-15 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | CR0008 | Created (Cancelled) | Named Patient Program | Named Patient Program |  | UCB Pharma Global | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Kelling D | Tzschaschel B | [5 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | CR0011 | Protocol Approved (Cancelled) | Treatment optimization based on CRP and HBI driven decisions | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Melton K | Beaman M | Parexel | SPI PXL |  |  | adults | No | A PHASE 3B, MULTI-CENTER, DOUBLE-BLIND, RANDOMIZED STUDY TO COMPARE CERTOLIZUMAB PEGOL 400MG EVERY 4 WEEKS VS 400MG EVERY 2 WEEKS IN SUBJECTS WITH MODERATELY TO SEVERELY ACTIVE CROHN´S DISEASE WHO INITIALLY RESPONDED TO OPEN-LABEL CERTOLIZUMAB PEGOL DOSING AT WEEK 6 BUT FAILED TO ACHIEVE REMISSION AT WEEK 16 | Indication for Internal Medicine | Immunology |  | 2005-01-07: 2012-05-01; 2005-02-04: 2011-05-20; 2005-05-09: 2012-06-08 | United States of America | United States of America (Created) |  | 140 | 0 | 0 | 900 | 308 | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | CR0012 | Study Archived | Extension study of Cimzia CD pediatric study C87035 | Phase II | Open | GCSO | Immunology | UCB Pharma Global | Murphy C | Russell R | N/A | Kendle was responsible from study start to January 2011. UCB Internal CSM team was responsible from January 2011 to August 2011. PRA International is responsible as of August 2011. | No | No | paediatrics | No | An open label multicenter study to assess the safety of certolizumab pegol in children and adolescents with active Crohn's disease who completed C87035. Phase 2b | Crohn's disease | Immunology | CR0012 is an extension of C87035 |  |  |  | 2010-05-11 | 2010-07-01 | 2010-08-06 | 2013-01-31 | 2012-07-02 | 2017-12-22 | 2017-11-27 | 2018-02-16 | 2018-02-16 | 2018-02-15 | 2018-05-15 | 2018-07-25 | 2019-04-01 | Australia, Canada, United States of America | Australia (LPLV), Canada (LPLV), United States of America (LPLV) | Australia, Canada, United States of America | 40 | 10 | 10 | 100 | 100 | 100 | 3 | 0 | 0 | 16 | 0 | 9 | 7 |  |  | 2012-01-06 | 2011-12-01 |  |  | 2011-12-02 | 2011-12-02
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | IDM027 | Created (Cancelled) | IIS CR |  |  | UCB Pharma Global | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | PS0002 | Study Archived | Phase 3 Placebo Controlled Study. CIMPASI-2 | Phase III | Double Blind | GCSO | Immunology | GCSO | Bollmann J, Will E | Beinhauer-Zellenka U, Copetti C | Parexel | PAREXEL | No | Hybrid | adults | No | A PHASE 3, MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PARALLEL-GROUP, STUDY FOLLOWED BY A DOSE-BLIND PERIOD AND OPEN-LABEL FOLLOW-UP TO EVALUATE THE EFFICACY AND SAFETY OF CERTOLIZUMAB PEGOL IN SUBJECTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIASIS | Psoriasis | Immunology | PS0002 is a "sister" study of PS0005 | 2014-03-18 | 2014-03-18 |  | 2014-08-06 | 2014-12-11 | 2014-12-15 | 2015-08-27 | 2015-09-01 | 2018-07-27 | 2018-09-12 | 2018-08-17 | 2018-10-02 | 2018-09-14 | 2019-03-19 | 2018-12-11 | 2019-05-20 | Austria, Canada, Poland, United States of America | Austria (LPLV), Canada (LPLV), Poland (LPLV), United States of America (LPLV) | Austria, Canada, Poland, United States of America | 25 | 23 | 23 | 300 | 225 | 150 | 302 | 0 | 74 | 228 | 0 | 74 | 154 |  |  | 2016-09-30 | 2016-09-30
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | PS0003 | Study Archived | Phase 3 Active Comparator Study (with placebo arm). CIMPACT | Phase III | Double Blind | GCSO | Immunology | GCSO | Kleine E, Will E | Bonny M, Copetti C | Parexel | PAREXEL | No | Hybrid | adults | No | A PHASE 3, MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PARALLEL-GROUP, PLACEBO- AND ACTIVE-CONTROLLED STUDY FOLLOWED BY A PLACEBO-CONTROLLED MAINTENANCE PERIOD AND OPEN-LABEL FOLLOW-UP TO EVALUATE THE EFFICACY AND SAFETY OF CERTOLIZUMAB PEGOL IN SUBJECTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIASIS | Psoriasis | Immunology |  | 2014-03-18 | 2014-03-18 |  | 2014-08-06 | 2015-01-13 | 2015-02-11 | 2016-03-09 | 2015-11-30 | 2019-02-05 | 2018-12-17 | 2019-03-19 | 2019-02-11 | 2019-04-30 | 2019-02-25 | 2019-07-23 | 2019-06-27 | Bulgaria, Czech Republic, France, Germany, Hungary, Netherlands, Poland, United Kingdom, United States of America | Bulgaria (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Netherlands (LPLV), Poland (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Bulgaria, Czech Republic, France, Germany, Hungary, Netherlands, Poland, United Kingdom, United States of America | 81 | 78 | 70 | 700 | 540 | 300 | 733 | 0 | 172 | 561 | 0 | 164 | 393 |  |  | 2017-01-24 | 2017-06-23
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | PS0005 | Study Archived | Phase 3 eff & safety Mod/Sev Chron Plaq Psoriasis. CIMPASI-1 | Phase III | Double Blind | GCSO | Immunology | GCSO | Will E | Copetti C | Parexel | PAREXEL | No | Hybrid | adults | No | A PHASE 3, MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PARALLEL-GROUP, STUDY FOLLOWED BY A DOSE-BLIND PERIOD AND OPEN-LABEL FOLLOW-UP TO EVALUATE THE EFFICACY AND SAFETY OF CERTOLIZUMAB PEGOL IN SUBJECTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIASIS | Psoriasis | Immunology | PS0005 is a "sister" study of PS0002 |  |  |  | 2014-08-06 | 2014-12-11 | 2014-12-16 | 2015-03-05 | 2015-10-14 | 2015-06-25 | 2018-10-24 | 2015-07-23 | 2018-11-29 | 2015-08-06 | 2018-12-28 | 2015-11-02 | 2019-05-22 | Canada, Czech Republic, Germany, Hungary, United States of America | Canada (LPLV), Czech Republic (LPLV), Germany (LPLV), Hungary (LPLV), United States of America (LPLV) | Canada, Czech Republic, Germany, Hungary, United States of America | 33 | 33 | 30 | 300 | 225 | 180 | 286 | 0 | 51 | 235 | 0 | 61 | 174 |  |  | 2016-12-19 | 2017-04-13
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | PS0017 | Study Archived | Japan Cimzia psorasis study | Phase II | Double Blind | GCSO | Immunology | UCB Pharma Global | Sakurai S | Zhou A | Parexel | PAREXEL | Yes | Yes | adults | No | PHASE 2/3, MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PARALLEL-GROUP, PLACEBO-CONTROLLED STUDY TO EVALUATE THE EFFICACY AND SAFETY OF CERTOLIZUMAB PEGOL IN JAPANESE SUBJECTS WITH MODERATE TO SEVERE CHRONIC PSORIASIS | Psoriasis | Immunology |  | 2016-08-01 | 2016-07-22 |  | 2016-09-26 | 2017-01-16 | 2017-02-21 | 2017-11-30 | 2017-11-06 | 2019-01-31 | 2019-01-16 | 2019-02-28 | 2019-03-01 | 2019-03-14 | 2019-04-26 | 2019-06-10 | 2019-06-05 | Japan | Japan (LPLV) | Japan | 35 | 35 | 33 | 160 | 135 | 120 | 191 | 0 | 42 | 149 | 0 | 20 | 129
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | PSA001 | Study Archived | Psoriatric Arthritis | Phase III | Open | GCSO | Immunology | UCB Pharma Global | Teichmann R | Tillery N | N/A | PRA | No | Hybrid | adults | No | PHASE 3, MULTICENTER, RANDOMIZED, DOUBLE BLIND, PARALLEL GROUP, PLACEBO CONTROLLED STUDY TO EVALUATE THE EFFICACY AND SAFETY OF CERTOLIZUMAB PEGOL IN SUBJECTS WITH ADULT ONSET ACTIVE AND PROGRESSIVE PSORIATIC ARTHRITIS (PSA) | Psoriatic Arthritis | Immunology |  | 2009-05-28 | 2009-05-28 |  | 2009-09-23 | 2010-03-02 | 2010-03-02 | 2011-03-02 | 2011-03-31 | 2014-07-10 | 2015-08-24 | 2014-09-11 | 2016-04-13 | 2014-12-11 | 2016-05-16 | 2015-04-20 | 2016-07-29 | Argentina, Belgium, Brazil, Canada, Czech Republic, France, Germany, Hungary, Ireland, Italy, Mexico, Poland, Spain, United Kingdom, United States of America | Argentina (LPLV), Belgium (LPLV), Brazil (LPLV), Canada (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Ireland (LPLV), Italy (LPLV), Mexico (LPLV), Netherlands (1st Site Initiation (Cancelled)), Poland (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Argentina, Belgium, Brazil, Canada, Czech Republic, France, Germany, Hungary, Ireland, Italy, Mexico, Poland, Spain, United Kingdom, United States of America | 150 | 116 | 92 | 700 | 390 | 390 | 611 | 0 | 202 | 409 | 1 | 143 | 265 |  |  | 2012-05-14 | 2012-06-29 |  |  | 2013-05-24 | 2013-05-24
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0002 | Protocol Approved (Cancelled) | Real Life study (In Europe) | Phase III |  | UCB Pharma Global | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Fayoux E, Pigetvieux L | [6 empty] | No |  |  |  |  | 2005-01-07: 2007-10-03; 2005-02-04: 2008-01-14; 2005-05-09: 2008-04-22 | Austria, Belgium, Denmark, Finland, France, Germany, Greece, Italy, Netherlands, Norway, Poland, Portugal, Spain, Sweden, Switzerland, United Kingdom | Austria (Created), Belgium (Regulatory Approval), Denmark (Created), Finland (Created), France (Created), Germany (Created), Greece (Created), Italy (Created), Netherlands (Created), Norway (Created), Poland (Created), Portugal (Created), Spain (Created), Sweden (Created), Switzerland (Created), United Kingdom (Created) | Belgium | 0 | 0 | 0 | 1310 | 1048 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0003 | CSR Approved | Lyophilized/Liquid/PFS BE Study | Phase I | Open | UCB Pharma Global | Clinical Pharmaco | R & D | Mccabe S | [6 empty] | Yes | Open label, randomized, parallel group, single dose, bioavailability comparison study of three certolizumab pegol solution formulations, given as a 400 mg single dose (two 200 mg subcutaneous injections of either a reconstituted lyophilized formulation, a liquid formulation or a pre-filled syringe) to healthy volunteers. |  |  |  | 2005-01-07: 2007-10-23; 2005-05-09: 2008-01-14; 2005-11-07: 2008-02-18; 2006-03-30: 2008-04-07; 2006-06-29: 2008-07-04; 2006-08-02: 2008-08-06; 2006-09-28: 2008-09-11; 2008-07-17: 2008-09-30 | France | France (LPLV) | France | 0 | 2 | 2 | 250 | 150 | 150 | 241 | 43 | 0 | 169 | 44 | 0 | 125
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0004 | Created (Cancelled) | Safety profile of certolizumab pegol in RA Patient Populatio | Non Interventional Study - Prospective |  | UCB Pharma Global |  | Global Medical Affairs | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0008 | Created (Cancelled) | Therapeutic biodistribution study PhIIIb | Phase III |  | UCB Pharma Global | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Ropson N | [6 empty] | No |  |  |  |  | 2005-01-07: 2008-07-21 |  |  |  | 1 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0011 | Created (Cancelled) | Cimzia 2G open label study | Phase III |  | UCB Pharma Global |  | R & D | [7 empty] | No |  |  |  |  | 2005-01-07: 2008-06-23 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0014 | Protocol Approved (Cancelled) | multi-center, Ph 3, single arm, open label tr. | Phase III | Open | Affiliates | GMA Allergy/Respiratory/Inflam | Affiliates | Ambarkhane S | Weinsberg F | N/A |  | No | No |  | No |  | Indication for Rheumato GI | Immunology |  | 2005-02-04: 2008-09-30; 2005-05-09: 2008-12-22 |  |  |  | 0 | 0 | 0 | 130 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0016 | Created (Cancelled) | Juvenile RA | Phase III |  | UCB Pharma Global | Immunology | R & D | [7 empty] | No |  | Indication for Rheumato GI | Immunology |  | 2005-01-07: 2009-06-13 |  |  |  | 0 | 0 | 0 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0017 | Study Archived | Vaccine Interference | Phase IV | Single Blind | UCB Pharma Global | Immunology | UCB Pharma Global | Salisbury R |  |  | PRA International |  |  |  | No | A Phase 4, randomized, single-blind, placebo-controlled, multicenter study to evaluate the immunogenicity of pneumococcal and influenza vaccines in adult subjects with rheumatoid arthritis receiving certolizumab pegol or placebo | Rheumatoid Arthritis | Immunology |  | 2008-10-24 | 2008-10-13 |  | 2008-10-23 | 2009-09-08 | 2009-09-18 | 2010-05-14 | 2010-04-20 | 2010-11-23 | 2011-02-01 | 2011-02-15 | 2011-04-06 | 2011-04-12 | 2011-05-10 | 2011-07-12 | 2011-09-21 | United States of America | United States of America (LPLV) | United States of America | 50 | 48 | 43 | 270 | 220 | 200 | 275 | 0 | 51 | 224 | 0 | 44 | 180 |  |  | 2010-10-15 | 2010-10-15
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0027 | Study Archived | FasT | Non Interventional Study - Prospective | Open | GCSO | Immunology | Affiliates | Sacre J | Copetti C | N/A | Winicker Norimed | No | No | adults | No | FasT: TNFα: Observation of Treatment with Certolizumab pegol in Daily Practice A MULTICENTER, OBSERVATIONAL, NONINTERVENTIONAL STUDY TO EVALUATE THE SAFETY AND EFFICACY OF ANTI TNF ALPHA THERAPY WITH CERTOLIZUMAB PEGOL OBSERVED IN DAILY PRACTICE IN ADULT RA patients | Indication for Rheumato GI | Immunology |  | 2009-04-02 | 2009-05-27 |  | 2009-07-06 | 2009-11-01 | 2009-10-07 | 2013-03-29 | 2012-09-06 |  | 2014-12-17 |  | 2015-11-03 |  | 2015-11-25 |  | 2016-03-14 | Germany | Germany (LPLV) | Germany | 175 | 178 | 163 | 1068 | 1068 | 1068 | 0 | 0 | 0 | 1117 | 0 | 715 | 402 |  |  | 2011-02-15 | 2011-02-11 |  |  | 2011-11-22 | 2011-12-20 |  |  | 2012-10-26 | 2012-10-26 |  |  | 2013-10-25 | 2013-10-31
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0028 | Study Archived | Early response to certolizumab pegol with MRI assessment in | Phase III | Double Blind | UCB Pharma Global | GMA Allergy/Respiratory/Inflam | UCB Pharma Global | De Smet J | Wajskop M | N/A | PRA |  |  | adults | No | Multicenter study with a 16-week double-blind, placebo-controlled (during the initial 2 weeks) randomized period, followed by a 24-week open-label extension to assess magnetic resonance image-verified early response to certolizumab pegol in Subjects with active rheumatoid arthritis | Indication for Rheumato GI | Immunology |  | 2009-06-19 | 2009-06-02 |  | 2009-09-21 |  | 2010-12-06 | 2011-11-08 | 2012-05-02 |  | 2013-05-02 |  | 2013-07-11 |  | 2013-08-23 |  | 2013-12-11 | Denmark, Netherlands, Poland, Sweden | Denmark (LPLV), Netherlands (LPLV), Poland (LPLV), Sweden (LPLV) | Denmark, Netherlands, Poland, Sweden | 6 | 11 | 10 | 43 | 36 | 36 | 49 | 0 | 8 | 41 | 0 | 5 | 36 |  |  | 2013-05-08
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0033 | Study Archived | US monitoring synovitis in subj. w/ RA treated for 12w w/CZP | Phase III | Open | GCSO | Immunology | UCB Pharma Global | Melton K | Beaman M | N/A | Parexel |  |  |  | No |  |  |  |  | 2010-05-17 | 2010-06-05 |  | 2010-08-23 | 2010-12-21 | 2011-02-15 | 2011-09-22 | 2011-06-22 | 2011-10-28 | 2012-01-10 | 2012-03-02 | 2012-03-29 | 2012-04-30 | 2012-05-02 | 2012-08-27 | 2012-07-16 | United States of America | United States of America (LPLV) | United States of America | 10 | 11 | 6 | 60 | 50 | 40 | 13 | 0 | 10 | 3 | 0 | 0 | 3
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0040 | Protoc. Summary Approved (Cancelled) | Cimzia vs Humira injector pain comparator | Phase III |  | Global Medical Affairs |  | UCB Pharma Global | Melton K | Beaman M | [5 empty] | No |  |  |  |  | 2005-02-04: 2010-05-21 | Canada, United States of America | Canada (Created), United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2011-08-11
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0041 | Created (Cancelled) | Assesment of Qol in patients with RA | Non Interventional Study - Prospective |  | Affiliates - Italy |  | Affiliates - Italy | [7 empty] | No |  |  |  |  | 2005-01-07: 2009-07-06 | Italy | Italy (Created) |  | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0043 | CSR Approved | Phase 3, multicenter, open label study | Phase III | Open | GCSO | Immunology | UCB Pharma Global | Weinsberg F | Anderson K | N/A | PRA | No | Hybrid | paediatrics | No | PHASE 3, MULTICENTER, OPEN-LABEL STUDY TO ASSESS THE PHARMACOKINETICS, SAFETY AND EFFICACY OF CERTOLIZUMAB PEGOL IN CHILDREN AND ADOLESCENTS WITH MODERATELY TO SEVERELY ACTIVE POLYARTICULAR JUVENILE IDIOPATHIC ARTHRITIS | Juvenile Idiopathic Arthritis | Immunology |  | 2010-01-19 | 2010-01-19 | 2010-01-19 | 2010-01-19 | 2011-12-01 | 2012-03-08 | 2013-03-28 | 2022-05-24 | 2015-11-17 | 2024-04-08 | 2015-12-22 | 2024-05-31 | 2016-02-16 | 2024-07-09 | 2016-07-14 | 2024-09-18 | Argentina, Brazil, Canada, Chile, Mexico, Russian Federation, United States of America | Argentina (LPLV), Brazil (LPLV), Canada (LPLV), Chile (LPLV), Mexico (LPLV), Russian Federation (LPLV), United States of America (LPLV) | Argentina, Brazil, Canada, Chile, Mexico, Russian Federation, United States of America | 51 | 47 | 36 | 203 | 156 | 109 | 245 | 0 | 50 | 195 | 0 | 192 | 3 | 2015-11-30 | 2015-11-30 | 2015-11-30 | 2015-12-15 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-03-02 | [14 empty] | yes
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0044 | Study Archived | Additional medication of CZP in subjects with active RA | Phase III | Double Blind | GCSO | Immunology | Affiliates | Tang Y | Wu G | Parexel | PAREXEL | Yes | Yes | adults | No | A PHASE 3, MULTICENTER, DOUBLE-BLIND, PLACEBOCONTROLLED, PARALLEL GROUP, RANDOMIZED, 24-WEEK STUDY TO EVALUATE THE SAFETY AND EFFICACY OF CERTOLIZUMAB PEGOL AS ADDITIONAL MEDICATION TO METHOTREXATE IN CHINESE SUBJECTS WITH ACTIVE RHEUMATOID ARTHRITIS WHO HAVE AN INCOMPLETE RESPONSE TO METHOTREXATE | Rheumatoid Arthritis | Immunology | RA0044 is a parent study of RA0078 | 2013-02-18 | 2010-11-30 |  | 2014-01-31 | 2014-06-10 | 2014-07-23 | 2015-12-10 | 2015-10-23 |  | 2016-06-07 |  | 2016-07-22 |  | 2016-08-05 | 2016-11-01 | 2016-10-27 | China | China (LPLV) | China | 20 | 30 | 30 | 535 | 400 | 320 | 675 | 0 | 231 | 444 | 0 | 34 | 410
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0045 | Study Archived | PK study for subcutaneous CZP in healthy Chinese volunteers | Phase I | Double Blind | GCSO | Immunology | Affiliates | Tang Y | Wu G | Parexel | PAREXEL |  |  |  | No | A Randomized, Double Blind, Placebo Controlled Single Escalating dose Study of Subcutaneous Certolizumab Pegol (CZP) to evaluate the phamacokinetics and safety of CZP in Healthy Chinese subjects |  |  |  | 2013-02-18 | 2010-11-30 |  | 2014-11-03 | 2015-03-12 | 2015-03-11 | 2015-04-14 | 2015-05-14 |  | 2015-08-03 |  | 2016-03-02 |  | 2016-01-15 |  | 2016-04-20 | China | China (LPLV) | China | 1 | 1 | 1 | 54 | 36 | 30 | 100 | 0 | 64 | 36 | 0 | 0 | 36
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0055 | Study Archived | Cimzia | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Conrath P | Copetti C | N/A | Parexel | Yes | No | adults | No | A MULTI-CENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED STUDY TO EVALUATE THE EFFICACY AND SAFETY OF CERTOLIZUMAB PEGOL IN COMBINATION WITH METHOTREXATE FOR INDUCING AND SUSTAINING CLINICAL RESPONSE IN THE TREATMENT OF DMARD-NAÏVE ADULTS WITH EARLY ACTIVE RHEUMATOID ARTHRITIS PHASE 3 | Indication for Rheumato GI | Immunology |  | 2011-03-31 | 2011-04-06 |  | 2011-06-28 | 2011-12-01 | 2012-01-25 | 2014-01-01 | 2013-05-31 |  | 2015-09-10 |  | 2015-10-13 |  | 2015-11-13 |  | 2016-03-26 | Argentina, Australia, Austria, Belgium, Canada, Colombia, Czech Republic, France, Germany, Hungary, Ireland, Italy, Mexico, Monaco, Netherlands, Poland, Romania, Spain, Sweden, Switzerland, United Kingdom, United States of America | Argentina (LPLV), Australia (LPLV), Austria (LPLV), Belgium (LPLV), Canada (LPLV), Colombia (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Ireland (LPLV), Italy (LPLV), Mexico (LPLV), Monaco (LPLV), Netherlands (LPLV), Poland (LPLV), Romania (LPLV), Spain (LPLV), Sweden (LPLV), Switzerland (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Argentina, Australia, Austria, Belgium, Canada, Colombia, Czech Republic, France, Germany, Hungary, Ireland, Italy, Mexico, Monaco, Netherlands, Poland, Romania, Spain, Sweden, Switzerland, United Kingdom, United States of America | 240 | 215 | 181 | 1067 | 800 | 655 | 1418 | 0 | 528 | 890 | 40 | 531 | 319 |  |  | 2014-10-08 | 2014-10-23
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0064 | Study Archived | Comparision of RAPID3 to CDAI in RA | Phase IV | Open | Affiliates - UK | GMA Allergy/Respiratory/Inflam | Affiliates - UK | Simpson J | Driver D | N/A | i3 Research |  |  | adults | No | A Phase 4, Multicenter, Randomized, 52-Week Study To Evaluate the Routine Assessment of Patient Index Data (RAPID3) compared to the Clinical Disease Activity Index(CDAI) To Prospectively Predict Treatment Success at 52 Weeks Based on a Treatment Decision At Week 12 in Subjects With Moderate To Severe Rheumatoid Arthritis Receiving Certolizumab Pegol (CZP) |  |  |  |  | 2010-07-27 |  | 2010-09-02 | 2010-11-16 | 2010-11-15 | 2012-02-28 | 2011-09-23 | 2012-12-17 | 2012-12-06 | 2013-02-18 | 2013-03-07 | 2013-04-16 | 2013-05-02 | 2013-09-05 | 2013-10-04 | United States of America | United States of America (LPLV) | United States of America | 150 | 113 | 111 | 900 | 720 | 0 | 961 | 0 | 225 | 736 | 2 | 357 | 377
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0069 | Study Archived | Long term management of RA patients | Phase IV | Open | GCSO | Immunology | Affiliates | Elyakhlifi S | Driver D | N/A | TheraMetrics |  |  | adults | No | MULTICENTER, OPEN LABEL STUDY TO EVALUATE THE PREDICTABILITY OF EARLY RESPONSE TO CERTOLIZUMAB PEGOL (IN COMBINATION WITH METHOTREXATE) AS CONFIRMED AT WEEK 52 IN SUBJECTS WITH MODERATE-SEVERE RHEUMATOID ARTHRITIS (RA): THE CZP-SPEED STUDY | Indication for Rheumato GI | Immunology |  | 2011-03-10 | 2011-04-04 |  | 2011-05-06 | 2011-09-15 | 2011-12-05 | 2012-06-02 | 2014-02-21 |  | 2015-05-12 |  | 2015-06-09 |  | 2015-07-21 |  | 2016-01-07 | Italy | Italy (LPLV) | Italy | 23 | 21 | 18 | 160 | 120 | 120 | 173 | 0 | 41 | 132 | 0 | 41 | 91
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0077 | Study Archived | H2H trial | Phase IV | Single Blind | GCSO | Immunology | UCB Pharma Global | Conrath P | Copetti C | N/A | Parexel | No | Hybrid | adults | No | A MULTICENTER, SINGLE-BLIND, RANDOMIZED PARALLEL-GROUP STUDY TO ASSESS THE SHORT- AND LONG-TERM EFFICACY OF CERTOLIZUMAB PEGOL PLUS METHOTREXATE COMPARED WITH ADALIMUMAB PLUS METHOTREXATE IN SUBJECTS WITH MODERATE TO SEVERE RHEUMATOID ARTHRITIS RESPONDING INADEQUATELY TO METHOTREXATE | Rheumatoid Arthritis | Immunology |  | 2011-04-19 | 2011-04-19 |  | 2011-08-01 | 2011-11-25 | 2011-12-14 | 2013-10-12 | 2013-11-11 |  | 2016-01-12 |  | 2016-06-17 |  | 2016-12-12 |  | 2016-12-19 | Australia, Austria, Bulgaria, Canada, Czech Republic, France, Germany, Hungary, Ireland, Italy, Mexico, Monaco, Poland, Portugal, Romania, Spain, Switzerland, United Kingdom, United States of America | Australia (LPLV), Austria (LPLV), Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Greece (1st Site Initiation (Cancelled)), Hungary (LPLV), Ireland (LPLV), Italy (LPLV), Mexico (LPLV), Monaco (LPLV), Poland (LPLV), Portugal (LPLV), Romania (LPLV), Spain (LPLV), Switzerland (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Austria, Bulgaria, Canada, Czech Republic, France, Germany, Hungary, Ireland, Italy, Mexico, Monaco, Poland, Portugal, Romania, Spain, Switzerland, United Kingdom, United States of America | 183 | 175 | 151 | 1190 | 892 | 892 | 1492 | 0 | 555 | 937 | 0 | 324 | 613
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0078 | Study Archived | Extension of study CZP in RA0044 | Phase III | Open | GCSO | Immunology | UCB Pharma Global | Tang Y | Wu G | Parexel | PAREXEL | No | Yes | adults | No | A phase 3, multicenter, open-label extension study to assess the safety and efficacy of certolizumab pegol as additional medication to methotrexate in Chinese subjects with active rheumatoid arthritis who participated in RA0044. | Rheumatoid Arthritis | Immunology | RA0078 is an extension of RA0044 | 2012-12-19 | 2010-11-30 |  | 2014-01-31 | 2014-10-07 | 2014-11-26 | 2016-04-07 | 2016-05-11 |  | 2016-12-23 |  | 2017-01-16 |  | 2017-02-07 |  | 2017-04-03 | China | China (LPLV) | China | 20 | 30 | 30 | 470 | 320 | 272 | 347 | 0 | 0 | 347 | 0 | 4 | 343
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0082 | Protoc. Summary Approved (Cancelled) | NIS in RA & CD eval. Saf. & Effic. of Cimzia use TB monitor | Phase IV | Open | Affiliates |  | Affiliates | De Smet J | Wajskop M | Parexel | PXL |  |  |  | No |  |  |  |  | 2005-01-07: 2011-08-10; 2005-02-04: 2011-08-10 | Russian Federation | Russian Federation (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0087 | Study Archived | Validation of ePRO vs pPRO in subjects with CZP for RA | Non Interventional Study - Prospective | Open | Affiliates | Immunology | Affiliates | Wuiame D | Baukens C | Parexel | SPI PXL | No | No | adults | No | A MULTICENTER, OPEN-LABEL, RANDOMIZED PARALLELGROUP AND CROSS-OVER STUDY TO VALIDATE THE USE OF ELECTRONIC PATIENT OUTCOME MEASUREMENT TOOL (EPRO) COMPARED TO THE ESTABLISHED PAPER REPORTED OUTCOME MEASUREMENT TOOLS (PPRO) IN PATIENTS TREATED WITH CERTOLIZUMAB PEGOL FOR RHEUMATOID ARTHRITIS | Osteoarthritis | Immunology |  | 2005-05-09: 2012-07-03; 2005-09-30: 2013-02-28; 2005-11-07: 2013-02-18; 2006-03-01: 2014-01-20; 2006-03-30: 2014-01-20; 2006-06-29: 2014-02-06; 2006-08-02: 2014-08-28; 2006-09-28: 2014-10-02; 2008-07-17: 2015-02-23 | Australia | Australia (LPLV) | Australia | 20 | 13 | 10 | 100 | 78 | 78 | 52 | 0 | 3 | 49 | 0 | 44 | 5
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0091 | Study Archived | Cimzia® Registry in RA and CD | Non Interventional Study - Prospective | Open | GCSO | Immunology | UCB Pharma Global | Schelstraete I | Driver D | N/A | N/A | No | No | adults | No | A MULTICENTER OBSERVATIONAL STUDY TO EVALUATE THE SAFETY AND EFFECTIVENESS OF CIMZIA (CERTOLIZUMAB PEGOL) IN ADULT RHEUMATROID ARTHRITIS (RA) AND CROHN'S DISEASE (CD) PATIENTS WHEN USING COMPREHENSIVE PROGRAM OF TUBERCULOSIS SCREENING AND MONITORING | Indication for Rheumato GI | Immunology |  | 2011-04-15 | 2011-04-15 |  | 2011-04-15 | 2011-05-19 | 2011-08-02 | 2014-05-19 | 2015-10-21 |  | 2015-10-21 |  | 2016-03-29 |  |  |  | 2016-03-16 | Russian Federation | Russian Federation (LPLV) | Russian Federation | 24 | 44 | 30 | 500 | 500 | 500 | 232 | 0 | 20 | 212 | 0 | 175 | 37 |  |  | 2014-12-09 | 2014-12-03
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0095 | Created (Cancelled) | Usability of Cimzia Auto-injector in subj. with active RA&CD | Phase III |  | Clinical Development USA | Immunology | Clinical Development USA | Jensen L, Nilius S, Thierfelder S | Beinhauer-Zellenka U, Driver D | N/A | PXL |  |  |  | No |  |  |  |  | 2005-01-07: 2018-12-03 |  |  |  | 6 | 0 | 0 | 50 | 40 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0097 | Study Archived | Non-Interventional Observational Study | Non Interventional Study - Prospective | Open | GCSO | Immunology | UCB Pharma Global | Hoeckendorff J | Anderson K | Parexel | PAREXEL | No | No | adults | No | “A MULTI-CENTER NONINTERVENTIONAL STUDY WITH CERTOLIZUMAB PEGOL IN COMPARISON TO ANY OTHER SUBCUTANEOUS TNF INHIBITOR IN TWO PARALLEL GROUPS IN BIOLOGIC NAIVE PATIENTS WITH RHEUMATOID ARTHRITIS” | Rheumatoid Arthritis | Immunology |  | 2012-09-04 | 2012-09-20 |  | 2012-09-20 | 2012-12-15 | 2012-12-17 | 2015-06-17 | 2018-06-19 | 2020-08-14 | 2020-06-16 | 2020-09-30 | 2020-08-14 | 2020-10-22 | 2020-09-04 | 2021-01-28 | 2021-03-31 | Germany | Germany (LPLV) | Germany | 154 | 152 | 122 | 1595 | 1595 | 1276 | 1727 | 0 | 0 | 1727 | 0 | 646 | 1081 |  |  | 2014-10-31 | 2014-10-31
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | RA0132 | Study Archived | e-Device study for CZP | Phase I | Open | GCSO | Immunology | GCSO | Brown E | Tillery N | Parexel | SPI PXL | Yes | No | adults | Yes | OPEN-LABEL, SINGLE-CENTER, RANDOMIZED, PARALLEL GROUP, SINGLE-DOSE, BIOEQUIVALENCE STUDY OF 200MG CERTOLIZUMAB PEGOL SOLUTION INJECTED EITHER BY A PREFILLED SYRINGE (REFERENCE) OR BY AN E-DEVICE (TEST) IN HEALTHY SUBJECTS | Ankylosing Spondylitis; Crohn's disease; Psoriatic Arthritis; Rheumatoid Arthritis | Immunology; Immunology; Immunology; Immunology |  | 2015-06-30 | 2015-10-23 |  | 2016-02-18 | 2016-03-01 | 2016-03-25 | 2016-05-24 | 2016-08-23 | 2016-08-19 | 2016-11-01 | 2016-09-19 | 2017-10-02 | 2016-10-03 | 2018-01-22 | 2017-01-02 | 2018-01-22 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 100 | 100 | 100 | 256 | 0 | 156 | 100 | 0 | 4 | 96
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | UP0016 | Study Archived | Phase1B Lactation Study | Phase I | Open | GCSO | Immunology | GCSO | Heinzen L | Smit R | N/A | PPD | Yes | Yes | adults | No | A MULTICENTER, POSTMARKETING STUDY TO EVALUATE THE CONCENTRATION OF CERTOLIZUMAB PEGOL IN THE BREAST MILK OF MOTHERS RECEIVING TREATMENT WITH CIMZIA® (CERTOLIZUMAB PEGOL). PHASE 1B (CLINICAL PHARMACOLOGY) | Indication for Rheumato GI | Immunology |  | 2013-06-24 | 2013-08-06 |  | 2013-12-19 | 2014-03-05 | 2014-09-08 | 2015-03-06 | 2015-11-25 |  | 2015-12-11 |  | 2016-01-25 |  | 2016-03-02 |  | 2016-05-25 | Netherlands, Switzerland, United States of America | France (1st Site Initiation (Cancelled)), Netherlands (LPLV), Switzerland (LPLV), United States of America (LPLV) | Netherlands, Switzerland, United States of America | 15 | 11 | 6 | 25 | 16 | 16 | 19 | 0 | 2 | 17 | 0 | 0 | 17
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | UP0017 | Study Archived | Phase 1B Mom and Infant Study | Phase I | Open | GCSO | Immunology | GCSO | Heinzen L | Smit R | N/A | PPD | Yes | Yes | adults | No | A MULTICENTER POSTMARKETING STUDY TO EVALUATE THE PLACENTAL TRANSFER OF CERTOLIZUMAB PEGOL IN PREGNANT WOMEN RECEIVING TREATMENT WITH CIMZIA® (CERTOLIZUMAB PEGOL) | Nonspecific | Immunology |  | 2013-06-18 | 2013-06-13 |  | 2013-09-16 | 2013-12-31 | 2014-01-09 | 2014-12-31 | 2016-09-29 | 2015-04-29 | 2016-11-21 | 2015-05-27 | 2016-12-13 | 2015-07-22 | 2017-01-16 | 2015-11-30 | 2017-02-24 | France, Netherlands, Switzerland, United States of America | France (LPLV), Netherlands (LPLV), Switzerland (LPLV), United States of America (LPLV) | France, Netherlands, Switzerland, United States of America | 15 | 13 | 11 | 30 | 20 | 20 | 21 | 0 | 5 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | CIMZIA | Immunology | UP0019 | Study Archived | Immunology Pregnancy Registry | Registry | Open | GCSO | Immunology | GCSO | Bolo A, Forbis K | Beaman M | N/A | INC | No | No | adults | No | AN OBSERVATIONAL FOLLOW-UP STUDY OF WOMEN WHO BECOME PREGNANT WHILE PARTICIPATING IN A CERTOLIZUMAB PEGOL (CZP) CLINICAL STUDY OR WHOSE PREGNANCIES HAVE OTHERWISE BEEN REPORTED TO UCB DUE TO POTENTIAL CZP EXPOSURE DURING PREGNANCY | Ankylosing Spondylitis; Crohn's disease; Psoriatic Arthritis; Rheumatoid Arthritis | Immunology; Immunology; Immunology; Immunology |  | 2014-09-09 | 2014-09-02 |  | 2015-12-14 | 2016-03-11 | 2016-11-16 | 2025-02-24 | 2017-12-18 |  | 2017-12-18 |  | 2018-07-26 |  | 2018-11-02 |  | 2018-12-03 | United States of America | United States of America (LPLV) | United States of America | 4 | 1 | 1 | 360 | 360 | 300 | 1 | 0 | 0 | 1 | 0 | 0 | 1
Yes | Not assigned | Managing Type | 1 | C-Peptide | not defined | SP0547 | Final TFLs released | C-peptide in diabetic cardiovascular autonomic neuropathy, p | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E | [6 empty] | No | Effects of a 12-week s.c. treatment with two different doses of C-Peptide versus placebo on diabetic cardiovascular autonomic neuropathy in IDDM patients | Cardiac Autonomic Neuropathy (CAN) | Immunology |  | 2005-01-07: 1999-11-30; 2005-02-04: 1999-11-30; 2005-05-09: 1999-11-30; 2005-11-07: 2000-02-02; 2006-03-30: 2000-06-14; 2006-06-29: 2000-08-28; 2006-09-28: 2001-01-30 | Germany | Germany (Created) |  | 5 | 0 | 0 | 60 | 48 | 36 | 0 | 0 | 0 | 35 | 0 | 8 | 27
Yes | Not assigned | Managing Type | 1 | C-Peptide | not defined | SP0558 | Protocol Approved | Effects of C-peptide on forearm blood flow (macro- and micro | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E | [6 empty] | No | Effects of C-peptide on forearm blood flow (macro- and microcirculation) |  |  |  | 2005-01-07: 1999-05-01; 2005-02-04: 1999-05-01; 2005-05-09: 1999-10-15 | Sweden | Sweden (Created) |  | 1 | 0 | 0 | 12 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | C-Peptide | not defined | SP0559 | Protocol Approved | C-peptide in autonomic neuropathy | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E | [6 empty] | No | C-peptide in autonomic neuropathy |  |  |  | 2005-01-07: 1999-06-01; 2005-02-04: 1999-06-01; 2005-05-09: 1999-11-29 | Sweden | Sweden (Created) |  | 0 | 0 | 0 | 12 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | C-Peptide | not defined | SP0574 | Created (Cancelled) | C-peptide in diabetic peripheral neuropathy in IDDM patients | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Schulz A | [6 empty] | No | C-peptide in diabetic peripheral neuropathy in IDDM patients - phase IIb | [22 empty] | 0 | 0 | 0 | 420 | 420 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | C-Peptide | not defined | SP0589 | Created | C-Peptide phase I trial (pilot trial bioavailability) | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | C-Peptide phase I trial (pilot trial bioavailability) | [22 empty] | 1 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Cylexin | not defined | SP0346 | Created | CYLEXIN (CY-1503) - in patients undergoing pulmonary thrombo |  |  | UCB Pharma Global |  | UCB Pharma Global | Stegmann B | [6 empty] | No | Single-center, double-blind, placebo-controlled study to evaluate the efficacy of CY-1503 in the prevention of pulmonary reperfusion injury in patients undergoing pulmonary thromboendarterectomy | [22 empty] | 0 | 0 | 0 | 53 | 51 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Cylexin | not defined | SP0347 | Created | CYLEXIN (CY-1503) - in patients with acute myocardial infarc |  |  | UCB Pharma Global |  | UCB Pharma Global | Stegmann B | [6 empty] | No | A double-blind, placebo-controlled, multicenter study of CY-1503 in prevention of myocardial reperfusion injury in patients with acute myocardial infarction treated with primary angioplasty | [22 empty] | 0 | 0 | 0 | 154 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Cylexin | not defined | SP0366 | Created | CYLEXIN (CY-1503) - in patients with acute myocardial infarc |  |  | UCB Pharma Global |  | UCB Pharma Global | Stegmann B | [6 empty] | No | A double-blind, dose optimization, placebo-controlled, multicenter study of CY-1503 in prevention of myocardial reperfusion injury in patients with acute myocardial infarction treated with thrombolytic therapy | [22 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Cytochalasin B | not defined | SP0071 | Protoc. Summary Approved | Biostent versus placebo in prevention of restenosis. | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Koch B | [6 empty] | No | Double-blind, placebo-controlled, randomized study to evaluate the efficacy and safety of Biostent at a dose of 8.0 µg/ml drug component versus placebo in the prevention of restenosis in patients undergoing PTCA | Prevention of Restenosis | Immunology |  | 2005-01-07: 1997-08-21; 2005-02-04: 1997-08-21 |  |  |  | 35 | 0 | 0 | 360 | 360 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Dapirolizumab pegol | Immunology | SL0013 | Study Archived | FIM | Phase I | Double Blind | UCB Pharma Global | Clinical Pharmaco | R & D | Soranson J | Grose-Hodge R | N/A | Acromonium |  | No | adults | Yes | A two‑part, randomized, double‑blind, placebo‑controlled, single-dose, dose‑escalating study to evaluate the safety, tolerability, pharmacokinetics, immunogenicity, and to explore the pharmacodynamics of CDP7657 administered in healthy subjects (Part 1) and in subjects with systemic lupus erythematosus (Part 2) |  |  |  | 2005-02-04: 2009-05-15; 2005-05-09: 2009-07-24; 2005-11-07: 2010-03-16; 2006-03-30: 2012-07-24; 2006-06-29: 2012-12-14; 2006-08-02: 2013-02-27; 2006-09-28: 2013-04-26; 2008-07-17: 2013-10-15 | Belgium, Bulgaria, Germany | Belgium (LPLV), Bulgaria (LPLV), Germany (LPLV) | Belgium, Bulgaria, Germany | 6 | 9 | 9 | 100 | 44 | 44 | 152 | 0 | 108 | 44 | 1 | 3 | 40
Yes | Not assigned | Managing Type | 1 | Dapirolizumab pegol | Immunology | SL0014 | Study Archived | Multi Centre multi dose exploratory study | Phase I | Double Blind | UCB Pharma Global | Clinical Pharmaco | GED | Soranson J | Grose-Hodge R | Parexel | PXL |  | No | adults | No | A MULTICENTER, INVESTIGATOR- AND SUBJECT BLIND, RANDOMIZED, PLACEBO CONTROLLED, PARALLEL GROUP, REPEAT DOSE STUDY TO EVALUATE THE EFFECT OF CDP7657 IN SUBJECTS WITH ACTIVE SYSTEMIC LUPUS ERYTHEMATOSUS | Systemic Lupus Erythematosus; Indication for Rheumato GI | Immunology; Immunology |  |  | 2012-07-09 |  | 2012-07-09 | 2013-01-08 | 2013-03-14 | 2014-07-23 | 2014-02-06 |  | 2014-08-26 |  | 2014-10-27 |  | 2014-12-18 |  | 2015-02-18 | Belgium, Bulgaria, Germany, Poland, Romania, Russian Federation, Spain | Belgium (LPLV), Bulgaria (LPLV), Germany (LPLV), Poland (LPLV), Romania (LPLV), Russian Federation (LPLV), Spain (LPLV) | Belgium, Bulgaria, Germany, Poland, Romania, Russian Federation, Spain | 25 | 21 | 16 | 72 | 24 | 24 | 68 | 0 | 44 | 24 | 0 | 2 | 22 |  |  | 2014-08-01 | 2014-08-01
Yes | Not assigned | Managing Type | 1 | Dapirolizumab pegol | Immunology | SL0023 | Study Archived | Dose ranging SLE study | Phase II | Double Blind | GCSO | NewMeds | UCB Pharma Global | Akintola J, Grasses T | Grose-Hodge R, Tillery N | N/A | Syneos | Yes | Yes | adults | No | A MULTI-CENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL-GROUP, DOSE-RANGING STUDY FOLLOWED BY AN OBSERVATIONAL PERIOD TO EVALUATE THE EFFICACY AND SAFETY OF DAPIROLIZUMAB PEGOL IN SUBJECTS WITH MODERATELY TO SEVERELY ACTIVE SYSTEMIC LUPUS ERYTHEMATOSUS | Systemic Lupus Erythematosus | Immunology |  |  |  |  | 2016-04-12 | 2016-06-03 | 2016-06-02 | 2017-07-20 | 2017-11-16 | 2018-09-05 | 2018-11-19 | 2018-10-03 | 2019-01-31 | 2018-10-17 | 2019-03-08 | 2019-01-11 | 2019-11-14 | Bulgaria, Chile, Colombia, Germany, Hungary, Mexico, Peru, Poland, Romania, Russian Federation, Spain, Ukraine, United States of America | Bulgaria (LPLV), Chile (LPLV), Colombia (LPLV), Germany (LPLV), Hungary (LPLV), Mexico (LPLV), Peru (LPLV), Poland (LPLV), Romania (LPLV), Russian Federation (LPLV), Spain (LPLV), Ukraine (LPLV), United States of America (LPLV) | Bulgaria, Chile, Colombia, Germany, Hungary, Mexico, Peru, Poland, Romania, Russian Federation, Spain, Ukraine, United States of America | 100 | 95 | 71 | 267 | 163 | 111 | 399 | 0 | 217 | 182 | 0 | 11 | 171
Yes | Not assigned | Managing Type | 1 | Dihydroergotamine | not defined | SP0605 | Final TFLs released | EFFICACY AND SAFETY OF SEGLOR | Phase IV | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Assous A | [6 empty] | No | Efficacy and safety of Seglor capsules 5 mg twice a day in migraine prophylaxis. | Migraine prophylaxis | Central Nervous System |  | 2005-01-07: 2000-08-01; 2005-02-04: 2000-08-01; 2005-05-09: 2000-08-01; 2005-11-07: 2000-11-01; 2006-03-30: 2001-05-01; 2006-06-29: 2001-11-01; 2006-09-28: 2002-05-01 |  |  |  | 113 | 0 | 0 | 450 | 300 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0069 | LPLV | A Pharmacokinetic Study to Assess the Effect of Food | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | A Pharmacokinetic Study to Assess the Effect of Food |  |  |  | 2005-01-07: 1997-07-08; 2005-02-04: 1997-07-08; 2005-05-09: 1997-08-06; 2005-11-07: 1997-08-07; 2006-03-30: 1997-08-07; 2006-06-29: 1997-08-24 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0381 | Created | Drug Safety Trial Data. Study drug: SPUS 760 (DILTIAZEM) |  |  | UCB Pharma Global |  | UCB Pharma Global | Dommaschk J | [6 empty] | No | Drug Safety Trial Data. Study drug: SPUS 760 (DILTIAZEM) | [22 empty] | 0 | 0 | 0 | 14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0382 | Created | Drug Safety Trial Data. Study drug: SPUS 760 (DILTIAZEM) |  |  | UCB Pharma Global |  | UCB Pharma Global | Dommaschk J | [6 empty] | No | Drug Safety Trial Data. Study drug: SPUS 760 (DILTIAZEM) | [22 empty] | 0 | 0 | 0 | 14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0424 | Created | Drug Safety Trial Data. Study drug: DILTIAZEM |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: DILTIAZEM | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0425 | Created | Drug Safety Trial Data. Study drug: DILTIAZEM |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: DILTIAZEM | [22 empty] | 0 | 0 | 0 | 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0426 | Created | Drug Safety Trial Data. Study drug: DILTIAZEM |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: DILTIAZEM | [22 empty] | 0 | 0 | 0 | 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0427 | Created | Drug Safety Trial Data. Study drug: DILTIAZEM |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: DILTIAZEM | [22 empty] | 0 | 0 | 0 | 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0428 | Created | Drug Safety Trial Data. Study drug: DILTIAZEM |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: DILTIAZEM | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0429 | Created | Drug Safety Trial Data. Study drug: DILTIAZEM |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: DILTIAZEM | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0430 | Created | Drug Safety Trial Data. Study drug: DILTIAZEM |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: DILTIAZEM | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0440 | Created | Drug Safety Trial Data. Study drug: DILTIAZEM |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: DILTIAZEM | [22 empty] | 0 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0441 | Created | Drug Safety Trial Data. Study drug: DILTIAZEM |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: DILTIAZEM | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0442 | Created | Drug Safety Trial Data. Study drug: DILTIAZEM |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: DILTIAZEM | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0443 | Created | Drug Safety Trial Data. Study drug: DILTIAZEM |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: DILTIAZEM | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0447 | Created | DILTIAZEM-120MG - primary hypertension |  |  | UCB Pharma Global |  | UCB Pharma Global | Mastej M | [6 empty] | No | Double-blind, randomized, parallel group study to evaluate efficacy and safety of controlled release diltiazem tablets in treatment of primary hypertension | [22 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem | not defined | SP0453 | Created | Drug Safety Trial Data. Study drug: DILTIAZEM |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: DILTIAZEM | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Diltiazem,Moexipril | not defined | SP0530 | Final TFLs released | Moexipril/Diltiazem in patients with hypertension | Phase IV | Single Blind | UCB Pharma Global |  | UCB Pharma Global | Mastej M | [6 empty] | No | Single blind in phase I and open in phase II, randomized study to compare efficacy and safety of combined therapy of primary hypertension with low dose Moexipril and Diltiazem versus monotherapy with either Moexipril or Diltiazem. | Hypertension | Immunology |  | 2005-05-09: 1999-01-15; 2006-09-28: 2000-05-30 | Poland | Poland (Created) |  | 3 | 0 | 0 | 240 | 200 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A00261 | Study Archived | Bioavailability study | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | [7 empty] | Yes | Randomized,open,cross-over comparative oral bioavaibility study of efleterizine administered either as 1 co-administrationof an extemporaenous solution10 mg and an experimental prolonged release tabelet 25 mg once in fasting conditions and once after solution 15 mg administered twice at 12 hours interval in healthy male subjects. | [5 empty] | 2000-01-31 | 2000-03-07 | 2000-04-03 | 2000-04-04 |  |  | 2000-05-12 | 2000-05-01 | 2000-06-30 | 2000-06-30 |  |  | 2000-12-15 | 2001-11-21 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 0 | 1 | 0 | 0 | 0 | 25 | 0 | 13 | 12 | 0 | 0 | 12
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A00283 | Study Archived | Pseudoephedrine Efletirizine Interaction | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A | [6 empty] | No | "Randomized, monocenter, open label, three-way crossover, bilateral pharmacokinetic interaction study of efletirizine dihydrochloride 15 mg immediate release tablet and pseudoephedrine hydrochloride 120 mg sustained release capsule after single oral admi" | Indication for Dermato Allergo | Immunology |  |  |  | 2002-04-25 | 2002-04-25 | 2002-06-01 | 2002-06-20 | 2002-08-01 |  | 2002-08-01 | 2002-07-26 | 2002-10-01 | 2002-10-31 |  | 2003-01-16 | 2003-02-01 | 2003-04-02 | France | France (LPLV) | France | 1 | 1 | 1 | 0 | 0 | 0 | 28 | 0 | 4 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A00284 | CSR Approved | EFZ 15 mg - Bioequivalence Study | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bennett D, Pinelli M, Voss G | [6 empty] | Yes | A randomized, single center, open label, four-way cross-over, single dose bioequivalence and food interaction study of efletirizine dihydrochloride immediate release (IR) 15 mg table and efleterizine dihydrochloride immediate release (IR) 15 mg capsule in healthy male and female volunteers. | Indication for Dermato Allergo | Immunology |  | 2003-02-10 |  | 2003-04-04 | 2003-05-05 | 2003-05-09 | 2003-05-16 | 2003-05-30 | 2003-06-03 | 2003-07-03 | 2003-07-24 | 2003-08-18 | 2003-10-03 | 2003-10-17 | 2003-12-17 | 2004-03-22 | 2004-03-25 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 43 | 16 | 12 | 47 | 0 | 31 | 16 | 0 | 1 | 15
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A00287 | Study Archived | Single dose final batch + Food effect | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Pigeolet E |  |  | SGS biopharma |  |  |  | Yes | Randomized, monocenter, open label, three-way crossover, relative bioavailability and food interaction study of efletirizine dihydrochloride extended release (ER) 35 mg tablet and efletirizine dihydrochloride immediate release (IR) 15 mg capsules in 21 healthy male and female subjects | Indication for Dermato Allergo | Immunology |  |  |  | 2001-06-20 | 2001-06-20 | 2001-07-10 | 2001-07-27 |  | 2001-08-10 | 2001-08-24 | 2001-08-29 | 2001-10-12 | 2002-01-22 |  |  | 2002-01-15 | 2003-07-17 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 21 | 21 | 21 | 32 | 0 | 11 | 21 | 0 | 0 | 21
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A00319 | Study Archived | Efletirizine sedation | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | De Smedt F |  |  | Forenap/UCB |  |  |  | Yes | A pilot randomized, double-blind, five-way, cross-over, placebo controlled study to explore in healthy male subjects the sedative effect of a single oral administration of efletirizine dihydrochloride (7, 10, 15 and 60 mg) capsules on pharmaco-EEG, Saccad auto-evaluation questionnaires | Indication for Dermato Allergo | Immunology |  |  |  | 2001-11-02 | 2001-10-17 | 2002-01-14 | 2002-01-09 |  |  | 2002-03-15 | 2002-03-28 | 2002-04-27 | 2002-04-19 |  | 2003-01-31 | 2002-06-27 | 2003-11-05 | France | France (LPLV) | France | 1 | 1 | 1 | 30 | 15 | 15 | 34 | 0 | 19 | 15 | 0 | 0 | 15
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A00320 | Study Archived | PAR Dose Ranging | Phase II | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | R & D | Le Gall M | [6 empty] | No | A double-blind placebo controlled randomized multicenter phase II trial: comparison to placebo of the efficacy and safety of efletirizine extended release 35mg once daily, efletirizine immediate release 7mg 10mg and 15mg administered twice daily, orally for four weeks to adults suffering from PAR | Indication for Dermato Allergo | Immunology |  |  |  | 2001-10-08 | 2001-10-08 | 2002-04-02 | 2002-04-26 | 2002-07-16 |  | 2002-08-31 | 2002-09-16 | 2002-11-01 | 2002-11-19 |  | 2003-03-15 | 2003-03-01 | 2003-08-14 | South Africa | South Africa (LPLV) | South Africa | 50 | 47 | 46 | 1000 | 700 | 700 | 934 | 0 | 216 | 718 | 0 | 40 | 678
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A00321 | CSR Approved | Efleterizine SAR | Phase II | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | R & D | Voss G | [6 empty] | No | A double-blind, randomized, placebo controlled, multi-center, phase II study with five parralel groups, comparing the efficacy and safety of oral efleterizine immediate release (IR) 7 mg, 10 mg, and 15 mg tablets administered twice a day and oral efletirizine extended release (ER) 35 mg tablets administered once a day in the morning for two weeks versus placebo in subjects suffering from seasonal allergic rhinitis. <RPCE01K3101> | Indication for Dermato Allergo | Immunology |  |  |  | 2002-01-18 | 2002-01-23 | 2002-04-08 | 2002-04-01 | 2002-07-12 | 2002-05-23 | 2002-08-09 | 2002-06-20 | 2002-11-06 | 2002-10-28 | 2003-01-06 | 2002-11-15 | 2003-05-28 | 2003-10-30 | United States of America | United States of America (LPLV) | United States of America | 23 | 24 | 24 | 1000 | 700 | 596 | 1018 | 0 | 314 | 704 | 0 | 28 | 676
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A00322 | Study Archived | Efletirizine Wheal & Flare 7,10,15 mg IR + 35 mg ER | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A | [6 empty] | Yes | Randomized, monocenter, double-blind, four-way crossover under fasting conditions, pharmacokinetics and pharmacodynamics (histamine prick test) study of efletirizine dihydrochloride immediate release (IR) 7mg, 10mg, 15mg oral tablets administered twice da | Indication for Dermato Allergo | Immunology |  |  |  | 2002-03-11 | 2002-03-08 | 2002-05-02 | 2002-04-29 |  |  | 2002-08-03 | 2002-08-07 | 2002-10-01 | 2002-10-18 |  | 2003-02-14 | 2003-01-01 | 2003-09-04 | France | France (LPLV) | France | 1 | 1 | 1 | 0 | 0 | 0 | 25 | 5 | 0 | 20 | 0 | 2 | 18
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A00330 | Created (Cancelled) | Dose response study and sedative effects | Phase I | Double Blind | Clinical Development Europe |  | R & D | De Smedt F | [6 empty] | Yes |  | Indication for Dermato Allergo | Immunology | [20 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A00386 | Study Archived | Once a day SR/ER | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S | [6 empty] | Yes | Monocenter, open label, non-randomized, crossover, single dose pharmacokinetic investigation of the bioavailability of efletirizine administered via novel modified release formulations in healthy volunteers | Indication for Dermato Allergo | Immunology |  |  |  | 2003-05-05: 2004-04-08; 2003-05-16: 2004-06-15; 2003-06-03: 2004-06-18; 2003-07-24: 2004-07-26; 2003-10-03: 2004-09-13; 2003-12-17: 2004-11-15; 2004-03-25: 2005-03-03 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 0 | 1 | 32 | 16 | 12 | 39 | 0 | 23 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A00402 | Study Archived | Efleterizine SR once a day new formulations | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S |  |  | Térapharm/UCB |  |  |  | Yes | Monocenter, open label, randomized, five-way crossover, oral single dose study to compare the pharmacokinetics of efletirizine administered via novel extended release formulations with a reference oral solution, and to assess the influence of food on one of the test formulations in healthy male volu | Indication for Dermato Allergo | Immunology |  |  |  | 2004-12-03 | 2004-12-13 | 2005-01-10 | 2005-01-27 |  | 2005-02-10 | 2005-03-22 | 2005-03-21 | 2005-04-20 | 2005-04-18 | 2005-05-24 | 2005-10-20 | 2005-07-24 | 2005-12-13 | France | France (LPLV) | France | 1 | 0 | 1 | 15 | 12 | 10 | 16 | 0 | 4 | 12 | 0 | 0 | 12
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A00406 | Created (Cancelled) | Pilot PK (added 13 oct 04 Dev meeting) | Phase I |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No |  | Indication for Dermato Allergo | Immunology | [20 empty] | 0 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A216 | Study Archived | Chronic idiopathic urticaria - Dose ranging | Phase II |  | Clinical Development Europe | TA Allergology / Respiratory | R & D | Daoust A, Liard A, Voss G | [6 empty] | No | Multicentre double-blind randomized trial, with four parallel groups, comparing the efficacy and safety of efletirizine capsules of 4 mg, 15 mg, and 60 mg, versus placebo, administered twice a day per os, during four weeks, in adult patients with chronic | [5 empty] | 2003-05-05: 1995-11-09; 2003-05-16: 1996-01-25; 2003-07-24: 1997-12-26; 2003-10-03: 1998-03-05; 2003-12-17: 2000-01-31; 2004-03-25: 2000-10-05 | Belgium, France, Germany | Belgium (LPLV), France (LPLV), Germany (LPLV) | Belgium, France, Germany | 44 | 0 | 40 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A218 | Study Archived | Interaction Efletirizine | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Arendt C | [6 empty] | Yes | Phase 1, double-blind, two-way cross-over, multiple dose study to assess possible influences on the pharmacokinetics of an oral contraceptives by concomitant administration of 60 mg of efletirizine or placebo capsules given orally twice a day during 20 da | [5 empty] | 2003-05-16: 1996-03-28; 2003-07-24: 1996-08-22 | Germany | Germany (LPLV) | Germany | 0 | 0 | 1 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A225 | Study Archived | PK with 3 different pilots slow release | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Arendt C | [6 empty] | Yes | Open, randomised, crossover, comparative bioavailability study of 3 experimental sustained release formulations of efletirizine dihydrochloride (30 mg tabelts) as reference, given as single doses, in 8 healthy male subjects. | [5 empty] | 2003-05-16: 1997-05-02; 2003-07-24: 1997-06-16; 2004-03-25: 1998-03-01 | Belgium | Belgium (LPLV) | Belgium | 1 | 0 | 1 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A226 | Study Archived | Enzymatic induction Pivotal study | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Giuliano A | [6 empty] | Yes | Influence of efletirizine on the pharmacokinetics and metabolism of oxazepam, antipyrine and nifedipine in 18 healthy male and female volunteers as assessed by a "cocktail" study design. | [5 empty] | 2003-05-16: 1997-04-03; 2003-07-24: 1997-05-17; 2004-03-25: 1999-01-12 | Germany | Germany (LPLV) | Germany | 1 | 0 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A231 | Study Archived | Tests of 3 different slow release formulations | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Arendt C | [6 empty] | Yes | Open, randomized, crossover, comparative bioavailability study 3 experimental sustained release formulations of efletirizine dihydrochloride (30 mg tablets) and an oral solution (30 mg) as reference, given as single doses, in 8 healthy male subjects. Pil | [5 empty] | 2003-05-16: 1997-09-26; 2003-07-24: 1997-10-31; 2003-10-03: 1998-05-06; 2004-03-25: 1999-02-04 | Belgium | Belgium (LPLV) | Belgium | 1 | 0 | 1 | 8 | 0 | 0 | 9 | 0 | 1 | 8 | 0 | 0 | 8
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A237 | Study Archived | Food / non food | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Arendt C, Martin L | [6 empty] | Yes | Open, randomised, crossover, comparative bioavailability study of efletirizine dihydrochloride (60 mg capsule) given as a single daily dose after a high fat meal or in fasting conditions. | [5 empty] | 2003-05-16: 1998-03-13; 2003-07-24: 1998-05-03; 2004-03-25: 1998-10-05 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 0 | 1 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A240 | Study Archived | Dose ranging PAR | Phase II |  | Clinical Development Europe | TA Allergology / Respiratory | R & D | [7 empty] | No | Etude multicentrique en double insu de phase II, randomisée, avec quatre groupes parallèles, comparant l'efficacité et la tolérance de gélules d'éflétirizine de 4 mg et 15 mg (deux fois par jour), de cétirizine 10 mg (une fois par jour) et d'un placebo ( | [5 empty] | 2003-05-05: 1998-04-17; 2003-05-09: 1998-09-01; 2003-05-16: 1998-09-08; 2003-07-03: 1999-01-31; 2003-07-24: 1999-02-23; 2003-10-03: 1999-04-14; 2004-03-22: 1999-04-01; 2004-03-25: 2000-11-21 | France | France (LPLV) | France | 40 | 0 | 39 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A241 | CSR Approved | Urticaria long term | Phase III | Open | Clinical Development Europe | TA Allergology / Respiratory | R & D | Le Gall M, Pinelli M | [6 empty] | No | Open, phase III multicentre study assessing the safety and efficacy of 15 mg efletirizine capsules administered orally twice a day, for up to one year, to adult patients with chronic urticaria | Indication for Dermato Allergo | Immunology |  |  |  |  | 1998-07-10 | 1998-10-01 | 1998-10-08 |  |  | 2000-10-01 | 2001-02-09 | 2001-02-02 | 2001-11-27 |  | 2002-02-07 | 2001-09-03 | 2004-04-02 | France, Germany, Sweden | France (LPLV), Germany (LPLV), Sweden (LPLV) | France, Germany, Sweden | 100 | 0 | 84 | 800 | 800 | 100 | 0 | 0 | 0 | 624 | 0 | 0 | 624
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A242 | Study Archived | Chronic idiopathic urticaria 15mg - 4 weeks | Phase III |  | Clinical Development Europe | TA Allergology / Respiratory | R & D | Wajskop M | [6 empty] | No | Rando,DB,plc-controlled,//-group, multicentre, phase III trial, of the efficacy and safety of 15 mg efletirizine capsules, or matching plc, administered twice daily, per os, during 4 weeks, in adult outpatients with chronic idiopathic urticaria | [6 empty] | 1998-10-23 | 1999-02-01 | 1999-05-11 |  |  | 2000-02-29 | 2000-01-24 | 2000-04-30 | 2000-06-23 |  | 2002-02-28 | 2000-10-31 | 2002-05-21 | Russian Federation | Russian Federation (LPLV) | Russian Federation | 8 | 0 | 8 | 122 | 0 | 0 | 153 | 18 | 0 | 135 | 15 | 0 | 120
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A243 | Study Archived | SAR comparative trial | Phase III |  | Clinical Development Europe | TA Allergology / Respiratory | R & D | Liard A | [6 empty] | No | Etude multicentrique en double insu de phase III, randomisé, avec trois groupes parallèles, comparant l'efficacité et la tolérance de gélules d'éflétirizine 15 mg (deux fois par jour), de cétirizine 10 mg (une fois par jour), et d'un placebo (deux fois pa | [5 empty] | 2003-05-05: 1999-02-08; 2003-10-03: 2000-03-03; 2003-12-17: 2000-10-03; 2004-03-25: 2001-03-20 | France | France (Created) |  | 50 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A244 | Study Archived | Efletirizine 3 formulations Extended Release | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A | [6 empty] | Yes | Open, randomised, cross-over, comparative bioavability study of 3 experimental extended release tabelets of efletirizine dihydrochloride (30 mg tabelets) and an oral solution as reference, each given as single doses of 30 mg, in 8 healthy male subjects | Indication for Dermato Allergo | Immunology |  |  |  | 2003-05-05: 1998-03-08; 2003-05-09: 1998-10-19; 2003-05-16: 1998-10-05; 2003-07-03: 1998-10-31; 2003-07-24: 1998-11-13; 2003-10-03: 1999-04-07; 2004-03-25: 2000-03-01 | Belgium | Belgium (LPLV) | Belgium | 1 | 0 | 1 | 0 | 0 | 0 | 10 | 0 | 2 | 8 | 0 | 0 | 8
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A248 | Study Archived | Efletirizine-PK hepatic insufficiency | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Pigeolet E | [6 empty] | No | Multicenter, open label, pharmacokinetic study of a single oral administration of 15 mg efletirizine dihydrochloride ucb 28754 in healthy subjects and patients with impaired liver function child-plugh classes b and c | Indication for Dermato Allergo | Immunology |  |  |  |  | 1999-04-13 | 1999-06-15 | 1999-07-15 |  | 2001-01-26 | 2000-04-01 | 2001-02-15 |  | 2002-12-13 |  | 2003-03-14 | 2000-04-01 | 2003-11-25 | Belgium, France | Belgium (LPLV), France (LPLV) | Belgium, France | 5 | 0 | 5 | 15 | 15 | 15 | 21 | 0 | 6 | 15 | 0 | 0 | 15
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A249 | Study Archived | Efletirizine-PK Renal insufficiency | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A |  |  | Aster-Cephac |  |  |  | No | Multicentre, open label, parallel group, not randomized, pharmacokinetic study of a single oral administration of 15 mg dihydrochloride capsule (ucb 28754) in subjects with normal renal function or with different degrees of renal function impairement. | Indication for Dermato Allergo | Immunology |  |  |  |  | 1999-06-22 | 1999-09-01 | 1999-10-04 |  | 2001-03-05 | 1999-12-01 | 2001-03-16 | 2000-02-01 | 2002-02-06 |  | 2002-03-01 | 2000-07-01 | 2003-07-01 | Belgium, France | Belgium (LPLV), France (LPLV) | Belgium, France | 6 | 6 | 5 | 24 | 24 | 24 | 29 | 5 | 0 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A250 | Study Archived | Efletirizine-PK Hemodialysed | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Pigeolet E | [6 empty] | No | Open-abel, Monocentre, single dose pharmacokinetic study of 15 mg of efletirizine dichloride capsul, orally administred in subjects with end renal disease undergoing hemodialysis. | Indication for Dermato Allergo | Immunology |  |  |  | 2000-12-20 | 2001-02-06 | 2001-03-12 | 2001-03-19 |  |  | 2001-04-15 | 2001-04-12 | 2001-05-30 | 2002-11-08 |  |  | 2001-08-31 | 2003-01-14 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 5 | 5 | 5 | 6 | 0 | 1 | 5 | 0 | 0 | 5
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A253 | Study Archived | Absorption site of Efletirizine (Scintigraphy method) | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Moulaert B | [6 empty] | Yes | Pharmacoscintigraphic evaluation of the regional gastrointestinal absorption of efletirizine dichloride (ucb 28754), delivered using the InteliSite Capsule : open-label, randomised, 4 way-cros-over study , 30 mg single dose in 8 healthy male volunteers | Indication for Dermato Allergo | Immunology |  |  |  | 1999-03-22 | 1999-03-22 | 1999-03-17 | 1999-03-30 |  |  | 1999-05-05 | 1999-05-13 | 1999-06-18 | 1999-08-27 |  |  | 1999-10-08 | 2000-11-21 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 0 | 1 | 0 | 0 | 0 | 17 | 0 | 5 | 12 | 0 | 3 | 9
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A255 | Study Archived | PAR - confirmatory | Phase III | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | R & D | Le Gall M | [6 empty] | No | Randomised multicentre double blind Phase III study with three parallel groups comparing the efficacy and safety of capsules of efletirizine 15 mg twice a day, of loratadine 10 mg once a day, and of placebo twice a day administered orally for four weeks to patients suffering from PAR | [5 empty] | 1999-05-01 | 1999-06-22 | 1999-09-01 | 1999-09-11 |  |  | 2000-03-01 | 2000-03-16 | 2000-05-01 | 2000-05-18 |  | 2000-10-05 | 2000-12-01 | 2003-03-28 | France | France (LPLV) | France | 45 | 0 | 41 | 0 | 0 | 0 | 450 | 80 | 0 | 370 | 370 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Efletirizine | Immunology | A258 | Study Archived | W&F - single oral dose - 24 hours | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Moulaert B | [6 empty] | Yes | A pilot, single center, double blind, randimized, Cross-over, placebo controlled, study of the effect over 24 hours and the 24-hour pharmacocinetics, of a single oral dose of 15 mg efleterizine dihydrochloride (capsule) on the histamine-induced W&F in healthy subjetcs | Indication for Dermato Allergo | Immunology |  |  |  | 1999-06-01 | 1999-09-14 | 1999-08-30 | 1999-10-05 |  |  | 1999-09-24 | 1999-10-17 | 1999-10-15 | 2000-02-16 |  |  | 2000-01-14 | 2000-11-21 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 0 | 1 | 0 | 0 | 0 | 43 | 0 | 24 | 19 | 0 | 1 | 18
Yes | Not assigned | Managing Type | 1 | ELANTAN | Immunology | HD0001 | Study Archived | PK Properties of Isosorbide-5-mononitrate fasting & fed Heal | Phase I | Open | Affiliates |  | Affiliates | Cawello W, Park M | Matsuoka K | N/A |  |  |  | adults | Yes | A RANDOMIZED, OPEN-LABEL, ONE DOSE, 2-WAY CROSSOVER STUDY TO EVALUATE THE BIOEQUIVALENCE OF ELANTAN SR 60MG IN COMPARISON WITH IMDUR SR 60MG UNDER FASTED AND FED CONDITIONS IN HEALTHY KOREAN MALE SUBJECTS | Indication for Internal Medicine | Immunology |  | 2011-02-24 | 2011-02-24 | 2003-05-05: 2011-02-24; 2003-05-16: 2011-06-13; 2003-07-24: 2011-07-18; 2003-10-03: 2011-10-06; 2003-12-17: 2011-11-30; 2004-03-25: 2011-12-19 | South Korea | South Korea (LPLV) | South Korea | 1 | 0 | 1 | 60 | 60 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | Immunology | SP0999 | CSR Approved | PK study for ElantanSR50 between 2 manufacture place in CHN | Phase I |  | Affiliate China |  | Affiliate China | Wang L | [6 empty] | Yes | A RANDOMIZED, OPEN-LABEL, SINGLE-DOSE, 2-WAY CROSSOVER TRIAL TO EVALUATE THE BIOEQUIVALENCE OF ELANTAN SR 50 FROM 2 DIFFERENT MANUFACTURING SITES IN 24 HEALTHY CHINESE MALE SUBJECTS. |  |  |  | 2010-06-21 | 2010-03-25 |  | 2010-06-21 | 2010-09-07 | 2010-09-15 | 2010-09-16 | 2010-09-20 |  | 2010-10-13 |  | 2011-01-19 |  | 2011-05-19 |  | 2011-07-12 | China | China (LPLV) | China | 1 | 1 | 1 | 24 | 0 | 0 | 27 | 25 | 2 | 24 | 24 | 0 | 24
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0057 | Created | Mononitrate in CHF | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Ermer W | [6 empty] | No | Double-blind, placebo-controlled, randomized multicenter trial to assess the effects of IS-5-MN sustained release given additionally to patients with chronic congestive heart failure - NYHA II-III - treated with Captopril. | Congestive Heart Failure | Immunology | [17 empty] | Israel | Israel (Created) |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0074 | Created | ELANTAN-LA-25 - healthy volunteers | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Baxter T | [6 empty] | No | The aim of this study is to assess the pharmacokinetics of Elantan LA25 over a 24 hour period in healthy volunteers. This study is being conducted to support the registration of Elantan LA25 in the Republic of Ireland | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0079 | Created | ELANTAN-LONG - in patients with coronary artery disease |  |  | UCB Pharma Global |  | UCB Pharma Global | Grosse-Freese M | [6 empty] | No | Single-centre, double-blind, cross-over study to compare the onset of action of Mono-Cedocard retard 50 mg and Promocard 60 mg in 8 patients with coronary artery disease | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0080 | Created | ELANTAN - in patients with chronic heart failure |  |  | UCB Pharma Global |  | UCB Pharma Global | Sabia R | [6 empty] | No | Randomised, double-blind, parallel group, controlled study of isosorbide-5-mononitrate vs placebo in patients with chronic heart failure | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0086 | Created | MONOKET - in patients with chronic stable angina pectoris |  |  | UCB Pharma Global |  | UCB Pharma Global | Kulkarni A | [6 empty] | No | A multicenter pilot study to assess safety and efficacy of monoket in patients with chronic stable angina pectoris | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0087 | Created | MONOKET-SR in patients with chronic stable angina pectoris |  |  | UCB Pharma Global |  | UCB Pharma Global | Kulkarni A | [6 empty] | No | A double-blind, randomized, parallel group multicenter study comparing monoket-sr and placebo in patients with chronic stable angina pectoris | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0127 | Created | Drug Safety Trial Data. Study drug: ELANTAN |  |  | UCB Pharma Global |  | UCB Pharma Global | Wlasak R | [6 empty] | No | Drug Safety Trial Data. Study drug: ELANTAN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0128 | Created | Drug Safety Trial Data. Study drug: ELANTAN-LONG |  |  | UCB Pharma Global |  | UCB Pharma Global | Hartlieb C | [6 empty] | No | Drug Safety Trial Data. Study drug: ELANTAN-LONG | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0129 | Created | Drug Safety Trial Data. Study drug: ELANTAN-LONG |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | Drug Safety Trial Data. Study drug: ELANTAN-LONG | [22 empty] | 0 | 0 | 0 | 461 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0239 | Created | ELANTAN - in patients with coronary artery disease and diabe |  |  | UCB Pharma Global |  | UCB Pharma Global | Ermer W | [6 empty] | No | Double-blind evaluation of the clinical efficacy of Elantan LA50 (Isosorbide-5-Mononitrate) compared to placebo in patients with coronary artery disease and diabetes mellitus, as measured by the abolition of silent ischaemia on 48 hour monitoring | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0248 | Created | ELANTAN - Isosorbide Mononitrate in Chagas Cardiomyopathy |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | Patients with angina pectoris and without significative lesions in their coronary arteries: comparative study between Isosorbide-5-Mononitrate and Diltiazen | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0256 | Created | ELANTAN-LONG im Vergleich zu elantan retard 80 mg bei Patie |  |  | UCB Pharma Global |  | UCB Pharma Global | Babst H | [6 empty] | No | ELANTAN-LONG im Vergleich zu elantan retard 80 mg bei Patienten mit stabiler Angina pectoris | [22 empty] | 0 | 0 | 0 | 24 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0259 | Created | ELANTAN-LONG - in patients with coronary artery disease and |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | Double-blind, active treatment-controlled, randomized, cross-over singel center study to compare the onset of action of Elantan long and Coleb-Duriles in patients with coronary artery disease and stable exercise induced angina pectoris | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 16 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0260 | Created | ELANTAN-LONG - in patients with CAD and stable exercise indu |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | Double-blind, placebo-controlled, randomized, cross-over multicenter study to assess the onset of action of Isosorbide-5-Mononitrate substained release in patients with coronary artery disease and stable exercise induced angina pectoris | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 50 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0263 | Created | Imdur, IS5N, Monoket, Single Dose, Healthy male Volunteers |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | An Open-Label, Single-Dose, Randomized Two-way Crossover Study to Bioequivalence Study Comparing Monoket SR versus Imdur Administered as a 60 mg Tablet in Twenty Four Healthy Male Volunteers | [22 empty] | 0 | 0 | 0 | 23 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0264 | Created | Drug Safety Trial Data. Study drug: MONOKET-SR |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Drug Safety Trial Data. Study drug: MONOKET-SR | [22 empty] | 0 | 0 | 0 | 28 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0265 | Created | IMDUR - Monoket - 60 mg tablet - twenty-for healthy male vol |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | An open-label single-dose, randomized three-way crossover study to evaluate the effect of food on the bioavailability of Monoket SR compared to Imdur administered as a 60 mg tablet in wenty-four healthy male volunteers | [22 empty] | 0 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0270 | Created | Drug Safety Trial Data. Study drug: ELANTAN-RETARD |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: ELANTAN-RETARD | [22 empty] | 0 | 0 | 0 | 40 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0271 | Created | ISMN - in patients with ischemic cardiopathy (stable effort |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | An assessment of a single dose of 20 mg isosorbide-5-mononitrate versus 20 mg isosorbide dinitrate using serial exercise tests | [22 empty] | 0 | 0 | 0 | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0272 | Created | ELANTAN-RETARD - in patients with mixed angina |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Reduction of total ischemic burden in patients with mixed angina. A comparative study of the combination of bisoprolol and sustained release isosorbide-5-mononitrate 50 mg versus the combination of bisoprolol and nifedipine | [22 empty] | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0274 | Created | ELANTAN - Isosorbide Mononitrate |  |  | UCB Pharma Global |  | UCB Pharma Global | Ermer W | [6 empty] | No | Prognosis study in patients with chronic heart failure NYHA stage II-III. One-year mortality study comparing standard therapy plus nitrate to standard therapy plus nitrate plus captopril (multicenter study). | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0312 | Created | Drug Safety Trial Data. Study drug: MONOKET-SR |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Drug Safety Trial Data. Study drug: MONOKET-SR | [22 empty] | 0 | 0 | 0 | 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0329 | Created | ELANTAN - Isosorbide Mononitrate and Isosorbide Dinitrate i |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Comparison between Hemodynamic effects of intravenous Isosorbide-5-Mononitrate and intravenous Isosorbide Dinitrate (a randomized study) in patients with chronic heart failure | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0338 | Created | double blind - Isosorbid-5-Mononitrate - healthy volunteers |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | double-blind, randomized, placebo-controlled cross-over study for the comparative evaluation of the initital time course of the hemodynamic effects of single oral doses of 20 mg immediate release and 50 and 60 mg controlled release isosorbide-5-mononitrate in healthy volunteers | [22 empty] | 0 | 0 | 0 | 16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0340 | Created | MONOLONG Koronare Herzkrankheit | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Stalleicken D | [6 empty] | No | Überprüfung und Dokumentation | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 11799 | 10766 | 10766 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0362 | Created | Drug Safety Trial Data. Study drug: MONOKET-SR (Listings) |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Study to evaluate the bioavailability of a newly IS 5 MN sustained release tablet in comparison with Imdur as reference preparation in 24 healthy male volunteers. | [22 empty] | 0 | 0 | 0 | 25 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0363 | Created | Drug Safety Trial Data. Study drug: MONOKET-SR (Listings) |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Study to evaluate the bioavailability of a newly developed IS 5 MN sustained release tablet in comparision with Imdur as reference preparation under steady state conditions in 24 healthy male volunteers. | [22 empty] | 0 | 0 | 0 | 31 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0364 | Created | Drug Safety Trial Data. Study drug: MONOKET-SR (Listings) |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Drug Safety Trial Data. Study drug: MONOKET-SR (Listings) | [22 empty] | 0 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0388 | Created | IS5MN, Imdur, 12 Healthy Male Volunteers, Tablet |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Pilot Study to Evaluate the Bioavailability of a Newly Developed IS-5-MN Sustained Release Tablet in Comparison with Imdur as Reference Preparation in 12 Healthy Male Volunteers | [22 empty] | 0 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0418 | Created | Drug Safety Trial Data. Study drug: MONOKET-SR |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Study to evaluate the bioavailability of a newly developed IS-MN sustained release tablet (Monoket SR) in comparision with Imdur as reference preparation in 30 healthy male volunteers. | [22 empty] | 0 | 0 | 0 | 30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0423 | Created | MONOLONG - Häufigkeit und Intensität von Angina pectoris Anf | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Stalleicken D | [6 empty] | No | Überprüfung und Dokumentation der Wirksamkeit und Verträglichkeit von Monolong bzw. Monolong retard unter regelmäßiger Einnahme des Medikaments | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0472 | Protoc. Summary Approved | Monoket-SR/ imdur 30mg : bioequivalence | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | A two-period, open-label, randomized, single dose, cross-over study in 30 healthy male volunteers to investigate the bioequivalence of two IS-5-MN preparations. |  |  |  | 1997-12-15 | 1997-12-15 | [17 empty] | 1 | 0 | 0 | 30 | 30 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0476 | Protoc. Summary Approved | ISMN Phase I | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | A two-period open-label randomized single dose cross-over study in thirty healthy male volunteers to investigate the bioequivalence of Isosorbide Mononitrate extended release tablet, 120 mg versus IMDUR 120 mg |  |  |  | 1998-04-08 | 1998-04-08 | [17 empty] | 0 | 0 | 0 | 30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0490 | Created | ISMN Extended Release Tab. 120 mg | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | A three-period open-label randomized single dose cross-over study in 30 healthy male volunteers to evaluate the effect of food on the bioavailability of Isosorbide Mononitrate extended release tablet of 120 mg versus IMDUR 120 mg. | [22 empty] | 0 | 0 | 0 | 30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0491 | Created | ISMN Extended Release Tablet 120 mg | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | A two-period open-label randomized cross-over multiple-dose study in 30 healthy male volunteers to evaluate the bioavailability of Isosorbide Mononitrate Extended Release Tablet 120 mg in comparision with IMDUR 120 mg under steady state conditions. | [22 empty] | 0 | 0 | 0 | 30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0528 | Created | Pharmacokinetic trial of Elantan long 25 versus Imdur 30 in | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | not available (DMCD) | [22 empty] | 0 | 0 | 0 | 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0703 | Protocol Approved | IQOLAN Portugal | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Marr I | [6 empty] | No | International Quality of Life assessment of patinets with Angina pectoris on Nitrate therapy (IQOLAN -Portugal) | Coronary Heart Disease | Immunology |  |  |  | 2003-05-05: 1999-05-21 |  |  |  | 10 | 0 | 0 | 1000 | 387 | 387 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0705 | Created | IQOLAN Latvia | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Marr I | [6 empty] | No | IQOLAN Latvia - International Quality of Life assessment of patients with Angina pectoris on Nitrate therapy | Coronary Heart Disease | Immunology | [20 empty] | 60 | 0 | 0 | 350 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0706 | Final TFLs released | IQOLAN Russia | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Marr I | [6 empty] | No | IQOLAN Russia - International Quality of Life assessment of patients with Angina pectoris on Nitrate therapy | Coronary Heart Disease | Immunology |  |  |  | 2003-12-17: 2002-08-01 |  |  |  | 2 | 0 | 0 | 1200 | 870 | 870 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0707 | Protoc. Summary Approved | IQOLAN China | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Marr I | [6 empty] | No | IQOLAN China - International Quality of Life assessment of patients with Angina pectoris on Nitrate therapy | Coronary Heart Disease | Immunology |  | 2003-11-03 | 2003-11-03 | [17 empty] | 8 | 0 | 0 | 1200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0708 | Created (Cancelled) | IQOLAN Finnland | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Marr I | [6 empty] | No | International Quality of LIfe assessment of patients with Angina pectoris on Nitrate Therapy | Coronary Heart Disease | Immunology | [20 empty] | 8 | 0 | 0 | 1200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0733 | Created (Cancelled) | IQOLAN Lithuania | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Marr I | [6 empty] | No | International Quality of LIfe assessment of patients with Angina pectoris on Nitrate Therapy | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0734 | Protoc. Summary Approved | IQOLAN Netherlands | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Marr I | [6 empty] | No | International Quality of LIfe assessment of patients with Angina pectoris on Nitrate Therapy | Coronary Heart Disease | Immunology |  | 2003-11-03 | 2003-11-03 | [17 empty] | 150 | 0 | 0 | 750 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0892 | Created | Comparison of relative bioavailability of three kinds of is | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | Comparison of relative bioavailability of three kinds of isosorbide mononitrate sustained release preparations | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0893 | Created | Pharmacokinetics of domestic and imported isosorbide mononi | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | Pharmacokinetics of domestic and imported isosorbide mononitrate sustained release capsule following a single and multiple dose in healthy volunteers | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ELANTAN | not defined | SP0894 | Created | Anti-ischemic effect and safety evaluation of 5-ISMN SR agen | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | Anti-ischemic effect and safety evaluation of three 5-ISMN sustained release agents on coronary heart disease with myocardial ischemia | Cardiac Ischemia | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0002 | CSR Approved | Lupus PK/PD (103/FLE/02) | Phase II | Open | Clinical Development USA | Clinical Pharmaco | R & D | Gladson E, Neilson S |  |  | PPD |  |  |  | No | A Randomized Phase II Pharmacokinetics Pharmacodynamics Study of Epratuzumab in Patients with Systemic Lupus Erythematosus | Indication for Rheumato GI | Immunology | SL0002 is a parent study of SL0005 | 2010-11-25 |  | 2003-05-05: 2004-10-12; 2003-05-16: 2005-04-19; 2003-06-03: 2006-03-31; 2003-07-24: 2007-06-27; 2003-10-03: 2007-04-23; 2003-12-17: 2009-01-26; 2004-03-25: 2010-03-17 | United States of America | United States of America (LPLV) | United States of America | 4 | 4 | 3 | 24 | 22 | 0 | 14 | 0 | 1 | 13 | 0 | 0 | 12
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0003 | CSR Approved | Severe Lupus (10303) | Phase III | Double Blind | Clinical Development USA | Immunology | R & D | Gladson E |  |  | PPD |  |  |  | No | A Phase III, Randomized, Double-Blind, Placebo-Controlled, Multi-Center Clinical Trial of Epratuzumab in Patients with Acute Severe SLE Flares Excluding the Renal or Neurologic Systems Planning dates are not complete as "Hold on Dosing" implemented on September 1, 2006. Planning depends on future action which are not yet determined. | Indication for Rheumato GI | Immunology | SL0003 is a feeder study of SL0006 | 2005-01-05 |  | 2003-05-05: 2005-02-08; 2003-05-16: 2005-09-02; 2003-06-03: 2006-11-08; 2003-07-24: 2007-03-07; 2003-10-03: 2007-06-28; 2003-12-17: 2007-12-31; 2004-03-25: 2008-04-22 | Belgium, Hungary, Netherlands, Spain, United Kingdom, United States of America | Belgium (LPLV), Brazil (1st Site Initiation (Cancelled)), Canada (1st Site Initiation (Cancelled)), France (1st Site Initiation (Cancelled)), Germany (1st Site Initiation (Cancelled)), Hungary (LPLV), Italy (1st Site Initiation (Cancelled)), Netherlands (LPLV), Slovakia (1st Site Initiation (Cancelled)), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Hungary, Netherlands, Spain, United Kingdom, United States of America | 95 | 61 | 20 | 512 | 512 | 0 | 46 | 0 | 10 | 36 | 0 | 28 | 8
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0004 | CSR Approved | Moderate Lupus (10304) | Phase III | Double Blind | Clinical Development USA | Immunology | R & D | Gladson E |  |  | PPD |  |  |  | No | A phase III, Randomized, Double-Blind, Placebo Controlled, Multi-Center Study of Epratuzumab in Patients with Active Systemic Lupus Erythematosus | Indication for Rheumato GI | Immunology | SL0004 is a feeder study of SL0006 | 2004-11-24 |  | 2003-05-05: 2005-02-08; 2003-05-16: 2005-05-11; 2003-06-03: 2006-08-30; 2003-07-24: 2007-02-16; 2003-10-03: 2007-06-28; 2003-12-17: 2007-12-31; 2004-03-25: 2008-04-22 | Belgium, Italy, Netherlands, Spain, United Kingdom, United States of America | Belgium (LPLV), Brazil (1st Site Initiation (Cancelled)), France (1st Site Initiation (Cancelled)), Germany (1st Site Initiation (Cancelled)), Italy (LPLV), Netherlands (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Italy, Netherlands, Spain, United Kingdom, United States of America | 100 | 62 | 34 | 315 | 315 | 300 | 99 | 5 | 41 | 54 | 0 | 45 | 9
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0005 | Protocol Approved (Cancelled) | F-U Severe lupus | Phase III |  | Clinical Development USA | Immunology | R & D | Gladson E |  |  | PPD |  |  |  | No | A Phase III, Multi-center, Open-label, Follow-up Study, to Assess the Safety and Efficacy of Epratuzumab in Patients with Acute Severe SLE Flares Excluding the Renal or Neurologic Systems | Indication for Rheumato GI | Immunology | SL0005 is a follow up of SL0002 |  | 2006-06-29 | 2003-05-05: 2006-08-15 | Belgium, Brazil, Canada, Czech Republic, France, Germany, Hungary, Italy, Netherlands, Slovakia, Spain, United Kingdom, United States of America | Belgium (Created), Brazil (Created), Canada (Created), Czech Republic (Created), France (Created), Germany (Created), Hungary (Created), Italy (Created), Netherlands (Created), Slovakia (Created), Spain (Created), United Kingdom (Created), United States of America (Created) |  | 95 | 0 | 0 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0006 | Study Archived | F-U Moderate Lupus | Phase II | Open | Clinical Development USA | Immunology | R & D | Brown E | Tillery N | N/A | PPD |  |  |  | No | An Open-Label Extension Trial for Patients Completing the Phase III, Randomized, Double-Blind, Placebo Controlled, Multi-Center Study of Epratuzumab in Patients with Active Systemic Lupus Erythematosus | Indication for Rheumato GI | Immunology | SL0006 is a follow up of SL0003, SL0004 and is a feeder study of SL0012 | 2010-11-25 |  | 2006-03-16 | 2006-03-16 | 2006-06-09 | 2006-05-03 | 2008-02-29 | 2008-03-12 | 2010-02-01 | 2012-01-11 | 2010-02-23 | 2013-02-01 | 2010-04-05 | 2013-02-28 | 2010-06-20 | 2014-08-28 | United States of America | United States of America (LPLV) | United States of America | 14 | 11 | 10 | 36 | 36 | 0 | 29 | 0 | 0 | 29 | 0 | 13 | 16
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0007 | Study Archived | PH IIB | Phase II | Double Blind | Clinical Development USA | Immunology | R & D | Neilson S | [6 empty] | No | A Phase IIb Randomized, Double-blind, Placebo-controlled, Dose and Dose Regimen-ranging Study of the Safety and Efficacy of Epratuzumab in Serologically-positive Systemic Lupus Erythematosus Patients with Active Disease | Indication for Rheumato GI | Immunology | SL0007 is a parent study of SL0008 | 2007-05-21 | 2007-07-10 | 2007-07-10 | 2007-10-19 | 2007-08-30 | 2008-01-29 | 2008-05-09 | 2009-03-09 | 2008-08-15 | 2009-08-17 | 2008-09-30 | 2009-10-21 | 2008-11-20 | 2010-01-08 | 2009-01-20 | 2010-11-12 | Belgium, Brazil, Hong Kong, Hungary, India, Lithuania, Poland, Spain, Ukraine, United Kingdom, United States of America | Belgium (LPLV), Brazil (LPLV), Hong Kong (LPLV), Hungary (LPLV), India (LPLV), Lithuania (LPLV), Poland (LPLV), Spain (LPLV), Ukraine (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Brazil, Hong Kong, Hungary, India, Lithuania, Poland, Spain, Ukraine, United Kingdom, United States of America | 60 | 59 | 52 | 210 | 210 | 210 | 310 | 0 | 83 | 227 | 0 | 13 | 214 | 2009-02-12 | 2009-02-12 | 2009-09-25
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0008 | Study Archived | PH IIB Extension study | Phase II | Open | Clinical Development USA | Immunology | R & D | Brown E | Tillery N | N/A | PPD |  |  |  | No | A Phase IIb, Multi-center, Open-label, Follow-up Study to Assess the Safety and Efficacy of Epratuzumab in Serologically-positive Systemic Lupus Erythematosus Patients with Active Disease who participated in Study SL0007 | Indication for Rheumato GI | Immunology | SL0008 is an extension of SL0007 and is a feeder study of SL0012 | 2010-11-25 |  | 2007-12-26 | 2007-11-27 | 2008-02-21 | 2008-05-05 | 2008-12-08 | 2009-06-24 | 2013-07-23 | 2011-12-28 | 2013-08-12 | 2012-11-21 | 2013-09-10 | 2012-12-12 | 2013-12-02 | 2013-03-05 | Belgium, Brazil, Hong Kong, Hungary, India, Lithuania, Poland, Spain, Ukraine, United Kingdom, United States of America | Belgium (LPLV), Brazil (LPLV), Hong Kong (LPLV), Hungary (LPLV), India (LPLV), Lithuania (LPLV), Poland (LPLV), Spain (LPLV), Ukraine (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Brazil, Hong Kong, Hungary, India, Lithuania, Poland, Spain, Ukraine, United Kingdom, United States of America | 0 | 46 | 44 | 170 | 170 | 0 | 0 | 0 | 0 | 203 | 0 | 92 | 111
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0009 | Study Archived | PH III Confirmatory | Phase III | Double Blind | GCSO | Immunology |  | Rowley K, Thierfelder S | Driver D, Smit R | N/A | Parexel | Yes | Hybrid | adults | No | A PHASE 3, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER STUDY OF THE EFFICACY AND SAFETY OF FOUR 12-WEEK TREATMENT CYCLES (48 WEEKS TOTAL) OF EPRATUZUMAB IN SYSTEMIC LUPUS ERYTHEMATOSUS SUBJECTS WITH MODERATE TO SEVERE DISEASE (EMBODY 1) | Systemic Lupus Erythematosus | Immunology | SL0009 is a feeder study of SL0011, SL0012 | 2010-03-31 | 2010-02-08 |  | 2010-06-08 | 2010-12-01 | 2010-12-09 | 2012-01-09 | 2014-05-15 |  | 2015-05-15 |  | 2015-06-24 |  | 2015-07-27 |  | 2015-11-11 | Australia, Belgium, Brazil, Bulgaria, Czech Republic, Estonia, France, Germany, India, Israel, Italy, Lithuania, Mexico, Romania, Russian Federation, South Korea, Spain, Taiwan, United Kingdom, United States of America | Australia (LPLV), Belgium (LPLV), Brazil (LPLV), Bulgaria (LPLV), Czech Republic (LPLV), Estonia (LPLV), France (LPLV), Germany (LPLV), India (LPLV), Israel (LPLV), Italy (LPLV), Lithuania (LPLV), Mexico (LPLV), Romania (LPLV), Russian Federation (LPLV), South Korea (LPLV), Spain (LPLV), Taiwan (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Belgium, Brazil, Bulgaria, Czech Republic, Estonia, France, Germany, India, Israel, Italy, Lithuania, Mexico, Romania, Russian Federation, South Korea, Spain, Taiwan, United Kingdom, United States of America | 165 | 154 | 142 | 1053 | 780 | 630 | 1258 | 0 | 465 | 793 | 0 | 263 | 530
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0010 | Study Archived | PH III Confirmatory | Phase III | Double Blind | GCSO | Immunology |  | Brown E | Tillery N | N/A | Parexel | Yes | Hybrid | adults | No | A PHASE 3, RANDOMIZED, DOUBLE-BLIND, PLACEBO CONTROLLED, MULTICENTER STUDY OF THE EFFICACY AND SAFETY OF FOUR 12-WEEK TREATMENT CYCLES (48 WEEKS TOTAL) OF EPRATUZUMAB IN SYSTEMIC LUPUS ERYTHEMATOSUS SUBJECTS WITH MODERATE TO SEVERE DISEASE (EMBODY 2) | Systemic Lupus Erythematosus | Immunology | SL0010 is a feeder study of SL0011, SL0012 | 2010-03-31 | 2010-02-08 |  | 2010-06-09 | 2010-10-05 | 2010-12-22 | 2012-01-20 | 2014-05-30 |  | 2015-06-03 |  | 2015-07-09 |  | 2015-07-28 |  | 2015-11-23 | Brazil, Canada, France, Germany, Hungary, India, Italy, Mexico, Poland, Romania, Russian Federation, South Africa, Spain, Ukraine, United Kingdom, United States of America | Brazil (LPLV), Canada (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), India (LPLV), Italy (LPLV), Mexico (LPLV), Netherlands (1st Site Initiation (Cancelled)), Poland (LPLV), Romania (LPLV), Russian Federation (LPLV), South Africa (LPLV), Spain (LPLV), Ukraine (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Brazil, Canada, France, Germany, Hungary, India, Italy, Mexico, Poland, Romania, Russian Federation, South Africa, Spain, Ukraine, United Kingdom, United States of America | 165 | 156 | 132 | 1053 | 780 | 630 | 1195 | 0 | 403 | 792 | 0 | 251 | 541
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0011 | Created (Cancelled) | PH III OL extension trial for responders from SL0010 | Phase III |  | UCB Pharma Global | Immunology | R & D |  |  | Parexel | PXL |  |  |  | No |  |  |  | SL0011 is an extension of SL0009, SL0010 and is a feeder study of SL0012 | 2020-12-11 | [18 empty] | 200 | 0 | 0 | 345 | 312 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0012 | Study Archived | PH III OLE - SL0009/10 pts.-completers & lack efficacy e/w's | Phase III | Open | GCSO | Immunology | GCSO | Grasses T | Tillery N | N/A | PAREXEL, International | No | Hybrid | adults | No | A PHASE 3, MULTICENTER, OPEN-LABEL, EXTENSION STUDY TO ASSESS THE SAFETY AND TOLERABILITY OF EPRATUZUMAB TREATMENT IN SYSTEMIC LUPUS ERYTHEMATOSUS SUBJECTS (EMBODY 4) | Systemic Lupus Erythematosus | Immunology | SL0012 is an extension of SL0006, SL0008, SL0009, SL0010, SL0011 | 2010-03-31 | 2010-06-04 |  | 2010-09-16 | 2011-04-05 | 2011-07-20 | 2013-08-23 | 2015-06-09 |  | 2016-02-16 |  | 2016-04-18 |  | 2016-05-02 |  | 2016-09-28 | Australia, Belgium, Brazil, Bulgaria, Canada, Czech Republic, Estonia, France, Germany, Hong Kong, Hungary, Israel, Italy, Lithuania, Mexico, Poland, Romania, Russian Federation, South Africa, South Korea, Spain, Taiwan, Ukraine, United Kingdom, United States of America | Australia (LPLV), Belgium (LPLV), Brazil (LPLV), Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), Estonia (LPLV), France (LPLV), Germany (LPLV), Hong Kong (LPLV), Hungary (LPLV), Israel (LPLV), Italy (LPLV), Lithuania (LPLV), Mexico (LPLV), Poland (LPLV), Romania (LPLV), Russian Federation (LPLV), South Africa (LPLV), South Korea (LPLV), Spain (LPLV), Taiwan (LPLV), Ukraine (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Belgium, Brazil, Bulgaria, Canada, Czech Republic, Estonia, France, Germany, Hong Kong, Hungary, Israel, Italy, Lithuania, Mexico, Poland, Romania, Russian Federation, South Africa, South Korea, Spain, Taiwan, Ukraine, United Kingdom, United States of America | 300 | 228 | 226 | 1250 | 1250 | 1000 | 1253 | 0 | 0 | 1253 | 0 | 1175 | 80 |  |  | 2015-05-21 | 2015-05-21
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0018 | Created (Cancelled) | Epratuzumab in Children and Adolescents with SLE | Phase III |  | Clinical Development Europe | Immunology | Clinical Development Europe | Bornemann T | Maier A | Parexel |  |  | Yes |  | No |  | Systemic Lupus Erythematosus | Immunology | SL0018 is a parent study of SL0019 | 2014-12-01 | [18 empty] | 40 | 0 | 0 | 200 | 150 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0019 | Created (Cancelled) | Long term Open Label Study in SLE Pediatrics | Phase III |  | Clinical Development Europe | Immunology | Clinical Development Europe | Webers T | Bonny M | Parexel | PXL SPI | Yes |  | paediatrics | No |  | Systemic Lupus Erythematosus | Immunology | SL0019 is an extension of SL0018 | 2015-03-23 | [18 empty] | 40 | 0 | 0 | 90 | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0026 | CSR Approved | Randomized, DB, Placebo-controlled, Multicenter Study | Phase I | Double Blind | UCB Pharma Global | TA Allergology / Respiratory | UCB Pharma Global | Mashimo H, Tatematsu S | Matsuoka K | N/A | ASKLEP Inc |  |  | adults | No | A phase 1/2, randomized, parallel-group, double-blind, placebo-controlled, multicenter study of one 12 week treatment cycle of epratuzumab in Japanese systemic lupus erythematosus subjects with modarate to severe disease | Systemic Lupus Erythematosus | Immunology | SL0026 is a parent study of SL0027 | 2010-07-20 | 2010-08-03 |  | 2011-01-19 | 2011-08-15 | 2011-10-03 | 2012-07-26 | 2012-11-05 |  | 2013-03-19 |  | 2013-04-24 |  | 2013-06-28 |  | 2014-01-28 | Japan | Japan (LPLV) | Japan | 6 | 11 | 7 | 30 | 20 | 20 | 22 | 1 | 1 | 20 | 0 | 1 | 19
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0027 | Study Archived | Open-label , Long-term esxtension, Multicenter Study | Phase II | Open | UCB Pharma Global | TA Allergology / Respiratory | UCB Pharma Global | Mashimo H, Tatematsu S | Matsuoka K | N/A | A2 Healthcare Corporation | No | Hybrid | adults | No | A phase 2, multicenter, open-label, long-term extension study to assess the safety of epratuzumab treatment in Japanese subjects with systemic lupus erythematosus | Systemic Lupus Erythematosus | Immunology | SL0027 is a follow up of SL0026 | 2010-07-20 | 2010-08-03 |  | 2011-01-19 | 2011-10-25 | 2012-01-25 | 2012-11-19 | 2013-03-13 |  | 2015-02-04 |  | 2015-03-25 |  | 2015-04-08 |  | 2015-06-16 | Japan | Japan (LPLV) | Japan | 6 | 11 | 6 | 20 | 20 | 20 | 0 | 0 | 0 | 17 | 0 | 7 | 10
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0032 | Study Archived | Phase 1, parallel group, BA study of Emab sc vs iv | Phase I | Open | GED | Immunology | UCB Pharma Global | Mollet M | Mccabe S | PRA | SPI PRA | No | Yes | adults | Yes | AN OPEN-LABEL, PARALLEL-GROUP, SINGLE-DOSE ESCALATION STUDY TO EVALUATE THE PHARMACOKINETICS, SAFETY, TOLERABILITY AND PHARMACODYNAMICS OF SUBCUTANEOUS EPRATUZUMAB IN HEALTHY CAUCASIAN AND JAPANESE SUBJECTS | Systemic Lupus Erythematosus | Immunology |  | 2013-10-31 | 2013-12-03 |  | 2014-09-19 | 2014-10-28 | 2014-11-05 | 2015-01-02 | 2015-01-26 |  | 2015-04-24 |  | 2015-09-14 |  | 2015-09-17 |  | 2016-01-06 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 42 | 42 | 42 | 138 | 0 | 96 | 42 | 0 | 0 | 42
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0033 | Protoc. Summary Approved (Cancelled) | Subcutaneous formulation - SLE | Phase II |  | Clinical Development Europe |  | UCB Pharma Global | Sacre J | Copetti C | Parexel |  |  |  | adults | No |  | Systemic Lupus Erythematosus | Immunology |  | 2015-03-06 | 2015-03-06 | [17 empty] | 80 | 0 | 0 | 475 | 365 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0035 | Protoc. Summary Approved (Cancelled) | Sub Cut OL Follow Up | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Sacre J | Copetti C | Parexel |  |  |  |  | No |  |  |  |  | 2015-03-17 | 2015-03-18 | [17 empty] | 100 | 0 | 0 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Epratuzumab | Immunology | SL0039 | Created (Cancelled) | Observational Pregnancy Study in SLE | Non Interventional Study - Prospective |  | Clinical Development USA |  | Clinical Development USA | Forbis K | Beaman M | Parexel | PXL SPI |  |  |  | No |  | Systemic Lupus Erythematosus | Immunology |  | 2015-06-22 | [18 empty] | 50 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Epratuzumab | not defined | SS0001 | Created (Cancelled) | Phase 2 | Phase II |  | Clinical Development USA |  | Clinical Development USA | Derby B | Christopher K | [5 empty] | No |  |  |  |  | 2015-12-01 | [18 empty] | 24 | 0 | 0 | 200 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Epratuzumab | not defined | SS0002 | Created (Cancelled) | Phase 2B Subcutaneous | Phase II |  | Clinical Development USA |  | Clinical Development USA |  |  | Parexel |  |  |  |  | No |  |  |  |  | 2015-12-31 | [18 empty] | 25 | 0 | 0 | 200 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Estradiol | not defined | SP0355 | Created | Multiple Dose - Estradiol TTS - Healthy Volunteers - Postmen |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Multiple Dose Pilot Evaluation of the Bioavailability of Four Transdermal Systems (Estradiol Patches) with Eight Healthy Postmenopausal Volunteers | [22 empty] | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Estradiol | not defined | SP0400 | Created | Pilot Study - Three Systems - Estradiol Patches - Twelve Hea |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Pilot Study to Evaluate the Pharmacokinetics of Three Transdermal Systems (Estradiol Patches) with Twelve Healthy Postmenopausal Volunteers | [22 empty] | 0 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Estradiol | not defined | SP0431 | Created | Drug Safety Trial Data. Study drug: ESTRADIOL |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Drug Safety Trial Data. Study drug: ESTRADIOL | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Estradiol | not defined | SP0449 | Created | Klebeeigenschaften - 100 healthy volunteers - patch |  |  | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | Adhesive Properties of four transdermal delivery systems 100 healthy subjects | [22 empty] | 0 | 0 | 0 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Estradiol,Norethisterone,Progesterone | not defined | SP0379 | Created | Gestagen - Oestrogen - NETA - Patch - of 7 days |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Release of active substance onto the skin and plasma concentration of norethisterone (NET) following application of a newly developed norethisterone-acetate (NETA) Mono-TES (SPM 938) in comparison with a combined progesterone/esstrogen patccch (SPM 937 over a period of 7 days | [22 empty] | 0 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Estradiol,Progesterone | not defined | SP0378 | Created | Serum Estradiol/Norethisterone - Patch - Combi - 7 days |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Serum Estradiol and Norethisterone lvels after application of a recently developed combined Progestogen/Estrogen Patch (SPM 937 - NETA/E2 - COMBI TDS) for 7 days | [22 empty] | 0 | 0 | 0 | 18 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Famotidine | not defined | SP0701 | Final TFLs released | Famotidine ODT single dose bioequivalence | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A Pharmacokinetic Study to Compare the Bioequivalence of a Unique New Formulation (Test), Orally Disintegrating Tablet (ODT), of Famotidine 40 mg, Administered With and Without water, to a Marketed Famotidine 40 mg Tablet Formulation (Reference), Pepcid®, by Merck |  |  |  | 2002-05-13 | 2002-05-13 | 2003-05-05: 2002-12-13; 2003-05-16: 2003-01-26; 2003-06-03: 2003-01-26; 2003-07-24: 2003-02-11; 2003-12-17: 2003-03-17 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 30 | 30 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | FERRO SANOL | Immunology | SP1000 | Created (Cancelled) | PK for Ferro Sanol-Registration | Phase I |  | Affiliate China |  | Affiliate China | [7 empty] | No |  |  |  |  | 2010-04-23 | [15 empty] | China | China (Created) |  | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Ferrous Glycine Sulfate | not defined | SP0784 | CSR Approved | bioavailibility study for three different iron preparatipons | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | Anwendungsbeobachtung zur Bioverfügbarkeit von therapeutischem, oralem Eisen bei Patienten mit mittelschwerer Eisenmangelanämie | Iron Deficiency Anemia | Immunology |  |  |  | 2004-03-25: 2006-11-02 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Ferrous Glycine Sulfate | not defined | SP0881 | Created | Bioavailability of iron from ferro sanol dragees | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | Bioavailability of iron from ferro sanol dragees, randomized, 2-way crossover single dose trial in 50 healthy volunteers | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Filgrastim | not defined | SP0527 | Final TFLs released | The efficacy and safety for Neutromax in patients with chemo | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | not available (DMCD) | Neutropenia | Immunology |  | 1999-09-01 | 1999-09-01 | 2003-05-05: 2000-06-28; 2003-05-16: 2000-07-07; 2003-06-03: 2000-09-21; 2003-07-24: 2000-11-19; 2003-12-17: 2001-01-30 | China | China (Created) |  | 4 | 0 | 0 | 73 | 73 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Fluticason-17-Propionate,Salmeterol | not defined | SP0622 | Created | 1. AWB Pneumologen mit atmadisc | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Plum C | [6 empty] | No | Atmadisc AWB | Asthma | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Fluticason-17-Propionate,Salmeterol | not defined | SP0623 | Created | 1. AWB atmadisc APIs | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Plum C | [6 empty] | No | Atmadisc AWB | Asthma | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Fluticason-17-Propionate,Salmeterol | not defined | SP0841 | Created (Cancelled) | PMS atmadisc plus sturcturized medical management program | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Huehn P | [6 empty] | No | Evaluation of the effects of a stucturized medical management program on top to a therapy with atmadisc. Post marketing survey in the "Ärztenetz Hamburg Ost" | Asthma | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Fluvastatin | not defined | SP0740 | Created | Fluvastatin trial in Italy |  |  | UCB Pharma Global |  | UCB Pharma Global | Sanguini M | [6 empty] | No | Biochemical profile of patients with non-ST-segment elevation acute coronary syndrome treated with stent implantation and fluvastatine 80 mg during follow up. Its relevance to futrue coronary events. | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | FOLIC ACID | not defined | SP0474 | Final TFLs released | bioequivalence study of acid folic | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Sanguini M | [6 empty] | No | Open, two way, cross-over, singledosa bioequivalence study of folic acid following administration of two oral formulation in healthy volunteers. | [5 empty] | 2003-05-05: 1998-01-05; 2003-12-17: 1998-08-04 | Switzerland | Switzerland (Created) |  | 0 | 0 | 0 | 18 | 18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Fosinopril | not defined | SP0095 | Created | DYNACIL - bei Patienten mit einer leichten bis mittelschwere |  |  | UCB Pharma Global |  | UCB Pharma Global | Fedder M | [6 empty] | No | DYNACIL - bei Patienten mit einer leichten bis mittelschweren essentiellen Hypertonie | Mild to Moderate Hypertension | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Fosinopril | not defined | SP0367 | Created | DYNACIL - bei Patienten mit Hypertonie | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Fedder M | [6 empty] | No | DYNACIL - bei Patienten mit Hypertonie | [22 empty] | 0 | 0 | 0 | 3656 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Fosinopril | not defined | SP0368 | Created | DYNACIL - bei Patienten mit Hypertonie / Mikroalbuminurie | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Fedder M | [6 empty] | No | DYNACIL - bei Patienten mit Hypertonie / Mikroalbuminurie | [22 empty] | 0 | 0 | 0 | 2924 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Fosinopril | not defined | SP0416 | Created | DYNACIL - bei Patienten mit Hypertonie | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | DYNACIL - bei Patienten mit Hypertonie | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Fosinopril | not defined | SP0484 | Protoc. Summary Approved | Dynacil Comp AWB 1998 - bei Patienten mit hypertonie die un | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | Dynacil Comp AWB 1998 - bei Patienten mit hypertonie die unzureichend eingestellt sind |  |  |  | 1998-07-08 | 1998-07-08 | [17 empty] | 0 | 0 | 0 | 7080 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Gadopentetate | not defined | SP0339 | Created | MAGNEVIST into the corpus cavernosum |  |  | UCB Pharma Global |  | UCB Pharma Global | Gutwald U | [6 empty] | No | Pilot study to determine settings (nozzle opening diameter, PSI) required for medi-jector device to permit injection of a 1 % magnevist-saline solution into the corpus cavernosum | [22 empty] | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Gallopamil | not defined | SP0098 | Created | GALLONORM - bei gallengesunden Probanden |  |  | UCB Pharma Global |  | UCB Pharma Global | Babst H | [6 empty] | No | GALLONORM - bei gallengesunden Probanden | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Gallopamil | not defined | SP0235 | Created | GALLONORM - bei Patienten mit dyspeptischen Beschwerden |  |  | UCB Pharma Global |  | UCB Pharma Global | Babst H | [6 empty] | No | GALLONORM - bei Patienten mit dyspeptischen Beschwerden | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Hydrochlorothiazide,Valsartan | not defined | SP0545 | Created | Anwendungsbeobachtung 1999 Provas / Provas Comp | Phase IV | Single Blind | UCB Pharma Global |  | UCB Pharma Global | Babst H | [6 empty] | No | Anwendungsbeobachtung 1999 Provas / Provas Comp | Essential Hypertension | Immunology | [20 empty] | 6000 | 0 | 0 | 18000 | 12600 | 12600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Hydrochlorothiazide,Valsartan | not defined | SP0546 | Created | Anwendungsbeobachtung Qualitätsnetze 1999 Provas / Provas Co | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Babst H | [6 empty] | No | Anwendungsbeobachtung Qualitätsnetze 1999 Provas / Provas Comp | Essential Hypertension | Immunology | [20 empty] | 1600 | 0 | 0 | 6000 | 4200 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Hydrochlorothiazide,Valsartan | not defined | SP0593 | Created | PROVAS COMP-AWB | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Babst H | [6 empty] | No | PROVAS COMP-AWB | Essential Hypertension | Immunology | [20 empty] | 930 | 0 | 0 | 4500 | 2764 | 2764 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Hyoscyamine | not defined | SP0531 | Created | Bioequivalence study comparing Levsinex Timecaps and Levbid | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Degen R | [6 empty] | No | Bioequivalence study comparing Levsinex Timecaps and Levbid ER Tablets | [22 empty] | 1 | 0 | 0 | 30 | 30 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Hyoscyamine Sulfate | not defined | SP0613 | Protoc. Summary Approved | Bioavailability of hyoscyamine sulfate ODT in healthy volunt | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Kastenholz K | [6 empty] | No | Bioavailability of hyoscyamine sulfate ODT in healthy volunteers |  |  |  | 2000-09-14 | 2000-09-14 | [14 empty] | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Hyoscyamine Sulfate | not defined | SP0631 | Created | hyoscyamine sulfate in healthy volunteers | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | 3-way crossover bioequivalence study of hyoscyamine sulfate tablet, extended release tablet, and extended release capsule | [22 empty] | 1 | 0 | 0 | 33 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Hyoscyamine Sulfate | not defined | SP0632 | Created | Hyoscyamine sulfate in healthy volunteers | Phase I | Single Blind | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | 2-way crossover bioequivalence of hyoscyamine sulfate extended release capsules made by SPKU and KV in healthy volunteers | [22 empty] | 1 | 0 | 0 | 28 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Hyoscyamine Sulfate | not defined | SP0654 | Final TFLs released | Hyoscyamine extended-release ODTsingle dose BE pilot | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Kastenholz K | [6 empty] | No | A single dose bioequivalence study comparing test product hyoscyamine sulfate 0.375 mg extended-release orally disintegrating tablets with reference product, Levbid, hyoscyamine sulfate extended-release tablets, when given in the fasted state |  |  |  | 2001-04-25 | 2001-04-25 | 2003-05-05: 2001-07-31; 2003-05-16: 2001-08-18; 2003-07-24: 2001-08-26; 2003-12-17: 2001-10-22 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 12
Yes | Not assigned | Managing Type | 1 | Hyoscyamine Sulfate | not defined | SP0675 | Protoc. Summary Approved (Cancelled) | Food effect single dose bioequivalence study comparing hyosc | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Kastenholz K | [6 empty] | No | Food effect single dose bioequivalence study comparing hyoscyamine ER ODT vs Levbid |  |  |  | 2002-01-09 | 2002-01-09 | [17 empty] | 1 | 0 | 0 | 36 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Hyoscyamine Sulfate | not defined | SP0676 | Protoc. Summary Approved (Cancelled) | Pivotal fasting single dose bioequivalence of hyoscyamine ER | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Kastenholz K | [6 empty] | No | Pivotal fasting single dose bioequivalence of hyoscyamine ER ODT vs. Levbid |  |  |  | 2001-10-03 | 2001-10-03 | [14 empty] | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 40 | 40 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Indapamide | not defined | SP0731 | CSR Approved | Indapamide Slow Release Tablets, Bioequivalence (after singl | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Mastej M | [6 empty] | No | A randomized 2-way crossover study of bioequivalence of investigational drug Indapamide Slow Release Tablets 1,5 mg (ID-ISR, Schwarz Pharma) and Reference Drug Indapamide Slow Release 1,5 mg (RD-ISR) after single dose administration | Hypertension | Immunology |  | 2003-02-12 | 2003-02-12 | 2003-05-16: 2003-02-18; 2003-06-03: 2003-02-18; 2003-07-24: 2003-03-12; 2003-10-03: 2003-03-12; 2003-12-17: 2003-04-08; 2004-03-25: 2003-05-27 | Poland | Poland (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Indapamide | not defined | SP0732 | CSR Approved | Indapamide Slow Release Tablets, Bioequivalence (after multi | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Mastej M | [6 empty] | No | A randomized 2-way crossover study of bioequivalence of investigational drug Indapamide Slow Release Tablets 1,5 mg (ID-ISR, Schwarz Pharma) and Reference Drug Indapamide Slow Release 1,5 mg (RD-ISR) after multiple dose administration | Hypertension | Immunology |  | 2003-02-12 | 2003-02-12 | 2003-05-16: 2003-02-19; 2003-06-03: 2003-02-28; 2003-07-24: 2003-03-26; 2003-10-03: 2003-03-26; 2003-12-17: 2003-04-17; 2004-03-25: 2003-05-30 | Poland | Poland (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | INNOVAIR | Immunology | A00433 | Created (Cancelled) | Inuvair Observational trial Italy; QoL (asthma) | Non Interventional Study - Prospective |  | Affiliates |  | Affiliates | Stancati A | [6 empty] | No |  |  |  |  | 2007-08-31 | [15 empty] | Italy | Italy (Created) |  | 60 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | INNOVAIR | Immunology | A00440 | Created (Cancelled) | NIS Turkish Asthma study | Non Interventional Study - Prospective |  | Affiliates |  | Affiliates | Oguz A | [6 empty] | No | [20 empty] | Turkey | Turkey (Created) |  | 0 | 0 | 0 | 3000 | 3000 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Iron Dextran Complex | not defined | SP0711 | Final TFLs released | The efficacy and safety study of iron dextran injection in c | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | The efficacy and safety study of iron dextran injection in chronic renal failure patients | Iron Deficiency Anemia | Immunology |  | 2001-12-21 | 2001-12-21 | 2003-05-05: 2001-12-21; 2003-05-16: 2002-01-30; 2003-06-03: 2002-04-10; 2003-07-24: 2002-06-05; 2003-12-17: 2002-06-21 | China | China (Created) |  | 5 | 0 | 0 | 159 | 159 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Iron Dextran Complex | not defined | SP0896 | Created | Cost-effectiveness analysis of oral vs intravenous iron supp | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | Cost-effectiveness analysis of oral vs intravenous iron supplement treatment for renal anemia patients | Renal Anemia | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Iron Dextran Complex | not defined | SP0897 | Created | Intravenous iron dextran treatment in chronic hemodialysis p | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | An open, oral iron product controlled multicenter clinical trial of intravenous iron dextran treatment in chronic hemodialysis patients | Renal Anemia | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0082 | Created | ISOKET SPRAY on the recovery from angina pectoris in CAD pat |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | Controlled acute study with Isoket Pump Spray in a dose of 2,5 mg ISDN versus a comparative spray in a dose of 0.8 mg GTN in patients with CAD. Effect on the velocity of regression of exercise-inducted moderate angina pectoris and ST segment depression. | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 68 | 62 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0090 | Created | ISOKET - after myocardial infarction on left ventricular vol |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | Influence of treatment with Isosorbide dinitrate and Captopril, respectively, within the first half year after myocardial infarction on left ventricular volume | [22 empty] | 0 | 0 | 0 | 126 | 126 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0091 | Created | ISOKET - in patients with stable angina (treated with aspiri |  |  | UCB Pharma Global |  | UCB Pharma Global | Sabia R | [6 empty] | No | Comparative evaluation of the effects of nitroglycerin and isosorbide dinitrate on bleeding time and correlations with the haemodynamic effects in patients with stable angina treated with aspirin | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0092 | Created | ISOKET - in stable anginal patients (with aspirin) |  |  | UCB Pharma Global |  | UCB Pharma Global | Sabia R | [6 empty] | No | Evaluation of the systemci haemodynamics, of the arterial and venous vasodilatation and of the antiplatelet effects following the acute intravenous administration of isosorbide dinitrate, before and after one-week treatment of Deponit, in stable anginal patients treated with aspirin | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0123 | Created | ISOKET - bei Patienten mit chronischer KHK |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | ISOKET - bei Patienten mit chronischer KHK | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 21 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0124 | Created | ISOKET-RET-40 - bei Patienten mit KHK |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | ISOKET-RET-40 - bei Patienten mit KHK | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0125 | Created | ISOKET-Spray in healthy volunteers |  |  | UCB Pharma Global |  | UCB Pharma Global | Stalder A | [6 empty] | No | Effect of trandermal Isosorbide dinitrate (ISDN) spray on venous compliance of superficial hand veins. An acute, single-blind, placebo-controlled pilot study of 2 x 2,5 mg Isoket Spray versus placebo in 10 healthy volunteers | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0126 | Created | ISOKET - hämodynamischer Vergleich zwischen IS-2-N und IS-5- |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | ISOKET - hämodynamischer Vergleich zwischen IS-2-N und IS-5-N bei koronarkranken Patienten | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 22 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0224 | Created | ISOKET-40 / ISOKET-RETARD-120 - bei Patienten mit koronarer |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | ISOKET-40 / ISOKET-RETARD-120 - bei Patienten mit koronarer Herzkrankheit | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0225 | Created | ISOKET-RETARD-120 - bei Patienten mit koronarer Herzkrankhei |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | ISOKET-RETARD-120 - bei Patienten mit koronarer Herzkrankheit | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0227 | Created | ISOKET-RETARD-120 bei Patienten mit chronischer Herzinsuffiz |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | ISOKET-RETARD-120 bei Patienten mit chronischer Herzinsuffizienz | [22 empty] | 0 | 0 | 0 | 30 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0228 | Created | ISOKET-RETARD-120 Nachbeobachtung zur Studie F8182, bei Pati |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | ISOKET-RETARD-120 Nachbeobachtung zur Studie F8182, bei Patienten mit chronischer Herzinsuffizienz | [22 empty] | 0 | 0 | 0 | 16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0325 | Created | ISOKET bei Patienten mit angiographisch gesicherter KHK |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | ISOKET bei Patienten mit angiographisch gesicherter KHK | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 40 | 39 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0326 | Created | ISOKET - bei Patienten mit chronisch erhöhten Druckwerten |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | ISOKET - bei Patienten mit chronisch erhöhten Druckwerten | [22 empty] | 0 | 0 | 0 | 29 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0327 | Created | ISOKET - bei Patienten mit chronisch erhöhten Druckwerten |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | ISOKET - bei Patienten mit chronisch erhöhten Druckwerten | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0328 | Created | ISOKET - bei Patienten mit chronisch erhöhten Druckwerten |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | ISOKET - bei Patienten mit chronisch erhöhten Druckwerten | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0336 | Created | ISOKET - in patients with angiographically normal coronary |  |  | UCB Pharma Global |  | UCB Pharma Global | Stalder A | [6 empty] | No | Medical treatment of typcial angina pectoris pain in patients with angiographically normal coronary anatomy | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0345 | Created | Isoket Spray - ISDN - 18 Healthy volunteers - Bioequivalence |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Bioequivalence Evaluation ofIsosorbide Dinitrate Administration as Two Oral Spray Preparations in 18 Healthy Volunteers | [22 empty] | 0 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0369 | Created | ISOKET - nach akutem Myokardinfarkt | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | ISOKET - nach akutem Myokardinfarkt | [22 empty] | 0 | 0 | 0 | 432 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0452 | Created | ISOKET-SALBE in healthy volunteers |  |  | UCB Pharma Global |  | UCB Pharma Global | Stalder A | [6 empty] | No | Effect of transdermal isosorbide dinitrate (ISDN) ointment on venous compliance of superficial hand veins. An acute, single-dose, randomized, double-blind, placebo-controlled pilot study of 500 mg isoket ointment versus placebo in 10 healthy volunteers | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0473 | Created | Isoket | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Bioavailability study in a three way cross-over, randomized, open-label single dose design with two different retard formulations and one immediate relase formulation of Isoket 20 in 12 healthy male volunteers. | [22 empty] | 0 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0480 | Protoc. Summary Approved (Cancelled) | ISDN Trial (PHAKI 923) | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Bioavailability study with two different batches of Isoket retard 60 (sustained release tablet, 60 mg ISDN) and Isoket 20 (immediate release tablet, 20 mg ISDN) following single dose administration of 60 mg or two daily doses of 20 mg in a three-way cross-over, randomized open-label design in 12 hea lthy volunteers. |  |  |  | 1998-06-15 | 1998-06-15 | [17 empty] | 0 | 0 | 0 | 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0634 | Created | IQOLAN (International quality of Life Assessment on Nitrates | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Behmer O | [6 empty] | No | IQOLAN | Coronary Heart Disease | Immunology | [20 empty] | 300 | 0 | 0 | 1200 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0704 | Final TFLs released | IQOLAN Czech Republic:patients with anhina pectoris on Nitra | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Marr I | [6 empty] | No | IQOLAN Czech Republic - International Quality of Life assessment of patients with Angina pectoris on Nitrate therapy | Coronary Heart Disease | Immunology |  |  |  | 2003-05-05: 1999-10-01; 2003-12-17: 2001-03-01 |  |  |  | 3 | 0 | 0 | 100 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0714 | Created (Cancelled) | Isoket retard 40 bioequivalence | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Isoket retard 40 bioequivalence | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0890 | Created | Comparison of the time to onset of action on myocardial isch | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | Comparison of the time to onset of action on myocardial ischemia following intravenous administration of isosorbide dinitrate and 5-isosorbide mononitrate | Cardiac Ischemia | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET | not defined | SP0891 | Created | Pharmacokinetics of three organic nitrates in chinese health | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | Pharmacokinetics of three organic nitrates in chinese healthy male volunteers | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET/ELANTAN | not defined | SP0093 | Created | ISOKET-RETARD/ ELANTAN LONG bei der Behandlung der isolierte |  |  | UCB Pharma Global |  | UCB Pharma Global | Baumgartner (Mig. From Sports) U | [6 empty] | No | ISOKET-RETARD/ ELANTAN LONG bei der Behandlung der isolierten systolischen Hypertonie | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET/ELANTAN | not defined | SP0712 | Final TFLs released | The pharmacokinetic study of isoket i.v., 5-ISMN tablet and | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | The pharmacokinetic study of isoket i.v. 5-ISMN tablet and 5-ISMN injection in healthy volunteers |  |  |  | 2001-12-28 | 2001-12-28 | 2003-05-05: 2001-12-28; 2003-05-16: 2002-04-06; 2003-06-03: 2002-04-20; 2003-07-24: 2002-04-21; 2003-12-17: 2002-05-30 | China | China (Created) |  | 1 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISOKET/ELANTAN | not defined | SP0713 | Final TFLs released (Stopped) | ISDN i.v. and 5-ISMN injection in cardiac ichemia | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | Comparison of time to onset of action after intravenous administration of ISDN i.v. and 5-ISMN injection | Cardiac Ischemia | Immunology |  | 2002-02-19 | 2001-10-30 | 2003-05-05: 2001-10-30; 2003-05-16: 2001-10-15; 2003-06-03: 2002-06-01; 2003-07-24: 2002-06-07; 2003-12-17: 2002-06-11 | China | China (Created) |  | 1 | 0 | 0 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Isosorbide Dinitrate,Pentaerithryl Tetranitrate | not defined | SP0311 | Created | PETN / ISDN - bei Patienten mit stabiler Angina pectoris |  |  | UCB Pharma Global |  | UCB Pharma Global | Platon (Migrated From Sports) U | [6 empty] | No | PETN / ISDN - bei Patienten mit stabiler Angina pectoris | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISRADIPINE | not defined | SP0222 | Created | VASCAL-UNO -Blutdruck und kardiale Belastbarkeit (Hypertonie | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Behmer O | [6 empty] | No | VASCAL-UNO -Blutdruck und kardiale Belastbarkeit (Hypertonie) | [22 empty] | 0 | 0 | 0 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISRADIPINE | not defined | SP0246 | Created | VASCAL - bei Patienten mit essentieller Hypertonie |  |  | UCB Pharma Global |  | UCB Pharma Global | Uhrmann J | [6 empty] | No | VASCAL - bei Patienten mit essentieller Hypertonie | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISRADIPINE | not defined | SP0310 | Created | VASCAL-UNO bei Patienten mit Hypertonie | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | not available (DMCD) | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ISRADIPINE | not defined | SP0313 | Created | VASCAL-UNO/UNO-MITE bei Patienten mit Hypertonie | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Uhrmann J | [6 empty] | No | Wirksamkeit und Verträglichkeit einer antihypertensiven Therapie mit vascal-Uno (Isradipin) | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | EP0038 | CSR Approved | Multiple doses in Japanese and Caucasian subjects | Phase I | Open | Clinical Development Japan | Clinical Development Japan | Clinical Development Japan | Okagaki T | Tsujii A | Parexel | SPI PXL |  |  | adults | Yes | A SINGLE-CENTER, OPEN-LABEL, MULTIPLE-DOSE STUDY TO EVALUATE THE PHARMACOKINETICS, SAFETY AND TOLERABILITY OF LEVETIRACETAM ADMINISTERED AS INTRAVENOUS INFUSION IN JAPANESE AND CAUCASIAN HEALTHY MALE SUBJECTS | Epilepsy | Central Nervous System |  | 2012-06-29 | 2012-06-29 | 2003-05-05: 2012-09-03; 2003-05-16: 2012-10-18; 2003-06-03: 2012-11-07; 2003-07-24: 2012-12-05; 2003-10-03: 2013-01-25; 2003-12-17: 2013-03-15; 2004-03-25: 2013-05-23 | Japan | Japan (LPLV) | Japan | 1 | 1 | 1 | 50 | 50 | 50 | 105 | 0 | 73 | 32 | 0 | 0 | 32 |  |  | 2013-03-25 | 2013-03-15
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | EP0056 | Study Archived | Keppra oral solution CUP | Compassionate Use | Open | Affiliates | GMA Neurology / Psychiatry | Affiliates | Park M | Matsuoka K | N/A | N/A | No | No | paediatrics | No | COMPASSIONATE USE PROGRAM WITH LEVETIRACETAM (KEPPRA®) ORAL SOLUTION IN PATIENTS WITH EPILEPSY IN KOREA | Epilepsy | Central Nervous System |  |  |  | 2003-05-05: 2013-03-11; 2003-05-09: 2013-04-30; 2003-05-16: 2013-10-29; 2003-05-30: 2013-08-31; 2003-06-03: 2014-03-15; 2003-07-24: 2015-01-09 | South Korea | South Korea (LPLV) | South Korea | 7 | 0 | 2 | 50 | 50 | 50 | 8 | 0 | 0 | 8 | 6 | 2 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | EP0079 | Protoc. Summary Approved (Cancelled) | Myoclonic Seizure Efficacy and Safety study in Japan | Registry |  | Clinical Development Japan | Clinical Development Japan | UCB Pharma Global |  |  |  |  | Yes | Yes |  | No |  | Epilepsy | Central Nervous System |  | 2015-05-15 | 2015-05-22 | [17 empty] | 25 | 0 | 0 | 20 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01000 | Study Archived | Acute Mania Proof of Concept | Phase II | Open | Clinical Development USA | CNS | R & D | Sharpe T | [6 empty] | No | An open-label, multicenter, 51 day study of the efficacy and safety of 2000-4000 mg/day levetiracetam in the treatment of an acute manic or mixed episode in adult subjects with bipolar I disorder | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2000-02-01 | 2000-07-28 | 1999-10-01 | 2001-01-18 | 2000-08-12 |  | 2000-10-01 | 2002-04-26 | 2001-02-01 | 2002-07-31 |  | 2002-06-28 | 2001-04-24 | 2003-03-04 | United States of America | United States of America (LPLV) | United States of America | 6 | 6 | 6 | 24 | 24 | 0 | 30 | 0 | 6 | 24 | 0 | 20 | 4
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01002 | Study Archived | Bioequivalence 6m Vs 18 m stability tablets | Phase I |  | Clinical Development Europe | CNS | R & D | Pigeolet E | [6 empty] | Yes | Randomised, single center, open label, cross-over, single dose bioequivalence study of L059 500 mg yellow oral tab with in vitro dissolution after 15min of <75% and levetiracetam 500 mg yellow oral tab. with in vitro dissolution after 15min of >95% in 16 healthy fasting males and females | [5 empty] | 1999-09-07 | 1999-09-14 | 1999-10-07 | 1999-10-08 |  |  | 1999-10-16 | 1999-10-18 | 1999-12-09 | 2000-01-13 |  |  | 2000-02-01 | 2000-03-14 | Belgium | Belgium (LPLV) | Belgium | 1 | 0 | 1 | 16 | 0 | 0 | 21 | 0 | 5 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01005 | Study Archived | Partial Seizures in Adults Add-On | Phase III |  | Clinical Development Europe | CNS | R & D | [7 empty] | No | A DOUBLE-BLIND,PLACEBO-CONTROLLED, RANDOMIZED STUDY: 14-WEEK EVALUATION OF THE EFFICACY AND SAFETY OF LEVETIRACETAM (LEV) (oral tablets OF 500 mg b.i.d.) UP TO 2000 mg/day IN ADULTS SUFFERING FROM TREATMENT-RESISTANT PARTIAL SEIZURES | [5 empty] | 2003-05-05: 1999-12-17; 2003-05-16: 2000-11-01; 2003-07-24: 2002-02-21; 2003-10-03: 2002-06-28; 2004-03-25: 2003-01-16 | Taiwan | Taiwan (LPLV) | Taiwan | 6 | 5 | 5 | 94 | 94 | 94 | 122 | 0 | 28 | 94 | 0 | 4 | 90
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01009 | CSR Approved | Pediatric Exclusivity Efficacy (1 month to less than 4yo) | Phase III | Double Blind | Clinical Development USA | CNS | R & D | Romano C |  |  | EU - PRA; S. America and Latin America - PPD; U.S/Canada - UCB |  |  |  | No | A Double-Blind, Randomized, Multicenter, Placebo-Controlled, Maximum 22 Day Study of Levetiracetam Oral Solution (20-40 mg/kg/day) as Adjunctive Treatment of Refractory Partial Onset Seizures in Pediatric Epileptic Subjects Ranging in Age from 1 Month to Less than 4 Years of Age | Indication for Neuro Psychiatry | Central Nervous System |  | 2003-05-05 | 2003-05-05 | 2003-08-30 | 2003-11-05 | 2003-10-01 | 2004-10-15 |  | 2007-01-19 | 2004-10-01 | 2007-01-26 | 2004-12-20 | 2007-03-22 |  | 2007-04-23 |  | 2007-08-27 | Belgium, Brazil, Czech Republic, France, Germany, Hungary, Italy, Mexico, Poland, Romania, Russian Federation, United Kingdom, United States of America | Belgium (LPLV), Brazil (LPLV), Canada (1st Site Initiation (Cancelled)), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Mexico (LPLV), Poland (LPLV), Romania (LPLV), Russian Federation (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Brazil, Czech Republic, France, Germany, Hungary, Italy, Mexico, Poland, Romania, Russian Federation, United Kingdom, United States of America | 70 | 78 | 62 | 220 | 110 | 98 | 172 | 0 | 56 | 116 | 0 | 4 | 112
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01010 | CSR Approved | Peds POS Add-On (4 -12) PK | Phase II | Open | Clinical Development USA | CNS | R & D | Salas V | [5 empty] | paediatrics | No | An open-label, multi-center, repeated dose pharmacokinetic study of 20, 40 and 60 mg/kg/day of levetiracetam in children (4-12 years of age inclusive) with partial onset seizures | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2000-09-15 | 2000-08-10 | 2000-11-15 | 2002-01-31 |  | 2003-05-29 | 2001-04-15 | 2003-07-28 | 2001-06-01 | 2003-11-17 |  | 2004-06-15 | 2001-10-31 | 2004-06-28 | Mexico, United States of America | Mexico (LPLV), United States of America (LPLV) | Mexico, United States of America | 6 | 15 | 9 | 18 | 12 | 0 | 23 | 0 | 2 | 21 | 0 | 4 | 17
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01014 | Study Archived | Proof of Concept - Migraine | Phase II | Double Blind | Clinical Development USA | CNS | R & D | Sharpe T | [6 empty] | No | An 18-week, multicenter, randomized, double-blind, placebo-controlled, parallel-group study of the efficacy and safety of oral tablets of levetiracetam 750 mg b.i.d. for the prophylactic treatment of migraine, with or without aura | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2000-06-15 | 2000-05-18 | 2000-06-30 | 2000-08-16 | 2000-10-24 |  | 2001-02-28 | 2001-08-07 | 2001-05-01 | 2001-10-30 |  | 2001-12-14 | 2001-08-01 | 2002-03-30 | United States of America | United States of America (LPLV) | United States of America | 8 | 10 | 10 | 100 | 80 | 68 | 120 | 0 | 40 | 80 | 0 | 16 | 64
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01015 | LPLV | Compassionate use Program | Managed Access Program | Open | Clinical Development Europe | CNS | R & D | De Smet J | Wajskop M | [5 empty] | No | Keppra - Compassionate Use in patients suffuring from epilepsy | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2000-02-01 | 2003-05-05: 2000-04-26; 2003-05-16: 2000-06-16; 2003-07-24: 2002-07-03 | Belgium, France, Ireland, Netherlands, Portugal, South Africa, Spain, United Kingdom | Belgium (LPLV), France (LPLV), Ireland (LPLV), Netherlands (LPLV), Portugal (LPLV), South Africa (LPLV), Spain (LPLV), United Kingdom (LPLV) | Belgium, France, Ireland, Netherlands, Portugal, South Africa, Spain, United Kingdom | 0 | 0 | 157 | 668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01020 | Study Archived | Long-term follow up | Phase III | Open | Clinical Development Japan | Clinical Development Japan | R & D | Suzuki A | Beinhauer-Zellenka U | [5 empty] | No | Follow-up Study of L059(Levetiracetam) in Epileptic Patients with Partial Onset Seizures by Open Label method | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2000-09-14 |  | 2000-09-25 |  | 2001-09-12 | 2003-07-31 | 2003-07-31 | 2006-12-31 | 2007-11-14 | 2007-06-29 | 2007-07-25 |  | 2008-01-21 | 2007-09-28 | 2008-08-05 | Japan | Japan (LPLV) | Japan | 48 | 0 | 61 | 154 | 154 | 154 | 0 | 0 | 0 | 154 | 0 | 69 | 85
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01031 | Study Archived | S.K.A.T.E:Safety of Keppra as Adjunctive Therapy in Epilepsy | Phase IV | Open | Clinical Development Europe | CNS | Global Medical Affairs | Falter U, Schelstraete I | Driver D |  | PPD |  |  |  | No | A Phase IV, OPEN-Label, Multi-Center, Community-Based Trial Studying the Safety and efficacy of Keppra as Adjunctive Therapy in adult patients with uncontrolled partial Epilepsy: S.K.A.T.E. (Safety of Keppra as Adjunctive Therapy in Epilepsy) | Indication for Neuro Psychiatry | Central Nervous System |  |  | 1999-11-02 | 2000-04-10 | 2000-04-21 | 2000-09-15 | 2000-08-18 |  | 2003-02-11 | 2003-12-31 | 2004-02-23 | 2004-03-31 | 2004-07-19 |  | 2005-03-31 | 2004-06-30 | 2005-07-18 | Argentina, Australia, Austria, Belgium, Bulgaria, Czech Republic, Finland, France, Germany, Hungary, Ireland, Mexico, Netherlands, Poland, Switzerland, United Kingdom | Argentina (LPLV), Australia (LPLV), Austria (LPLV), Belgium (LPLV), Bulgaria (LPLV), Czech Republic (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Ireland (LPLV), Mexico (LPLV), Netherlands (LPLV), Poland (LPLV), Switzerland (LPLV), United Kingdom (LPLV) | Argentina, Australia, Austria, Belgium, Bulgaria, Czech Republic, Finland, France, Germany, Hungary, Ireland, Mexico, Netherlands, Poland, Switzerland, United Kingdom | 300 | 294 | 240 | 3000 | 0 | 0 | 1 | 0 | 0 | 1548 | 2 | 200 | 1346
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01033 | Study Archived | S.K.A.T.E : Spain | Phase IV | Open | Clinical Development Europe | CNS | Global Medical Affairs | Schelstraete I | Driver D |  | PPD |  |  |  | No | A Phase IV, pharmacovigilance Study of Keppra SPAIN - S.K.A.T.E. (Safety of Keppra as Adjunctive Therapy in Epilepsy) | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2000-09-21 | 2003-05-05: 2001-05-03; 2003-05-16: 2002-01-15; 2003-06-03: 2003-02-11; 2003-07-24: 2003-05-30; 2003-10-03: 2003-07-25; 2003-12-17: 2003-09-03; 2004-03-25: 2003-12-04 | Spain | Spain (LPLV) | Spain | 80 | 85 | 76 | 400 | 400 | 0 | 0 | 0 | 0 | 341 | 7 | 37 | 297
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01034 | LPLV | Named Patient Program (phase IV Follow-up) | Managed Access Program | Open | Clinical Development Europe | CNS | Global Medical Affairs | De Smet J, Falter U | Wajskop M | [5 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2001-04-03 | 2003-05-05: 2001-05-04; 2003-05-16: 2001-06-13; 2003-07-24: 2002-07-04 | Belgium | Belgium (LPLV) | Belgium | 28 | 0 | 28 | 106 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01035 | Study Archived | S.K.A.T.E : Greece | Phase IV | Open | Global Medical Affairs Europe | GMA Neurology / Psychiatry | Global Medical Affairs Europe | Falter U, Schelstraete I | Driver D |  | PPD |  |  |  | No | A Phase IV, pharmacovigilance Study of Keppra GREECE - S.K.A.T.E. (Safety of Keppra as Adjunctive Therapy in Epilepsy) | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2001-05-22 |  | 2001-07-10 | 2001-10-01 | 2003-03-24 |  |  | 2003-01-01 | 2004-07-07 | 2003-04-01 | 2005-07-05 |  | 2005-08-26 |  | 2006-01-19 | Greece | Greece (LPLV) | Greece | 14 | 6 | 4 | 70 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 6 | 28
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01036 | Study Archived | SKATE II | Phase IV | Open | Clinical Development Europe | CNS | Global Medical Affairs | Schelstraete I | Driver D |  | PPD |  |  |  | No | A phase IV study, open-label, multicenter, community based trial studying the safety and efficacy of KEPPRA as adjunctive therapy in adult patients with uncontrolled partial epilepsy (SKATE II) | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2002-05-06 | 2002-07-31 | 2002-08-21 | 2003-02-15 | 2003-11-24 | 2005-12-31 | 2006-01-09 | 2005-12-15 | 2006-05-29 | 2006-05-15 | 2007-01-26 |  | 2007-02-15 | 2006-11-15 | 2007-11-29 | Hong Kong, Malaysia, Philippines, Singapore, Taiwan, Thailand | Hong Kong (LPLV), Malaysia (LPLV), Philippines (LPLV), Singapore (LPLV), Taiwan (LPLV), Thailand (LPLV) | Hong Kong, Malaysia, Philippines, Singapore, Taiwan, Thailand | 150 | 2 | 29 | 1000 | 1000 | 0 | 0 | 0 | 0 | 252 | 89 | 31 | 132
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01037 | CSR Approved | Conversion to Monotherapy | Phase IV | Open | Clinical Development Europe | GMA Neurology / Psychiatry | Global Medical Affairs | Falter U, Schelstraete I | Driver D |  | PPD |  |  |  | No | A phase IV, open-label, multi-center trial to evaluate the safety and efficacy of Keppra after conversion to monotherapy in adult subjects with partial epilepsy having previously participed in a Phase IV, open-label trial of Keppra as adjunctive therapy (SKATE). | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2002-07-15 | 2002-08-05 | 2002-08-26 | 2002-10-15 | 2003-03-27 |  | 2004-02-18 | 2004-04-15 | 2004-07-12 | 2004-08-15 | 2005-05-02 |  | 2005-05-24 | 2004-11-15 | 2005-10-25 | Australia | Australia (LPLV) | Australia | 10 | 9 | 3 | 50 | 50 | 0 | 0 | 0 | 0 | 14 | 0 | 7 | 7
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01052 | CSR Approved | Oral solution PK study for 1 mo - <4 years | Phase II | Open | Clinical Development USA | CNS | R & D | Campbell K | [6 empty] | No | Open-Label, Pharmacokinetic Study of 20 mg/kg of levetiracetam in Epileptic Children ranging in age from 1 month to less than 4 years old | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2001-03-15 | 2002-06-06 | 2001-05-15 | 2002-09-18 |  |  | 2001-11-15 | 2003-05-16 | 2002-02-15 | 2003-07-10 | 2003-07-21 | 2003-07-25 | 2002-05-15 | 2003-11-24 | United States of America | United States of America (LPLV) | United States of America | 5 | 7 | 5 | 18 | 12 | 12 | 15 | 0 | 2 | 13 | 0 | 0 | 13
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01053 | Study Archived | Acute Mania Follow-up | Phase II | Open | Clinical Development USA | CNS | R & D | Sharpe T | [6 empty] | No | An open-label, multicenter, follow-up maintenance study of the safety and efficacy of 2000-4000 mg/day levetiracetam in the treatment of an acute manic or mixed episode in adult subjects with Bipolar I Disorder | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2000-06-30 | 2000-07-26 | 2000-09-15 | 2001-02-19 | 2001-05-15 |  | 2001-09-15 |  | 2001-02-01 | 2002-10-31 |  | 2002-06-28 | 2001-04-02 | 2003-03-04 | United States of America | United States of America (FPFV) | United States of America | 6 | 6 | 2 | 24 | 24 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 1
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01057 | CSR Approved | Generalized Tonic-Clonic Seizures (TGTC) | Phase III | Double Blind | Clinical Development USA | CNS | R & D | Mccarthy G, Wash M |  |  | Parexel |  |  |  | No | A double-blind, multicenter, placebo-controlled study to evaluate the efficacy and safety of adjunctive treatment with 3000 mg/day (pediatric target dose of 60 mg/kg/day) oral levetiracetam (LEV) (166, 250, and 500mg tablets), in adult and pediatric subjects (4-65 years) suffering from idiopathic generalized epilepsy with primary generalized tonic-clonic (PGTC) seizures. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2000-11-30 | 2001-02-02 | 2001-03-31 | 2001-09-19 | 2002-09-30 | 2004-10-29 | 2003-04-01 | 2005-06-27 | 2003-07-01 | 2005-09-02 | 2003-09-30 | 2005-12-09 | 2003-10-30 | 2006-03-31 | Australia, Canada, Estonia, Mexico, New Zealand, Poland, Russian Federation, United Kingdom, United States of America | Australia (LPLV), Canada (LPLV), Estonia (LPLV), Mexico (LPLV), New Zealand (LPLV), Poland (LPLV), Russian Federation (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Canada, Estonia, Mexico, New Zealand, Poland, Russian Federation, United Kingdom, United States of America | 40 | 82 | 57 | 200 | 154 | 139 | 229 | 0 | 65 | 164 | 74 | 24 | 66
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01059 | Study Archived | Neuropathic Pain | Phase II | Double Blind | Clinical Development USA | CNS | R & D | Johnston J | [6 empty] | No | A 12-week, multicenter, randomized, double-blind, placebo-controlled, parallel-group study to evaluate the efficacy and safety of flexible dosing of levetiracetam at 500 mg to 1500 mg b.i.d. in the treatment of subjects with painful diabetic neuropathy Report Number <RRCEO2K0101> | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2000-09-08 | 2001-02-27 | 2000-11-20 | 2001-05-11 |  |  | 2001-06-04 | 2002-07-23 | 2001-08-30 | 2002-10-04 |  | 2002-12-18 | 2001-11-30 | 2003-06-12 | United States of America | United States of America (LPLV) | United States of America | 15 | 11 | 14 | 130 | 103 | 69 | 216 | 0 | 111 | 105 | 0 | 36 | 69
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01061 | Study Archived | Monotherapy newly diagnosed | Phase III | Double Blind | Clinical Development Europe | CNS | R & D | Pietteur V |  |  | PPD development |  |  |  | No | A multicenter, double-blind, randomized, parallel group, positive-controlled trial comparing the efficacy and safety of levetiracetam (1000 to 3000 mg/day oral b.i.d.) to carbamazepine (400 to 1200 mg/day oral b.i.d.), used as monotherapy for up to a maximum of 121 weeks in subjects (>=16 years) newly or recently diagnosed as suffering from epilepsy, and experiencing partial or generalized tonic-clonic seizures. | Indication for Neuro Psychiatry | Central Nervous System | N01061 is a follow up of N01091, N01093, N01127 |  | 2001-07-25 | 2001-11-30 | 2002-02-21 | 2002-03-30 | 2002-06-20 |  | 2004-03-29 | 2006-05-31 | 2005-07-12 | 2006-08-31 | 2005-07-29 |  | 2005-09-16 | 2006-12-31 | 2005-12-07 | Belgium, Czech Republic, Finland, France, Germany, Hungary, Italy, Netherlands, Poland, South Africa, Spain, Sweden, United Kingdom | Belgium (LPLV), Czech Republic (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Netherlands (LPLV), Poland (LPLV), South Africa (LPLV), Spain (LPLV), Sweden (LPLV), United Kingdom (LPLV) | Belgium, Czech Republic, Finland, France, Germany, Hungary, Italy, Netherlands, Poland, South Africa, Spain, Sweden, United Kingdom | 100 | 106 | 85 | 700 | 580 | 464 | 0 | 0 | 0 | 579 | 0 | 264 | 315
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01077 | Study Archived | PK - single and multiple dose administrat | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | De Smedt F |  |  | SGS Biopharma |  |  |  | Yes | Randomized, monocenter, open label two-way cross-over bioavailability comparison study of levetiracetam 1500 mg (500 mg/5 mL ampoules) administred as a 15 minutes intravenous perfusion and levetiracetam 3x500 mg tablet (part A); and a randomized double-blind, placebo-controlled (12:6), safety, toler | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2002-01-30 | 2002-09-20 | 2002-09-30 | 2003-03-13 | 2003-01-22 |  |  | 2003-05-30 | 2003-03-08 | 2003-07-18 | 2003-05-09 |  | 2003-08-07 | 2003-10-20 | 2003-10-20 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 18 | 18 | 18 | 35 | 17 | 0 | 18 | 0 | 0 | 18
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01083 | Protocol Approved (Cancelled) | An open-label, non comparative trial | Phase IV | Open | Clinical Development Europe |  | R & D | [7 empty] | No | An open-label, non-comparative multicenter trial : evaluation of the efficacy and safety in adults suffering from epilepsy with partial-onset seizures of levetiracetam 500 mg tablets, given at individualized doses from 1000 to 3000 mg/day taken orally b.i.d. for 16 weeks as add-on treatment. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2003-04-04: 2002-03-31; 2003-05-05: 2002-04-16; 2003-05-09: 2002-10-15; 2003-07-03: 2003-12-31; 2003-08-18: 2004-03-31; 2004-03-22: 2004-06-30 | Thailand | Thailand (Created) |  | 2 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01085 | CSR Approved (Stopped) | Sleep Architecture | Phase IV | Double Blind | Global Medical Affairs US | GMA Neurology / Psychiatry | Global Medical Affairs | [7 empty] | No | A 9-11 Week Multicenter, Randomized, Double-blind, Placebo-controlled, Parallel Group Study to Determine the Effects of Adjunctive Levetiracetam on the Sleep Architecture of Adult Subjects (18-45 years of age) with Partial Onset Epilepsy Receiving a First Generation Anti-epileptic Drug. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2002-08-25 | 2002-09-25 | 2002-10-30 | 2003-02-17 |  | 2004-09-20 | 2003-10-21 | 2004-11-19 | 2003-12-04 | 2006-03-30 | 2005-06-20 |  | 2004-05-05 | 2007-01-02 | United States of America | United States of America (LPLV (Stopped)) | United States of America | 7 | 4 | 7 | 52 | 40 | 36 | 23 | 0 | 1 | 17 | 0 | 2 | 15
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01086 | CSR Approved | Social Anxiety Disorder (Generalized type) | Phase II | Double Blind / Double Dummy | Global Medical Affairs US | GMA Neurology / Psychiatry | Global Medical Affairs | [7 empty] | No | A Multicenter, Randomized, Double-Blind, Placebo-Controlled, Parallel Group Study to Assess the Efficacy and Safety of Levetiracetam Versus Placebo for the Treatment of Social Anxiety Disorder (Generalized Type) | Indication for Neuro Psychiatry | Central Nervous System |  | 2003-03-09 | 2003-03-12 | 2003-05-01 | 2003-04-25 | 2003-09-15 | 2003-09-05 | 2004-05-03 | 2004-02-11 | 2004-09-01 | 2004-06-15 | 2004-12-23 | 2004-08-10 | 2005-02-17 | 2005-01-31 | 2005-04-22 | 2006-08-28 | United States of America | United States of America (LPLV) | United States of America | 20 | 20 | 20 | 224 | 215 | 0 | 265 | 0 | 48 | 217 | 0 | 70 | 147
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01087 | CSR Approved | Postherpetic Neuralgia | Phase II | Double Blind | Global Medical Affairs US | GMA Neurology / Psychiatry | Global Medical Affairs | Hollis A |  |  | Contract CRAs: Daniela Andrei Carl Branch Sue Haley Evila Lopex Sheryn McLoughlin |  |  |  | No | evaluating the efficacy and safety of levetiracetam 500 mg tablets in bid administration (daily dose ranging from 1000 mg to 3000 mg), in adults (> = 18 years of age) suffering from postherpetic neuralgia | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2003-11-11 | 2003-11-19 | 2004-02-23 | 2004-04-30 | 2005-03-18 | 2005-06-02 | 2005-07-20 | 2005-09-23 | 2005-10-14 | 2006-01-13 | 2005-12-09 | 2006-03-29 | 2006-03-17 | 2006-08-28 | United States of America | United States of America (LPLV) | United States of America | 31 | 34 | 29 | 227 | 170 | 136 | 254 | 0 | 84 | 170 | 0 | 50 | 120
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01088 | CSR Approved (Stopped) | Catamenial Epilepsy | Phase II | Double Blind | Global Medical Affairs US |  | Global Medical Affairs | Digiandomenico M | [6 empty] | No | A Multicenter, Double-blind, Placebo-controlled, Parallel Group Study of the Safety and Efficacy of Levetiracetam in the Adjunctive Treatment of Adult Female Subjects (18 to 40 Years of Age) with C1 Catamenial Epilpsy | Indication for Neuro Psychiatry | Central Nervous System |  | 2002-07-01 |  | 2002-07-29 | 2002-08-06 | 2002-09-25 | 2002-11-18 | 2003-07-23 | 2003-12-03 | 2004-01-25 | 2004-01-30 | 2004-03-28 |  | 2005-08-13 |  | 2005-09-27 | 2006-07-06 | United States of America | United States of America (LPLV (Stopped)) | United States of America | 18 | 14 | 6 | 156 | 130 | 110 | 8 | 0 | 0 | 5 | 0 | 2 | 3
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01093 | CSR Approved | Double-blind F-U Monotherapy (DB F-U/N01061) | Phase III | Double Blind | Clinical Development Europe | CNS | R & D | De Smet J | Wajskop M |  | PPD |  |  |  | No | A multicenter, double-blind, follow-up trial evaluating the long-term safety of levetiracetam (1000 to 3000 mg/day oral b.i.d. and carbamazepine (400 to 1200 mg/day oral b.i.d.), used as monotherapy in subjects (> or = 16 years) coming from the N01061 trial. | Indication for Neuro Psychiatry | Central Nervous System | N01093 is a feeder study of N01061 |  |  |  | 2002-04-17 |  | 2003-07-23 |  | 2005-07-12 | 2005-11-08 | 2005-11-10 | 2006-01-13 | 2006-01-30 | 2006-02-28 | 2006-02-28 | 2006-05-10 | 2006-06-20 | Belgium, Czech Republic, Finland, France, Germany, Hungary, Italy, Netherlands, Poland, South Africa, Spain, Sweden, United Kingdom | Belgium (LPLV), Czech Republic (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Netherlands (LPLV), Poland (LPLV), South Africa (LPLV), Spain (LPLV), Sweden (LPLV), United Kingdom (LPLV) | Belgium, Czech Republic, Finland, France, Germany, Hungary, Italy, Netherlands, Poland, South Africa, Spain, Sweden, United Kingdom | 100 | 76 | 72 | 335 | 335 | 0 | 0 | 0 | 0 | 336 | 272 | 57 | 7
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01098 | Study Archived | BE saliva / serum | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | De Smedt F | [6 empty] | Yes | Monocentre, open label, parallel group study of the correlation between plasma and saliva concentrations of levetiracetam after a 750 mg single oral dose, given either as 7.5 ml of a 10% oral solution or as tablets to 8 healthy male volunteers | [5 empty] | 2002-03-11 | 2002-03-13 | 2002-04-08 | 2002-04-09 |  | 2002-04-09 | 2002-05-06 | 2002-04-30 | 2002-06-20 | 2002-07-04 |  | 2002-07-23 | 2002-08-12 | 2003-03-13 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 0 | 0 | 0 | 11 | 0 | 3 | 8 | 0 | 0 | 8
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01099 | CSR Approved | LVTM Korean Registration Study | Phase III | Open | Affiliates | Neurology | Affiliates | Thambypillai V | [6 empty] | No | A Korean open-label, multi-center community, based trial studying the safety and efficacy of Keppra TM as adjuntive therapy in adults subjects with uncontrolled partial epilepsy for bridging purpose with a similar study on Caucasian. | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2002-09-15 | 2002-11-01 | 2002-12-18 | 2003-05-01 | 2004-03-05 |  | 2004-06-08 | 2004-02-01 | 2004-10-06 | 2004-04-30 | 2004-12-22 |  | 2005-03-24 | 2004-09-01 | 2005-08-09 | South Korea | South Korea (LPLV) | South Korea | 9 | 10 | 10 | 100 | 100 | 100 | 0 | 0 | 0 | 100 | 0 | 8 | 92
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01101 | Protocol Approved (Cancelled) | Postherpetic neuralgia (PoC) | Phase II | Double Blind | Clinical Development Europe |  | R & D | Jacobs A |  |  | ICON |  |  |  | No | A double-blind, randomized, placebo-controlled, parallel group, multicenter trial evaluating the efficacy and safety of LEV 500 mg oral tablets in b.i.d. administration (daily dose ranging from 1g to 4g), for a duration of 18 weeks in adults (>=18 years) suffering from postherpetic neuralgia | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2003-04-04: 2002-08-31; 2003-05-05: 2002-11-12; 2003-05-09: 2002-11-30; 2003-07-03: 2004-04-30; 2003-08-18: 2004-07-31; 2004-03-22: 2004-11-30 |  |  |  | 25 | 0 | 0 | 155 | 124 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01102 | Study Archived | Add on to partial Onset Seizure - China | Phase III | Double Blind | Clinical Development Asia | CNS | R & D | He G |  |  | Excel |  |  |  | No | A double-blind, placebo controlled, randomised study : 16 weeks evaluation of the efficacy and safety of Levetiracetam (LEV) as add-on therapy in adults and adolescents older than 16 years suffering from partial seizures. | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2002-11-27 | 2002-12-16 | 2004-03-25 | 2003-03-31 | 2004-07-01 |  | 2005-01-05 | 2003-12-31 | 2005-05-25 | 2005-05-31 | 2005-07-22 |  | 2005-08-17 | 2005-08-31 | 2005-11-16 | China | China (LPLV) | China | 6 | 0 | 6 | 192 | 160 | 160 | 224 | 18 | 0 | 206 | 0 | 17 | 189
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01103 | Study Archived | Pediatric Cognition Study | Phase II | Double Blind | Clinical Development USA | CNS | R & D | Stalvey T | Edwards M |  | INC Research |  |  |  | No | A 19-week, randomized, double-blind, multicenter, placebo-controlled, safety study to evaluate the cognitive and neuropsycholocial effects of levetiracetam 20-60 mg/kg/day, divided in twice daily dosing, as adjunctive treatment in children 4-16 years old, inclusive with refractory partial onset seizures | Indication for Neuro Psychiatry | Central Nervous System |  | 2003-03-10 | 2003-03-07 | 2004-03-15 | 2004-03-15 | 2004-07-12 | 2004-09-28 | 2007-01-28 | 2006-12-28 | 2007-06-18 | 2007-03-21 | 2007-08-20 | 2007-04-25 | 2007-09-28 | 2007-06-15 | 2008-02-18 | 2008-01-04 | Canada, South Africa, United States of America | Canada (LPLV), South Africa (LPLV), United States of America (LPLV) | Canada, South Africa, United States of America | 40 | 33 | 29 | 110 | 87 | 60 | 119 | 0 | 20 | 99 | 0 | 20 | 79
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01105 | CSR Approved | Dyskinesia in PD | Phase II | Double Blind | Clinical Development Europe | CNS | R & D | Mahieu V | [6 empty] | No | A therapeutic exploratory, single arm, multicenter trial to evaluate the efficacy and the safety of levetiracetam up to 4000mg/day (500mg oral tablets) on levodopa induced dyskinesias in adults with Idiopathic Parkinson's Disease | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2002-09-27 |  | 2003-02-10 | 2003-04-30 | 2003-07-03 | 2003-12-15 | 2004-02-27 | 2004-08-07 | 2004-11-08 | 2004-10-09 | 2005-02-22 |  | 2005-06-30 | 2004-12-31 | 2007-08-07 | Belgium, France, Portugal | Belgium (LPLV), France (LPLV), Portugal (LPLV) | Belgium, France, Portugal | 8 | 8 | 8 | 40 | 30 | 25 | 36 | 0 | 3 | 31 | 0 | 9 | 22
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01112 | Study Archived | Levetiracetam BE MCC-Tartrate | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S |  |  | SGS |  |  |  | Yes | Randomized, monocentre, open label, two-way crossover, single dose bioequivalence study of levetiracetam 750 mg tablets manufactured by the Multi-Column Chromatography (MCC) process with levetiracetam 750 mg tablets manufactured by the tartrate process, in 18 healthy fasting male and female subjects | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2002-11-20 | 2002-11-21 | 2002-11-22 | 2002-11-25 | 2002-11-22 |  | 2002-12-26 | 2002-12-26 | 2003-02-10 | 2003-02-11 |  |  | 2003-04-30 | 2003-05-14 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 34 | 18 | 18 | 30 | 0 | 12 | 18 | 0 | 0 | 18
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01127 | CSR Approved | FU monotherapy Open label trial N01061 (CZ,H,...) | Phase III | Open | Clinical Development Europe | CNS | R & D | Verkest (Health Care Interim) S | [6 empty] | No | A multicenter, open-label, follow-up trial evaluating the long-term safety of levetiracetam individualized dose from 1000 to 3000 mg/day (oral tablets of 500 mg b.i.d;), used as monotherapy in subjects (> or = 16 years) suffering from epilepsy and coming from the N01061 or the N01093 trials. | Indication for Neuro Psychiatry | Central Nervous System | N01127 is a feeder study of N01061 | 2002-12-05 | 2002-12-20 |  | 2003-03-04 | 2003-06-30 | 2005-08-11 | 2005-12-31 | 2005-10-26 | 2009-12-31 | 2007-05-29 | 2010-04-30 | 2007-09-14 |  | 2008-03-18 | 2010-08-31 | 2008-08-08 | Czech Republic, Hungary, Poland, Sweden | Czech Republic (LPLV), Hungary (LPLV), Poland (LPLV), Sweden (LPLV) | Czech Republic, Hungary, Poland, Sweden | 22 | 22 | 18 | 82 | 67 | 0 | 0 | 0 | 0 | 66 | 62 | 4 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01128 | CSR Approved | Single dose PK study | Phase I | Open | Clinical Development Asia | Clinical Pharmaco | R & D | He G |  |  | Beijing Kendle Wits Medical Consulting |  |  |  | Yes | A randomized, mono-center, open-label, single dose, two-way crossover study of the pharmacokinetics of levetiracetam 500 mg tablets given as two single doses of 500 mg and 1500 mg, in 26 healthy Chinese fasting male adults | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2003-02-07 | 2003-05-05: 2003-03-20; 2003-05-16: 2003-06-17; 2003-06-03: 2003-06-19; 2003-07-24: 2003-06-30; 2004-03-25: 2004-06-21 | China | China (LPLV) | China | 1 | 0 | 1 | 52 | 26 | 0 | 39 | 0 | 13 | 26 | 0 | 0 | 26
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01130 | Created (Cancelled) | LEV intravenous safety trial | Phase II | Open | Clinical Development Europe |  | R & D | Voss G | [6 empty] | No | A multicenter, open-label, single arm, exploratory trial evaluating the safety and tolerability of levetiracetam intravenous (500 mg/5ml ampoules) 15-minute infusion at doses ranging from 1000mg to 3000mg/day, administered in b.i.d. regimen as an adjunctive antiepileptic treatment for a maximum of 4 days in subjects from 16 to 65 years suffering from partial onset seizures. | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01134 | Created (Cancelled) | Named patient program | Compassionate Use |  | Clinical Development Europe |  | R & D | Falter U, Mahieu V | [6 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01138 | Study Archived | Bioequivalence Oral Solution / Tablets | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | De Smedt F, Riethuisen J | [6 empty] | Yes | Randomized, monocenter, open label, two-way crossover, single dose bioequivalence study of levetiracetam given as either 5 mL (500 mg) of a 10% oral solution or as a 500 mg oral tablet in 18 healthy male and female subjects. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2003-10-02 | 2003-09-30 | 2004-01-05 | 2003-12-16 |  | 2003-12-31 | 2004-02-20 | 2004-01-19 | 2004-03-31 | 2004-03-26 | 2004-05-07 | 2004-05-14 | 2004-06-30 | 2004-07-26 | France | France (LPLV) | France | 1 | 1 | 1 | 24 | 18 | 18 | 36 | 0 | 18 | 18 | 0 | 0 | 18
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01139 | Study Archived | META PK Analysis | Meta-analysis |  | Clinical Development Europe | CNS | R & D | [7 empty] | No | [6 empty] | 2004-03-25: 2004-11-23 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01140 | Study Archived | pilot study Keppra once a day | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | De Smedt F | [6 empty] | Yes | A single dose study to compare the pharmacokinetics of levetiracetam from three modified release test formulations with the immediate release reference formulation in 12 healthy male volunteers and to assess the influence of food on one of the test formulations. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2005-01-10 | 2005-01-07 | 2005-03-22 | 2005-03-17 | 2005-04-06 | 2005-04-06 | 2005-05-13 | 2005-05-25 | 2005-06-13 | 2005-06-24 | 2005-07-20 | 2005-10-25 | 2005-09-15 | 2005-11-07 | France | France (LPLV) | France | 1 | 1 | 1 | 20 | 12 | 12 | 16 | 0 | 4 | 12 | 0 | 1 | 11
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01142 | Study Archived | Tardive Dyskinesia | Phase II | Double Blind | Clinical Development Europe | CNS | R & D | Voss G |  |  | Monitoring done by MDS PS |  |  |  | No | An 8-week exploratory, double-blind, placebo controlled, randomized trial : Evaluation of the efficacy and safety of lev up to 3000mg (250-500mg oral tablets in b.i.d. administration) on neuroleptic-induced tardive dyskinesia in subjects with stable axis I psychiatric disorder, aged from at least 18 years to 80 years. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 2004-10-18 | 2005-04-15 | 2005-05-12 | 2005-07-31 | 2005-10-12 | 2005-10-31 | 2005-12-29 | 2005-12-15 | 2006-03-01 |  | 2006-05-18 | 2006-04-30 | 2006-07-25 | Belgium, Bulgaria, Germany, Hungary, Poland | Belgium (LPLV), Bulgaria (LPLV), Germany (LPLV), Hungary (LPLV), Poland (LPLV) | Belgium, Bulgaria, Germany, Hungary, Poland | 19 | 19 | 15 | 90 | 70 | 48 | 74 | 0 | 3 | 70 | 0 | 7 | 63
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01146 | Created (Cancelled) | BE between tablets & dispersable |  |  | Clinical Development Europe |  | R & D | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01148 | CSR Approved | Long-term Follow-up Pediatric Exclusivity | Phase III | Open | Clinical Development USA | CNS | R & D | Rasmussen M, Ryckaert B |  |  | PRA in Europe, PPD in Latin America, and contract monitors in the US |  |  |  | No | A Multi-Center, Open-Label, Long-Term, Follow-Up Study Of The Safety And Efficacy Of Levetiracetam In Children With Partial Onset Seizures. | Indication for Neuro Psychiatry | Central Nervous System |  | 2004-03-12 |  | 2004-03-15 | 2004-03-18 | 2004-10-01 | 2004-10-21 | 2007-06-18 | 2007-04-16 | 2008-07-10 | 2008-04-29 | 2008-09-11 | 2008-08-08 | 2008-11-19 | 2008-10-30 | 2009-03-11 | 2009-02-02 | Belgium, Brazil, Canada, Czech Republic, France, Germany, Hungary, India, Italy, Mexico, Poland, Romania, Russian Federation, South Africa, United Kingdom, United States of America | Australia (1st Site Initiation (Cancelled)), Belgium (LPLV), Brazil (LPLV), Canada (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), India (LPLV), Italy (LPLV), Mexico (LPLV), Poland (LPLV), Romania (LPLV), Russian Federation (LPLV), South Africa (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Brazil, Canada, Czech Republic, France, Germany, Hungary, India, Italy, Mexico, Poland, Romania, Russian Federation, South Africa, United Kingdom, United States of America | 100 | 98 | 85 | 290 | 250 | 225 | 0 | 0 | 0 | 255 | 62 | 75 | 118 |  |  | 2007-12-04
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01150 | Study Archived | BE wet granulation vs direct compression | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A | [6 empty] | Yes | Randomized, single center, open label, three-way crossover, single dose bioequivalence study of levetiracetam tablets manufactured by the Wet Granulation process (WG, 500 mg) or by Dry Granulation process (DG, 500 mg or 1000 mg), in 18 healthy fasting male and female subjects. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2003-05-05: 2004-05-06; 2003-05-16: 2004-06-01; 2003-06-03: 2004-06-11; 2003-07-24: 2004-07-05; 2003-10-03: 2004-08-12; 2003-12-17: 2004-09-17; 2004-03-25: 2004-11-04 | France | France (LPLV) | France | 1 | 1 | 1 | 36 | 18 | 18 | 35 | 0 | 17 | 18 | 0 | 0 | 18
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01159 | Study Archived | DB, Placebo controlled, 2-arm, multi-center Study | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global | Sano T | Suzuki A | N/A | ASKLEP Inc for Japan and PXL for China | No | Hybrid | adults | No | A DOUBLE-BLIND, MULTICENTER, RANDOMIZED, PLACEBO-CONTROLLED STUDY TO EVALUATE THE EFFICACY AND SAFETY OF ADJUNCTIVE TREATMENT WITH ORAL LEVETIRACETAM (L059) IN EPILEPSY PATIENTS AGED FROM 16 YEARS WITH GENERALIZED TONIC-CLONIC (GTC) SEIZURES | Epilepsy | Central Nervous System | N01159 is a feeder study of N01361 | 2010-01-29 | 2010-01-29 |  | 2010-05-20 | 2011-07-15 | 2010-10-21 | 2012-03-30 | 2013-09-05 |  | 2014-05-27 |  | 2014-07-30 |  | 2014-10-20 |  | 2014-12-22 | China, Japan | China (LPLV), Japan (LPLV) | China, Japan | 108 | 115 | 58 | 276 | 232 | 186 | 0 | 0 | 0 | 251 | 0 | 110 | 141
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01160 | CSR Approved | LVTM-XR Single dose | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S | [6 empty] | Yes | A randomized, monocenter, open-label, three-way cross-over study of oral levetiracetam 500 mg extended release (XR) formulation and 250 mg immediate release formulation: single and multiple dose bioequivalence and the assessment food effect on the XR formulation in 24 healthy male and female volunteers | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 2006-02-08 | 2006-07-01 | 2006-07-04 | 2006-07-15 | 2006-07-20 | 2006-09-30 | 2006-09-02 | 2006-10-23 | 2006-10-27 | 2006-12-30 | 2007-02-16 | 2007-02-15 | 2007-05-11 | France | France (LPLV) | France | 1 | 1 | 1 | 35 | 24 | 24 | 34 | 0 | 10 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01161 | Created (Cancelled) | Multiple dose | Phase I |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01165 | Study Archived | Fast infusion/high dose study | Phase I | Single Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A | [6 empty] | Yes | Randomized, single center, investigator blind, placebo-controlled, safety study of single ascending doses of levetiracetam (500 mg/5 mL vials) up to 4 g in 15 minute intravenous infusion and 5 minute intravenous infusion, in male and female healthy volunteers. | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2004-01-21 | 2003-05-05: 2004-03-01; 2003-05-16: 2004-04-21; 2003-06-03: 2004-05-26; 2003-07-24: 2004-06-03; 2003-10-03: 2004-07-13; 2003-12-17: 2004-08-24; 2004-03-25: 2004-10-15 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 90 | 48 | 48 | 83 | 0 | 35 | 48 | 0 | 0 | 48
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01166 | Study Archived | Lev IV Europe | Phase II | Open | Clinical Development Europe | CNS | R & D | Voss G | [6 empty] | No | A multicenter, open-label, single arm, exploratory trial evaluating the safety and tolerability of levetiracetam intravenous (500 mg/ 5 ml ampoules) 15-minute infusion at doses ranging from 1000 mg to 3000 mg/ day, administed in b.i.d. regimen as an adjunctive antiepileptic treatment for a maximum of 4 days in subjects from 16 to 65 years suffering from partial onset seizures | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 2004-02-19 |  | 2004-06-09 |  | 2004-08-05 | 2004-09-15 | 2004-08-20 | 2004-12-31 | 2004-09-17 |  | 2004-10-07 | 2005-03-15 | 2004-12-14 | France, Germany, United Kingdom | France (LPLV), Germany (LPLV), United Kingdom (LPLV) | France, Germany, United Kingdom | 5 | 5 | 4 | 25 | 25 | 25 | 26 | 0 | 1 | 25 | 0 | 0 | 25
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01173 | Study Archived | Pharmacoscintigraphy trial | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S | [6 empty] | Yes | Pharmacoscintigraphic investigation of the regional drug absorption of levetiracetam (250 mg) delivered using the EnterionTM capsule in 3 different sites of the GI tract in comparison with the IR 250 mg oral tablet: open-label, randomized, four-way cross-over study, in 9 healthy adult male volunteer | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2004-04-05 | 2004-04-01 | 2004-05-24 | 2004-06-02 | 2004-06-30 | 2004-06-30 | 2004-07-14 | 2004-07-28 | 2004-09-06 | 2004-09-07 | 2005-01-17 | 2005-01-17 | 2005-04-15 | 2005-09-05 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 18 | 9 | 6 | 31 | 0 | 22 | 9 | 0 | 3 | 6
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01174 | Created (Cancelled) | META PK Analysis |  |  | Clinical Development Europe |  | Clinical Development Europe | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01175 | Study Archived | Monotherapy newly diagnosed epilepsy Keppra vs VPA or CBZ | Phase III | Open | Global Medical Affairs Europe | GMA Neurology / Psychiatry | Global Medical Affairs | Baukens C, Marovac J | Tillery N |  | COVANCE BELGIUM |  |  |  | No | A therapeutic confirmatory, open-label, multi-center, randomized 2 parallel groups, community-based trial studying the efficacy and safety of levetiracetam (1000 to 3000 mg/day oral tablets 250-500 mg b.i.d.) compared to sodium valproate (1000 to 2000 mg/day oral ER tablets 300-500 mg b.i.d.) and carbamazepine (600 to 1600 mg/day oral CR tablets 200-400 mg b.i.d.) as monotherapy in subjects with newly diagnosed epilepsy. | Indication for Neuro Psychiatry | Central Nervous System |  | 2004-03-26 | 2004-06-28 | 2004-06-16 | 2004-08-23 | 2004-11-01 | 2005-02-09 | 2006-09-30 | 2006-12-21 | 2007-11-15 | 2007-10-13 | 2007-11-30 | 2007-12-03 | 2008-04-02 | 2008-02-22 | 2008-04-30 | 2008-10-20 | Australia, Austria, Belgium, Bulgaria, Czech Republic, Denmark, Finland, France, Germany, Greece, Hungary, Ireland, Italy, Netherlands, Norway, Poland, Romania, Russian Federation, Slovakia, Spain, Sweden, Switzerland, Turkey, United Kingdom | Australia (LPLV), Austria (LPLV), Belgium (LPLV), Bulgaria (LPLV), Czech Republic (LPLV), Denmark (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Greece (LPLV), Hungary (LPLV), Ireland (LPLV), Italy (LPLV), Netherlands (LPLV), Norway (LPLV), Poland (LPLV), Romania (LPLV), Russian Federation (LPLV), Slovakia (LPLV), Spain (LPLV), Sweden (LPLV), Switzerland (LPLV), Turkey (LPLV), United Kingdom (LPLV) | Australia, Austria, Belgium, Bulgaria, Czech Republic, Denmark, Finland, France, Germany, Greece, Hungary, Ireland, Italy, Netherlands, Norway, Poland, Romania, Russian Federation, Slovakia, Spain, Sweden, Switzerland, Turkey, United Kingdom | 400 | 373 | 269 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 1701 | 0 | 431 | 1270
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01176 | Created (Cancelled) | Monotherapy failed first mono : Keppra mono vs Keppra add-on |  |  | UCB Pharma Global |  | Global Medical Affairs | Schelstraete I | Driver D | [5 empty] | No |  |  |  |  | 2004-05-02 | [18 empty] | 200 | 0 | 0 | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01181 | Created (Cancelled) | Social Phobia PhIII Dose ranging |  |  | UCB Pharma Global |  | UCB Pharma Global | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01194 | Study Archived | BE LEV tablets versus overencapsulated | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Perreaux A |  |  | Biotrial |  |  |  | Yes | Randomized, open label, monocenter, two-way crossover, single dose bioequivalence study of levetiracetam 250 mg oral tablet with levetiracetam 250 mg oral overencapsulated tablet in 24 healthy fasting male and female subjects. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2003-05-05: 2005-03-22; 2003-05-16: 2005-06-01; 2003-06-03: 2005-06-09; 2003-07-24: 2005-07-01; 2003-10-03: 2005-08-01; 2003-12-17: 2005-08-31; 2004-03-25: 2005-10-20 | France | France (LPLV) | France | 1 | 0 | 1 | 50 | 24 | 24 | 44 | 0 | 20 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01195 | Protoc. Summary Approved (Cancelled) | Pharmacoeco LVTM vs Phenytoin Monotherapy | Phase III | Open | Global Medical Affairs US | GMA Neurology / Psychiatry | Global Medical Affairs |  |  |  | Adv. Biol |  |  |  | Yes |  | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2005-06-21 | [14 empty] | United States of America | United States of America (Created) |  | 60 | 0 | 0 | 340 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01200 | Study Archived | BE between CBZ & Overcapsuled tablets | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Perreaux A | [6 empty] | Yes | Randomized, monocenter, open label, two-way crossover, single dose bioavailability study of carbamazepine 200 mg CR oral tablet with carbamazepine 200 mg CR oral over encapsulated tablet, in 14 healthy fasting male subjects. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2005-07-08 | 2005-07-07 | 2005-08-30 | 2005-08-30 | 2005-09-12 | 2005-09-05 | 2005-10-10 | 2005-10-10 | 2005-11-07 | 2005-11-07 | 2005-11-21 | 2005-12-12 | 2006-02-14 | 2006-02-10 | Belgium | Belgium (LPLV) | Belgium | 1 | 0 | 1 | 28 | 14 | 14 | 26 | 0 | 12 | 14 | 0 | 0 | 14
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01216 | Created (Cancelled) | China Named patient program | Phase IV |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01220 | Created (Cancelled) | Suicidality Classification Project (FDA) |  |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01221 | Study Archived | A DB comparative trial of L059 in epilepsy patient with POS | Phase III | Double Blind | Clinical Development Japan | Clinical Development Japan | R & D | Osakabe T | [6 empty] | No | A double-blind, randomized, placebo-controlled 5 parallel groups, confirmatory trial on the efficacy and safety od L059*levetiracetam( used as add-on therapy at doses of 500 to 3000 mg/day in patients from 16 to 65 years with epilepsy with partial onset seizures under treatment with 1 to 3 anti-epil eptic drug(s) | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-09-30 | 2005-09-08 |  | 2005-09-29 | 2005-11-14 | 2005-11-15 | 2006-11-30 | 2007-03-31 | 2007-06-30 | 2007-11-07 |  | 2007-12-12 |  | 2008-02-21 | 2007-10-30 | 2008-09-09 | Japan | Japan (LPLV) | Japan | 65 | 55 | 55 | 423 | 352 | 320 | 418 | 0 | 66 | 352 | 0 | 36 | 316
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01222 | CSR Approved | Adult follow-up trial (Japan) | Phase III | Open | Clinical Development Japan | Clinical Development Japan | R & D | Suzuki A | Beinhauer-Zellenka U | N/A |  |  |  |  | No | A multicenter, open, long-term follow-up study to evaluated the safety and efficacy of L059 (levetiracetam) at individual optimal dose ranging from 500 to 3000 mg/day in b.i.d. administration in subjects from 16 to 65 years with epilepsy suffering from partial onset seizures whether or not secondarily generalized who completed in a previous study. | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-01-31 | 2006-02-03 | 2006-02-28 | 2006-03-24 | 2006-06-01 | 2006-07-12 | 2007-07-01 | 2007-11-14 | 2008-12-31 | 2010-12-28 |  | 2011-06-03 |  | 2012-11-15 | 2009-10-31 | 2012-12-20 | Japan | Japan (LPLV) | Japan | 82 | 17 | 82 | 400 | 400 | 0 | 251 | 0 | 3 | 398 | 0 | 3 | 257 |  |  | 2008-04-08 |  |  |  | 2009-03-13 |  |  |  | 2009-10-28
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01223 | Study Archived | Open label, Japanese Ped Patients with Partial Seizures | Phase III | Open | Clinical Development Japan | Clinical Development Japan | UCB Pharma Global | Yokoyama T | Shimizu S | N/A | ASKLEP Inc |  |  | paediatrics | No | A open label, single-arm, and multi-center study on the efficacy, safety, and pharmacokinetics of Levetiracetam used as adjunctive therapy in Japanese pediatric patients equal to or older than 4 and younger than 16 years of age with uncontrolled partial seizures despite treatment with 1 or 2 anti-epileptic drug(s) | Epilepsy | Central Nervous System |  | 2009-04-27 | 2009-05-24 |  | 2009-09-18 | 2010-01-29 | 2010-01-29 | 2010-11-30 | 2010-10-29 | 2013-11-29 | 2013-10-24 | 2014-05-30 | 2014-01-10 | 2014-09-01 | 2014-02-20 | 2014-12-01 | 2014-03-27 | Japan | Japan (LPLV) | Japan | 40 | 30 | 29 | 82 | 70 | 70 | 0 | 0 | 0 | 73 | 0 | 38 | 35 |  |  | 2012-01-30 | 2012-02-10 |  |  | 2012-05-16 | 2012-07-31
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01224 | CSR Approved | Suicidality Classification Project (EMEA) | Non Interventional Study - Retrospective |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2004-03-25: 2005-07-05 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01226 | Created (Cancelled) | Keppra IN Drop Attacks (KIND study) | Phase III |  | Global Medical Affairs Europe | GMA Neurology / Psychiatry | Global Medical Affairs | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-10-15 | [18 empty] | 20 | 0 | 0 | 50 | 40 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01227 | Created (Cancelled) | Keppra IV infusion Phase IIIb | Phase III |  | Global Medical Affairs Europe | GMA Neurology / Psychiatry | Global Medical Affairs | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-11-30 | [18 empty] | 20 | 0 | 0 | 40 | 40 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01228 | CSR Approved | aEscape Study | Non Interventional Study - Prospective | Open | Global Medical Affairs Europe | GMA Neurology / Psychiatry | Global Medical Affairs | Baukens C | Tillery N | [5 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-09-30 | 2006-10-18 | 2006-11-09 | 2007-01-17 | 2007-01-01 | 2007-04-18 | 2007-06-30 | 2007-08-16 | 2007-06-30 | 2007-08-16 | 2007-10-01 | 2007-10-03 | 2007-12-14 | 2007-10-25 | 2008-01-30 | 2008-03-05 | Czech Republic, Germany, Italy, Poland, Romania, Spain | Austria (1st Site Initiation (Cancelled)), Czech Republic (LPLV), Germany (LPLV), Italy (LPLV), Poland (LPLV), Romania (LPLV), Spain (LPLV) | Czech Republic, Germany, Italy, Poland, Romania, Spain | 100 | 69 | 60 | 1000 | 1000 | 0 | 0 | 0 | 0 | 1062 | 0 | 0 | 1062
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01229 | Created (Cancelled) | Levorcom study | Phase IV | Open | Affiliates - Spain | GMA Neurology / Psychiatry | Affiliates - Spain | Marin E | [6 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-07-01 | [15 empty] | Spain | Spain (Created) |  | 28 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01230 | CSR Approved | QT study in healthy volunteers | Phase I |  | Clinical Development USA | Clinical Pharmaco | R & D | Salas V | [6 empty] | Yes | A Four-Way Crossover, Randomized, Placebo and Moxifloxacin-Controlled Study of the Effect of Levetiracetam on Cardiac Repolarization in 52 Healthy Male and Female Subjects | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-11-07 | 2005-11-07 | 2006-01-06 | 2005-12-16 | 2006-04-03 | 2006-03-27 | 2006-04-10 | 2006-05-08 | 2006-06-05 | 2006-06-01 | 2006-06-26 | 2006-07-11 | 2006-09-30 | 2006-09-27 | 2006-10-31 | 2006-11-20 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 104 | 52 | 52 | 113 | 0 | 61 | 52 | 0 | 5 | 47
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01231 | Created (Cancelled) | Proof of principle PK/PD study in healthy volunteers | Phase I |  | Clinical Development Europe | CNS | R & D | De Smedt F | [6 empty] | No |  |  |  |  | 2005-10-07 | [18 empty] | 1 | 0 | 0 | 30 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01235 | CSR Approved | 500 mg in POS vs placebo | Phase III | Double Blind | Clinical Development USA | CNS | R & D | Sykes D | [6 empty] | No | A double-blind, placebo-controlled randomized efficacy and safety study of levetiracetam extended release formulation (LEV XR), administered as 2 x 500 mg LEV XR tablets once daily as add-on therapy in subject from 12-70 years with refractory epilepsy suffering from partial onset seizures | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-01-31 | 2006-01-06 | 2006-02-28 | 2006-02-21 | 2006-07-01 | 2006-08-21 |  | 2007-01-08 |  | 2007-05-31 |  | 2007-07-18 |  | 2007-08-24 |  | 2007-10-11 | Brazil, Finland, India, Mexico, Russian Federation, South Africa, Ukraine | Brazil (LPLV), Finland (LPLV), India (LPLV), Mexico (LPLV), Russian Federation (LPLV), South Africa (LPLV), Ukraine (LPLV) | Brazil, Finland, India, Mexico, Russian Federation, South Africa, Ukraine | 36 | 29 | 34 | 162 | 132 | 106 | 188 | 0 | 30 | 158 | 0 | 15 | 143
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01237 | CSR Approved | KOMET Expansion | Phase III | Open | Global Medical Affairs Europe | GMA Neurology / Psychiatry | Global Medical Affairs | Marovac J | [6 empty] | No | A multicenter, open-label single-arm follow-up trial evaluating the long-term safety of levetiracetam, for patients suffering from epilepsy and coming from the study N01175 | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2006-01-24 | 2005-12-15 | 2006-01-24 | 2006-05-01 | 2006-06-26 | 2007-09-30 | 2007-09-26 | 2007-12-30 | 2008-04-29 | 2008-01-25 | 2008-06-13 | 2008-04-20 | 2008-10-14 | 2008-06-30 | 2009-01-16 | Belgium, Bulgaria, Finland, France, Poland, Switzerland | Belgium (LPLV), Bulgaria (LPLV), Finland (LPLV), France (LPLV), Poland (LPLV), Switzerland (LPLV) | Belgium, Bulgaria, Finland, France, Poland, Switzerland | 200 | 40 | 39 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 130 | 0 | 15 | 115
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01242 | CSR Approved | Cross sectional study - SOLUCION study | Phase IV | Open | Affiliates - Spain | GMA Neurology / Psychiatry | Affiliates - Spain | Marin E | [6 empty] | No | A cross-sectional study to assess the acceptability of Levetiracetam (Keppra) in oral solution (SOLUCION Study) | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2006-01-09 | 2003-05-16: 2006-01-07; 2004-03-25: 2006-10-26 | Spain | Spain (FPFV) | Spain | 0 | 85 | 85 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01248 | CSR Approved | Simulations Keppra IV pediatrics | Meta-analysis |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No | [6 empty] | 2004-03-25: 2006-03-20 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01260 | CSR Approved | LVTM-XR Dose Proportionality PK study | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Valgaeren A | Mccabe S | [5 empty] | Yes | A randomized, monocenter, open-label, three way cross-over dose proportionality study of oral levetiracetam in 24 healthy male and females volunteers. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2006-11-05 | 2006-10-20 | 2007-01-05 | 2007-01-05 | 2007-01-25 | 2007-02-02 | 2007-02-19 | 2007-02-26 | 2007-03-29 | 2007-03-30 | 2007-06-08 | 2007-06-06 | 2007-08-01 | 2007-08-07 | France | France (LPLV) | France | 1 | 1 | 1 | 49 | 24 | 24 | 49 | 0 | 25 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01270 | Study Archived | BE Keppra XR 750 mg | Phase I | Open | UCB Pharma Global | Clinical Pharmaco | UCB Pharma Global | Valgaeren A | Mccabe S | [5 empty] | Yes | A Randomized, monocenter, open-label, three-way cross-over, single dose bioequivalence study, with the assessment of food effect, with oral levetiracetam extended release tablets in healthy male and female volunteers. |  |  |  | 2007-11-02 |  | 2007-11-05 | 2007-10-26 | 2008-02-18 | 2008-02-21 | 2008-03-06 |  | 2008-03-31 | 2008-03-31 | 2008-04-29 | 2008-04-29 | 2008-05-28 | 2008-07-07 | 2008-08-11 | 2008-08-25 | France | France (LPLV) | France | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01274 | Study Archived | Pediatric Commitment 4-16 yrs | Phase II | Open | Clinical Development Europe | CNS | R & D | Gerard D | [6 empty] | No | Open-label, single-arm, multi-center, pharmacokinetic, safety and tolerability study of levetiractema intravenous infuison in children (4-16 years old) with epilepsy. | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-09-22 | 2006-09-25 | 2007-01-29 | 2007-01-29 | 2007-05-15 | 2007-09-10 | 2008-06-30 | 2010-01-19 | 2008-07-16 | 2010-02-02 | 2008-09-16 | 2010-03-24 |  | 2010-04-20 | 2008-12-16 | 2010-06-14 | Belgium, France, Germany, Mexico, Turkey, United States of America | Belgium (LPLV), France (LPLV), Germany (LPLV), Mexico (LPLV), Turkey (LPLV), United States of America (LPLV) | Belgium, France, Germany, Mexico, Turkey, United States of America | 15 | 30 | 18 | 36 | 30 | 30 | 33 | 0 | 0 | 33 | 0 | 0 | 33
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01275 | CSR Approved | Pediatric Commitment 1m-4yrs | Phase II | Open | UCB Pharma Global | Neurology | R & D | Gerard D | [6 empty] | No | Open-label, single-arm, multi-center, pharmacokinetic, safety and tolerability study of levetiractema intravenous infuison in children (1 month - 4 years old) with epilepsy. | Indication for Neuro Psychiatry | Central Nervous System |  | 2007-05-11 | 2007-07-09 | 2007-08-12 | 2007-08-03 | 2007-02-15 | 2008-05-16 | 2008-12-01 | 2010-02-23 | 2008-12-19 | 2010-03-11 | 2009-01-08 | 2010-06-14 | 2009-02-06 | 2010-08-04 | 2009-07-01 | 2010-11-03 | Belgium, Germany, Mexico, Turkey, United States of America | Belgium (LPLV), France (1st Site Initiation (Cancelled)), Germany (LPLV), Mexico (LPLV), Turkey (LPLV), United States of America (LPLV) | Belgium, Germany, Mexico, Turkey, United States of America | 20 | 24 | 11 | 22 | 18 | 18 | 23 | 0 | 3 | 20 | 0 | 0 | 20
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01280 | Study Archived | XR Conversion to Mono Efficacy | Phase III | Double Blind | Clinical Development USA | CNS | R & D | Stalvey T | Edwards M |  | PRA |  |  |  | No | A multi-center, double-blind, historical control, randomized conversion to monotherapy study with Keppra XR for treatment of partial onset seizures. | Indication for Neuro Psychiatry | Central Nervous System | N01280 is a parent study of N01281 | 2006-11-15 | 2006-11-03 | 2007-03-02 | 2006-12-14 | 2007-04-30 | 2007-08-06 | 2007-11-16 | 2009-03-02 | 2008-07-31 | 2009-09-14 | 2008-08-18 | 2009-11-06 | 2008-09-08 | 2010-04-15 | 2010-08-10 | 2010-09-01 | Mexico, Poland, Russian Federation, United States of America | Mexico (LPLV), Poland (LPLV), Russian Federation (LPLV), United States of America (LPLV) | Mexico, Poland, Russian Federation, United States of America | 82 | 82 | 57 | 280 | 220 | 200 | 303 | 0 | 75 | 228 | 0 | 38 | 190
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01281 | Study Archived | XR conversion to Mono FU | Phase III | Open | Clinical Development USA | CNS | R & D | Stalvey T | Edwards M |  | PRA |  |  |  | No | An open label long term follow up study with Keppra XR for treatment of partial onset seizures. | Indication for Neuro Psychiatry | Central Nervous System | N01281 is a follow up of N01280 | 2006-11-20 | 2006-11-03 | 2007-05-18 | 2006-12-13 | 2007-07-16 | 2008-02-28 | 2008-02-01 | 2009-09-04 | 2009-07-31 | 2010-03-31 | 2009-08-18 | 2010-06-02 | 2009-09-07 | 2010-07-30 | 2010-10-26 | 2010-11-23 | Mexico, Poland, Russian Federation, United States of America | Mexico (LPLV), Poland (LPLV), Russian Federation (LPLV), United States of America (LPLV) | Mexico, Poland, Russian Federation, United States of America | 82 | 50 | 41 | 220 | 220 | 220 | 0 | 0 | 0 | 190 | 1 | 24 | 165
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01286 | Created | Pop PK OD | Meta-analysis |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01288 | Created | Pop PK N01103-N01148 | Meta-analysis |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01289 | CSR Approved | BE oral solution - China | Phase I | Open | Clinical Development Asia | Clinical Pharmaco | UCB Pharma Global | Daoust A |  |  | Excel PharmaStudies, Inc. |  |  |  | Yes | Title of the trial: Randomized, monocenter, open label, two-way crossover, single dose bioequivalence study of levetiracetam given as either 5 mL (500 mg) of a 10% oral solution or as a 500 mg oral tablet in 18 healthy fasting male subjects. | Indication for Neuro Psychiatry | Central Nervous System |  | 2007-02-23 | 2007-04-04 | 2007-03-28 | 2007-04-04 | 2007-06-05 | 2007-06-04 | 2007-06-03 |  | 2007-06-26 | 2007-06-25 | 2007-08-09 | 2007-08-03 | 2007-10-05 | 2007-09-28 | 2007-11-23 | 2007-12-03 | China | China (LPLV) | China | 1 | 1 | 1 | 18 | 18 | 0 | 31 | 0 | 13 | 18 | 0 | 1 | 17
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01314 | Created (Cancelled) | Epilepsy in Deutschland (EID) | Phase IV |  | Affiliates | GMA Neurology / Psychiatry | Affiliates | [7 empty] | No | [20 empty] | Germany | Germany (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01316 | Created (Cancelled) | Dose response modelling in Japanese adults with Epilepsy | Phase I |  | UCB Pharma Global | Clinical Pharmaco | UCB Pharma Global | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01334 | Created (Cancelled) | Open-label, multi-center, non-interventional study |  |  | UCB Pharma Global |  | Affiliates | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01336 | Created | Keppra Pooling (Safety Dataset to AGS India) | Meta-analysis |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01339 | CSR Approved | BE dry syrup vs tabs | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Omadoye J | [6 empty] | Yes | Randomized, monocenter, open label, two-way cross-over, single dose bioequivalence study of two oral formulations of Levetiracetam in healthy male & female Japanese subjects. |  |  |  | 2009-05-20 |  | 2003-05-05: 2009-07-08; 2003-05-16: 2009-09-07; 2003-06-03: 2009-10-02; 2003-07-24: 2009-10-25; 2003-10-03: 2009-12-21; 2003-12-17: 2010-03-05; 2004-03-25: 2010-09-06 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 26 | 26 | 26 | 52 | 0 | 26 | 26 | 0 | 0 | 26
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01340 | Study Archived | A study comparing Keppra XR Pharmacokinetics between childre | Phase II | Open | UCB Pharma Global | Neurology | UCB Pharma Global | Carpenter M | Driver D | [5 empty] | No | An open label, multicenter, parallel-group, two-arm study comparing the pharmacokinetics of Keppra XR in children (aged 12-16 years old) with epilepsy and in adults (aged 18-55 years old) with epilepsy | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2009-02-27 |  | 2009-03-30 | 2009-09-21 | 2009-09-01 | 2010-03-17 | 2010-02-25 | 2010-04-08 | 2010-03-16 | 2010-05-10 | 2010-05-27 | 2010-07-15 | 2010-07-26 | 2010-11-19 | 2010-10-22 | United States of America | United States of America (LPLV) | United States of America | 8 | 6 | 6 | 30 | 24 | 24 | 27 | 0 | 2 | 25 | 0 | 0 | 25
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01353 | Study Archived | LEV trial Adjunctive therapy in patients with refractory POS | Phase IV | Open | UCB Pharma Global | GMA Neurology / Psychiatry | UCB Pharma Global | Lee J | Matsuoka K | N/A | DreamCIS | No | No | adults | No | A RANDOMIZED, OPEN-LABEL, PARALLEL GROUP, MULTI-CENTER, COMPARATIVE, PHASE IV TRIAL OF LEVETIRACETAM VERSUS TOPIRAMATE AS ADJUNCTIVE THERAPY TO EVALUATE THE SAFETY AND EFFICACY IN SUBJECTS WITH REFRACTORY PARTIAL ONSET SEIZURES Versio 2.0 | Epilepsy | Central Nervous System |  | 2010-04-23 | 2010-05-04 |  | 2010-07-15 | 2010-09-30 | 2010-11-17 | 2011-11-17 | 2014-04-15 |  | 2015-05-12 |  | 2015-06-10 |  | 2015-08-07 |  | 2015-10-20 | South Korea | South Korea (LPLV) | South Korea | 50 | 25 | 24 | 340 | 340 | 196 | 447 | 0 | 104 | 343 | 0 | 132 | 211
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01357 | Study Archived | Observational Study in Infants < 12 months treated with Kepp | Non Interventional Study - Prospective | Open | UCB Pharma Global | GMA Neurology / Psychiatry | UCB Pharma Global | Wuiame D | Baukens C | N/A | PXL |  |  | paediatrics | No | Observational sentinel sites study (N01357) in infants younger than 12 months, who are prescribed the treatment with Keppra oral solution in usual clinical practice | Indication for Neuro Psychiatry | Central Nervous System |  | 2009-09-09 | 2009-12-07 | 2009-11-27 | 2010-06-15 | 2010-05-07 | 2011-01-20 | 2011-08-26 | 2013-02-14 | 2012-08-25 | 2013-11-12 | 2012-10-22 | 2014-01-24 | 2012-12-01 | 2014-03-07 | 2013-02-09 | 2014-05-21 | France, Germany, Greece, Italy, Poland, Spain, United Kingdom | France (LPLV), Germany (LPLV), Greece (LPLV), Italy (LPLV), Poland (LPLV), Spain (LPLV), United Kingdom (LPLV) | France, Germany, Greece, Italy, Poland, Spain, United Kingdom | 33 | 29 | 27 | 100 | 100 | 80 | 103 | 0 | 0 | 103 | 0 | 27 | 76
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01359 | LPLV | Keppra Medical Need Program | Named Patient Program |  | Affiliates | GMA Neurology / Psychiatry | Affiliates | Hollanders W | [6 empty] | No | Medical Need Program for Individual Patient Supply of KEPPRA 100 mg/ml Oral Solution in Belgium | [5 empty] | 2003-05-05: 2009-10-10; 2003-05-16: 2008-03-31; 2003-06-03: 2010-12-31; 2003-07-24: 2010-12-31 | Belgium | Belgium (LPLV) | Belgium | 21 | 0 | 0 | 79 | 79 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01361 | Study Archived | Open-label, long-term extension study | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Matsuo T | Beinhauer-Zellenka U | N/A | A2 Healthcare Corporation | Yes | Hybrid | paediatrics | Yes | An open-label, multicenter, long-term, follow-up study in Japan to evaluate the safety, tolerability, and efficacy of adjunctive treatment with oral L059 (levetiracetam) in epilepsy subjects with generalized tonic-clonic (GTC) seizures. | Epilepsy | Central Nervous System | N01361 is a follow up of N01159, N01363 | 2010-04-20 | 2009-10-10 |  | 2010-08-24 | 2011-05-05 | 2011-06-30 | 2012-12-21 | 2013-12-25 |  | 2016-04-19 |  | 2016-05-24 |  | 2016-06-28 |  | 2016-08-19 | Japan | Japan (LPLV) | Japan | 50 | 36 | 32 | 52 | 52 | 32 | 44 | 0 | 0 | 44 | 0 | 10 | 34 |  |  | 2014-10-22 | 2014-10-22 |  |  | 2015-05-06 | 2015-05-07
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01362 | CSR Approved | Bioequivalence and Pharmacokinetics study for Keppra in Chin | Phase I | Open | UCB Pharma Global | Clinical Pharmaco | Affiliate China | Tang Y | Wu G | N/A | PXL |  |  | adults | Yes | A MONOCENTER, OPEN-LABEL, TWO-WAY RANDOMIZED CROSS-OVER STUDY TO EVALUATE THE BIOEQUIVALENCE OF LEVETIRACETAM ADMINISTERED AS A 45 MINUTES INTRAVENOUS INFUSION AND SAME DOSAGE LEVETIRACETAM ORAL TABLET (PART A); AND A RANDOMIZED, DOUBLE-BLIND, PLACEBOCONTROLLED, PARALLEL STUDY ON THE SAFETY, TOLERABILITY AND PHARMACOKINETICS OF LEVETIRACETAM 45 MINUTES INTRAVENOUS INFUSION DURING 4 DAYS OF B.I.D. DOSING (PART B), IN CHINESE HEALTHY VOLUNTEERS. | Indication for Neuro Psychiatry | Central Nervous System |  | 2010-11-30 | 2009-12-28 | 2003-05-05: 2011-10-11; 2003-05-16: 2012-05-25; 2003-06-03: 2012-06-28; 2003-07-24: 2012-07-17; 2003-10-03: 2012-09-27; 2003-12-17: 2012-11-26; 2004-03-25: 2013-03-18 | China | China (LPLV) | China | 1 | 1 | 1 | 48 | 24 | 24 | 63 | 0 | 39 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01363 | Study Archived | Open-Label, Multi-Center study | Phase III | Open | Clinical Development Japan | Clinical Development Japan | UCB Pharma Global | Matsuo T | Beinhauer-Zellenka U | N/A | ASKLEP Inc | No | No | paediatrics | No | An open-label, single-arm, multicenter study to evaluate the efficacy and safety of adjunctive treatment with levetiracetam in Japanese pediatric patients (>=4 to <16 years) with uncontrolled generalized tonic-clonic (GTC) seizures despite treatment with 1 or 2 antiepileptic drug(s) | Epilepsy | Central Nervous System | N01363 is a feeder study of N01361 | 2010-03-31 | 2010-03-31 |  | 2010-06-30 | 2011-01-14 | 2011-02-09 | 2012-04-25 | 2012-11-13 |  | 2013-06-04 |  | 2013-09-09 |  | 2013-10-31 |  | 2014-03-04 | Japan | Japan (LPLV) | Japan | 40 | 26 | 8 | 15 | 15 | 12 | 13 | 0 | 0 | 13 | 0 | 2 | 11
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01364 | Study Archived | Study of LEV used as monotherapy subjects (>=16 years) newly | Phase III | Open | GCSO | Neurology | Affiliates | Schelstraete I | Driver D | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, OPEN LABEL, RANDOMIZED, PARALLEL GROUP, ACTIVE CONTROLLED STUDY COMPARING THE EFFICACY AND SAFETY OF LEVETIRACETAM TO CARBAMAZEPINE USED AS MONOTHERAPY IN SUBJECTS (>=16 YEARS) NEWLY OR RECENTLY DIAGNOSED AS SUFFERING FROM EPILEPSY AND EXPERIENCING PARTIAL SEIZURES | Epilepsy | Central Nervous System |  | 2012-06-25 | 2013-02-07 |  | 2013-04-08 | 2014-02-24 | 2013-09-26 | 2015-08-25 | 2015-03-06 |  | 2015-09-30 |  | 2015-10-30 |  | 2015-11-13 |  | 2016-02-10 | China | China (LPLV) | China | 28 | 28 | 28 | 550 | 436 | 261 | 520 | 0 | 82 | 438 | 0 | 106 | 332
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01367 | Study Archived | Keppra initial Mono in Adult with POS | Phase IV | Open | UCB Pharma Global | GMA Neurology / Psychiatry | Affiliates | Namgoong K | Beinhauer-Zellenka U | N/A | A Plus Company | No | No | adults | No | A MULTI-CENTER, OPEN-LABEL, RANDOMIZED STUDY TO EVALUATE THE LONG TERM EFFECTIVENESS OF LEVETIRACETAM AS MONOTHERAPY IN COMPARISON WITH OXCARBAZEPINE IN SUBJECTS WITH NEWLY OR RECENTLY DIAGNOSED PARTIAL EPILEPSY | Epilepsy | Central Nervous System |  |  | 2010-11-17 |  | 2011-01-20 | 2011-06-16 | 2011-06-08 | 2012-06-21 | 2013-07-30 |  | 2014-07-15 |  | 2014-10-09 |  | 2014-12-04 |  | 2015-03-02 | South Korea | South Korea (LPLV) | South Korea | 15 | 23 | 23 | 600 | 600 | 352 | 385 | 0 | 32 | 353 | 0 | 110 | 243
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01373 | Study Archived | PK study in Japanese non-epileptic renal impaired patients | Phase IV | Open | UCB Pharma Global | Clinical Development Japan | Clinical Development Japan | Yamamoto J |  | N/A | PXL |  |  | adults | Yes | SINGLE-DOSE PHARMACOKINETICS OF ORALLY ADMINISTERED LEVETIRACETAM (E KEPPRA) IN JAPANESE SUBJECTS WITH NORMAL RENAL FUNCTION AND VARIOUS DEGREES OF RENAL IMPAIRMENT USING A DOSING REGIMEN ADJUSTED TO RENAL FUNCTION (250MG OR 500MG) | Renal Impairment | Central Nervous System |  | 2011-04-13 | 2011-04-13 | 2003-05-05: 2011-06-28; 2003-05-16: 2011-11-18; 2003-05-30: 2012-05-11; 2003-06-03: 2012-10-30; 2003-07-24: 2012-11-16; 2003-10-03: 2013-01-22; 2003-12-17: 2013-03-28; 2004-03-25: 2013-08-09 | Japan | Japan (LPLV) | Japan | 4 | 2 | 2 | 42 | 30 | 28 | 49 | 0 | 19 | 30 | 0 | 0 | 30
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01375 | Study Archived | Open-label, multicenter study | Phase III | Open | Clinical Development Japan | CNS | Clinical Development Japan | Nakatsu T | Suzuki A | N/A | ASKLEP | Yes | Yes | adults | No | AN OPEN-LABEL, RANDOMIZED, MULTICENTER STUDY TO EVALUATE THE EFFICACY AND SAFETY OF LEVETIRACETAM USED AS MONOTHERAPY IN NEWLY OR RECENTLY DIAGNOSED EPILEPSY PATIENTS AGED OLDER THAN OR EQUAL TO 16 YEARS WITH PARTIAL SEIZURES | Epilepsy | Central Nervous System |  | 2011-05-31 | 2011-05-31 | 2011-07-15 | 2011-07-15 | 2011-12-15 | 2011-12-15 | 2013-02-18 | 2012-12-14 | 2016-03-31 | 2015-04-14 | 2016-05-26 | 2015-05-21 | 2016-08-04 | 2015-07-23 | 2016-12-08 | 2015-09-28 | Japan | Japan (LPLV) | Japan | 40 | 32 | 27 | 95 | 70 | 70 | 99 | 0 | 0 | 71 | 0 | 29 | 42 |  |  | 2013-11-27 | 2013-11-27 |  |  | 2014-06-04 | 2014-06-12
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01377 | Study Archived | IV vs oral BE study of Keppra / Japanese Patients | Phase I |  | GED |  | R & D | Okagaki T, Watanabe S | Cain D, Tsujii A | [5 empty] | Yes | A Single Site, Open-Label, Randomized, Single-Dose, Two-Way Cross-Over Study in Healthy Japanese Subjectgs to Evaluate the Bioequivalence, Safety & Tolerability of Levetiracetam Administered as an Oral Tablet or Intravenous Infusion | Epilepsy | Central Nervous System |  |  | 2011-02-04 |  | 2011-03-23 |  | 2011-06-29 | 2011-08-02 | 2011-09-05 | 2011-09-20 | 2011-09-28 | 2011-11-24 | 2011-10-28 | 2011-12-22 | 2011-12-23 | 2012-06-15 | 2012-05-02 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 36 | 26 | 26 | 50 | 0 | 23 | 27 | 0 | 1 | 26
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N01378 | CSR Approved | Safety study for LVTM IV in Japanese patients | Phase II |  | Clinical Development Japan |  | Clinical Development Japan | Suzuki A | Beinhauer-Zellenka U | N/A |  |  |  |  | No |  | Epilepsy | Central Nervous System |  |  | 2011-01-14 | 2003-05-05: 2011-02-28; 2003-05-16: 2011-07-13; 2003-06-03: 2012-02-02; 2003-07-24: 2012-02-13; 2003-10-03: 2012-06-19; 2003-12-17: 2012-07-31; 2004-03-25: 2012-10-24 | Japan | Japan (LPLV) | Japan | 4 | 4 | 3 | 15 | 10 | 10 | 17 | 0 | 1 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N052 | Study Archived | 2g-4g long term Tolerability | Phase III |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No | A 24-week multicenter, double-blind, parallel group, add-on study to compare the efficacy and the tolerability of oral daily doses of ucb L059 (2000 mg and 4000 mg tablets) with placebo in patients with refractory epilepsy, followed by a 24-week open-la | [5 empty] | 2003-05-05: 1993-03-17; 2003-10-03: 1998-09-21; 2004-03-25: 1998-11-23 | Belgium, United Kingdom | Belgium (Created), United Kingdom (Created) |  | 37 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N126 | Study Archived | FU Study : N039 | Phase III |  | Clinical Development Europe | CNS | R & D | Stiff J | [6 empty] | No | A long-term multicentre study of the safety and efficacy of oral 250 mg capsules ucb L059: open treatment at individualized doses up to 4000 mg in patients with epilepsy. | [5 empty] | 2003-05-16: 1994-01-03; 2003-07-24: 1995-11-06; 2003-10-03: 1998-07-03; 2004-03-25: 1998-10-09 | Belgium, United Kingdom | Belgium (LPLV), United Kingdom (LPLV) | Belgium, United Kingdom | 2 | 0 | 2 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N129 | Study Archived | Long term FU study: safety/efficacy | Phase III | Open | Clinical Development Europe | CNS | R & D | Jacobs A |  |  | PPD Development |  |  |  | No | A long-term multicentre follow-up study of the safety and efficacy of oral 500 mg tablets ucb L059 : open treatment at individualized doses up to 4000 mg daily in patients with epilepsy | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2003-05-05: 1993-12-16; 2003-05-16: 1994-04-15; 2003-07-24: 2001-09-26; 2003-10-03: 2001-11-19; 2004-03-25: 2002-03-15 | Belgium, Czech Republic, France, Germany, Hungary, Netherlands, Poland, Sweden, Switzerland, United Kingdom | Belgium (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Netherlands (LPLV), Poland (LPLV), Sweden (LPLV), Switzerland (LPLV), United Kingdom (LPLV) | Belgium, Czech Republic, France, Germany, Hungary, Netherlands, Poland, Sweden, Switzerland, United Kingdom | 93 | 0 | 94 | 0 | 0 | 0 | 505 | 0 | 0 | 505 | 0 | 231 | 274
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N133 | Study Archived | 1-year FU study : European Epilepsy , Study N051 | Phase II |  | Clinical Development Europe | CNS | R & D | Schelstraete I | Driver D | [5 empty] | No | A long-term multicentre follow-up study of the safety and efficacy of oral 500 mg tablets ucb L059: open treatment at individualized doses between 1000 mg and 3000 mg daily in patients with partial-onset epoleptic seizures. | [5 empty] | 2003-05-16: 1995-03-27; 2003-10-03: 1998-06-15; 2004-03-25: 1998-11-05 | Belgium, France, Germany, Switzerland, United Kingdom | Belgium (FPFV), France (Created), Germany (Created), Switzerland (Created), United Kingdom (Created) | Belgium | 58 | 0 | 5 | 279 | 0 | 0 | 3 | 0 | 0 | 3 | 3 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N138 | Study Archived | Add-on to Monotherapy | Phase III | Double Blind | Clinical Development Europe | CNS | R & D | Falter U |  |  | PPD Pharmaco |  |  |  | No | Evaluation of the efficacy and tolerability of ucb L059 (1500 mg bid, 500 mg tablets) monotherapy in epileptic patients with complex partial onset seizures, having experienced improval seizure control under add-on treatment. A 60-week (maximum), double-blind, multicenter, responder-selected trial (Phase III study, placebo comparator) | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2003-05-05: 1995-01-25; 2003-05-16: 1995-06-02; 2003-07-24: 1998-05-13; 2003-10-03: 1998-08-18; 2004-03-25: 1998-11-30 | Czech Republic, Denmark, France, Germany, Hungary, Netherlands, Norway, Poland, Sweden, Switzerland, United Kingdom | Czech Republic (LPLV), Denmark (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Netherlands (LPLV), Norway (LPLV), Poland (LPLV), Sweden (LPLV), Switzerland (LPLV), United Kingdom (LPLV) | Czech Republic, Denmark, France, Germany, Hungary, Netherlands, Norway, Poland, Sweden, Switzerland, United Kingdom | 51 | 0 | 47 | 350 | 0 | 0 | 0 | 0 | 0 | 286 | 0 | 87 | 199
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N141 | Study Archived | Long term FU study : N052 | Phase III |  | Clinical Development Europe | CNS | R & D | De Smet J | Wajskop M | [5 empty] | No | "A long-term multicenter follow-up study: open label treatment with ucb L059 at individualized doses of 2000 mg or 4000 mg daily in patients with refractory epilepsy, initially treated with at least one (1) standard antiepileptic drug." | [5 empty] | 2003-05-05: 1995-08-21; 2003-10-03: 1998-08-05; 2004-03-25: 1998-11-05 | Belgium | Belgium (Created) |  | 15 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N146 | Study Archived | L059/Warfarin interaction | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Arendt C | [6 empty] | Yes | "Phase I, Double-blind, Two-Way, Cross-over, multiple Dose Study to assess possible influences on the Pharmacokinetics and Pharmacodynamics of Warfarin by concomitant administration of ucb L059 or placebo in healthy volunteers receiving protracted treatm" | [5 empty] | 2003-05-16: 1996-11-14; 2003-07-24: 1997-05-18 | Germany | Germany (LPLV) | Germany | 1 | 0 | 1 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N152 | Study Archived | L059 in haemodialysis | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Arendt C | [6 empty] | No | Open label, single dose pharmacokinetic study of orally administered 500 mg. ucb L059 in five end-stage renal insufficiency subjects undergoing haemodialysis. | [5 empty] | 2003-05-05: 1998-05-11; 2003-05-16: 1998-05-11; 2003-07-24: 1998-06-08; 2004-03-25: 1998-11-18 | Belgium | Belgium (LPLV) | Belgium | 1 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N154 | Created (Cancelled) | PME add-on | Phase III |  | Clinical Development Europe |  | R & D | Mahy P | [6 empty] | No | [23 empty] | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N157 | CSR Approved | Long Term Follow-up Study 4-16 years | Phase III | Open | Clinical Development USA | CNS | R & D | [7 empty] | No | A Multi-center, Open-label, Long-term, Follow-up Study of the Safety and Efficacy of Levetiracetam (UCB L059) in Children With Epilepsy | Indication for Neuro Psychiatry | Central Nervous System |  | 1997-06-13 |  | 1997-12-01 | 1997-12-01 | 1998-02-01 | 1998-01-26 | 2003-07-01 | 2003-07-28 | 2006-06-30 | 2006-01-25 | 2003-03-24 | 2006-05-04 | 2006-06-06 | 2006-06-28 | 2004-01-01 | 2007-10-25 | Canada, Mexico, United States of America | Canada (LPLV), Mexico (LPLV), United States of America (LPLV) | Canada, Mexico, United States of America | 24 | 53 | 50 | 24 | 24 | 0 | 239 | 0 | 0 | 239 | 0 | 163 | 76
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N159 | CSR Approved | Pivotal Efficacy & Safety POS Study 4-16 years | Phase III | Double Blind | Clinical Development USA | CNS | R & D | Campbell K | [6 empty] | No | Evaluation of the Efficacy and Tolerability of Levetiracetam Add-on Treatment in Refractory Pediatric Patients With Partial Onset Seizures: A 28-Week Double-blind, Placebo-controlled Multicenter Trial | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 1999-08-03 | 1999-09-01 | 1999-09-21 | 2000-06-13 | 2002-07-31 | 2001-01-29 | 2003-03-03 | 2001-03-05 | 2004-03-26 | 2001-04-16 | 2004-06-14 | 2001-07-23 | 2004-10-26 | Canada, United States of America | Canada (LPLV), United States of America (LPLV) | Canada, United States of America | 24 | 59 | 53 | 160 | 120 | 0 | 292 | 0 | 76 | 216 | 0 | 20 | 196
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N160 | Study Archived | Valproate steady state | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Pigeolet E | [6 empty] | Yes | Open label, one-way, one sequence cross-over study to assess the effect of valproate steady state administration on the single dose pharmacokinetics of levetiracetam (1500 mg, per os, 500 mg tablets) in healthy male and female volunteers | [6 empty] | 1999-02-19 | 1999-03-22 | 1999-03-24 |  |  | 1999-04-16 | 1999-04-18 | 1999-08-03 | 1999-09-10 |  |  | 1999-10-15 | 1999-11-25 | Belgium | Belgium (LPLV) | Belgium | 1 | 0 | 1 | 16 | 0 | 0 | 26 | 0 | 10 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N161 | Study Archived | Partial Seizures in Adults - Add on Therapy | Phase IV |  | UCB Pharma Global | Neurology | Global Medical Affairs | [7 empty] | No | Open label, multicentre study: evaluation of the efficacy and safety of Levetiracetam (LEV) (oral tablets of 500 mg b.I.d.) given for 16 weeks at individualized doses up to 3000 mg/day, add-on therapy in adults suffering from partial seizures. | [5 empty] | 2000-01-30 | 2000-03-16 | 2000-05-01 | 2000-07-17 |  |  | 2001-10-01 | 2001-09-24 | 2001-12-01 | 2001-11-30 |  |  | 2002-04-01 | 2002-09-02 | Australia | Australia (LPLV) | Australia | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N162 | Study Archived | Typical absence - pilot | Phase II | Open | Clinical Development Europe | CNS | R & D | Jacobs A | [6 empty] | No | A 3 to 16 week pilot open multicenter study, add-on or monotherapy, with 83, 125, 166, 250 and 500 mg levetiracetam oral tablets in bid administration (doses ranging from 10 to 60 mg/kg/day up to a maximum of 3 g/day) in children (4 - 16 years old) suffering from typical absences in childhood absence epilepsy (CAE) or juvenile absence epilepsy (JAE). | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2003-05-05: 1999-07-07; 2003-05-16: 2000-04-10; 2003-06-03: 2001-04-10; 2003-07-24: 2001-09-04; 2003-10-03: 2001-12-10; 2004-03-25: 2002-09-17 | Belgium, United Kingdom | Belgium (LPLV), United Kingdom (LPLV) | Belgium, United Kingdom | 3 | 0 | 3 | 10 | 5 | 5 | 0 | 0 | 0 | 6 | 0 | 0 | 6
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N164 | Study Archived | Typical absence - Follow-up | Phase III | Open | Clinical Development Europe | CNS | R & D | Jacobs A | [6 empty] | No | A 30-month safety and efficacy open multicenter follow-up study, add-on or monotherapy, with 83, 125, 166, 250 and 500 mg levetiracetam oral tablets in b.i.d. administration (individualized optimal dose with a maximum of 60 mg/kg/day or 3g/day) in children (4-17 years old at inclusion) suffering from typical absences in childhood absence epilepsy (CAE) or juvenile absence epilepsy (JAE). | Indication for Neuro Psychiatry | Central Nervous System |  |  | 1999-06-01 | 2003-05-05: 1999-10-26; 2003-05-16: 2000-05-26; 2003-06-03: 2001-05-21; 2003-07-24: 2003-05-28; 2003-10-03: 2003-09-08; 2003-12-17: 2003-11-06; 2004-03-25: 2004-01-12 | Belgium | Belgium (LPLV) | Belgium | 3 | 0 | 2 | 45 | 6 | 6 | 0 | 0 | 0 | 4 | 0 | 1 | 3
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N165 | CSR Approved | Bridging study (Tab) | Phase II | Double Blind | Clinical Development Japan | Clinical Development Japan | R & D | Osakabe T | [6 empty] | No | Bridging study of L059 (Levetiracetam) in patients with epilepsy be double blind method | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2003-10-03: 2004-05-16; 2003-12-17: 2004-12-03; 2004-03-25: 2006-12-13 | Japan | Japan (Created) |  | 83 | 0 | 0 | 210 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N166 | CSR Approved | Myoclonic Seizures | Phase III | Double Blind | Clinical Development Europe | CNS | R & D | Vandendriessche A | Beaman M |  | PAREXEL |  |  |  | No | A double-blind, multicenter, randomized, placebo-controlled study to evaluate the efficacy and safety of levetiracetam (LEV) (oral tablets of 500 mg b.i.d.) at a dose of 3000 mg/day as adjunctive treatment in adolescents ( 12 years) and adults ( 65 years) sufferingE from idiopathic generalized epilepsy with myoclonic seizures. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2000-11-30 | 2001-02-08 | 2001-01-30 | 2001-09-03 |  | 2004-05-17 | 2003-02-28 | 2004-12-13 | 2003-05-30 | 2005-02-22 |  | 2005-05-03 | 2003-08-31 | 2005-07-25 | Australia, Austria, Belgium, Canada, France, Germany, Ireland, Italy, Mexico, New Zealand, Poland, Spain, United Kingdom, United States of America | Australia (LPLV), Austria (LPLV), Belgium (LPLV), Canada (LPLV), France (LPLV), Germany (LPLV), Ireland (LPLV), Italy (LPLV), Mexico (LPLV), Netherlands (1st Site Initiation (Cancelled)), New Zealand (LPLV), Poland (LPLV), Spain (LPLV), Switzerland (1st Site Initiation (Cancelled)), United Kingdom (LPLV), United States of America (LPLV) | Australia, Austria, Belgium, Canada, France, Germany, Ireland, Italy, Mexico, New Zealand, Poland, Spain, United Kingdom, United States of America | 40 | 53 | 40 | 140 | 116 | 116 | 0 | 0 | 0 | 122 | 0 | 17 | 105
Yes | Not assigned | Managing Type | 1 | KEPPRA | Central Nervous System | N167 | Study Archived | Primary Generalized Seizures - follow-up study | Phase III | Open | Clinical Development USA | CNS | R & D | Wash M |  |  | Parexel |  |  |  | No | An open-label, multicenter, follow-up study to evaluate the safety and efficacy of levetiracetam (LEV) (oral tablets of 166, 250 or 500 mg b.i.d.) at individualized doses up to a maximum of 4000 mg/day (or 80 mg/kg/day for children and adolescents less than 50 kg), in children (>= 4 years old), adolescents and adults suffering from primary generalized seizures | Indication for Neuro Psychiatry | Central Nervous System |  | 2001-01-05 |  | 2000-10-10 | 2001-02-05 | 2000-12-01 | 2001-11-01 | 2005-02-28 |  | 2005-08-31 |  | 2005-11-30 | 2008-03-14 | 2007-02-15 | 2008-10-15 | 2007-02-28 | 2009-03-06 | Australia, Austria, Belgium, Canada, Estonia, France, Germany, Ireland, Italy, Mexico, New Zealand, Poland, Russian Federation, Spain, United Kingdom, United States of America | Australia (LPLV), Austria (LPLV), Belgium (LPLV), Canada (LPLV), Estonia (LPLV), France (LPLV), Germany (LPLV), Ireland (LPLV), Italy (LPLV), Mexico (LPLV), New Zealand (LPLV), Poland (LPLV), Russian Federation (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Austria, Belgium, Canada, Estonia, France, Germany, Ireland, Italy, Mexico, New Zealand, Poland, Russian Federation, Spain, United Kingdom, United States of America | 80 | 63 | 69 | 300 | 300 | 150 | 0 | 0 | 0 | 241 | 0 | 107 | 134
Yes | Not assigned | Managing Type | 1 | LERCANIDIPINE | not defined | SP0895 | Created | A double blind,multicenter randomised clinical trial on the | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | A double blind,multicenter randomised clinical trial on the efficacy and tolerability of lercanidipine on patients with mild to moderate essential hypertension | Essential Hypertension | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | LERCARNIDIPINE | Immunology | LE2503 | Final TFLs released | LER-25-03 Lercanidipine in hypertensive subjects | Phase IV | Double Blind | Affiliates - Germany |  | Affiliates - Germany | Ney U | [6 empty] | No | A double-blind, randomized, multicenter, placebo-controlled, parallel, dose-titration study to assess the efficacy of lercanidipine 10mg and 20mg once daily p.o. in hypertensive subjects (I or II WHO) with elevated body weight. | [5 empty] | 2003-05-05: 2003-12-12; 2003-05-16: 2004-05-19; 2003-06-03: 2005-10-08; 2003-07-24: 2005-08-31; 2003-10-03: 2005-11-30; 2003-12-17: 2006-07-27 | Germany | Germany (LPLV) | Germany | 18 | 21 | 18 | 200 | 180 | 0 | 208 | 0 | 14 | 194 | 1 | 28 | 165
Yes | Not assigned | Managing Type | 1 | Limaprost | not defined | SP0099 | Created (Cancelled) | LIMAPROST / OP-1206 - safety and tolerance of limaprost on p |  |  | UCB Pharma Global |  | UCB Pharma Global | Schaefer M | [6 empty] | No | Double-blind, randomized, placebo-controlled trial to test the safety and tolerance of limaprost on patients with intermittent claudication (Fontaine Stage II) | [22 empty] | 0 | 0 | 0 | 120 | 116 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Limaprost | not defined | SP0100 | Created | LIMAPROST - effects, safety and tolerance of Limaprost in pa |  |  | UCB Pharma Global |  | UCB Pharma Global | Schaefer M | [6 empty] | No | Double-blind, randomized, placebo-controlled study to investigate clinical effects, safety and tolerance of Limaprost in patients with thromboangiitis obliterans (Buerger's syndrom) | [22 empty] | 0 | 0 | 0 | 52 | 52 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Limaprost | not defined | SP0233 | Created | LIMAPROST - OP1206 (healthy volunteers) |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Single Dose Tolerance Study with ascending oral doses of OP-1206 in healthy male caucasian volunteers | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Limaprost | not defined | SP0242 | Created | OP-1206 - PAOD |  |  | UCB Pharma Global |  | UCB Pharma Global | Rogatti W | [6 empty] | No | Dosisfindungs- und Verträglichkeitsstudie zum Einfluß von OP 1206 oral auf die Hämodynamik und Mikrozirkulation bei Patienten mit AVK, Stadium IIb | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Limaprost | not defined | SP0257 | Created | OP-1206 - bei gesunden Probanden |  |  | UCB Pharma Global |  | UCB Pharma Global | Rogatti W | [6 empty] | No | Dosisfindungs- und Verträglichkeitsstudie zum Einfluß von OP1206 oral auf Hämodynamik und Mikrozirkulation bei gesunden Probanden | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | LORAZEPAM | not defined | SP0735 | Protoc. Summary Approved (Cancelled) | Lorazepam ODT single dose bioequivalence | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to evaluate the bioequivalence of a new formulation ODT of lorazepam 2 mg, administered with and without water, compared to a marketed lorazepam 2 mg tablet formulation, Ativan by Wyeth Laboratories |  |  |  | 2002-12-18 | 2002-12-18 | [14 empty] | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | LORTAB | not defined | SP0729 | Final TFLs released | APAP/HB ODT single dose bioequivalence | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to evaluate the bioequivalence of a unique new formulation (test) oral disintegrating tablet (ODT) of hydrocodone bitartrate 5 mg/acetaminophen 500 mg administered with and without water, compared to a marketed hydrocodone bitartrate 5 mg/acetaminophen 500 mg tablet (referenc e) Vicodin, by Abbott Laboratories |  |  |  | 2002-12-18 | 2002-12-18 | 2003-05-05: 2003-02-11; 2003-05-16: 2003-02-22; 2003-06-03: 2003-02-22; 2003-07-24: 2003-03-10; 2003-12-17: 2003-04-24 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 30 | 30 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | LORTAB | not defined | SP0849 | Created (Cancelled) | Preference study comparing hydrocodone bitartrate/acetaminop | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Papke A | [6 empty] | No | A randomized, multicenter, open-label, two-way crossover study to determine the preference of hydrocodone bitartrate/acetaminophen when administered as the orally disintegrating tablet compared to hydrocodone bitartrate/acetaminophen tablets in subjects with moderate to moderately severe pain after outpatient orthopedic surgery. | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Lovastatin | not defined | SP0609 | Protoc. Summary Approved (Cancelled) | Lovastatin in primary prevention on cardiovascular diseases | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Sierra J | [6 empty] | No | Prospective, observational study to evaluate treatment compliance with Lovastatin in primary prevention of cardiovascular disease. (Prelovas) |  |  |  | 2000-06-09 | 2000-06-09 | [17 empty] | 200 | 0 | 0 | 1200 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | LR-3280 | not defined | SP0068 | Protoc. Summary Approved | LR-3280 vs. Placebo in the Prevention of Restenosis in Patie | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Dommaschk J | [6 empty] | No | A study to evaluate the safety and efficacy of three doses of the antisense oligonucleotide LR-3280 versus placebo in the prevention of restonsis in patients undergoing PTCA and stent implantation | Prevention of Restenosis | Immunology |  | 1997-01-30 | 1997-01-30 | [14 empty] | United States of America | United States of America (Created) |  | 46 | 0 | 0 | 747 | 720 | 624 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | LR-3280 | not defined | SP0439 | Created | LR3280 - in the prevention of restenosis in patients undergo |  |  | UCB Pharma Global |  | UCB Pharma Global | Koch B | [6 empty] | No | A dose response trial to evaluate the efficacy and safety of three doses of the antisense oligonucleotide LR-3280 versus sham in the prevention of restenosis in patients undergoing PTCA | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | LR-3280 | not defined | SP0463 | Created | LR-3280 - intracoronary infusions in patients undergoing ele |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | A phase I study to evaluate the safety of intracoronary administration of c-myc (LR-3280) antisense oligomers | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | LR-3280 | not defined | SP0464 | Created | Drug Safety Trial Data. Study drug: LR-3280 |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: LR-3280 | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Magnesium Hydrogen Aspartate,Potassium Aspartate | not defined | SP0898 | Created | The observation of efficacy and safety of potassium magnesiu | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | The observation of efficacy and safety of potassium magnesium aspartate on patients with ventricular extrasystole | Ventricular Extrasystole | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Magnesium Hydrogen Aspartate,Potassium Aspartate | not defined | SP0899 | Created | Clinical investigation of the protective effects on arrhythm | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | Clinical investigation of the protection effects on arrhythmia by potassium magnesium aspartate and its possible anti-oxidative mechanisms | Arrhythmia | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Magnesium Hydrogen Aspartate,Potassium Aspartate | not defined | SP0900 | Created | Clinical investigation on the treatment of abnormal liver fu | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | Clinical investigation on the treatment of abnormal liver function with potassium magnesium aspartate | Abnormal Liver Function | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Meclozine | Immunology | G01051 | Study Archived | Bioequivalence | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S, Perreaux A |  |  | SGS |  |  |  | Yes | Randomized, monocentre, open label, two-way crossover, single dose bioequivalence study of meclozine 50 mg oral dose (2 x 25 mg new formulation tablets) with meclozine 50 mg oral dose (2 x 25 mg marketed tablets), in 24 healthy fasting male and female subjects. | Indication for Internal Medicine | Immunology |  |  | 2005-03-14 | 2003-05-05: 2005-03-14; 2003-05-16: 2005-04-26; 2003-06-03: 2005-04-28; 2003-07-24: 2005-05-25; 2003-10-03: 2005-06-27; 2003-12-17: 2005-10-20; 2004-03-25: 2005-11-14 | Belgium | Belgium (LPLV) | Belgium | 1 | 0 | 1 | 58 | 24 | 24 | 58 | 0 | 34 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | Mediject | not defined | SP0422 | Created (Cancelled) | MEDIJECT with immunocytochemical assessment of marker penetr |  |  | UCB Pharma Global |  | UCB Pharma Global | Gutwald U | [6 empty] | No | Pilot study of medi-ject drug delivery system with immunocytochemical assessment of marker penetration | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Metadate/Equasym | Central Nervous System | 04_624 | CSR Approved | Ongoing OL Safety Study (Australia) | Compassionate Use | Open | Global Medical Affairs Europe | CNS | Global Medical Affairs |  |  |  | Novotech |  |  |  | No | An Open Label Safety Study of Methylphenidate Modified Release (Methadate CD) in Children with Attention-deficit/Hyperactivity Disorder (ADHD) who participated in study MD1003-002 | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2003-05-05: 2003-01-17; 2003-05-16: 2003-03-10; 2003-07-03: 2005-11-17; 2003-07-24: 2005-10-24; 2003-08-18: 2006-01-30; 2003-10-17: 2006-02-27; 2004-03-22: 2006-04-14; 2004-03-25: 2009-02-17 | Australia | Australia (LPLV) | Australia | 19 | 0 | 17 | 178 | 140 | 0 | 165 | 0 | 26 | 139 | 0 | 45 | 94
Yes | Not assigned | Managing Type | 1 | Metadate/Equasym | Central Nervous System | C10304 | Created (Cancelled) | Equasym XL 40,50,60 mg | Phase III |  | Global Medical Affairs Europe | CNS | Global Medical Affairs | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 0 | 0 | 0 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Metadate/Equasym | Central Nervous System | C10306 | Created (Cancelled) | Psychiatric Adverse Events (FDA Request) | Phase II |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Metadate/Equasym | Central Nervous System | C10307 | CSR Approved | Equasym XL vs Medikinet single dose & Food effect | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Mccabe S, Perreaux A | [6 empty] | Yes | A single dose, four-way crossover, open, randomized, relative bioavailability study comparing two different modified release methylphenidate 20 mg oral capsule formulations under fasted and fed conditions, in 24 healthy male and female volunteers. | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-12-31 | 2005-12-12 | 2006-04-05 | 2006-03-31 | 2006-05-15 | 2006-06-08 | 2006-05-29 | 2006-06-13 | 2006-07-15 | 2006-07-07 | 2006-08-15 | 2006-08-25 | 2006-09-30 | 2006-09-22 | 2006-10-30 | 2006-11-30 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 50 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Metadate/Equasym | Central Nervous System | C10308 | Created (Cancelled) | MHRA request survey | Non Interventional Study - Prospective |  | Global Medical Affairs Europe | GMA Neurology / Psychiatry | Global Medical Affairs | [7 empty] | No |  |  |  |  | 2006-02-20 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Metadate/Equasym | Central Nervous System | C10310 | Created (Cancelled) | Equasym XL efficacy in reaching clinically significant impro |  |  | Affiliates |  | Affiliates | Verboven D | [6 empty] | No | [23 empty] | 70 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Methyltestosterone | not defined | SP0776 | Created (Cancelled) | Bioequivalence of Virilon methyltestosterone and Testred | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | Bioequivalence of Virilon methyltestosterone and Testred | [19 empty] | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 44 | 44 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Metoclopramide HCL | not defined | SP0693 | Final TFLs released | Metoclopramide ODT single dose bioavailability | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Kastenholz K | [6 empty] | No | A pharmacokinetic study to compare the bioavailability of a unique new formulation (test), orally disintegrating tablet (ODT) of metoclopramide HCl EQ 10 mg base to a marketed immediate release metoclopramide formulation (reference), Reglan EQ 10 mg base by A H Robins |  |  |  | 2002-01-03 | 2002-01-03 | 2003-05-05: 2002-09-04; 2003-05-16: 2002-10-12; 2003-06-03: 2002-10-12; 2003-07-24: 2002-10-27; 2003-12-17: 2003-01-10 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 21 | 21 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Metoclopramide HCL | not defined | SP0751 | Created (Cancelled) | Metoclopramide 10 mg change in manufacturing site | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A single dose bioequivalence study comparing a 10 mg metoclopramide HCl tablet, Reglan (R), manufactured by Schwarz Pharma Manufacturing, Inc., Seymour, IN (test) with the 10 mg metoclopramide HCl tablet, Reglan (R), manufactured by A.H. Robins, Richmond, VA (reference) when given in the fasted sta te | [19 empty] | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 18 | 18 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Metoclopramide HCL | not defined | SP0759 | Protoc. Summary Approved | metaclopramide ODT single dose bioavailability - new formula | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to determine the bioavailability of a unique new formulation (test), orally disintegrating tablet (ODT) of metoclopramide HCl 10 mg base and a marketed immediate release metoclopramide formulation (reference), Reglan 10 mg base by Schwarz Pharma, Inc. |  |  |  | 2003-06-02 | 2003-06-02 | [14 empty] | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 21 | 21 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Metoclopramide HCL | not defined | SP0850 | Created | Pharmacokinetics of metoclopramide ODT compared to Reglan® t | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A randomized open-label, two-way crossover study to determine the pharmacokinetics of metoclopramide when administered as the orally disintegrating tablet compared to Reglan® tablets in subjects with diabetic gastroparesis | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Metopimazine | not defined | SP0748 | Final TFLs released | Metopimazine-SPF-02-11-2 nausea and vomiting induced by chem | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Delgado A | [6 empty] | No | SPF-02-11-02: Efficiency assessment of metopimazine + methylprednisolone versus ondansetron + methylprednisolone for prevention of delayed nausea and emesis induced by moderately to severe emetogenic chemotherapy. |  |  |  | 2003-04-14 | 2003-04-14 | 2003-05-05: 2002-11-29; 2003-05-16: 2003-02-28; 2003-06-03: 2003-07-17; 2003-07-24: 2003-07-14; 2003-12-17: 2003-11-24 | France | France (Created) |  | 1 | 0 | 0 | 100 | 100 | 100 | 0 | 0 | 0 | 87 | 0 | 0 | 87
Yes | Not assigned | Managing Type | 1 | Metopimazine | not defined | SP0749 | Protoc. Summary Approved | Metopimazine-SPF 02-11-3 emesis and nausea | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Guesnier L | [6 empty] | No | SPF 02-11-3: assessment of the relative and the absolute bioavailability of two forms of metopimazine |  |  |  | 2003-02-25 | 2003-02-25 | [17 empty] | 1 | 0 | 0 | 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Metopimazine | not defined | SP0750 | Created (Cancelled) | Metopimazine-SPF-02-12-4 emesis and nausea | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Delgado A | [6 empty] | No | - SPF 02-11-4: Efficiency assessment of metopimazine versus ondansetron for prevention of delayed nausea and emesis induced by moderately emetogenic chemotherapy. | [22 empty] | 1 | 0 | 0 | 200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Metopimazine | not defined | SP0767 | Created (Cancelled) | VOGALENE Metopimazine antiemetic drug vomiting | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Delgado A | [6 empty] | No | Evaluation of efficacy of metopimazine in the prevention of nausea and vomiting inducted by morphinic drugs | [19 empty] | France | France (Created) |  | 13 | 0 | 0 | 300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Metopimazine | not defined | SP0920 | Created | Metopimazine and driving capability | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Joubert J | [6 empty] | No | Metopimazine effect on simulated driving in young healthy subjects. A double blind diazepam controlled study. | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Midazolam HCL | not defined | SP0856 | Study Archived | single-site, randomized, 2-period cross-over trial to determ | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | Yes | A single-site, randomized, two-period cross-over trial to determine the absolute bioavailability, pharmacokinetics, safety and local tolerability of 5mg nasality administered Midozolam in healthy male volunteers. | Epilepsy | Central Nervous System |  | 2005-01-31 | 2005-01-27 | 2003-05-05: 2005-03-07; 2003-05-16: 2005-04-26; 2003-06-03: 2005-04-28; 2003-07-24: 2005-06-07; 2003-10-03: 2005-06-30; 2003-12-17: 2005-09-06; 2004-03-25: 2005-12-14 | Germany | Germany (Created) |  | 1 | 0 | 0 | 18 | 18 | 18 | 40 | 20 | 0 | 18 | 0 | 1 | 17
Yes | Not assigned | Managing Type | 1 | Midazolam HCL | not defined | SP0870 | Protocol Approved (Cancelled) | Randomized 3 way crossover dose proportionality of 3 differe | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | Yes | Single site double-blind, randomized, three period cross-over trial to determine the dose proportionality pharmacokinetics safety and local tolerability of 4mg, 8mg and 12mg intranasally adminstered midazolam in healthy male subjects | Epilepsy | Central Nervous System |  | 2005-08-26 | 2005-08-26 | 2003-05-05: 2005-09-20 | Germany | Germany (Created) |  | 1 | 0 | 0 | 24 | 24 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Minzasolmin | New Medicines | UP0023 | Study Archived | Open-label, two-part NPT200-11 14C Mass Balance Stiudy | Phase I | Open | GED | Neurology | GED |  |  | PRA | PRA SPI | No | Yes | adults | No | SINGLE-center, OPEN-LABEL, SINGLE DOSE STUDY OF THE EXCRETION balance, pharmacokinetics AND METABOLISM of 14C‑labeled UCB0599 ([R]‑NPT200-11) and UCB2713 ([S]‑NPT200-11) | Parkinson's disease | Central Nervous System |  | 2015-08-14 | 2015-08-17 |  | 2015-11-02 | 2015-11-27 | 2015-11-30 | 2016-01-06 | 2015-12-14 |  | 2016-02-27 |  | 2016-04-22 |  | 2016-07-07 |  | 2016-10-24 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 12 | 12 | 12 | 40 | 0 | 27 | 13 | 0 | 0 | 13
Yes | Not assigned | Managing Type | 1 | Minzasolmin | New Medicines | UP0030 | Study Archived | SAFETY/TOLERABILITY IN ELDERLY HEALTHY SUBJECTS AND PD PATIE | Phase I | Double Blind | GED | Neurology | UCB Pharma Global | Van Den Steen B | Cain D | Parexel | PAREXEL | No | Yes | geriatrics | Yes | UP0030 A DOSE ESCALATION STUDY TO ASSESS THE SAFETY/TOLERABILITY AND PHARMACOKINETICS OF UCB0599 IN OLDER HEALTHY SUBJECTS AND SUBJECTS WITH PARKINSON’S DISEASE AND TO EVALUATE THE FOOD EFFECT AND DRUG-DRUG INTERACTION FOR UCB0599 IN HEALTHY SUBJECTS Phase 1 | Parkinson's disease (early); Patients and Healthy Volunteers | Central Nervous System; Central Nervous System |  |  |  |  | 2016-09-27 | 2016-12-20 | 2017-03-08 | 2017-07-13 | 2018-01-18 | 2017-09-29 | 2018-05-18 | 2017-10-27 | 2018-08-22 | 2017-11-24 | 2018-11-16 | 2018-04-04 | 2019-01-29 | Germany | Germany (LPLV) | Germany | 3 | 1 | 1 | 64 | 64 | 64 | 393 | 0 | 328 | 65 | 0 | 43 | 22
Yes | Not assigned | Managing Type | 1 | MITOMYCIN | not defined | SP0783 | Created | Mitem PMS | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Gundlach C | [6 empty] | No | Post Marketing Surveillance with Mitem | Bladder cancer | Oncology | [20 empty] | 500 | 0 | 0 | 1500 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Mizolastine | not defined | SP0482 | Protoc. Summary Approved | Zolim AWB - bei Patienten mit allergischer Rhinitis und/oder | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Plum C | [6 empty] | No | Zolim AWB | Allergy | Immunology |  | 1998-06-19 | 1998-06-19 | [17 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Mizolastine | not defined | SP0575 | Created | Zolim Anwendungsbeobachtung 2000 | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Plum C | [6 empty] | No | Zolim AWB | Allergy | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | MOGRIL | not defined | SP0255 | Created | ERGO-SANOL - bei Patienten mit episodischen Spannungskopfsch |  |  | UCB Pharma Global |  | UCB Pharma Global | Babst H | [6 empty] | No | ERGO-SANOL - bei Patienten mit episodischen Spannungskopfschmerzen | Systemic Lupus Erythematosus | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | MOGRIL | not defined | SP0266 | Created | Pilotstudie - Bioverfügbarkeit/Pharmakokinetik - Kapsel - 6 |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Pilotstudie zur Evaluierbarkeit der Bioverfügbarkeit und Pharmakokinetik einer neu entwickelten Kapsel-Zubereitung von Ergotamin an sechs gesunden, Freiweilligen | Migraine prophylaxis | Central Nervous System | [20 empty] | 0 | 0 | 0 | 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Molsidomine | not defined | SP0387 | Created | MOLSIDOMIN-RETARD - after morning versus evening application |  |  | UCB Pharma Global |  | UCB Pharma Global | Behmer O | [6 empty] | No | Pharmacokinetics of sustained-release molsidomine after morning versus evening application in healthy subjects | [22 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | PD0004 | Study Archived | Pain in Parkinson's disease | Phase IV | Double Blind | UCB Pharma Global | GMA Neurology / Psychiatry | Global Medical Affairs | Nilius S | Beinhauer-Zellenka U | PRA | PRA | No | No | adults | No | A multicenter, multinational, double-blind, placebo-controlled, two-arm study to evaluate the efficacy of Rotigotine on Parkinson´s disease associated pain | Parkinson's disease | Central Nervous System |  | 2012-04-20 | 2012-04-20 |  | 2012-07-05 | 2012-11-16 | 2012-11-19 | 2014-08-15 | 2013-07-25 |  | 2014-01-30 |  | 2014-05-07 |  | 2014-07-24 |  | 2014-10-25 | Germany, Poland, Slovakia, United States of America | Germany (LPLV), Hungary (1st Site Initiation (Cancelled)), Poland (LPLV), Slovakia (LPLV), South Korea (1st Site Initiation (Cancelled)), United States of America (LPLV) | Germany, Poland, Slovakia, United States of America | 92 | 31 | 16 | 481 | 401 | 382 | 84 | 0 | 16 | 68 | 0 | 12 | 56
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | PD0005 | Study Archived | Mood in Parkinson's Disease | Phase IV | Double Blind | UCB Pharma Global | GMA Neurology / Psychiatry | Global Medical Affairs | Nilius S | Beinhauer-Zellenka U | PRA | PRA | No | No | adults | No | A multi-center, multinational, double-blind, placebo-controlled, three-arm, Phase 4 study to evaluate the efficacy of Rotigotine on Parkinson´s disease associated apathy, motor symptoms and mood | Parkinson's disease | Central Nervous System |  | 2012-04-20 | 2012-05-03 |  | 2012-07-17 | 2013-01-02 | 2013-02-05 | 2014-09-02 | 2013-08-23 |  | 2014-03-04 |  | 2014-09-08 |  | 2014-12-08 |  | 2015-01-28 | Austria, Hungary, Poland, Slovakia, Spain, United States of America | Austria (LPLV), Hungary (LPLV), Poland (LPLV), Slovakia (LPLV), Slovenia (1st Site Initiation (Cancelled)), Spain (LPLV), United States of America (LPLV) | Austria, Hungary, Poland, Slovakia, Spain, United States of America | 120 | 44 | 30 | 600 | 504 | 480 | 158 | 0 | 36 | 122 | 0 | 23 | 99
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | PD0006 | Created (Cancelled) | NIS invest. Neupro in daily clin. pract. in Hung. PD patient | Non Interventional Study - Prospective |  | Global Medical Affairs Europe |  | Affiliates | Irrgang V, Joeres L |  | PRA | PRA |  |  |  | No |  |  |  |  | 2012-07-09 | [18 empty] | 20 | 0 | 0 | 200 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | PD0010 | Created (Cancelled) | OL Study to invest PK of L-dopa +/- Roti.in PD subj. gastrop | Phase IV | Open | Clinical Development Europe |  | Clinical Development Europe | Will E | Copetti C | PRA | SPI PRA |  |  | adults | No |  | Parkinson's disease (advanced) | Central Nervous System |  | 2015-05-29 | [18 empty] | 5 | 0 | 0 | 50 | 40 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | PD0011 | CSR Approved | Bioequivalence in Chinese between 2 different formulations | Phase I | Open | GED |  | GED | Guo J | Grose-Hodge R | N/A | PRA | No | No | adults | Yes | SINGLE-SITE, OPEN-LABEL, RANDOMIZED, CROSS-OVER STUDY IN HEALTHY CHINESE SUBJECTS TO EVALUATE THE BIOEQUIVALENCE OF SINGLE-DOSE ROTIGOTINE TRANSDERMAL PATCH (2MG/24H) COMPARING 2 DIFFERENT FORMULATIONS |  |  | PD0011 is a "sister" study of SP1049 |  |  |  | 2013-08-08 | 2014-01-09 | 2014-02-17 | 2014-02-11 | 2014-06-23 |  | 2014-07-17 |  | 2014-08-18 |  | 2014-10-20 |  | 2015-01-12 | China | China (LPLV) | China | 1 | 1 | 1 | 50 | 50 | 50 | 73 | 0 | 23 | 50 | 0 | 3 | 47
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | PD0012 | Study Archived | BE Study of New RT Neupro adhesiveness (Germany) | Phase I | Open | GED |  | GED | Mollet M | Mccabe S | PRA | SPI PRA | No | Yes | adults | Yes | SINGLE-SITE, OPEN-LABEL, RANDOMIZED, CROSSOVER STUDY IN HEALTHY SUBJECTS TO EVALUATE BIOEQUIVALENCE OF ROTIGOTINE TRANSDERMAL PATCHES (2MG/24H) FROM 2 DIFFERENT MANUFACTURING SITES | Parkinson's disease | Central Nervous System |  | 2014-08-30 | 2014-08-29 |  | 2014-10-21 | 2015-01-12 | 2015-01-13 | 2015-02-05 | 2015-02-26 |  | 2015-03-16 |  | 2015-07-24 |  | 2015-08-17 |  | 2015-11-06 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 50 | 50 | 36 | 131 | 0 | 81 | 50 | 0 | 2 | 48
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | PD0013 | Study Archived | Neupro partner to L-dopa in elderly pts with Parkinson's Dis | Non Interventional Study - Prospective | Open | GCSO | Neurology | GCSO | Kleine E | Bonny M | PRA | SPI PRA | No | No | other | No | A MULTICENTER NONINTERVENTIONAL STUDY TO EVALUATE THE EFFECTIVENESS OF NEUPRO® (ROTIGOTINE TRANSDERMAL PATCH) AND LEVODOPA COMBINATION THERAPY IN PATIENTS WITH PARKINSON’S DISEASE (NEUPART) | Parkinson's disease | Central Nervous System |  | 2014-04-03 | 2014-07-08 |  | 2014-07-08 | 2014-10-01 | 2014-09-29 | 2016-05-02 | 2015-11-04 |  | 2016-06-01 |  | 2016-07-28 |  | 2016-11-02 |  | 2016-12-15 | France, Germany, Italy, Spain, United Kingdom | France (LPLV), Germany (LPLV), Italy (LPLV), Spain (LPLV), United Kingdom (LPLV) | France, Germany, Italy, Spain, United Kingdom | 60 | 54 | 41 | 170 | 170 | 138 | 195 | 0 | 0 | 195 | 0 | 65 | 130
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | PD0017 | Study Archived | Compare adhesiveness | Phase I | Double Blind | GED |  | GED | Mollet M | Mccabe S | PRA | SPI PRA |  |  |  | Yes | A SINGLE-CENTER, DOUBLE-BLIND STUDY TO COMPARE THE ADHESIVENESS OF TWO DIFFERENT ROTIGOTINE PATCH FORMULATIONS IN HEALTHY SUBJECTS | Parkinson's disease; Restless legs syndrome | Central Nervous System; Central Nervous System |  | 2012-07-19 |  | 2003-05-05: 2012-08-27; 2003-05-16: 2012-10-12; 2003-06-03: 2012-10-12; 2003-07-24: 2012-12-06; 2003-10-03: 2012-12-21; 2003-12-17: 2013-02-19; 2004-03-25: 2013-04-18 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 52 | 52 | 50 | 108 | 0 | 56 | 52 | 0 | 2 | 50
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | PD0018 | Study Archived | Phase I Adhesiveness Study of Large Size Patch RTG improved | Phase I | Double Blind | UCB Pharma Global | Clinical Pharmaco | R & D | Goldammer N | Beinhauer-Zellenka U | PRA | SPI PRA | No | Yes | adults | Yes | A MULTICENTER, RANDOMIZED, DOUBLE-BLIND, 2-WAY CROSS-OVER STUDY TO COMPARE THE ADHESIVENESS OF 2 DIFFERENT ROTIGOTINE PATCH FORMULATIONS IN SUBJECTS WITH PARKINSON’S DISEASE | Parkinson's disease | Central Nervous System |  | 2014-02-10 | 2014-02-10 |  | 2014-04-17 | 2014-08-29 | 2014-09-12 | 2014-12-01 | 2014-11-06 |  | 2014-12-01 |  | 2015-01-21 |  | 2015-02-04 |  | 2015-05-12 | Germany | Germany (LPLV) | Germany | 1 | 11 | 10 | 50 | 38 | 38 | 59 | 0 | 2 | 57 | 0 | 1 | 56
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | PD0025 | Created (Cancelled) | Phase I Adhesiveness Study of Small Site Patch RTG Imroved R | Phase I |  | UCB Pharma Global | Clinical Pharmaco | R & D | Mollet M | Mccabe S | PRA | SPI PRA |  |  |  | No |  | Parkinson's disease | Central Nervous System |  | 2014-06-30 | [18 empty] | 1 | 0 | 0 | 50 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | PD0029 | Created (Cancelled) | Randomized, placebo-controlled efficacy of Rotigotine | Phase IV |  | Clinical Development USA | CNS | Clinical Development USA | Heinzen L | Smit R | PRA | SPI PRA |  |  |  | No |  | Parkinson's disease (advanced) | Central Nervous System |  | 2015-06-20 | [18 empty] | 50 | 0 | 0 | 400 | 336 | 302 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | PD0031 | Created (Cancelled) | Pilot study using the Parkinson Kinetigraph (pkg | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Bare S | Baukens C | Parexel | SPI PRA |  |  | adults | No |  | Parkinson's disease | Central Nervous System |  | 2016-08-01 | [18 empty] | 3 | 0 | 0 | 25 | 22 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | RL0002 | Study Archived | Neuro Saliva/Plasma concentr. Steady-State in healthy males | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Whitesides J | [6 empty] | Yes | A Single Site, Open Label Study in Healthy Male Subjects to Compare Rotigotine Saliva and Plasma Concentrations in Steady-State after Multiple-Dose Application of Rotigotine Transdermal Patch. | Restless legs syndrome | Central Nervous System |  | 2011-04-21 | 2011-05-31 |  | 2011-08-04 |  | 2011-09-15 | 2011-10-06 | 2011-10-28 | 2011-11-24 | 2011-12-02 | 2012-01-23 | 2012-03-08 | 2012-03-12 | 2012-03-30 | 2012-05-07 | 2012-07-03 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 30 | 14 | 12 | 16 | 0 | 2 | 14 | 0 | 0 | 14
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | RL0003 | Study Archived | Phase 3b double-blind, randomized, placebo-controlled study | Phase III | Double Blind | Global Medical Affairs US | CNS | Clinical Development USA | Schollmayer E, Smit R | Kime J | N/A | PRA |  |  | adults | No | A Phase 3B, Double-Blind, Randomized, Placebo-Controlled Study of Rotigotine and Its Effect on All-Day Functioning and Quality of Life in Subjects with Moderate to Severe Idiopathic Restless Legs Syndrome (RL0003) | Restless legs syndrome | Central Nervous System |  | 2011-09-10 | 2011-09-09 |  | 2011-11-21 | 2012-04-06 | 2012-04-03 | 2012-12-13 | 2013-02-08 |  | 2013-04-30 |  | 2013-06-03 |  | 2013-07-26 |  | 2013-11-19 | United States of America | United States of America (LPLV) | United States of America | 20 | 19 | 18 | 200 | 144 | 136 | 230 | 0 | 80 | 150 | 0 | 15 | 135
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0502 | Final TFLs released | SPM 962/Rotigotine: Single dose bioavailability of SPM962 fr | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Horstmann R, Whitesides J | [6 empty] | No | Pilot study for the comparative bioavailability and dose proportionality of one and two silicone based and one acrylic based transdermal preparation of N-0923 in a 3-way cross-over design in 12 healthy male subjects. | [5 empty] | 2003-05-05: 1999-01-11; 2003-12-17: 1999-12-01 | Germany | Germany (Created) |  | 1 | 0 | 0 | 14 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0503 | CSR Approved | SPM 962/Rotigotine: Multiple dose pharmacokinetics and pharm | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Horstmann R, Whitesides J | [6 empty] | No | Multiple dose pharmacokinetics anf pharmacodynamics of N-0923 and the metabolites during 7 days of q.d. administration to 24 healthy male volunteers. | [5 empty] | 2003-05-05: 1999-03-24; 2003-12-17: 1999-08-01; 2004-03-25: 2000-02-16 | Germany | Germany (Created) |  | 1 | 0 | 0 | 30 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0506 | CSR Approved | US: SPM962 in subjects wiith early stage idiopathic Parkinso | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Poole K, Whitesides J | [6 empty] | No | A multicenter, randomized, double-blind, placebo controlled, parallel group, dose ranging study to access the efficacy, safety and tolerability of escalating transdermal doses of SPM 962 in subjects with early stage parkinson 's diseases. | Parkinson's disease (early) | Central Nervous System |  | 1999-08-06 | 1999-08-06 | 2003-05-05: 1999-08-27; 2003-05-16: 1999-11-29; 2003-06-03: 2000-07-13; 2003-07-24: 2000-11-20; 2004-03-25: 2004-08-04 | Canada, Estonia, India, Latvia, Lithuania, Poland, South Africa, Ukraine, United States of America | Canada (Created), Estonia (Created), India (Created), Latvia (Created), Lithuania (Created), Poland (Created), South Africa (Created), Ukraine (Created), United States of America (Created) |  | 75 | 0 | 0 | 300 | 225 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0511 | CSR Approved | Europe: SPM962 TDS in subjects with advanced stage idiopathi | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Poole K, Whitesides J | [6 empty] | No | Multicenter, double-blind, randomized, placebo-controlled, 4-arm, parallel-group trial of SPM 962 TDS in subjects with advanced stage idiopathic Parkinson's Disease. | Parkinson's disease (advanced) | Central Nervous System |  | 1999-05-04 | 1999-05-04 | 2003-05-05: 1999-09-09; 2003-05-16: 1999-11-17; 2003-07-24: 2000-09-14; 2004-03-25: 2004-04-20 | Croatia, Czech Republic, Estonia, Finland, Germany, Ireland, Latvia, Lithuania, Netherlands, Poland, South Africa, Sweden, United Kingdom | Croatia (Created), Czech Republic (Created), Estonia (Created), Finland (Created), Germany (Created), Ireland (Created), Latvia (Created), Lithuania (Created), Netherlands (Created), Poland (Created), South Africa (Created), Sweden (Created), United Kingdom (Created) |  | 0 | 0 | 0 | 320 | 290 | 260 | 0 | 0 | 0 | 334 | 7 | 53 | 274
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0512 | CSR Approved | US: SPM962 in subjects with early stage idiopathic Parkinson | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Neilson S, Whitesides J | [6 empty] | No | A multi-center, multinational, phase III, randomized, double-blind, placebo controlled trial, of the efficacy and safety of the rotigotine CDS patch in subjects with early stage, idiopathic Parkinson's disease (Part I), and an open-label extension to assess the safety of long-term treatment of rotig otine CDS (Part II). | Parkinson's disease (early) | Central Nervous System |  | 2001-05-18 | 2001-05-18 | 2003-05-05: 2001-09-27; 2003-05-16: 2001-11-20; 2003-06-03: 2002-08-26; 2003-07-24: 2003-04-11; 2004-03-25: 2004-07-29 | Canada, United States of America | Canada (Created), United States of America (Created) |  | 35 | 0 | 0 | 300 | 250 | 240 | 0 | 0 | 0 | 277 | 4 | 50 | 223
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0513 | Study Archived | Europe and ROW: Rotigotine CDS in subjects with early stage | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Raetz M, Whitesides J | Bonny M | [5 empty] | No | A multi-centre, multinational, phase III randomised double blind double-dummy 3-arm parallel group, placebo- and ropinirole-controlled trial of the efficacy and safety of the rotigotine CDS patch in subjects with early stage idopathic Parkinson`s disease. | Parkinson's disease (early) | Central Nervous System |  | 2001-06-29 | 2001-06-29 | 2003-05-05: 2001-08-15; 2003-05-16: 2002-03-06; 2003-06-03: 2002-11-05; 2003-07-24: 2003-08-26; 2003-10-03: 2003-10-06; 2003-12-17: 2004-03-19; 2004-03-25: 2004-09-10 | Australia, Austria, Belgium, Croatia, Czech Republic, Denmark, Finland, France, Germany, Hungary, Israel, Italy, Netherlands, New Zealand, Norway, Poland, South Africa, Spain, Sweden, Switzerland, United Kingdom | Australia (Created), Austria (Created), Belgium (Created), Croatia (Created), Czech Republic (Created), Denmark (Created), Finland (Created), France (Created), Germany (Created), Hungary (Created), Israel (Created), Italy (Created), Netherlands (Created), New Zealand (Created), Norway (Created), Poland (Created), South Africa (Created), Spain (Created), Sweden (Created), Switzerland (Created), United Kingdom (Created) |  | 82 | 0 | 0 | 540 | 470 | 450 | 0 | 0 | 0 | 561 | 3 | 147 | 411
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0514 | Created (Cancelled) | US: SPM962 in subjects with advanced stage idiopathic Parkin | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Poole K, Whitesides J | [6 empty] | No | not available (DMCD) | Parkinson's disease (advanced) | Central Nervous System | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0515 | Study Archived | EU/ Rest of world advanced comperator contol trial in parkin | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Driver D, Whitesides J | [6 empty] | No | A multi centre, multi national, phase III ranomised double blind, double dummy, 3 arm parallel roup, placebo and pramipexole controlled trial of the efficacy and safety of rotigotine patch in subjects with advanced stage idiopathic parkinson's disease who are not well controlled on levo dopa. | Parkinson's disease (advanced) | Central Nervous System |  | 2003-02-03 | 2003-02-03 | 2003-05-05: 2003-12-05; 2003-05-16: 2004-03-02; 2003-06-03: 2004-11-12; 2003-07-24: 2005-07-12; 2003-10-03: 2005-09-29; 2003-12-17: 2006-02-03; 2004-03-25: 2006-02-23 | Australia, Austria, Croatia, Czech Republic, Finland, France, Germany, Hungary, Israel, Italy, New Zealand, Norway, Poland, South Africa, Spain, Sweden, United Kingdom | Australia (Created), Austria (Created), Croatia (Created), Czech Republic (Created), Finland (Created), France (Created), Germany (Created), Hungary (Created), Israel (Created), Italy (Created), New Zealand (Created), Norway (Created), Poland (Created), South Africa (Created), Spain (Created), Sweden (Created), United Kingdom (Created) |  | 88 | 0 | 0 | 590 | 470 | 450 | 366 | 0 | 0 | 507 | 3 | 74 | 430
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0516 | Study Archived | Open label extension trial for SP515 (Rotigotine in Advanced | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Raetz M, Whitesides J | Bonny M | [5 empty] | No | A multi-center, multinational, phase 3, open-label extension trial to assess the safety of long term treatment of rotigotine patch in subjects with advanced-stage, idiopathic Parkinson's disease who are not well controlled on levodopa | Parkinson's disease (advanced) | Central Nervous System |  | 2004-03-04 | 2004-03-04 | 2003-05-05: 2004-03-08; 2003-05-09: 2004-08-15; 2003-05-16: 2004-08-30; 2003-06-03: 2005-07-01; 2003-07-24: 2008-12-19; 2003-10-03: 2009-05-15; 2003-12-17: 2009-09-28; 2004-03-25: 2010-04-23 | Australia, Austria, Croatia, Czech Republic, Finland, France, Germany, Hungary, Israel, Italy, New Zealand, Norway, Poland, South Africa, Spain, Sweden, United Kingdom | Australia (1st Site Initiation), Austria (1st Site Initiation), Croatia (1st Site Initiation), Czech Republic (1st Site Initiation), Finland (1st Site Initiation), France (1st Site Initiation), Germany (1st Site Initiation), Hungary (1st Site Initiation), Israel (1st Site Initiation), Italy (1st Site Initiation), New Zealand (1st Site Initiation), Norway (1st Site Initiation), Poland (1st Site Initiation), South Africa (1st Site Initiation), Spain (1st Site Initiation), Sweden (1st Site Initiation), United Kingdom (1st Site Initiation) | Australia, Austria, Croatia, Czech Republic, Finland, France, Germany, Hungary, Israel, Italy, New Zealand, Norway, Poland, South Africa, Spain, Sweden, United Kingdom | 74 | 63 | 0 | 360 | 360 | 360 | 0 | 0 | 0 | 395 | 0 | 206 | 189
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0533 | CSR Approved | Maximum tolerated dose study (advanced PD patients) - Dr. T. | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Poole K, Whitesides J | [6 empty] | No | Maximum tolerated dose study (advanced PD patients) - Dr. T. Chase | Parkinson's disease (advanced) | Central Nervous System |  |  |  | 2004-03-25: 2003-05-06 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0534 | CSR Approved | Safety and tolerability study (early PD patients) - Dr. L. K | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Poole K, Whitesides J | [6 empty] | No | Safety and tolerability study (early PD patients) - Dr. L. Kirby | Parkinson's disease (early) | Central Nervous System |  |  |  | 2004-03-25: 2004-09-10 | United States of America | United States of America (Created) |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0535 | CSR Approved | Safety and tolerability study (early PD patients) - Dr. M. L | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Poole K, Whitesides J | [6 empty] | No | Safety and tolerability study (early PD patients) - Dr. M. Lew | Parkinson's disease (early) | Central Nervous System |  | 1999-05-01 | 1999-05-01 | 2004-03-25: 2003-06-03 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 3 | 3 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0540 | CSR Approved | SPM962 in subjects with early stage , idiopathic Parkinson D | Phase II | Single Blind | UCB Pharma Global |  | UCB Pharma Global | Horstmann R, Whitesides J | [6 empty] | No | A multicenter, single-blind, dose-escalation study to access potential benefits and safety limitations of transdermal doses of SPM 962 in subjects with early stage, idiophatic, Parkinson's Disease. | Parkinson's disease (early) | Central Nervous System |  |  |  | 2003-05-05: 1999-06-15; 2004-03-25: 2001-04-04 | Estonia, Latvia, Lithuania, South Africa | Estonia (Created), Latvia (Created), Lithuania (Created), South Africa (Created) |  | 7 | 0 | 0 | 31 | 31 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0542 | Created (Cancelled) | Ease of patch use (placebo) at three defined sites in advanc | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Poole K, Whitesides J | [6 empty] | No | Ease of patch use (placebo) at three defined sites in advanced parkinsonian patients | Parkinson's disease (advanced) | Central Nervous System | [20 empty] | 1 | 0 | 0 | 48 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0579 | Protoc. Summary Approved (Cancelled) | SPM 962/Rotigotine: Pharmacokinetics of SPM 962 - different | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Whitesides J, Person (Migrated From Sports) U | [6 empty] | No | SPM 962/Rotigotine: Pharmacokinetics of SPM 962 - different patch sizes |  |  |  | 2001-03-12 | 2001-03-12 | [17 empty] | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0581 | Final TFLs released | SPM 962/Rotigotine: Bioequivalence evaluation of SPM 962 (Ba | Phase I | Single Blind | UCB Pharma Global |  | UCB Pharma Global | Cawello W, Whitesides J | [6 empty] | No | SPM 962/Rotigotine: Bioequivalence evaluation of SPM 962 (Base vs Hydrochloride) |  |  |  | 2000-03-30 | 2000-03-30 | 2003-05-05: 2000-05-19; 2003-05-16: 2000-07-03; 2003-06-03: 2000-07-15; 2003-07-24: 2000-08-01; 2003-12-17: 2000-09-22 | Germany | Germany (Created) |  | 1 | 0 | 0 | 30 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0591 | CSR Approved | SPM 962 Maximal Achievable Dose with two Titration Schemes | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Randerath O, Whitesides J | [6 empty] | No | Paralell, Open-Label, Dose-Escalation Trial to Assess the Individual Maximal Achievable Dose (MAD) with two Titration Schemes for Transdermal Doses of SPM 962 in Subjects with Advanced Stage, Idiopathic, Parkinson's Disease | Parkinson's disease (advanced) | Central Nervous System |  | 2000-02-22 | 2000-02-22 | 2003-05-05: 2000-05-09; 2003-05-16: 2000-07-24; 2003-06-03: 2000-08-31; 2003-07-24: 2001-01-05; 2004-03-25: 2003-04-01 | Croatia, Czech Republic, South Africa, United Kingdom | Croatia (Created), Czech Republic (Created), South Africa (Created), United Kingdom (Created) |  | 17 | 0 | 0 | 36 | 30 | 30 | 0 | 0 | 0 | 34 | 2 | 5 | 27
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0596 | CSR Approved | SPM 962/Rotigotine: PK in ethnic groups | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Poole K, Whitesides J | [6 empty] | No | A Single Center, Open Label, Matched Pairs, Multiple Dose Study to Assess the Comparative Bioavailability of SPM962 in Healthy Black versus Caucasian Subjects |  |  |  | 2000-05-01 | 2000-05-01 | 2003-05-05: 2001-01-04; 2003-05-16: 2001-02-16; 2003-06-03: 2001-05-25; 2003-07-24: 2001-06-10; 2003-12-17: 2001-07-16; 2004-03-25: 2001-08-24 | France | France (Created) |  | 1 | 0 | 0 | 51 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0604 | Created (Cancelled) | SPM 962 in patients with advanced PD and concomitant CV dise | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Gutwald U, Whitesides J | [6 empty] | No | Multicener, double-blind, randomized, placebo-controlled, parallel-group, dose-escalation trial of SPM 962 transdermal system in subjects with advanced idiopathic Parkinson's disease and concomitant cardiovascular disease | Parkinson's disease (advanced) | Central Nervous System | [20 empty] | 12 | 0 | 0 | 44 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0606 | CSR Approved | SPM 962/Rotigotine: 14C-SPM962 patch - human subjects | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Cawello W, Whitesides J | [6 empty] | No | SPM 962/Rotigotine: 14C-SPM962 patch - human subjects | [5 empty] | 2003-05-16: 2001-02-05; 2003-06-03: 2001-02-17; 2003-07-24: 2001-02-28; 2003-12-17: 2001-05-02; 2004-03-25: 2001-07-31 | Netherlands | Netherlands (Created) |  | 1 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0610 | CSR Approved | SPM 962/Rotigotine: 14C-SPM962 patch human ADME | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Cawello W, Whitesides J | [6 empty] | No | SPM 962/Rotigotine: 14C-SPM962 patch human ADME |  |  |  | 2000-08-30 | 2000-08-30 | 2003-05-05: 2000-10-14; 2003-05-16: 2000-12-04; 2003-06-03: 2000-12-02; 2003-07-24: 2001-01-01; 2003-12-17: 2001-05-01; 2004-03-25: 2001-07-16 | Czech Republic | Czech Republic (Created) |  | 1 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0626 | CSR Approved | SPM 962/Rotigotine: BE site of administration | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Cawello W, Whitesides J | [6 empty] | No | SPM 962/Rotigotine: BE site of administration |  |  |  | 2000-10-12 | 2000-10-12 | 2003-05-05: 2000-10-27; 2003-05-16: 2000-11-23; 2003-06-03: 2000-12-01; 2003-07-24: 2000-12-18; 2003-12-17: 2001-03-13; 2004-03-25: 2001-05-17 | Germany | Germany (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0627 | CSR Approved | SPM 962/Rotigotine: Drug drug interaction SPM962 | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Cawello W, Whitesides J | [6 empty] | No | drug drug interaction between SPM962 and cimetidine |  |  |  | 2000-10-27 | 2000-10-27 | 2003-05-05: 2001-03-07; 2003-05-16: 2001-03-22; 2003-06-03: 2001-04-06; 2003-07-24: 2001-04-27; 2003-12-17: 2001-06-25; 2004-03-25: 2001-07-30 | Germany | Germany (Created) |  | 1 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0628 | Study Archived | SPM 962/Rotigotine: Drug drug interaction between rotigotine | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Braun M, Whitesides J | [6 empty] | No | Open, parallel group, drug-drug interaction trial to evaluate pharmacokinetics of rotigotine CDS and levodopa/carbidopa in patients with idiopathic Restless Legs Syndrome | Restless legs syndrome | Central Nervous System |  | 2002-08-06 | 2002-08-06 | 2003-05-05: 2002-08-23; 2003-05-16: 2002-10-15; 2003-06-03: 2003-03-12; 2003-07-24: 2003-04-16; 2003-10-03: 2003-05-20; 2003-12-17: 2004-05-13; 2004-03-25: 2004-08-20 | Germany | Germany (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 42 | 18 | 0 | 24 | 0 | 1 | 23
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0629 | Study Archived | SPM 962/Rotigotine: Cumulative skin irritation | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | Yes | Single site, placebo-controlled investigation of cumulative skin irritation after repetitive administration of rotigotine transdermal patch (2,5cm2, 1.125mg) to the same skin site in comparision to multiple administration of rotigotine transdermal patch (2,5cm2, 1.125mg) 2 daily rotating skin sites in healthy subjects. |  |  |  | 2003-06-13 | 2003-06-13 | 2003-05-05: 2003-08-15; 2003-05-16: 2003-09-15; 2003-06-03: 2003-11-06; 2003-07-24: 2004-03-10; 2003-10-03: 2004-04-05; 2003-12-17: 2004-05-07; 2004-03-25: 2004-09-09 | Germany | Germany (Created) |  | 1 | 0 | 0 | 40 | 40 | 32 | 56 | 16 | 0 | 40 | 0 | 2 | 38
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0630 | CSR Approved | SPM 962/Rotigotine PD: PK and cardiac safety | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Auer S, Whitesides J | [6 empty] | No | An open-label, multi-site, randomized trial of the pharmacokinetics and cardiac safety of rotigotine transdermal patch (18.0mg) in subjects with early-stage, idiopathic Parkinson's disease |  |  |  | 2004-01-16 | 2004-01-19 | 2003-05-05: 2004-02-02; 2003-05-16: 2004-03-28; 2003-06-03: 2004-05-20; 2003-07-24: 2004-06-28; 2003-10-03: 2004-07-14; 2003-12-17: 2004-08-13; 2004-03-25: 2006-09-09 | South Africa, United States of America | South Africa (Created), United States of America (Created) |  | 5 | 0 | 0 | 64 | 48 | 48 | 90 | 20 | 0 | 70 | 0 | 7 | 63
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0633 | Created (Cancelled) | SPM962 TDS administration in subjects with idiopathic PD | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Puttick R, Whitesides J | [6 empty] | No | A multi-centre open-label trial of long-term SPM962 TDS administration in subjects with idiopathic Parkinson's disease | Parkinson's disease (advanced) | Central Nervous System | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0650 | CSR Approved | SPM962 in subjects with advanced stage, idiopathic Parkinso | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Neilson S, Whitesides J | [6 empty] | No | A multi-center, multi-national, phase III, randomized, double-blind, parallel group, placebo controlled trial of the efficacy and safety of rotigotine CDS patch (2 tareget doses) in subjects with advanced stage, idiopathic Parkinson's Disease who are not well controlled on levodopa (Part I) and open -label extension to assess the safety of long-term treatment of rotigotine CDS (Part II). | Parkinson's disease (advanced) | Central Nervous System |  | 2001-05-18 | 2001-05-18 | 2003-05-05: 2001-10-12; 2003-05-16: 2001-12-19; 2003-06-03: 2003-09-15; 2003-07-24: 2004-04-19; 2003-10-03: 2004-06-24; 2003-12-17: 2005-08-31; 2004-03-25: 2006-01-19 | Canada, United States of America | Canada (Created), United States of America (Created) |  | 55 | 0 | 0 | 470 | 260 | 260 | 0 | 0 | 0 | 351 | 3 | 84 | 264
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0651 | CSR Approved | Relative bioavailability of SPM962 (40cm2 vs 2 x 20 cm2) in | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | No | A single-center, randomized, open-label crossover trial to assess the relative bioavailability of rotigotine after multiple-dose applications of rotigotine transdermal patch (18.0mg/40cm2 or 2 x 9.0mg/20 cm2) at different sites of application in subjects with idiopathic Parkinson's disease |  |  |  | 2005-02-02 | 2005-02-02 | 2003-05-05: 2005-03-02; 2003-05-16: 2005-06-21; 2003-06-03: 2005-07-22; 2003-07-24: 2005-09-21; 2003-10-03: 2005-12-06; 2003-12-17: 2006-02-01; 2004-03-25: 2006-06-15 | South Africa | South Africa (Created) |  | 1 | 0 | 0 | 36 | 36 | 28 | 38 | 2 | 0 | 36 | 0 | 0 | 36
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0666 | CSR Approved | SPM 936 in restless leg syndrome | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E, Whitesides J | [6 empty] | No | Multicenter, double-blind, randomized, placebo-controlled, four-arm, parallel-group trial of Rotigotine CDS in subjects with idiopathic Restless Leg Syndrome | Restless legs syndrome | Central Nervous System |  | 2001-06-27 | 2001-06-27 | 2003-05-05: 2001-10-04; 2003-05-16: 2001-11-26; 2003-06-03: 2002-03-14; 2003-07-24: 2002-03-28; 2003-12-17: 2002-11-07; 2004-03-25: 2004-04-02 | Germany | Germany (Created) |  | 8 | 0 | 0 | 48 | 40 | 40 | 0 | 0 | 0 | 63 | 1 | 0 | 62
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0670 | Study Archived | SPM 962/Rotigotine: 4.5 mg interaction with domperidone | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | No | Open, randomized, two-fold crossover trial to evaluate the influence of domperidone on the pharmacokinetics and saftey/tolerability of multiple dose treatment of rotigotine in young healthy male subjects |  |  |  | 2001-08-24 | 2001-08-24 | 2003-05-05: 2001-10-23; 2003-05-16: 2001-12-17; 2003-06-03: 2002-01-14; 2003-07-24: 2002-02-16; 2003-10-03: 2002-04-19; 2003-12-17: 2003-12-18; 2004-03-25: 2004-05-11 | France | France (Created) |  | 1 | 0 | 0 | 16 | 16 | 16 | 26 | 10 | 0 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0671 | Study Archived | SPM 962/Rotigotine: Liver impairment | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Lueck H, Whitesides J | [6 empty] | No | Open, group-comparison trial to evaluate the influence of liver impairment on the pharmacokinetics and safety/tolerability of multiple dose treatment with rotigotine in hepatic impaired patients |  |  |  | 2001-10-26 | 2001-10-26 | 2003-05-05: 2002-01-17; 2003-05-16: 2002-08-07; 2003-06-03: 2003-05-07; 2003-07-24: 2003-05-23; 2003-10-03: 2003-08-19; 2003-12-17: 2004-01-23; 2004-03-25: 2004-07-02 | Hungary, Slovakia | Hungary (Created), Slovakia (Created) |  | 1 | 0 | 0 | 16 | 16 | 16 | 1 | 0 | 0 | 17 | 0 | 0 | 17
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0672 | Study Archived | SPM 962/Rotigotine-evaluation of PK and safety in subjects w | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | Yes | Open-label, group comparison investigation of pharmacokinetics, safety and tolerability of single dose transdermal treatment with rotigotine (10cm² / 4.5 mg) in patients with impaired renal function including patients requiring dialysis compared to healthy subjects |  |  |  | 2003-01-09 | 2003-01-09 | 2003-05-05: 2003-02-12; 2003-05-16: 2003-06-17; 2003-06-03: 2004-01-28; 2003-07-24: 2004-02-16; 2003-10-03: 2004-03-08; 2003-12-17: 2004-05-25; 2004-03-25: 2004-08-12 | Poland | Poland (Created) |  | 2 | 0 | 0 | 40 | 40 | 40 | 82 | 50 | 0 | 32 | 0 | 0 | 32
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0673 | Study Archived | SPM 962/Rotigotine transdermal patch: Skin sensitization | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | Yes | Two-Site, placebo-controlled investigation of skin sensitization after repeated administration of rotigotine transdermal patch (2.5 cm2/1.125 mg) in healthy subjects |  |  |  | 2003-07-29 | 2003-07-29 | 2003-05-05: 2003-08-26; 2003-05-16: 2003-10-08; 2003-06-03: 2003-11-26; 2003-07-24: 2004-02-09; 2003-10-03: 2004-03-12; 2003-12-17: 2004-05-06; 2004-03-25: 2004-08-24 | Germany | Germany (Created) |  | 2 | 0 | 0 | 240 | 240 | 200 | 406 | 177 | 0 | 229 | 0 | 8 | 221
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0688 | Protoc. Summary Approved (Cancelled) | SPM962 with idiopathic, Parkinson's disease | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Randerath O, Whitesides J | [6 empty] | No | A Phase III, open trial to provide subjects with idiopathic, Parkinson's disease that participated in previous trials, benefited from therapy with rotigotine CDS and asked for continuation of treatment with rotigotine CDS patch and to show that the long-term use of rotigotine CDS patch is safe in th is population. | Parkinson's disease (advanced) | Central Nervous System |  | 2001-10-01 | 2001-10-01 | [14 empty] | Germany | Germany (Created) |  | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0695 | Created (Cancelled) | Rotigotine CDS in subjects with early stage, idiopathic Park | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Neilson S, Whitesides J | [6 empty] | No | A multi-center, multi-national, phase III, open-label trial of the safety and efficacy of long-term treatment of Rotigotine CDS in subjects with early stage, idiopathic Parkinson's Disease. | Parkinson's disease (early) | Central Nervous System | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0696 | Created (Cancelled) | Rotigotine CDS in subjects with advanced stage, idiopathic P | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Neilson S, Whitesides J | [6 empty] | No | A multi-center, multi-national, phase III, open-label trial of the safety and efficacy of long-term treatment of Rotigotine CDS in subjects with advanced stage, idiophathic Parkinson's Disease. | Parkinson's disease (advanced) | Central Nervous System | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0702 | CSR Approved | Open Label Extension Study of Trial No. SP512, Rotigotine CD | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Neilson S, Whitesides J | [6 empty] | No | Open Label Extension Study of Trial No. SP512, Rotigotine CDS | Parkinson's disease (early) | Central Nervous System |  |  |  | 2003-05-16: 2002-02-24; 2003-06-03: 2003-04-11; 2003-07-24: 2008-11-12; 2003-10-03: 2009-04-09; 2003-12-17: 2009-08-04; 2004-03-25: 2010-04-08 | Canada, United States of America | Canada (Created), United States of America (Created) |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0709 | CSR Approved | Rotigotine CDS RLS dose finding trial | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Berger W, Whitesides J | [6 empty] | No | Phase IIb Dose-Finding Trial to determine efficacy, safety and tolerability of five different transdermal doses of rotigotine (1.125mg/2.25mg/4.5mg/6.75mg/9mg) in idiopathic RLS patients | Restless legs syndrome | Central Nervous System |  | 2002-09-15 | 2002-09-15 | 2003-05-05: 2003-02-27; 2003-05-16: 2003-04-30; 2003-06-03: 2003-12-26; 2003-07-24: 2004-02-26; 2003-10-03: 2004-04-26; 2003-12-17: 2004-08-31; 2004-03-25: 2006-03-17 | Austria, Germany, Italy, Spain, Switzerland | Austria (Created), Germany (Created), Italy (Created), Spain (Created), Switzerland (Created) |  | 30 | 0 | 0 | 300 | 210 | 210 | 0 | 0 | 0 | 341 | 19 | 13 | 309
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0710 | Study Archived | Rotigotine CDS open label extension trial of SP709 | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Raetz M, Whitesides J | Bonny M | [5 empty] | No | An open-label extension trial to determine safety and tolerability of long-term transdermal application of rotigotine in subjects with idiopathic restless legs sysndrome | Restless legs syndrome | Central Nervous System |  | 2002-09-15 | 2002-09-15 | 2003-05-05: 2003-02-27; 2003-05-16: 2003-07-31; 2003-06-03: 2004-02-26; 2003-07-24: 2009-04-15; 2003-10-03: 2009-06-19; 2003-12-17: 2009-08-13; 2004-03-25: 2009-12-08 | Austria, Germany, Spain | Austria (1st Site Initiation), Germany (1st Site Initiation), Spain (1st Site Initiation) | Austria, Germany, Spain | 25 | 31 | 0 | 250 | 175 | 175 | 0 | 0 | 0 | 295 | 0 | 173 | 122
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0715 | CSR Approved | Open Label Extension Study of Trial No. SP650, Rotigotine CD | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Neilson S, Whitesides J | [6 empty] | No | Open Label Extension Study of Trial No. SP650, Rotigotine CDS | Parkinson's disease (advanced) | Central Nervous System |  |  |  | 2003-05-16: 2002-08-25; 2003-06-03: 2004-04-19; 2003-07-24: 2008-12-04; 2003-10-03: 2009-04-09; 2003-12-17: 2009-08-04; 2004-03-25: 2010-04-22 | Canada, United States of America | Canada (Created), United States of America (Created) |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0716 | Study Archived | Open Label Extension Study of Trial No. SP513, Rotigotine CD | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Raetz M, Whitesides J | Bonny M | [5 empty] | No | A multi-centre, multinational, Phase III, randomised, double blind, double-dummy, 3-arm parallel group, placebo- and ropinirole-controlled, trial of the efficacy and safety of the rotigotine CDS patch in subjects with early stage, idiopathic Parkinson's disease (Part I), and an open-label extension to assess the safety of long-term treatment of rotigotine CDS (Part II). | Parkinson's disease (early) | Central Nervous System |  |  |  | 2003-05-05: 2002-05-08; 2003-05-09: 2002-11-04; 2003-05-16: 2002-10-30; 2003-06-03: 2003-08-26; 2003-07-24: 2008-12-15; 2003-10-03: 2009-06-11; 2003-12-17: 2009-11-02; 2004-03-25: 2010-04-12 | Australia, Austria, Belgium, Croatia, Czech Republic, Finland, France, Germany, Hungary, Israel, Italy, Netherlands, New Zealand, Norway, Poland, South Africa, Spain, Sweden, Switzerland, United Kingdom | Australia (1st Site Initiation), Austria (1st Site Initiation), Belgium (1st Site Initiation), Croatia (1st Site Initiation), Czech Republic (1st Site Initiation), Finland (1st Site Initiation), France (1st Site Initiation), Germany (1st Site Initiation), Hungary (1st Site Initiation), Israel (1st Site Initiation), Italy (1st Site Initiation), Netherlands (1st Site Initiation), New Zealand (1st Site Initiation), Norway (1st Site Initiation), Poland (1st Site Initiation), South Africa (1st Site Initiation), Spain (1st Site Initiation), Sweden (1st Site Initiation), Switzerland (1st Site Initiation), United Kingdom (1st Site Initiation) | Australia, Austria, Belgium, Croatia, Czech Republic, Finland, France, Germany, Hungary, Israel, Italy, Netherlands, New Zealand, Norway, Poland, South Africa, Spain, Sweden, Switzerland, United Kingdom | 81 | 70 | 0 | 470 | 470 | 300 | 0 | 0 | 0 | 380 | 0 | 380 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0717 | Study Archived | SPM 962/Rotigotine: SD bridging study in Japanese and Caucas | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | Yes | Parallel group trial to evaluate the pharmacokinetics and safety/tolerability of single dose treatment with rotigotine CDS (10 cm²/4.5 mg) in Japanese and Caucasian healthy subjects |  |  |  | 2002-08-22 | 2002-08-22 | 2003-05-05: 2002-09-03; 2003-05-16: 2002-10-10; 2003-06-03: 2002-12-11; 2003-07-24: 2002-12-21; 2003-10-03: 2003-03-21; 2003-12-17: 2003-06-30; 2004-03-25: 2004-06-09 | Germany | Germany (Created) |  | 1 | 0 | 0 | 48 | 48 | 48 | 92 | 42 | 0 | 50 | 0 | 2 | 48
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0718 | Study Archived | SPM 962/Rotigotine: Multiple dose bridging trial in Japanese | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | Yes | Parallel group trial to evaluate the pharmacokinetics and safety/tolerability of repeated dose treatment with rotigotine CDS in three different dosages (5 cm²/2.25 mg, 10 cm²/4.5 mg, 20 cm²/9 mg) in Japanese and Caucasian healthy subjects |  |  |  | 2002-09-10 | 2002-10-25 | 2003-05-05: 2002-10-25; 2003-05-16: 2002-12-10; 2003-06-03: 2003-02-19; 2003-07-24: 2003-03-12; 2003-10-03: 2003-04-28; 2003-12-17: 2004-01-16; 2004-03-25: 2004-06-23 | Germany | Germany (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 47 | 21 | 0 | 26 | 0 | 2 | 24
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0788 | CSR Approved | SPM 962/rotigotine PD: OLE SP630 | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | No | AN OPEN-LABEL, MULTI-SITE, EXTENSION TRIAL TO ASSESS THE LONG-TERM SAFETY AND TOLERABILITY OF ROTIGOTINE TRANSDERMAL PATCH IN SUBJECTS WITH EARLY-STAGE, IDIOPATHIC PARKINSON'S DISEASE | Parkinson's disease (early) | Central Nervous System |  | 2004-03-18 | 2004-03-18 | 2003-05-05: 2004-04-14; 2003-05-16: 2004-05-07; 2003-06-03: 2004-06-20; 2003-07-24: 2008-10-14; 2003-10-03: 2009-01-19; 2003-12-17: 2009-03-06; 2004-03-25: 2009-11-17 | South Africa, United States of America | South Africa (Created), United States of America (Created) |  | 2 | 0 | 0 | 64 | 64 | 48 | 62 | 0 | 0 | 62 | 0 | 32 | 30
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0790 | CSR Approved | Rotigotine-RLS Pivotal trial phase 3 EU | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Berger W, Whitesides J | [6 empty] | No | Multicenter, randomized, double-blind, placebo-controlled, 4 arm parallel-group trial to investigate the efficacy and safety of 3 different transdermal doses of rotigotine in subjects with idiopathic restless legs syndrome | Restless legs syndrome | Central Nervous System |  | 2004-03-26 | 2004-03-26 | 2003-05-05: 2005-02-18; 2003-05-16: 2005-05-31; 2003-06-03: 2005-12-16; 2003-07-24: 2006-08-23; 2003-10-03: 2006-09-22; 2003-12-17: 2006-12-01; 2004-03-25: 2007-08-07 | Austria, Finland, Germany, Italy, Netherlands, Spain, Sweden, United Kingdom | Austria (Created), Finland (Created), Germany (Created), Italy (Created), Netherlands (Created), Spain (Created), Sweden (Created), United Kingdom (Created) |  | 50 | 0 | 0 | 450 | 400 | 380 | 59 | 0 | 0 | 459 | 0 | 99 | 360
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0791 | Study Archived | Rotigotine-RLS phase 3 EU extension trial | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Raetz M, Whitesides J | Bonny M | [5 empty] | No | An open-label extension trial to investigate the safety and tolerability of long-term treatment with transdermal rotigotine in subjects with idiopathic restless legs syndrome | Restless legs syndrome | Central Nervous System |  | 2005-06-04 | 2005-06-04 | 2003-05-05: 2005-06-28; 2003-05-16: 2006-01-06; 2003-06-03: 2006-07-11; 2003-07-24: 2007-09-06; 2003-10-03: 2007-11-30; 2003-12-17: 2008-02-19; 2004-03-25: 2008-08-13 | Austria, Finland, Germany, Italy, Netherlands, Spain, Sweden, United Kingdom | Austria (1st Site Initiation), Finland (1st Site Initiation), Germany (1st Site Initiation), Italy (1st Site Initiation), Netherlands (Created), Spain (1st Site Initiation), Sweden (1st Site Initiation), United Kingdom (1st Site Initiation) | Austria, Finland, Germany, Italy, Spain, Sweden, United Kingdom | 50 | 44 | 0 | 420 | 420 | 320 | 0 | 0 | 0 | 341 | 0 | 91 | 250
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0792 | Study Archived | Rotigotine-RLS pivotal trial phase 3 US | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Carpenter M, Whitesides J | Driver D | [5 empty] | No | A multi-center, randomized, double-blind, placebo-controlled, 5-arm parallel-group trial to investigate the efficacy and safety of four different transdermal doses of Rotigotine in subjects with idiopathic restless legs syndrome | Restless legs syndrome | Central Nervous System |  | 2005-01-20 | 2005-01-20 | 2003-05-05: 2005-02-16; 2003-05-16: 2005-05-10; 2003-06-03: 2006-04-10; 2003-07-24: 2006-11-06; 2003-10-03: 2006-12-19; 2003-12-17: 2007-02-16; 2004-03-25: 2007-08-17 | United States of America | United States of America (Created) |  | 60 | 0 | 0 | 600 | 500 | 425 | 811 | 0 | 0 | 505 | 0 | 183 | 322
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0793 | Study Archived | Rotigotine-RLS phase 3 extension trial US | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Carpenter M, Whitesides J | Driver D | [5 empty] | No | An open-label extension trial to investigate the safety and tolerability of long-term treatment with transdermal rotigotine in subjects with idiopathic restless legs sysndrome | Restless legs syndrome | Central Nervous System |  | 2005-06-13 | 2005-06-13 | 2003-05-05: 2005-06-28; 2003-05-16: 2005-12-15; 2003-06-03: 2006-10-26; 2003-07-24: 2007-12-18; 2003-10-03: 2008-02-12; 2003-12-17: 2008-04-15; 2004-03-25: 2008-08-19 | United States of America | United States of America (Created) |  | 57 | 0 | 0 | 450 | 450 | 400 | 0 | 0 | 0 | 279 | 1 | 104 | 174
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0794 | Study Archived | Rotigotine-RLS Sleeplab trial | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Raetz M, Whitesides J | Bonny M | [5 empty] | No | A multicenter, double-blind, randomized, placebo-controlled, two-arm, parallel-group, sleep lab trial to investigate the efficacy and safety of transdermal rotigotine in subjects with idiopathic restless legs syndrome | Restless legs syndrome | Central Nervous System |  | 2005-06-01 | 2005-06-01 | 2003-05-05: 2005-07-19; 2003-05-16: 2005-11-24; 2003-06-03: 2006-05-23; 2003-07-24: 2006-07-21; 2003-10-03: 2006-10-10; 2003-12-17: 2006-12-22; 2004-03-25: 2007-08-01 | Austria, Finland, Germany, Italy, Spain | Austria (Created), Finland (Created), Germany (Created), Italy (Created), Spain (Created) |  | 12 | 0 | 0 | 90 | 60 | 51 | 96 | 0 | 0 | 67 | 0 | 6 | 61
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0795 | Created (Cancelled) | Rotigotine-RLS Sleeplab extension trial | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Berger W, Whitesides J | [6 empty] | No | Rotigotine-RLS Sleeplab extension trial | Restless legs syndrome | Central Nervous System | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0824 | Study Archived | Open-label,multinational trial of rotigotine when switched o | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Neilson S, Whitesides J | [6 empty] | No | A phase IIIb, open-label, multinational trial to assess the efficacy of rotigotine transdermal patch when switched overnight from ropinirole, pramipexole or cabergoline therapy in patients with idiopathic, Parkinson's disease (H&Y stage I-IV) | Parkinson's disease | Central Nervous System |  | 2004-04-13 | 2004-04-13 | 2003-05-05: 2004-09-28; 2003-05-16: 2004-12-21; 2003-06-03: 2005-05-27; 2003-07-24: 2005-07-11; 2003-10-03: 2005-10-05; 2003-12-17: 2005-12-05; 2004-03-25: 2006-05-18 | United Kingdom, United States of America | United Kingdom (Created), United States of America (Created) |  | 13 | 0 | 0 | 100 | 100 | 100 | 119 | 0 | 0 | 116 | 5 | 11 | 100
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0825 | Study Archived | Rotigotine compared to ropinirole in early stage PD patients | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Dank N, Whitesides J | [6 empty] | No | A phase 3, randomized, open-label, two-arm, parallel-group, multicenter, multinational trial to compare the efficacy of rotigotine transdermal patch to that of ropinirole on early morning motor impairment and sleep disorders in subjects with early-stage, idiopathic Parkinson's disease | Parkinson's disease (early) | Central Nervous System |  | 2004-05-26 | 2004-05-26 | 2003-05-05: 2004-09-16; 2003-05-16: 2004-12-14; 2003-06-03: 2005-06-29; 2003-07-24: 2005-10-25; 2003-10-03: 2006-01-10; 2003-12-17: 2006-03-02; 2004-03-25: 2006-10-02 | Germany, Italy, Spain | Germany (Created), Italy (Created), Spain (Created) |  | 13 | 0 | 0 | 53 | 50 | 45 | 49 | 0 | 0 | 51 | 0 | 3 | 48
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0826 | Study Archived | rotigotine in early am akinesia and sleep disorders in PD | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Dank N, Whitesides J | [6 empty] | No | A phase IIIb, open-label, multinational trial to evaluate the effects of rotigotine transdermal patch on early morning motor problems, quality of night time sleep, and excessive day time drowsiness in patients with idiopathic, Parkinson's disease | Parkinson's disease | Central Nervous System |  | 2004-05-26 | 2004-05-26 | 2003-05-05: 2004-08-19; 2003-05-16: 2004-12-24; 2003-06-03: 2005-04-07; 2003-07-24: 2005-07-21; 2003-10-03: 2005-10-05; 2003-12-17: 2005-12-01; 2004-03-25: 2006-05-04 | Austria, Israel, South Africa, United Kingdom | Austria (Created), Israel (Created), South Africa (Created), United Kingdom (Created) |  | 6 | 0 | 0 | 50 | 50 | 40 | 28 | 0 | 0 | 54 | 0 | 6 | 48
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0832 | Created (Cancelled) | Ropinirole in early morning akinesia/motor problems | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Dank N, Whitesides J | [6 empty] | No | A phase 3b open label multinational trial to evaluate the effects of ropinirole on early morning motor problems, quality of nightime sleep, and excessive daytime drowsiness in patients with idiopathic Parkinson's Disease. | Parkinson's disease | Central Nervous System | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0833 | CSR Approved | Open label follow up trial of rotigotine in Parkinson's Dise | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Schmid M, Whitesides J | [6 empty] | No | Multicenter multinational phase 3b open label extension trial to assess the safety of long term treatment of rotigotine patch in subjects with Parkinson's disease | Parkinson's disease | Central Nervous System |  | 2004-08-16 | 2004-08-16 | 2003-05-05: 2004-09-28; 2003-05-09: 2005-02-17; 2003-05-16: 2005-02-17; 2003-06-03: 2005-10-25; 2003-07-24: 2008-12-16; 2003-10-03: 2009-05-21; 2003-12-17: 2009-10-14; 2004-03-25: 2010-04-08 | Austria, Germany, Israel, Italy, South Africa, Spain, United Kingdom, United States of America | Austria (Created), Germany (Created), Israel (Created), Italy (Created), South Africa (Created), Spain (Created), United Kingdom (Created), United States of America (Created) |  | 32 | 0 | 0 | 170 | 170 | 125 | 0 | 0 | 0 | 186 | 0 | 144 | 42
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0852 | Created (Cancelled) | Efficacy and tolerability of Rotigotine in subjects who are | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Lebedeva N, Whitesides J | [6 empty] | No | A multi-center, national, phase 3, randomized, double-blind, parallel group, placebo controlled trial of the efficacy and safety of Rotigotine CDS patch (2 target doses) in subjects wiht advanced stage, idopathic Parkinson's disease who are not well controlled on Levodopa | Parkinson's disease (advanced) | Central Nervous System | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0854 | Study Archived | Neupro® in Parkinson's Disease (TRUST Study) | Non Interventional Study - Prospective | Open | UCB Pharma Global | GMA Neurology / Psychiatry | UCB Pharma Global | Will E | Copetti C | N/A | Aptiv Solutions + inVentiv Health clinical |  |  | adults | No | Transdermal Rotigotine user Surveillance Study (Trust): A naturalistic, multisite, observational study of rotigotine transdermal patch and other currently prescribed therapies in patients with idiopathic Parkinson's Disease | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-02-10 | 2006-02-10 |  | 2006-03-22 | 2006-06-22 | 2006-06-26 | 2011-05-24 | 2011-07-13 |  | 2014-04-11 |  | 2014-06-12 |  | 2014-08-19 |  | 2014-12-10 | Czech Republic, Denmark, Germany, Greece, Italy, Mexico, Romania, Slovakia, Spain, Switzerland | Czech Republic (LPLV), Denmark (LPLV), Germany (LPLV), Greece (LPLV), Italy (LPLV), Mexico (LPLV), Romania (LPLV), Slovakia (LPLV), Spain (LPLV), Switzerland (LPLV) | Czech Republic, Denmark, Germany, Greece, Italy, Mexico, Romania, Slovakia, Spain, Switzerland | 260 | 266 | 211 | 2000 | 2000 | 1250 | 0 | 0 | 0 | 2195 | 13 | 650 | 1532 |  |  | 2010-11-30 | 2011-11-30 |  |  | 2012-06-23 | 2012-07-09
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0861 | Study Archived | Contraceptive Interaction trial | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Strauss B, Whitesides J | [6 empty] | Yes | Single site randomized double-blind placebo-controlled crossover multiple dose trial to investigate the influence of 6.75 mg Rotigotine on the suppresion of ovulation by oral hormonal contraceptive in healthy female subjects | Restless legs syndrome | Central Nervous System |  | 2005-07-22 | 2005-07-22 | 2003-05-05: 2005-08-18; 2003-05-16: 2006-01-13; 2003-06-03: 2006-03-30; 2003-07-24: 2006-06-12; 2003-10-03: 2006-07-07; 2003-12-17: 2006-09-21; 2004-03-25: 2006-11-29 | South Africa | South Africa (Created) |  | 1 | 0 | 0 | 45 | 42 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0862 | Study Archived | CYP2C19 Inhibitor Interaction trial | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Goldammer N, Whitesides J | Beinhauer-Zellenka U | [5 empty] | Yes | OPEN-LABEL, MULTIPLE DOSE TRIAL TO INVESTIGATE THE EFFECTS OF OMEPRAZOLE (40MG) ON STEADY-STATE PHARMACOKINETICS AND SAFETY AND TOLERABILITY OF ROTIGOTINE TRANSDERMAL PATCH (9MG/20CM2) IN 40 HEALTHY MALE SUBJECTS | Restless legs syndrome | Central Nervous System |  | 2005-06-14 | 2005-06-14 | 2003-05-05: 2005-08-16; 2003-05-16: 2006-01-24; 2003-06-03: 2006-06-21; 2003-07-24: 2006-07-20; 2003-10-03: 2006-09-01; 2003-12-17: 2006-11-29; 2004-03-25: 2007-07-05 | South Africa | South Africa (Created) |  | 1 | 0 | 0 | 40 | 40 | 36 | 126 | 72 | 0 | 54 | 0 | 16 | 38
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0864 | CSR Approved | Thorough QTC trial | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | No | Double-blind, randomized, placebo- and positive-controlled, parallel-group trial to assess the potential electrocardiographic effects of rotigotine transdermal system up to 120cm2/54.0mg/day in subjects with advanced-stage idiopathic Parkinson's disease: a 'thorough' QT/QTc trial | Parkinson's disease | Central Nervous System |  | 2005-05-11 | 2005-05-11 | 2003-05-05: 2005-08-23; 2003-05-16: 2006-01-06; 2003-06-03: 2006-08-03; 2003-07-24: 2006-10-19; 2003-10-03: 2006-12-18; 2003-12-17: 2007-03-02; 2004-03-25: 2007-07-02 | South Africa | South Africa (Created) |  | 2 | 0 | 0 | 96 | 96 | 80 | 180 | 50 | 0 | 130 | 0 | 4 | 126
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0871 | Study Archived | Relative Bioavailability | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Goldammer N, Whitesides J | Beinhauer-Zellenka U | [5 empty] | Yes | Single-site, open-label, crossover trial to assess relative Bioavailability of rotigotine after administration of rotigotine transdermal patch (6.75 mg/15m2 to different application sites and compared to combined Application of 1x 2.25mg/5cm2 plus 1x 4.5mg/10cm2) in healthy male subjects | Restless legs syndrome | Central Nervous System |  | 2005-07-27 | 2005-07-27 | 2003-05-05: 2005-08-19; 2003-05-16: 2006-03-16; 2003-06-03: 2006-07-05; 2003-07-24: 2006-07-31; 2003-10-03: 2006-09-14; 2003-12-17: 2007-01-17; 2004-03-25: 2007-04-27 | South Africa | South Africa (Created) |  | 1 | 0 | 0 | 42 | 42 | 42 | 100 | 44 | 0 | 56 | 0 | 15 | 41
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0880 | CSR Approved | NEUCOM - Compliance with the application of Neupro in the da | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Leffers K, Whitesides J | [6 empty] | No | NEUCOM - Compliance with the application of Neupro in the daily practice. | Parkinson's disease | Central Nervous System |  |  |  | 2004-03-25: 2008-10-30 |  |  |  | 500 | 0 | 0 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0882 | Study Archived | Neupro in peripoerative settings (Neupos) | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Abbe C, Whitesides J | [6 empty] | No | An open-label multi site feasibility trial with Rotigotine transdermal patch in early stage PD patients to assess perioperative PD therapy with NEUPRO. | Parkinson's disease | Central Nervous System |  | 2006-10-31 | 2006-10-25 | 2003-05-05: 2007-01-30; 2003-05-09: 2007-07-30; 2003-05-16: 2008-09-06; 2003-06-03: 2008-05-02; 2003-07-24: 2008-05-26; 2003-10-03: 2008-10-08; 2003-12-17: 2008-11-13; 2004-03-25: 2009-04-07 | Germany | Germany (1st Site Initiation) | Germany | 15 | 5 | 0 | 30 | 30 | 30 | 14 | 0 | 0 | 14 | 0 | 3 | 11
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0883 | Created (Cancelled) | Assessment of administration time with video monitoring | Phase IV | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Haeck H, Whitesides J | [6 empty] | No | A double-blind single site randomized cross-over feasibility trial with Rotigotine transdermal patch in PD patients to investigate early morning versus evening application as assessed by video monitoring | Parkinson's disease | Central Nervous System | [17 empty] | Germany | Germany (Created) |  | 1 | 0 | 0 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0885 | CSR Approved | Pharmacokinetic trial with Korean subjects | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Strauss B, Whitesides J | [6 empty] | Yes | SINGLE-SITE, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, REPEATED-DOSE TRIAL TO EVALUATE THE PHARMOCOKINETICS AND SAFETY/TOLERABILITY OF ROTIGOTINE IN 2 DIFFERENT DOSAGES (2MG/24HRS [10CM^2], 4MG/24HRS [20CM^2]) IN HEALTHY KOREAN SUBJECTS | Parkinson's disease | Central Nervous System |  | 2006-06-30 | 2006-06-30 | 2003-05-05: 2006-08-16; 2003-05-16: 2006-12-21; 2003-06-03: 2007-02-02; 2003-07-24: 2007-02-23; 2003-10-03: 2007-04-05; 2003-12-17: 2007-06-06; 2004-03-25: 2007-08-08 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0886 | CSR Approved | Pivotal trial 4-day patch vs. 1-day patch | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | Yes | SINGLE-SITE, OPEN-LABEL, RANDOMIZED, CROSS OVER TRIAL TO EVALUATE THE PHARMACOKINETICS OF 2 ROTIGOTINE TRANSDERMAL PATCH FORMULATIONS COMPARING A SINGLE APPLICATION OF 13.5MG/10CM2 FOR 4 DAYS WITH ONCE-DAILY APPLICATIONS OF 4.5MG/10CM2 OVER 4 DAYS | Parkinson's disease | Central Nervous System |  | 2006-07-27 | 2006-07-27 | 2003-05-05: 2006-08-29; 2003-05-16: 2006-11-07; 2003-06-03: 2006-11-07; 2003-07-24: 2006-12-15; 2003-10-03: 2007-02-02; 2003-12-17: 2007-06-28; 2004-03-25: 2007-12-05 | Germany | Germany (Created) |  | 1 | 0 | 0 | 14 | 14 | 12 | 20 | 6 | 0 | 14 | 0 | 2 | 12
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0888 | CSR Approved | Proof of Concept Trial to Assess the Efficacy and Safety of | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Derby B | Christopher K |  |  |  |  | adults | No | A Parallel, Randomized, Double-Blind, Placebo Controlled Multicenter Trial to Assess the Efficacy and Safety of Two different Doses of Rotigotine in Subjects with Signs and Symptoms Associated with Fibromyalgia Syndrome | Fibromyalgia | Immunology |  | 2006-06-21 | 2006-06-21 | 2003-05-05: 2007-01-04; 2003-05-09: 2007-03-15; 2003-05-16: 2007-03-30; 2003-06-03: 2008-07-31; 2003-07-24: 2008-11-25; 2003-10-03: 2009-01-06; 2003-12-17: 2009-06-19; 2004-03-25: 2010-03-26 | United States of America | United States of America (1st Site Initiation) | United States of America | 30 | 7 | 0 | 240 | 240 | 180 | 0 | 0 | 0 | 230 | 9 | 114 | 107
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0889 | Study Archived | RECOVER - Rotigotine Akinesia Trial | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Schmid M, Whitesides J | [6 empty] | No | A phase 3b, placebo-controlled, double-blind, multicenter, multinational trial to evaluate the effects of Rotigotine transdermal patch on early morning motor impairment and sleep disorders in patients with idiopathic Parkinson's disease | Parkinson's disease | Central Nervous System |  | 2006-11-10 | 2006-11-09 | 2003-05-05: 2006-12-19; 2003-05-09: 2007-04-30; 2003-05-16: 2007-05-02; 2003-06-03: 2008-11-17; 2003-07-24: 2009-03-09; 2003-10-03: 2009-05-26; 2003-12-17: 2009-07-24; 2004-03-25: 2009-12-09 | Australia, Austria, Finland, Germany, Hungary, Italy, New Zealand, Poland, South Africa, Spain, United Kingdom, United States of America | Australia (1st Site Initiation), Austria (1st Site Initiation), Finland (1st Site Initiation), Germany (1st Site Initiation), Hungary (1st Site Initiation), Italy (1st Site Initiation), New Zealand (1st Site Initiation), Poland (1st Site Initiation), South Africa (1st Site Initiation), Spain (1st Site Initiation), United Kingdom (1st Site Initiation), United States of America (1st Site Initiation) | Australia, Austria, Finland, Germany, Hungary, Italy, New Zealand, Poland, South Africa, Spain, United Kingdom, United States of America | 58 | 58 | 0 | 400 | 336 | 336 | 333 | 0 | 46 | 287 | 0 | 41 | 246
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0901 | Study Archived | Comparison bioavailabity 7-day patch vs once daily patch | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | Yes | SINGLE-SITE, OPEN-LABEL, RANDOMIZED, CROSS-OVER TRIAL TO EVALUATE THE PHARMACOKINETICS OF 2 ROTIGOTINE TRANSDERMAL PATCH FORMULATIONS COMPARING A SINGLE APPLICATION OF 27MG/10CM2 FOR 168 HOURS (7 DAYS) WITH ONCE-DAILY APPLICATIONS OF 4.5MG/10CM2 OVER 7 DAYS | Parkinson's disease | Central Nervous System |  | 2007-03-01 | 2007-02-28 | 2003-05-05: 2007-04-24; 2003-05-16: 2007-06-13; 2003-06-03: 2007-07-03; 2003-07-24: 2007-08-09; 2003-10-03: 2007-09-27; 2003-12-17: 2008-01-17; 2004-03-25: 2008-04-18 | Germany | Germany (Created) |  | 1 | 0 | 0 | 16 | 16 | 12 | 0 | 0 | 0 | 16 | 16 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0908 | CSR Approved | Switching trial from Ropinirole to Neupro® | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Kim C, Whitesides J | [6 empty] | No | A Phase 3b, Open-label, multicenter trial to assess the Safety and tolerability of switching Korean subjects from ropinirole to the rotigotine transdermal system and its effect on symptoms in idiopathic parkinson's disease | Parkinson's disease | Central Nervous System |  | 2007-01-17 | 2007-01-17 | 2003-05-05: 2007-04-24; 2003-05-16: 2007-07-23; 2003-06-03: 2007-10-31; 2003-07-24: 2007-12-28; 2004-03-25: 2008-11-10 | North Korea, South Korea | North Korea (Created), South Korea (Created) |  | 8 | 0 | 0 | 120 | 120 | 100 | 124 | 8 | 0 | 116 | 0 | 18 | 98
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0909 | Created (Cancelled) | Medicus-AWB (Observational study "AWB") | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Haeck H, Whitesides J | [6 empty] | No | Medicus-AWB (Observational study "AWB") | Parkinson's disease | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0910 | CSR Approved | Advance-AWB (Observational Study "AWB") | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Leffers K, Whitesides J | [6 empty] | No | Advance-AWB (Observational Study "AWB") | Parkinson's disease | Central Nervous System |  |  |  | 2004-03-25: 2009-10-30 |  |  |  | 445 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0911 | Created (Cancelled) | Advanced Trial, long-term dyskinesia | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Haeck H, Whitesides J | [6 empty] | No | Advanced Trial | Parkinson's disease | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0912 | Created (Cancelled) | Taiwan PK trial | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Li Z, Whitesides J | [6 empty] | No | Taiwan PK trial | Parkinson's disease | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0913 | Study Archived | Pharmacokinetic trial in healthy Chinese subjects | Phase I | Open | Clinical Development Asia | CNS | UCB Pharma Global | Tang Y | Wu G | N/A | PXL for China |  |  | adults | No | Open-label, single-site, single and repeated dose trial to evaluate the pharmacokinetics and safety/tolerability of rotigotine in 2 different dosages (2 mg/24h [10cm2], 4 mg/24h [20cm2]) in healthy, male Chinese subjects | Parkinson's disease | Central Nervous System |  |  | 2010-07-28 | 2003-05-05: 2012-01-23; 2003-05-09: 2012-08-07; 2003-05-16: 2012-08-06; 2003-06-03: 2012-08-22; 2003-07-24: 2012-09-13; 2003-10-03: 2013-04-02; 2003-12-17: 2013-04-08; 2004-03-25: 2013-07-08 | China | China (LPLV) | China | 1 | 1 | 1 | 24 | 24 | 20 | 52 | 0 | 28 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0914 | Study Archived | Double-blind placebo controlled trial with Rotigotine in Chi | Phase III | Double Blind | Clinical Development Asia | CNS | UCB Pharma Global | Wang L | Wu G | N/A | PXL |  |  | adults | No | A multicenter, randomized, double-blind, parallel-group, placebo-controlled study of the efficacy and safety of the Rotigotine transdermal patch in Chines subjects with early-stage idiopathic Parkinson’s disease Phase 3 | Parkinson's disease (advanced) | Central Nervous System |  | 2010-06-03 | 2010-05-29 |  | 2012-01-23 | 2012-06-21 | 2012-07-11 | 2013-07-20 | 2013-10-25 |  | 2014-05-27 |  | 2014-07-22 |  | 2014-09-03 |  | 2014-11-21 | China | China (LPLV) | China | 24 | 24 | 24 | 320 | 248 | 248 | 289 | 0 | 40 | 249 | 0 | 29 | 220
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0915 | CSR Approved | RECOVER - long term trial | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Schmid M, Whitesides J | [6 empty] | No | Long-term extension of RECOVER- A MULTICENTER, MULTINATIONAL, PHASE 3B, OPEN-LABEL EXTENSION TRIAL TO EVALUATE THE LONG-TERM EFFECT OF THE 24-HOUR TRANSDERMAL DELIVERY OF ROTIGOTINE ON MOTOR FUNCTION, SLEEP QUALITY, AND NOCTURNAL AND NON-MOTOR SYMPTOMS IN SUBJECTS WITH IDIOPATHIC PARKINSON'S DISEASE | Parkinson's disease | Central Nervous System |  | 2006-11-26 | 2006-11-26 | 2003-05-05: 2007-01-16; 2003-05-09: 2007-06-15; 2003-05-16: 2007-07-30; 2003-06-03: 2008-04-17; 2003-07-24: 2009-05-05; 2003-10-03: 2009-08-05; 2003-12-17: 2009-10-22; 2004-03-25: 2010-03-08 | Australia, Austria, Finland, Germany, Hungary, Italy, New Zealand, Poland, South Africa, Spain, United Kingdom, United States of America | Australia (1st Site Initiation), Austria (1st Site Initiation), Finland (1st Site Initiation), Germany (1st Site Initiation), Hungary (1st Site Initiation), Italy (1st Site Initiation), New Zealand (1st Site Initiation), Poland (Created), South Africa (1st Site Initiation), Spain (1st Site Initiation), United Kingdom (Created), United States of America (1st Site Initiation) | Australia, Austria, Finland, Germany, Hungary, Italy, New Zealand, South Africa, Spain, United States of America | 58 | 23 | 0 | 270 | 270 | 243 | 84 | 0 | 0 | 84 | 0 | 19 | 65
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0918 | Created (Cancelled) | Neupro in hospital setting | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Whitesides J | [6 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0919 | Study Archived | Neupro - Sleep lab study | Phase IV | Double Blind | UCB Pharma Global | GMA Neurology / Psychiatry | UCB Pharma Global | Dubois F | Anderson K | N/A | PRA |  |  | adults | No | A multi-centre, randomized, double-blind, placebo controlled study to evaluate the effects of Rotigotine on Sleep Efficiency in patients with Advanced Parkinson's disease. Amendment 1 dd 29 June 2011 | Parkinson's disease (advanced) | Central Nervous System |  | 2010-12-03 | 2010-12-03 | 2003-05-05: 2011-03-03; 2003-05-09: 2011-07-26; 2003-05-16: 2012-03-07; 2003-06-03: 2012-10-02; 2003-07-24: 2013-01-14; 2003-10-03: 2013-02-11; 2003-12-17: 2013-06-28; 2004-03-25: 2013-10-08 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 15 | 14 | 2 | 60 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 1
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0921 | Study Archived | A multi-center, randomized, double-blind, placebo-controlled | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Thierault S | Driver D |  | PharmaNet |  |  |  | No | A multicenter, randomized, double-blind, placebo-controlled, 5-arm, parallel-group study to assess rotigotine transdermal system dose response in subjects with advanced-stage Parkinson's disease | Parkinson's disease | Central Nervous System |  | 2007-02-09 | 2007-01-15 |  | 2007-06-01 | 2007-08-27 | 2007-07-27 | 2010-12-31 | 2011-02-04 | 2011-06-30 | 2011-07-08 | 2011-08-25 | 2011-09-08 | 2011-10-14 | 2011-12-22 | 2012-01-20 | 2012-04-03 | Chile, India, Mexico, Peru, United States of America | Chile (LPLV), India (LPLV), Mexico (LPLV), Peru (LPLV), United States of America (LPLV) | Chile, India, Mexico, Peru, United States of America | 80 | 88 | 85 | 700 | 500 | 500 | 702 | 4 | 184 | 514 | 4 | 105 | 405
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0927 | Created (Cancelled) | Phase 1 trial to Investigate bioequivalence between x-day pa | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | No | Long Title to be entered | Parkinson's disease | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0929 | CSR Approved | CUMPLIPARK Study | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Ayuga A, Whitesides J | [6 empty] | No | Therapeutic compliance in Parkinsons disease patients under pharmacological treatment in Spain | Parkinson's disease | Central Nervous System |  |  |  | 2004-03-25: 2008-12-10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0930 | Created (Cancelled) | Rotigotine effect in the Dose-Response Curve of levodopa | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Whitesides J | [6 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0931 | Created (Cancelled) | Double-blind placebo controlled trial with rotigotine in Chi | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Whitesides J | [6 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0932 | Created (Cancelled) | STRADA STUDY | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Whitesides J | [6 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0933 | Protocol Approved (Cancelled) | Randomized, 3-way crossover, relative bioavailability trial | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Strauss B, Whitesides J | [6 empty] | No | SINGLE SITE, RANDOMIZED, OPEN-LABEL, 3-WAY CROSSOVER TRIAL TO INVESTIGATE THE RELATIVE BIOAVAILABILITY OF 6.75MG/DAY (15CM2) ROTIGOTINE PATCH ON 3 DIFFERENT APPLICATION SITES IN HEALTHY MALE SUBJECTS. | Restless legs syndrome | Central Nervous System |  | 2007-08-31 | 2007-08-30 | 2003-05-05: 2008-01-07 | Germany | Germany (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0934 | Study Archived | Rotigotine in subjects with secondary RLS - Dialysis Trial - | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global | Goldammer N | Beinhauer-Zellenka U | N/A | PRA |  |  | adults | No | A MULTI-CENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL-GROUP, POLYSOMNOGRAPHY STUDY TO INVESTIGATE SAFETY AND EFFICACY OF THE ROTIGOTINE TRANSDERMAL PATCH IN SUBJECTS WITH RESTLESS LEGS SYNDROME AND END-STAGE RENAL DISEASE REQUIRING HEMODIALYSIS PHASE 3B | Restless legs syndrome | Central Nervous System |  | 2011-05-25 | 2011-06-02 |  | 2011-08-16 | 2012-01-31 | 2012-04-25 | 2012-10-30 | 2013-09-02 |  | 2013-10-29 |  | 2014-02-06 |  | 2014-02-24 |  | 2014-08-06 | Austria, Finland, France, Germany, Italy, United States of America | Austria (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), United States of America (LPLV) | Austria, Finland, France, Germany, Italy, United States of America | 20 | 20 | 15 | 48 | 33 | 24 | 50 | 0 | 20 | 30 | 0 | 5 | 25
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0935 | Protocol Approved (Cancelled) | Practicability/tolerability of switching idiopathic RLS subj | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Kelling D, Whitesides J | Tzschaschel B | [5 empty] | No | A PHASE 3B, OPEN-LABEL, MULTICENTER TRIAL TO ASSESS THE PRACTICABILITY AND TOLERABILITY OF SWITCHING SUBECTS OVERNIGHT FROM PRAMIPEXOLE OR ROPINIROLE TO ROTIGOTINE TRANSDERMAL PATCH AND ITS EFFECT ON SYMPTOMS IN SUBJECTS WITH IDIOPATHIC RESTLESS LEGS SYNDROME | Restless legs syndrome | Central Nervous System |  | 2007-09-17 |  | 2003-05-05: 2008-01-17 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0936 | Created (Cancelled) | Safety and tolerability of Rotigotine in subjects with secon | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Whitesides J | [6 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0937 | Created (Cancelled) | FU-Trial on SP882 | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Haeck H, Whitesides J | [6 empty] | No | _ | Parkinson's disease | Central Nervous System | [17 empty] | Germany | Germany (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0938 | Created (Cancelled) | Trial on GI-disorders | Phase IV |  | Affiliates |  | Affiliates | Whitesides J | [6 empty] | No |  |  |  |  | 2009-06-11 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0939 | Study Archived | CARE-ACT - NIS of RTG in PD re. caregivers (Germany) | Non Interventional Study - Retrospective | Open | Affiliates - Germany | GMA Neurology / Psychiatry | Affiliates - Germany | Kelling D | Tzschaschel B | N/A | Winicker Norimed |  |  |  | No | A multi-site, non interventional, cross-sectional evaluation of the caregivers preferred route of administration and the physicians rationale for the choice of Neupro as add-on therapy in patients with idiopathic Parkinson's desease requiring caregivers support |  |  |  | 2010-08-31 | 2010-11-15 | 2003-05-05: 2010-12-17; 2003-05-09: 2011-03-31; 2003-05-16: 2011-03-16; 2003-06-03: 2012-08-14; 2003-07-24: 2012-08-14; 2003-10-03: 2012-09-26; 2003-12-17: 2012-12-07; 2004-03-25: 2013-03-14 | Germany | Germany (LPLV) | Germany | 100 | 57 | 41 | 140 | 140 | 0 | 148 | 0 | 0 | 148 | 148 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0943 | Study Archived | Named Patient Program with Rotigotine Transdermal Patch | Named Patient Program | Open | UCB Pharma Global | Neurology | UCB Pharma Global |  |  | N/A | N/A | No | No | adults | No | NAMED PATIENT PROGRAM WITH ROTIGOTINE TRANSDERMAL PATCH IN PATIENTS WITH EARLY AND ADVANCED IDIOPATHIC PARKINSON'S DISEASE | Parkinson's disease (early); Parkinson's disease (advanced); Restless legs syndrome | Central Nervous System; Central Nervous System; Central Nervous System |  | 2008-02-11 | 2008-02-11 |  | 2008-07-25 | 2008-08-27 | 2008-08-27 | 2009-03-16 | 2014-10-08 | 2011-12-01 | 2015-05-30 |  |  |  |  | 2012-04-19 | 2015-10-19 | Belgium, Bulgaria, China, France, Hungary, India, Netherlands, New Zealand, South Africa | Belgium (LPLV), Bulgaria (LPLV), China (LPLV), France (LPLV), Hungary (LPLV), India (LPLV), Italy (1st Site Initiation (Cancelled)), Netherlands (LPLV), New Zealand (LPLV), South Africa (LPLV) | Belgium, Bulgaria, China, France, Hungary, India, Netherlands, New Zealand, South Africa | 81 | 54 | 52 | 735 | 735 | 600 | 0 | 0 | 0 | 665 | 490 | 77 | 98
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0949 | Created (Cancelled) | An open-label trial to assess the safety and tolerability of | Phase III | Open | Affiliates |  | Affiliates | Whitesides J | [6 empty] | No |  |  |  |  | 2009-06-11 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0950 | Created (Cancelled) | Neupro in Indian patients with advanced PD | Phase III | Open | Affiliates |  | Affiliates | [7 empty] | No |  |  |  |  | 2011-03-11 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0951 | CSR Approved | BE of rotigotine patches from registered vs. modified manufa | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | Yes | single-site, open-label, randomized, Cross-over trial to evaluate the Bioequivalence of single dose rotigotine transdermal patch (4.5mg/10cm2) from 2 different manufacturing processes | Parkinson's disease | Central Nervous System |  | 2008-04-18 | 2008-04-08 | 2003-05-05: 2008-08-04; 2003-05-16: 2008-10-17; 2003-06-03: 2008-11-18; 2003-07-24: 2008-12-08; 2003-10-03: 2009-01-12; 2003-12-17: 2009-02-12; 2004-03-25: 2009-02-27 | Germany | Germany (Created) |  | 1 | 0 | 0 | 52 | 52 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0953 | Study Archived | NPP with rotigotine transdermal system in US | Named Patient Program | Open | UCB Pharma Global | GMA Neurology / Psychiatry | UCB Pharma Global | Doe-Anderson J |  | N/A | Next Generation |  |  | adults | No | Named Patient Program with Rotigotine Transdermal System | [6 empty] | 2008-07-16 | 2008-11-19 | 2008-11-19 | 2009-02-09 | 2012-07-24 |  | 2012-12-03 |  | 2013-05-01 |  | 2013-07-12 |  | 2013-10-25 | United States of America | United States of America (LPLV) | United States of America | 70 | 57 | 51 | 750 | 500 | 300 | 0 | 0 | 0 | 520 | 0 | 319 | 201
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0957 | CSR Approved | Ph1 study - BE betw rotigotine patches from diff manuf sites | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | Yes | Single-site, open-label, randomized, cross-over study in healthy subjects to evaluate the bioequivalence of single dose rotigotine transdermal patch (4.5mg/10cm2) from 2 different manufacturing sites |  |  |  | 2009-05-06 |  | 2003-05-05: 2009-05-06; 2003-05-16: 2009-07-20; 2003-06-03: 2009-08-07; 2003-07-24: 2009-08-28; 2003-10-03: 2009-10-15; 2003-12-17: 2009-11-06; 2004-03-25: 2010-02-10 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 70 | 40 | 36 | 91 | 51 | 0 | 40 | 23 | 0 | 17
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0959 | Created (Cancelled) | RLS-Life: Non Interventional Study in Patients with Restless | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Randerath O, Whitesides J | [6 empty] | No | RLS-Life: Non Interventional Study in Patients with Restless Legs Syndrome (RLS) to Assess the Safety, Efficacy, and Influence on Quality of Life of Neupro® in Daily Practise | Restless legs syndrome | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0970 | Study Archived | NON-GI - NIS of RTG in PD patients with GI problems (Germany | Non Interventional Study - Prospective | Open | Affiliates - Germany | GMA Neurology / Psychiatry | Affiliates - Germany | Kelling D | Tzschaschel B |  |  |  |  | adults | No | Patients with gastrointestinal complaints non interventional |  |  |  | 2009-01-31 | 2010-01-28 |  | 2010-02-15 | 2010-05-31 | 2010-06-21 | 2011-06-24 | 2012-01-05 | 2012-02-17 | 2012-03-12 | 2012-04-17 | 2012-04-18 | 2012-06-18 | 2012-06-20 | 2012-11-19 | 2013-01-08 | Germany | Germany (LPLV) | Germany | 40 | 38 | 20 | 70 | 70 | 55 | 76 | 0 | 0 | 76 | 0 | 21 | 55
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0976 | Study Archived | Non Motor symptoms - Parkinson's disease | Phase IV | Double Blind | UCB Pharma Global | GMA Neurology / Psychiatry | Global Medical Affairs | Vandendriessche A | Beaman M | N/A | PRA |  |  | adults | No | MULTICENTER, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL-GROUP, PHASE IV STUDY TO ASSESS THE EFFECT OF ROTIGOTINE ON NON-MOTOR SYMPTOMS IN PATIENTS WITH IDIOPATHIC PARKINSON’S DISEASE | Parkinson's disease | Central Nervous System |  | 2010-05-03 | 2010-05-28 |  | 2010-09-14 | 2011-03-17 | 2011-02-23 | 2012-05-23 | 2012-05-24 |  | 2012-11-20 |  | 2013-01-22 |  | 2013-03-18 |  | 2013-07-17 | Austria, Belgium, Bulgaria, Czech Republic, France, Germany, Hungary, Italy, Romania, Slovakia, Spain, Switzerland | Austria (LPLV), Belgium (LPLV), Bulgaria (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Romania (LPLV), Slovakia (LPLV), Spain (LPLV), Switzerland (LPLV) | Austria, Belgium, Bulgaria, Czech Republic, France, Germany, Hungary, Italy, Romania, Slovakia, Spain, Switzerland | 80 | 88 | 71 | 400 | 345 | 333 | 377 | 3 | 25 | 349 | 0 | 64 | 285
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0977 | Study Archived | ENCORE | Phase IV | Double Blind | UCB Pharma Global | GMA Neurology / Psychiatry | Global Medical Affairs US | Nilius S, Wang Y | Beinhauer-Zellenka U | N/A | RPS Research Germany GmbH, Scheurlstr. 21, 90478 Nuremberg, Germany |  |  | adults | No | MULTICENTER, DOUBLE-BLIND, PLACEBOCONTROLLED, TWO-ARM, RANDOMIZED, PARALLEL, TREATMENT INTERVENTION, SLEEP LAB PHASE 4 STUDY TO ASSESS THE EFFECT OF ROTIGOTINE ON NOCTURNAL BLOOD PRESSURE IN PATIENTS WITH IDIOPATHIC RESTLESS LEGS SYNDROME | Restless legs syndrome | Central Nervous System |  | 2010-11-12 | 2010-12-22 |  | 2011-02-17 | 2011-08-23 | 2011-09-29 | 2012-04-19 | 2012-03-09 |  | 2012-06-21 |  | 2013-02-11 |  | 2013-02-28 |  | 2013-06-24 | Germany | Germany (LPLV) | Germany | 12 | 10 | 9 | 90 | 72 | 60 | 120 | 27 | 11 | 82 | 0 | 15 | 67
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP0987 | Study Archived | BE Study for Rotigotine 2.1.1 vs.2.2.1 | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K |  | in-house |  |  |  | Yes | Single-site, open-label, randomised, cross-over study in healthy subjects to evaluate the bioequivalence of single dose rotigotine transdermal patch (4.5 mg/10 cm2) comparing 2 different formulations | Parkinson's disease | Central Nervous System |  | 2009-08-05 |  |  | 2009-09-28 | 2010-01-14 | 2010-01-07 | 2010-02-05 | 2010-02-08 | 2010-06-17 | 2010-03-05 | 2010-04-16 | 2010-04-16 | 2010-05-21 | 2010-05-20 | 2010-11-10 | 2010-12-03 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 100 | 50 | 45 | 85 | 0 | 35 | 50 | 0 | 0 | 48
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP1004 | Study Archived | A MULTICENTER, OPEN-LABEL, 2-GROUP, DOSE ESCALATION STUDY | Phase II | Open | UCB Pharma Global | Neurology | R & D | Doggett K | Smit R | N/A | PRA |  |  | paediatrics | No | A MULTICENTER, OPEN-LABEL, 2-GROUP, DOSE ESCALATION STUDY OF MONOTHERAPY ADMINISTRATION OF ROTIGOTINE IN PEDIATRIC SUBJECTS WITH IDIOPATHIC RESTLESS LEGS SYNDROME | Restless legs syndrome | Central Nervous System | SP1004 is a parent study of SP1005 | 2011-01-19 | 2011-01-19 |  | 2011-03-14 | 2011-06-30 | 2011-12-01 | 2014-01-31 | 2014-03-18 |  | 2014-04-30 |  | 2014-08-13 |  | 2014-09-30 |  | 2014-10-22 | United States of America | United States of America (LPLV) | United States of America | 12 | 13 | 8 | 35 | 24 | 24 | 42 | 0 | 18 | 24 | 0 | 1 | 23 |  |  | 2015-11-16
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP1005 | Study Archived | AN OPEN-LABEL, LONG-TERM FOLLOW-UP STUDY TO DETERMINE | Phase II | Open | GCSO | Neurology | GCSO | Hernandez D | Smit R | N/A | PRA | No | No | paediatrics | No | AN OPEN-LABEL, LONG-TERM FOLLOW-UP STUDY TO DETERMINE THE SAFETY, TOLERABILITY, AND EFFICACY OF ROTIGOTINE TRANSDERMAL SYSTEM AS MONOTHERAPY IN ADOLESCENTS WITH RESTLESS LEGS SYNDROME | Restless legs syndrome | Central Nervous System | SP1005 is a follow up of SP1004 | 2011-03-14 | 2011-03-18 | 2003-05-05: 2011-03-31; 2003-05-09: 2011-09-14; 2003-05-16: 2012-01-21; 2003-05-30: 2014-06-24; 2003-06-03: 2014-04-30; 2003-07-24: 2015-12-07; 2003-10-03: 2016-02-08; 2004-03-25: 2016-05-05 | United States of America | United States of America (LPLV) | United States of America | 12 | 13 | 5 | 24 | 24 | 24 | 0 | 0 | 0 | 14 | 1 | 12 | 1
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP1009 | Study Archived | AURORA: NIS-AWB of Neupro in RLS (Germany) | Non Interventional Study - Prospective | Open | Affiliates - Germany | CNS | UCB Pharma Global | Kelling D | Tzschaschel B | N/A | Acromion |  |  | adults | No | multi-site, non interventional observational study to collect explorative Data for the Effect of switching to Neupro on severity of RLS Symptoms and Augmentation as well as the change in Treatment Regimen used in patients with idiopathic Restless Legs Syndrom who experienced Augmentation during previous oral dopaminergic Therapy in physicians routince practice | Restless legs syndrome | Central Nervous System |  | 2010-08-27 | 2010-11-24 |  | 2011-03-15 | 2011-07-01 | 2011-07-06 | 2012-04-05 | 2012-07-30 |  | 2013-08-07 |  | 2013-12-10 |  | 2014-02-04 |  | 2014-06-27 | Germany | Germany (LPLV) | Germany | 20 | 21 | 18 | 100 | 100 | 100 | 102 | 0 | 0 | 102 | 0 | 61 | 41 |  |  | 2012-11-15 | 2012-11-15
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP1020 | Created (Cancelled) | NIS to investigate the effectiveness of Neupro in daily clin | Non Interventional Study - Prospective | Open | Global Medical Affairs Europe | GMA Neurology / Psychiatry | Affiliates | Awedikian R, Joeres L | Baukens C | PRA | PRA |  |  |  | No |  | Parkinson's disease | Central Nervous System |  | 2013-11-05 | [15 empty] | France | France (Created) |  | 100 | 0 | 0 | 300 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP1036 | Study Archived | Comparison rotigotine plasma conc cs. saliva | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Hoeckendorff J, Whitesides J | Anderson K | [5 empty] | Yes | A single-site, open-label study in healthy male subjects to compare rotigotine saliva and plasma concentrations after single dose application of rotigotine transdermal patch |  |  |  | 2010-04-17 |  |  | 2010-06-28 | 2010-10-01 | 2010-09-28 | 2010-10-08 | 2010-10-05 | 2010-10-27 | 2010-10-27 | 2010-12-14 | 2010-12-14 | 2011-02-08 | 2011-02-08 | 2011-04-29 | 2011-05-17 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 28 | 14 | 12 | 27 | 0 | 10 | 14 | 0 | 0 | 14
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP1037 | Study Archived | China advanced DB PC | Phase III | Double Blind | Clinical Development Asia | CNS | Affiliate China | Wang L | Wu G | N/A | PXL |  |  | adults | No | A MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PARALLEL-GROUP, PLACEBO-CONTROLLED STUDY OF THE EFFICACY AND SAFETY OF ROTIGOTINE TRANSDERMAL PATCH IN CHINESE SUBJECTS WITH ADVANCED-STAGE, IDIOPATHIC PARKINSON’S DISEASE WHO ARE NOT WELL CONTROLLED ON LEVODOPA PHASE 3 | Parkinson's disease (advanced) | Central Nervous System |  | 2010-06-03 | 2010-05-29 |  | 2012-01-23 | 2012-06-30 | 2012-08-03 | 2013-08-28 | 2014-05-09 |  | 2014-10-21 |  | 2014-11-25 |  | 2015-01-30 |  | 2015-03-03 | China | China (LPLV) | China | 26 | 25 | 24 | 430 | 346 | 332 | 414 | 0 | 67 | 347 | 0 | 34 | 313
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP1041 | Study Archived | PROVE-D | Phase IV | Double Blind | UCB Pharma Global | GMA Neurology / Psychiatry | Affiliates | Park M | Matsuoka K | N/A | A Plus Company | No | No | adults | No | DOUBLE BLIND, PLACEBO-CONTROLLED, PARALLEL, MULTICENTER, RANDOMIZED INTERVENTIONAL PHASE IV STUDY TO EVALUATE THE EFFICACY OF ROTIGOTINE ON DEPRESSIVE SYMPTOMS IN IDIOPATHIC PARKINSON’S DISEASE PATIENTS | Parkinson's disease | Central Nervous System |  | 2011-03-17 | 2011-03-17 |  | 2011-09-10 | 2012-01-17 | 2012-04-06 | 2013-03-30 | 2014-05-22 |  | 2014-10-23 |  | 2014-11-20 |  | 2015-02-03 |  | 2015-04-27 | South Korea | South Korea (LPLV) | South Korea | 30 | 29 | 29 | 461 | 392 | 242 | 439 | 0 | 57 | 382 | 0 | 69 | 313
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP1049 | Study Archived | BE Study of new RT Neupro adhesiveness (Germany) | Phase I | Open | GED |  | GED | Mollet M | Mccabe S | N/A | Feth Monitoring |  |  | adults | Yes | SINGLE-SITE, OPEN-LABEL, RANDOMIZED, CROSS-OVER STUDY IN HEALTHY SUBJECTS TO EVALUATE THE BIOEQUIVALENCE OF SINGLE DOSE ROTIGOTINE TRANSDERMAL PATCH (2MG/24H) COMPARING 2 DIFFERENT FORMULATIONS | Parkinson's disease (early); Parkinson's disease (advanced); Restless legs syndrome | Central Nervous System; Central Nervous System; Central Nervous System | SP1049 is a "sister" study of PD0011 | 2012-01-19 |  | 2003-05-05: 2012-04-03; 2003-05-09: 2012-08-27; 2003-05-16: 2012-08-30; 2003-06-03: 2012-12-04; 2003-07-24: 2012-12-28; 2003-10-03: 2013-02-15; 2003-12-17: 2013-04-18; 2004-03-25: 2013-07-10 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 50 | 50 | 38 | 148 | 0 | 76 | 72 | 0 | 0 | 72
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP1055 | Study Archived | Effect of rotigotine in PD patients with motor fluctuations | Phase III | Double Blind | Clinical Development USA | CNS | Global Medical Affairs US | Thierault S | Driver D | N/A | PRA |  |  | adults | No | A MULTICENTER, DOUBLE-BLIND, RANDOMIZED, PLACEBO-CONTROLLED, PARALLEL-GROUP STUDY TO ASSESS THE EFFECT OF ROTIGOTINE ON MOTOR SYMPTOMS IN PATIENTS WITH ADVANCED PARKINSON’S DISEASE WITH MOTOR FLUCTUATIONS AND SYMPTOMS OF GASTROINTESTINAL DYSFUNCTION | Parkinson's disease (advanced) | Central Nervous System |  | 2011-07-29 | 2011-07-19 |  | 2011-10-10 | 2012-01-13 | 2012-01-31 | 2012-12-29 | 2013-09-10 |  | 2013-10-17 |  | 2014-01-10 |  | 2013-12-16 |  | 2014-03-20 | United States of America | United States of America (LPLV) | United States of America | 25 | 26 | 20 | 250 | 190 | 150 | 61 | 0 | 36 | 25 | 0 | 17 | 8
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP1057 | Created (Cancelled) | Phase IIIb RLS CV Encore 2 | Phase III |  | Clinical Development USA | CNS | UCB Pharma Global | Oortgiesen M |  | PRA | SPI PRA |  |  |  | No |  | Restless legs syndrome | Central Nervous System |  | 2015-05-12 | [18 empty] | 15 | 0 | 0 | 90 | 85 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP1058 | Study Archived | Pain in Parkinson's disease | Non Interventional Study - Prospective | Open | UCB Pharma Global | GMA Neurology / Psychiatry | Affiliates - Germany | Will E | Copetti C | PRA | SPI PRA |  |  | adults | No | NEUPAD: A multicenter, noninterventional study with Neupro to evaluate the perception of pain associated with idiopathic Parkinson’s disease | Parkinson's disease | Central Nervous System |  | 2011-02-23 | 2012-03-19 |  | 2012-03-19 | 2012-05-04 | 2012-05-04 | 2013-05-11 | 2014-03-28 |  | 2014-07-03 |  | 2014-07-30 |  | 2014-09-10 |  | 2014-12-09 | Austria, Germany | Austria (LPLV), Germany (LPLV) | Austria, Germany | 50 | 50 | 28 | 90 | 90 | 90 | 93 | 0 | 0 | 93 | 0 | 16 | 77
Yes | Not assigned | Managing Type | 1 | NEUPRO | Central Nervous System | SP1066 | Study Archived | patch adhesiveness study | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Lemmerz U | Weinsberg F |  | In-house management, by UCB |  |  |  | No | A MULTICENTER, RANDOMIZED, DOUBLE-BLIND, TWO WAY CROSS-OVER STUDY TO COMPARE THE ADHESIVENESS OF TWO DIFFERENT ROTIGOTINE PATCH FORMULATIONS IN SUBJECTS WITH PARKINSON'S DISEASE PHASE 1 | Parkinson's disease | Central Nervous System |  | 2010-11-11 | 2010-11-23 |  | 2010-12-21 | 2011-04-15 | 2011-04-08 | 2011-06-03 | 2011-05-09 | 2011-06-02 | 2011-06-02 | 2011-07-07 | 2011-07-07 | 2011-08-10 | 2011-08-10 | 2011-10-12 | 2011-10-20 | Austria, Germany, United Kingdom | Austria (LPLV), Germany (LPLV), United Kingdom (LPLV) | Austria, Germany, United Kingdom | 22 | 16 | 14 | 56 | 52 | 50 | 58 | 0 | 2 | 56 | 0 | 0 | 56
Yes | Not assigned | Managing Type | 1 | NEUPRO | not defined | PD0028 | Study Archived | Parkinson's Disease Device Study_mc10 | Phase I | Open | GCSO | Neurology | GCSO | Melton K | Beaman M | Parexel | SPI PXL | No | No | adults | No | A TWO-PART PILOT STUDY TO ASSESS THE FEASIBILITY OF THE NIMBLE PATCH TO CONTINUOUSLY MEASURE MOTOR SYMPTOMS IN SUBJECTS WITH PARKINSON’S DISEASE | Parkinson's disease | Central Nervous System |  | 2014-07-31 08:00 | 2014-07-31 |  | 2014-11-13 | 2015-01-17 | 2014-12-09 | 2015-06-19 | 2016-03-07 | 2015-06-26 | 2016-07-01 | 2015-07-24 | 2016-08-10 | 2015-09-18 | 2016-09-13 | 2016-01-08 | 2017-01-25 | United States of America | United States of America (LPLV) | United States of America | 3 | 2 | 2 | 23 | 20 | 20 | 24 | 0 | 1 | 23 | 0 | 3 | 20
Yes | Not assigned | Managing Type | 1 | NEUPRO | not defined | PD0049 | Study Archived | Device Study in Patients with PD | Phase IV | Not Applicable | GCSO | Neurology | UCB Pharma Global | Brown E | Tillery N | Parexel | SPI PXL | No | Yes | adults | No | A MULTICENTER, OPEN-LABEL, TWO-ARM STUDY TO EVALUATE THE IMPACT OF USING WEARABLE DEVICES IN ADDITION TO STANDARDCLINICAL PRACTICE ON PARKINSON’S. | Parkinson's disease | Central Nervous System |  | 2016-09-22 | 2016-09-12 |  | 2016-12-21 | 2017-05-04 | 2017-03-16 | 2017-07-27 | 2017-10-20 |  | 2018-01-02 |  | 2018-02-05 |  | 2018-02-22 |  | 2018-05-29 | United States of America | United States of America (LPLV) | United States of America | 6 | 9 | 8 | 40 | 40 | 40 | 57 | 0 | 17 | 40 | 0 | 4 | 36
Yes | Not assigned | Managing Type | 1 | NEUPRO | not defined | SP0786 | Study Archived | SPM 952:SD pilot PK | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J | Anderson K | [5 empty] | Yes | Randomized, open-label, single-dose, two-way crossover pilot trial to investigate the pharmacokinetics, safety and tolerability of a rotigotine nasal spray (2.5mg/mL) in comparison to a single dose administration of a rotigotine transdermal patch (4.5mg/10cm2 ) in six healthy male subjects |  |  |  | 2004-02-20 | 2004-02-20 | 2003-05-05: 2004-03-08; 2003-05-16: 2004-04-14; 2003-06-03: 2004-04-19; 2003-07-24: 2004-05-17; 2003-10-03: 2004-08-16; 2003-12-17: 2005-04-15; 2004-03-25: 2006-07-11 | Germany | Germany (Created) |  | 1 | 0 | 0 | 6 | 6 | 5 | 21 | 15 | 0 | 6 | 0 | 1 | 5
Yes | Not assigned | Managing Type | 1 | NEUPRO | not defined | SP0787 | Study Archived | Comparison of PK, bioavailability, safety and tolerability o | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Hoeckendorff J | Anderson K | [5 empty] | Yes | SPM 952: multiple dose trial |  |  |  | 2004-08-05 | 2004-08-05 | 2003-05-05: 2004-08-26; 2003-05-16: 2004-11-12; 2003-06-03: 2005-01-13; 2003-07-24: 2005-02-10; 2003-10-03: 2005-03-29; 2003-12-17: 2005-09-16; 2004-03-25: 2006-07-26 | Germany | Germany (Created) |  | 1 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 13 | 0 | 1 | 12
Yes | Not assigned | Managing Type | 1 | NEUPRO | not defined | SP0789 | Created (Cancelled) | rotigotine Nasal Spray | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | rotigotine Nasal Spray | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NEUPRO | not defined | SP0873 | Study Archived | Proof of concept trial of rotigotine nasal spray for acute t | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Schmid M | [6 empty] | No | A double blind, placebo controlled, parallel group, proof of concept trial to assess the tolerability, safety, and efficacy of rotigotine nasal spray for the acute treatment of 'off' symptoms in patients with advanced stage, idiopathic Parkinson's disease | Parkinson's disease (advanced) | Central Nervous System |  | 2005-09-09 | 2005-09-09 | 2003-05-05: 2005-11-17; 2003-05-16: 2006-02-08; 2003-06-03: 2006-05-22; 2003-07-24: 2006-06-23; 2003-10-03: 2006-08-28; 2003-12-17: 2006-10-31; 2004-03-25: 2008-03-10 | Austria, Germany, Spain, United Kingdom | Austria (Created), Germany (Created), Spain (Created), United Kingdom (Created) |  | 12 | 0 | 0 | 100 | 80 | 75 | 104 | 0 | 0 | 79 | 0 | 0 | 79
Yes | Not assigned | Managing Type | 1 | NEUPRO | not defined | SP0879 | Study Archived | Nasal spray for RLS | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Raetz M | Bonny M | [5 empty] | No | A RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL-GROUP PROOF-OF-CONCEPT TRIAL TO ASSESS THE EFFICACY, SAFETY AND TOLERABILITY OF ASCENDING DOSES OF ROTIGOTINE NASAL SPRAY FOR THE ACUTE TREATMENT OF RLS SYMPTOMS IN SUBJECTS WITH IDIOPATHIC RESTLESS LEGS SYNDROME | Restless legs syndrome | Central Nervous System |  | 2006-04-13 | 2006-04-13 | 2003-05-05: 2006-06-06; 2003-05-16: 2006-08-31; 2003-06-03: 2006-10-26; 2003-07-24: 2006-11-29; 2003-10-03: 2007-01-09; 2003-12-17: 2007-03-01; 2004-03-25: 2007-08-09 | Germany | Germany (Created) |  | 2 | 0 | 0 | 60 | 40 | 30 | 59 | 0 | 0 | 44 | 0 | 7 | 37
Yes | Not assigned | Managing Type | 1 | Nicotine | not defined | SP0374 | Created | Drug Safety Trial Data. Study drug: NIKOTIN-TTS |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Drug Safety Trial Data. Study drug: NIKOTIN-TTS | [22 empty] | 0 | 0 | 0 | 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Nicotine | not defined | SP0376 | Created | Nicotine - SPM 743 - Patch - Nicotinell TTS 20 - 18 Healthy |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Evaluation of the Skin Tolerability, Adhesiveness and Apparent Dose of Two Newly Developed Types of Nicotine Patch (Nicotine-TTS (SPM 743), Type I and Type II) in Comparison to the Reference patch (Nicotinell TTS 20) in 18 Healty Volunteers | [22 empty] | 0 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Nicotine | not defined | SP0393 | Created | Nicotine - Nicotinell TTS 20 - Patches - Healthy Volunteers |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Evaluation of the Bioavailability Skin Tolerability and Apparent Dose of Two Newly Developed Types of Nicotine Patches (Nicotine 20 mg, 7 % and 8 % - SXS) in Comparison to the Reference Patch (Nicotinell TTS 20) in 18 Healthy Volunteers | [22 empty] | 0 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Nicotine | not defined | SP0417 | Created | Drug Safety Trial Data. Study drug: NICOTIN-TDS |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Drug Safety Trial Data. Study drug: NICOTIN-TDS | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Nitrendipine | not defined | SP0461 | Created | Drug Safety Trial Data. Study drug: NITRENDIPINE |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: NITRENDIPINE | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0088 | Created | Drug Safety Trial Data. Study drug: DEPONIT |  |  | UCB Pharma Global |  | UCB Pharma Global | Grosse-Freese M | [6 empty] | No | Drug Safety Trial Data. Study drug: DEPONIT | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0089 | Created | DEPONIT - in patients suffering from stable angina pectoris |  |  | UCB Pharma Global |  | UCB Pharma Global | Sabia R | [6 empty] | No | Randomized, double blind, parallel group study on the correlations between the sympathetic activation, the response rate to a nitrate therapy and the development of tolerance in patients suffering from stable angina pectoris | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0102 | Created | DEPONIT - on unselected groups of patients undergoing periph |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | A study of the effect of transdermal glyceryl Trinitrate deponit (5 & 10) on the incidence of peri-operative silent myocardial ischaemia, and clinical events after surgery on unselected groups of patients undergoing peripheral vascular surgery | [22 empty] | 0 | 0 | 0 | 174 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0113 | Created | GTN-PFLASTER / BIOPHASE-5 (Kanülenverweildauer unter Begleit |  |  | UCB Pharma Global |  | UCB Pharma Global | Gathmann-Lewik U | [6 empty] | No | GTN-PFLASTER / BIOPHASE-5 (Kanülenverweildauer unter Begleittherapie) | [22 empty] | 0 | 0 | 0 | 60 | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0114 | Created | GTN - in CHD patients |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | Effect of Perlinganit Spray 0.2 on the recovery from exercise - Induced ST Depression in CHD patients as compared with twice the dosage of a reference aerosol | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0115 | Created | GTN in patients with angina pectoris |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | Double-blind, placebo controlled trial to assess efficacy and dose response relationship of nitroglycerin spray in patients with angina pectoris | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0212 | Created | DEPONIT - during coronary angioplasty |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | Randomized, double-blind, placebo controlled study about Deponit 10 given before and Perlinganit 0,2 mg given during coronary angioplasty | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0223 | Created | DEPONIT - in patients with known coronary artery disease |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | Perioperative myocardial ischemia in patients undergoing noncardia surgery: effect of transdermal glyceryl trinitrate | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 150 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0229 | Created | DEPONIT - in patients in pre-term labour between 32 and 36 w |  |  | UCB Pharma Global |  | UCB Pharma Global | Lees C | [6 empty] | No | A double-blind, placebo-controlled, randomised, parallel group, dose-reponse study of the safety and efficacy of transdermal glyceryl trinitrate (GTN) in doses of 5, 10, 15 and 20 mg versus placebo in patients in pre-term labour between 32 and 36 weeks of pregnancy | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0269 | Created | Acrylic Transdermal Nitroglycerin Patch - Nitro Dur Patch |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | A Bioequivalence Study of One (0.6 mg/hour) Acrylic Transdermal Nitroglycerin Patch (Schwarz Pharma Ag) and One Nitro-Dur Patch (Key Pharmaceuticals) | [22 empty] | 0 | 0 | 0 | 50 | 47 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0316 | Created | Bioequivalence - two different GTN-patches- 40 healthy volun |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Bioequivalence Evaluation of two different GTN-patches after twelve hours of usage in 40 healthy volunteers | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0331 | Created | Apparent release of Nitroglycerin in vivo |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Apparent release of Nitroglycerin in vivo | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0335 | Created | Skin Tolerability - Glycerol Trinitrate Patch SPM 751 in He |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Open Multiple Application Study to Evaluate the Skin T olerability of the Glcerol Trinirate patch SPM 751 in Comparison to a Placebo Patch and a W ound Patch in 24 Healthy Volunteers | [22 empty] | 0 | 0 | 0 | 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0341 | Created | DEPONIT - in pre-term labour as compared to placebo |  |  | UCB Pharma Global |  | UCB Pharma Global | Lees C | [6 empty] | No | A double-blind, placebo-controlled, randomised, parallel group study of the efficacy and safety of transdermal glyceryl trinitrate (GTN) compared to placebo in preterm labour between 24 weeks and 31 weeks + 6 days of pregnancy | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0342 | Created | DEPONIT - in pre-term labour as compared to intravenous rito |  |  | UCB Pharma Global |  | UCB Pharma Global | Lees C | [6 empty] | No | A randomised parallel group study of the efficacy of transdermal glyceryl trinitrate (GTN) compared to the ß-mimetic ritodrine in preterm labour between 24 weeks and 31 weeks + 6 days of pregnancy | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0348 | Created | Bioequivalence of SPM 752 - Acrylat TTS vs Nitrodur |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Bioequivalence of SPM 752 - BV von Acrylat TTS (SP 752) gegenüber Nitrodur | [22 empty] | 0 | 0 | 0 | 50 | 47 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0360 | Created | GTN-Patch, Two different dose, 40 Healthy Volunteers |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | An Open Label Phase I Study to Compare the Bioavailability of Two Different Dose Regimens of a Newly Developed GTN-Patch after Twelve Hours of Usage in 40 Healthy Volunteers | [22 empty] | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0361 | Created | Bioequivalence of SPM 751 (0.4 mg/h) |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Bioequivalence of SPM 751 | [22 empty] | 0 | 0 | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0408 | Created | Drug Safety Trial Data. Study drug: DEPONIT |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: DEPONIT | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0471 | LPLV | Deponit in subjects with CHD | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Quellhorst A | [6 empty] | No | Open study to evaluate the adhesiveness of Deponit 5 versus Venetrin T5, Nitrodur 5 mg, Nitrosylon 5 mg and Nitroderm TTS 5. | Coronary Heart Disease | Immunology |  | 1997-09-01 | 1997-09-01 | 2003-05-05: 1998-08-05; 2003-05-16: 1999-03-01; 2003-06-03: 1999-07-09; 2003-07-24: 1999-07-09 | Italy | Italy (Created) |  | 1 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 34 | 0 | 0 | 34
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0478 | Protoc. Summary Approved | Acrylic Transdermal Nitroglycerin Patches and two Diafusor P | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | A bioequivalence study of two (0.2 MG/Hour) acrylic transdermal nitroglycerin patches (Schwarz Pharma AG) and two Diafusor (5 MG/24Hour) patches (Pierre Fabre Cardio Vasulaire) |  |  |  | 1998-08-03 | 1998-08-03 | [14 empty] | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 50 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0492 | Created | Acrylic GTN TDS 10 mg / 24h | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | A two-period open label randomized single dose cross-over study in 50 healthy male volunteers to evaluate the bioequivalence of acrylic GTN TDS, 10 mg/24h (Schwarz Pharma) versus Diafusor 10mg/24h (Pierre Fabre Cardio Vasulaire) after 16 hours of usage. | [22 empty] | 0 | 0 | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0493 | Protoc. Summary Approved | Nitroglycerin Phase 1 | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Delgado A | [6 empty] | No | Comparison of the bioavailabilities of Nitroglycerin after cutaneous applications using two forms of transdermal delivery systems |  |  |  | 1998-08-18 | 1998-08-18 | [14 empty] | France | France (Created) |  | 0 | 0 | 0 | 72 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0494 | Created | FIV Trinitrine-patch - not available (DMCD) | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Investigation of NO in in vitro fertilisation | [19 empty] | France | France (Created) |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NITROCINE | not defined | SP0781 | Final TFLs released (Stopped) | Quality of life assestment of patients with Angina Pectoris | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Gallego C | [6 empty] | No | Evaluate the quality of life (QOL) of patients with stable Angina Pectoris with or without previous treatment, both 3 months before and after starting treatment with Cordiplast. |  |  |  | 2001-12-24 | 2001-06-01 | 2003-05-05: 2001-09-01; 2003-05-16: 2001-11-28; 2003-06-03: 2002-06-01; 2003-07-24: 2002-09-01; 2003-12-17: 2003-07-01 |  |  |  | 0 | 0 | 0 | 1734 | 1309 | 1198 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NOOTROPIL | Central Nervous System | 9120 | Study Archived | Acute stroke - PASS | Phase III |  | Clinical Development Europe | CNS | Global Medical Affairs | Trippas E | [6 empty] | No | Piracetam vs. placebo in the acute treatment of acute ischemic supratentorial cerebrovascular accidents - a double-blind, randomized, multicenter study. | [5 empty] | 2003-05-05: 1991-11-08; 2003-10-03: 1995-07-30; 2004-03-25: 1998-12-16 | Austria, Belgium, France, Germany, Greece, Hungary, Netherlands, Portugal, Spain, United Kingdom | Austria (Created), Belgium (Created), France (Created), Germany (Created), Greece (Created), Hungary (Created), Netherlands (Created), Portugal (Created), Spain (Created), United Kingdom (Created) |  | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NOOTROPIL | Central Nervous System | 9542 | CSR Approved | Age Related Cognitive Decline | Phase III | Double Blind | Affiliates - France | CNS | Affiliates - France | Benkaci D | [6 empty] | No | Etude en double aveugle contrôlée par un placebo de 2 doses de piracetam 2.4 g et 4.8g chez des patients présentant un déclin cognitif lié à l'âge (ARCD) | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2003-05-05: 1996-01-04; 2003-05-16: 1996-09-01; 2003-07-24: 1998-07-01; 2003-10-03: 1999-02-12; 2003-12-17: 1999-02-25; 2004-03-22: 1998-12-31; 2004-03-25: 2005-05-25 | France | France (LPLV) | France | 15 | 0 | 1 | 333 | 306 | 0 | 333 | 0 | 27 | 306 | 0 | 31 | 275
Yes | Not assigned | Managing Type | 1 | NOOTROPIL | Central Nervous System | 9640 | CSR Approved | Angelman syndrome (myoclonus) | Phase III | Double Blind | Affiliates - Italy | CNS | Affiliates - Italy | [7 empty] | No | A randomized, cross-over, double blind, placebo controlled clinical study to evaluate the eficacy of piracetam 400mg/kg/day as add-on therapy in the treatment of cortical myoclonus of Angelman syndrome | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 1997-05-23 | 1998-10-01 | 1998-11-25 |  |  | 1999-12-31 | 2001-06-02 | 2000-04-30 | 2001-08-07 |  |  | 2000-08-31 | 2005-06-15 | Italy | Italy (LPLV) | Italy | 1 | 0 | 1 | 18 | 18 | 16 | 18 | 0 | 0 | 18 | 0 | 2 | 16
Yes | Not assigned | Managing Type | 1 | NOOTROPIL | Central Nervous System | 9642 | Study Archived | ACUTE STROKE (PASS II) | Phase III | Double Blind | Clinical Development Europe | CNS | Global Medical Affairs | [7 empty] | No | PIRACETAM IN THE TREATMENT OF ACUTE STROKE: PASS II A randomised ,Double Blinded, placebo controlled, 2 parallel group study to evaluate the efficacy and safety of piracetam, 12 g IV infusion within 7 hours post stroke onset, followed by 12/d for 4 weeks (IV ampoules, oral solution) and 4.8 g/d for 8 weeks (tablets) in adult patients with an ischemic middle cerebral artery stroke. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2003-05-05: 1998-02-17; 2003-05-09: 1998-03-30; 2003-05-16: 1998-08-18; 2003-07-03: 2000-12-31; 2004-03-22: 2001-09-01; 2004-03-25: 2002-07-17 | Argentina, Austria, Belgium, France, Germany, Greece, Hungary, Italy, Netherlands, Norway, Poland, Singapore, Spain, Sweden, Taiwan, Turkey | Argentina (LPLV), Austria (LPLV), Belgium (FPFV), France (FPFV), Germany (FPFV), Greece (LPLV), Hungary (FPFV), Italy (LPLV), Netherlands (1st Site Initiation), Norway (LPLV), Poland (FPFV), Singapore (FPFV), Spain (LPLV), Sweden (LPLV), Taiwan (FPFV), Turkey (FPFV) | Argentina, Austria, Belgium, France, Germany, Greece, Hungary, Italy, Netherlands, Norway, Poland, Singapore, Spain, Sweden, Taiwan, Turkey | 40 | 52 | 44 | 1200 | 1200 | 1200 | 0 | 0 | 0 | 571 | 0 | 153 | 418
Yes | Not assigned | Managing Type | 1 | NOOTROPIL | Central Nervous System | 9723 | Study Archived | REPP I : Perpheral vestibular deficit | Phase II | Open | Affiliates - Italy | CNS | Affiliates - Italy | [7 empty] | No | Re-education plus piracetam versus vestibular re-education alone in the treatment of patients affected by peripheral vestibular deficit with difficulties in compensation - A multicenter randomized clinical trial (REPPI) | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2003-05-05: 1999-02-04; 2003-05-09: 1999-04-01; 2003-05-16: 1999-05-24; 2003-07-03: 1999-12-31; 2003-07-24: 2001-02-08; 2003-10-03: 2001-08-08; 2004-03-25: 2003-06-05 | Italy | Italy (LPLV) | Italy | 14 | 0 | 1 | 200 | 200 | 160 | 90 | 0 | 5 | 85 | 0 | 2 | 83
Yes | Not assigned | Managing Type | 1 | NOOTROPIL | Central Nervous System | 9921 | Study Archived | Vertigo | Phase III | Double Blind | Affiliates - France | CNS | Affiliates - France | Benkaci D | [6 empty] | No | Etude exploratoire, multicentrique, randomisée, en double insu (piracetam 4.8 g versus placebo) en parallèle chez des sujets de 18 à 79 inclus présentant des vertiges prolongés, traités pendant 3 mois | [5 empty] | 2000-10-01 | 2001-02-27 | 2000-11-15 | 2001-05-29 |  |  | 2001-08-01 | 2002-10-25 | 2001-11-01 | 2002-11-29 |  | 2003-05-12 | 2001-12-01 | 2004-08-19 | France | France (LPLV) | France | 25 | 0 | 1 | 100 | 100 | 0 | 95 | 0 | 15 | 80 | 23 | 15 | 42
Yes | Not assigned | Managing Type | 1 | NOOTROPIL | Central Nervous System | COD023 | Protocol Approved (Cancelled) | Vertigo Observational Survey | Drug Survey |  | Global Medical Affairs Europe | GMA Neurology / Psychiatry | Global Medical Affairs | Conrath P | Copetti C | [5 empty] | No |  |  |  |  | 2007-06-15 |  | 2003-05-05: 2007-09-29 |  |  |  | 1000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NOOTROPIL | Central Nervous System | N01001 | CSR Approved | Mild Cognitve Impairment | Phase III | Double Blind | Clinical Development Europe | CNS | Global Medical Affairs | Hemdal P, Van Asbroeck I |  |  | Ingenix |  |  |  | No | A multicenter, randomized, double blind, placebo controlled, parallel group study of the efficacy and safety of 9600 and 4800 mg/day piracetam (oral 800 mg tablets, bid) taken for 12 months by subjects suffering from Mild Cognitive Impairment (MCI). | Indication for Neuro Psychiatry | Central Nervous System |  |  | 1999-09-01 | 1999-11-30 | 1999-12-23 | 2000-01-31 | 2000-05-18 |  | 2003-01-08 | 2002-01-01 | 2004-01-21 | 2002-03-01 | 2004-04-30 | -691971 | 2004-06-24 | 2002-06-30 | 2005-04-08 | Austria, Belgium, Czech Republic, Denmark, Finland, France, Germany, Hungary, Ireland, Italy, Netherlands, Poland, Portugal, Slovakia, Spain, Sweden, United Kingdom | Austria (LPLV), Belgium (LPLV), Czech Republic (LPLV), Denmark (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Ireland (LPLV), Italy (LPLV), Netherlands (LPLV), Poland (LPLV), Portugal (LPLV), Slovakia (LPLV), Spain (LPLV), Sweden (LPLV), United Kingdom (LPLV) | Austria, Belgium, Czech Republic, Denmark, Finland, France, Germany, Hungary, Ireland, Italy, Netherlands, Poland, Portugal, Slovakia, Spain, Sweden, United Kingdom | 60 | 79 | 74 | 2000 | 600 | 450 | 1078 | 0 | 402 | 676 | 0 | 161 | 515
Yes | Not assigned | Managing Type | 1 | NOOTROPIL | Central Nervous System | N01018 | Study Archived | Piracetam Beeding - Pharmacodynamics | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | Affiliates - France | Daoust A |  |  | Aster-Cephac |  |  |  | Yes | Effects of piracetam on haematostasis and safety in adult healthy male and female volunteeres. A double-blind, placebo-controlled, randomizes, 4-way crossover study of piracetam 1200mg tabelets administred orally, twice daily, in multiple doses (3.6g bid, 8.4g bid and 12 g bid) for 3.5 days | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2000-04-12 | 2000-07-18 | 2000-05-01 | 2000-10-17 |  |  | 2000-05-31 | 2001-06-16 | 2000-08-30 | 2001-09-05 |  |  | 2000-08-30 | 2001-12-19 | France | France (LPLV) | France | 1 | 0 | 1 | 20 | 20 | 20 | 85 | 0 | 65 | 20 | 0 | 2 | 18
Yes | Not assigned | Managing Type | 1 | NOOTROPIL | Central Nervous System | N01232 | Created (Cancelled) | Bioequivalence Turkey | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Mccabe S | [6 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2007-06-08 | [18 empty] | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NUMEROUS | not defined | SP0529 | Final TFLs released | Sodium heparin s.c. 12.500 UI / 0.5 ml in healthy volunteers | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Sanguini M | [6 empty] | No | Tolerability evaluation of an heparin subcutaneous formulation Clarisco (12.500 UI/0.5 ml) in comparision with a reference formulation of calcium heparin (12.500 UI/0.5 ml) and Placebo in healthy volunteers. | [5 empty] | 2003-05-05: 1999-02-09; 2003-12-17: 1999-06-24 | Switzerland | Switzerland (Created) |  | 1 | 0 | 0 | 40 | 40 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NUMEROUS, P643 BNF | not defined | SP0525 | Created | HHT-growth retard | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | not available (DMCD) | [22 empty] | 0 | 0 | 0 | 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NUMEROUS, P643 BNF | not defined | SP0553 | LPFV (Stopped) | Nutropin Depot vs Nutropin AQ in children with GHD | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Driver D | [6 empty] | No | A multicenter, open label, randomized, parallel group trial of the efficacy and safety of 2 dosage regiments of Nutropin Depot in comparison with Nutropin AQ, studied over a duration of 12 months in children with growth failure due to growth hormone deficiency. | Growth Hormone Deficiency | Immunology |  | 2000-02-18 | 1999-09-01 | 2003-05-05: 1999-10-29; 2003-05-16: 2000-03-02; 2003-06-03: 2000-09-15 | France, Germany, Italy, Poland, Spain, Sweden, Switzerland, United Kingdom | France (Created), Germany (Created), Italy (Created), Poland (Created), Spain (Created), Sweden (Created), Switzerland (Created), United Kingdom (Created) |  | 30 | 0 | 0 | 90 | 85 | 69 | 0 | 0 | 0 | 84 | 3 | 2 | 79
Yes | Not assigned | Managing Type | 1 | NUMEROUS, P643 BNF | not defined | SP0592 | Protoc. Summary Approved (Cancelled) | Nutropin Depot in children with growth failure due to GHD | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Driver D | [6 empty] | No | A multicenter, multinational open label, randomized parallel group trial of the efficacy and safety of Nutropin Depot in comparison with Daily Growth Hormone, studied over a duration of 12 months in children with growth failure due to GHD ( who have been previously treated GH) | Growth Hormone Deficiency | Immunology |  | 2000-10-02 | 2000-10-02 | [17 empty] | 38 | 0 | 0 | 105 | 99 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NUMEROUS, P643 BNF | not defined | SP0625 | Created (Cancelled) | Nutropin Depot trial, Sweden | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Oegren E | [6 empty] | No | A multicenter trial of the metabolic effects on safety of Nutropin Depot administered as sc injection at 0.75 mg/kg twice monthly during 6 months in children with GHD on daily GH treatment for at least one year. | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | NUMEROUS, P643 BNF | not defined | SP0646 | Protoc. Summary Approved (Cancelled) | Extension Trial - Nutropin Depot in GHD children | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Driver D | [6 empty] | No | A multicentre, multi national, open label, long term extension trial of the safety and efficacy of NutropinDepot in children with growth failure due to growth hormone deficiency | Growth Hormone Deficiency | Immunology |  | 2001-01-24 | 2001-01-24 | [14 empty] | France, Germany, Italy, Poland, Spain, Switzerland | France (Created), Germany (Created), Italy (Created), Poland (Created), Spain (Created), Switzerland (Created) |  | 0 | 0 | 0 | 84 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Olokizumab | Immunology | CD0001 | Study Archived | Ph2a Study of OKZ (sc) in moderate to severe Crohn's disease | Phase II | Double Blind | UCB Pharma Global | Immunology | UCB Pharma Global | Bretschneider M | Tillery N | N/A | PXL |  |  | adults | No |  | Indication for Internal Medicine | Immunology |  | 2011-05-13 | 2011-05-12 | 2003-05-05: 2011-11-14; 2003-05-09: 2012-02-16; 2003-05-16: 2012-06-20; 2003-05-30: 2012-12-15; 2003-06-03: 2012-10-01; 2003-07-24: 2012-10-10; 2003-10-03: 2012-12-04 | Bulgaria, Germany, Hungary, Poland | Bulgaria (LPLV), Czech Republic (1st Site Initiation (Cancelled)), Germany (LPLV), Hungary (LPLV), Poland (LPLV) | Bulgaria, Germany, Hungary, Poland | 48 | 34 | 7 | 130 | 96 | 96 | 13 | 0 | 13 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Olokizumab | Immunology | PA0005 | Created (Cancelled) | Phase IIB OLE | Phase II |  | Clinical Development USA |  | Clinical Development USA |  |  | Parexel | PXL |  |  |  | No |  | Osteoarthritis | Immunology |  | 2014-11-12 | [18 empty] | 35 | 0 | 0 | 120 | 120 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Olokizumab | Immunology | RA0001 | CSR Approved | FIH (Healthy Volunteer) | Phase I | Double Blind | UCB Pharma Global | Clinical Pharmaco | R & D | Mccabe S | [6 empty] | Yes | A Phase 1, randomized, double-blind, placebo-controlled, single-center, single-dose, dose escalating study to evaluate the safety and tolerability, pharmacokinetics and pharmacodynamics of CDP6038 in healthy male and female subjects |  |  |  | 2007-10-30 | 2007-12-14 |  | 2008-03-05 | 2008-09-05 | 2008-09-10 | 2009-07-17 | 2009-07-17 | 2009-10-26 | 2009-10-23 | 2009-12-08 | 2009-11-25 | 2010-02-15 | 2010-02-14 | 2010-05-14 | 2010-06-01 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 284 | 66 | 66 | 620 | 0 | 0 | 67 | 1 | 0 | 66
Yes | Not assigned | Managing Type | 1 | Olokizumab | Immunology | RA0010 | CSR Approved | Safety and PK multiple-dose trial | Phase I | Double Blind | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No | A MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, SINGLE DOSE STUDY TO EVALUATE THE PHARMACOKINETICS, PHARMACODYNAMICS, SAFETY AND TOLERABILITY OF INTRAVENOUS AND SUBCUTANEOUS CDP6038 IN MALE AND FEMALE SUBJECTS WITH RHEUMATOID ARTHRITIS ON A STABLE DOSE OF METHOTREXATE |  |  |  | 2009-04-06 | 2009-04-22 |  | 2009-06-02 |  | 2009-10-15 |  | 2010-06-15 | 2010-09-21 | 2010-09-20 | 2010-11-02 | 2010-10-19 | 2010-12-09 | 2010-12-06 | 2011-04-06 | 2011-04-28 | Germany, United States of America | Germany (LPLV), United States of America (LPLV) | Germany, United States of America | 5 | 6 | 6 | 80 | 80 | 72 | 128 | 0 | 88 | 40 | 0 | 2 | 38
Yes | Not assigned | Managing Type | 1 | Olokizumab | Immunology | RA0056 | Study Archived | Dose ranging study/active comparator to eval. effic. CDP6038 | Phase II | Double Blind | UCB Pharma Global | Immunology | UCB Pharma Global | Derby B | Christopher K | N/A | Quintiles International |  |  | adults | No | A randomized, double-blind, placebo-controlled, dose ranging study with an active comparator to evaluate the efficacy and safety of CDP6038 administered subcutaneously for 12 weeks ro subjects with active rheumatoid arthritis having previously failed TNF blocker therapy. | Indication for Rheumato GI | Immunology | RA0056 is a parent study of RA0057 |  | 2010-05-04 |  | 2010-08-11 | 2010-11-03 | 2010-11-23 | 2011-09-27 | 2012-04-02 | 2012-06-29 | 2012-06-29 | 2012-08-13 | 2012-08-16 | 2012-10-09 | 2012-10-22 | 2013-03-26 | 2013-06-11 | Belgium, United Kingdom, United States of America | Belgium (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, United Kingdom, United States of America | 100 | 99 | 82 | 350 | 220 | 220 | 398 | 0 | 177 | 221 | 2 | 23 | 196
Yes | Not assigned | Managing Type | 1 | Olokizumab | Immunology | RA0057 | Study Archived | Open Label Extension Study for subj. that completed RA0056 | Phase II | Open | UCB Pharma Global | Immunology | UCB Pharma Global | Derby B | Christopher K | N/A | Quintiles International |  |  | adults | No | A phase 2 Multicenter, open-label, follow up study to assess the long term safety and efficacy of CDP6038 administered subcutaneously to subjects with active rheumatoid arthritis who completed study RA0056. | Indication for Rheumato GI | Immunology | RA0057 is an extension of RA0056 |  | 2010-07-12 |  | 2010-08-11: 2010-08-11; 2010-11-03: 2011-02-18; 2010-11-23: 2011-03-07; 2011-09-27: 2011-11-14; 2012-04-02: 2012-06-29; 2012-06-29: 2013-08-05; 2012-08-16: 2013-10-11 | Belgium, United Kingdom, United States of America | Belgium (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, United Kingdom, United States of America | 100 | 57 | 55 | 190 | 190 | 190 | 0 | 0 | 0 | 188 | 0 | 85 | 0
Yes | Not assigned | Managing Type | 1 | Olokizumab | Immunology | RA0061 | Created (Cancelled) | 6 month long term extension study | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Derby B | Christopher K | Parexel | PXL |  |  |  | No |  |  |  |  | 2014-11-22 | [18 empty] | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Olokizumab | Immunology | RA0062 | Created (Cancelled) | 6 month long term extension study | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Derby B | Christopher K | Parexel | PXL |  |  |  | No |  |  |  |  | 2014-11-22 | [18 empty] | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Olokizumab | Immunology | RA0074 | CSR Approved | Single dose study in healthy Japanese subjects | Phase I | Double Blind | Clinical Development Japan | Clinical Development Japan | R & D | Watanabe S | Cain D | [5 empty] | Yes | A Phase I, randomized, double-blind, placebo-controlled, single-dose study to evaluate the safety, tolerability, pharmacokinetics and pharmacodynamics of CDP6038 administered subcutaneously to healthy Japanese males. |  |  |  | 2010-09-02 | 2010-07-15 |  | 2010-09-03 | 2010-11-30 | 2010-11-30 |  | 2011-05-27 | 2011-09-27 | 2011-09-23 | 2011-10-20 | 2011-12-19 | 2011-12-14 | 2011-12-21 | 2012-02-29 | 2012-04-12 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 80 | 22 | 20 | 50 | 0 | 30 | 20 | 0 | 4 | 16
Yes | Not assigned | Managing Type | 1 | Olokizumab | Immunology | RA0083 | Study Archived | Randomized, D-B, Placebo control.,Dose-Ranging Multic. study | Phase II | Double Blind | UCB Pharma Global | Immunology | UCB Pharma Global | Mashimo H | Matsuoka K | N/A | PAREXEL |  |  | adults | No | A randomized, double-blind, placebo-controlled, dose-ranging study to evaluate the efficacy and safety of CDP6038 administered subcutaneously for 12 weeks to Asian subjects with active rheumatoid arthritis having previously failed TNF-blocker therapy | Indication for Rheumato GI | Immunology | RA0083 is a parent study of RA0089 | 2010-12-08 | 2010-12-08 | 2011-03-30 | 2010-08-11: 2011-03-30; 2010-11-23: 2011-10-19; 2012-04-02: 2012-11-22; 2012-06-29: 2013-02-21; 2012-08-16: 2013-03-22; 2012-10-22: 2013-05-23; 2013-06-11: 2013-09-17 | Japan, South Korea, Taiwan | Japan (LPLV), South Korea (LPLV), Taiwan (LPLV) | Japan, South Korea, Taiwan | 60 | 43 | 39 | 150 | 120 | 120 | 179 | 0 | 60 | 119 | 0 | 14 | 105
Yes | Not assigned | Managing Type | 1 | Olokizumab | Immunology | RA0089 | Study Archived | Multicenter, Open-Label, Follow-up study | Phase II | Open | UCB Pharma Global | Immunology | UCB Pharma Global | Mashimo H | Matsuoka K | N/A | PAREXEL |  |  | adults | No | Multi-center, open-label, follow-up study to assess the long-term safety and efficacy of CDP6038 administered subcutaneously to Asian subjects with active rheumatoid arthritis who completed study RA0083 | Indication for Rheumato GI | Immunology | RA0089 is an extension of RA0083 |  | 2011-01-17 |  | 2011-03-30 | 2012-01-06 | 2012-01-26 | 2012-11-01 | 2013-02-21 |  | 2013-11-29 |  | 2014-01-20 |  |  |  | 2015-04-01 | Japan, South Korea, Taiwan | Japan (LPLV), South Korea (LPLV), Taiwan (LPLV) | Japan, South Korea, Taiwan | 60 | 32 | 32 | 110 | 110 | 110 | 103 | 0 | 0 | 103 | 0 | 21 | 82
Yes | Not assigned | Managing Type | 1 | Olokizumab | Immunology | RA0100 | Created (Cancelled) | 6 month MTX-IRs | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Derby B | Christopher K | Parexel | PXL |  |  |  | No |  |  |  |  | 2014-09-19 | [18 empty] | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Olokizumab | Immunology | RA0118 | Created (Cancelled) | Dose reduction in Non-Biologic DMARD IRs | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Derby B | Christopher K | Parexel | PXL |  |  |  | No |  |  |  |  | 2014-09-19 | [18 empty] | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Olokizumab | Immunology | UC0003 | Created (Cancelled) | Ph2a Study of OKZ (sc) moderate to severe Ulcerative Colitis | Phase II |  | R & D |  | R & D | Thierfelder S | Driver D | Parexel |  |  |  |  | No |  |  |  |  | 2011-05-17 | [18 empty] | 25 | 0 | 0 | 70 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2013-03-20
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0432 | Created | Drug Safety Trial Data. Study drug: OMEPRAZOL |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: OMEPRAZOL | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0433 | Created | Drug Safety Trial Data. Study drug: OMEPRAZOL |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: OMEPRAZOL | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0444 | Created | Drug Safety Trial Data. Study drug: OMEPRAZOLE |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: OMEPRAZOLE | [22 empty] | 0 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0445 | Created | Drug Safety Trial Data. Study drug: OMEPRAZOLE |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: OMEPRAZOLE | [22 empty] | 0 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0454 | Created | Drug Safety Trial Data. Study drug: OMEPRAZOLE |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: OMEPRAZOLE | [22 empty] | 0 | 0 | 0 | 48 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0460 | Created | Omeparazole - Capsules Single dose fasting |  |  | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | Single dose fasting bioequivalence study of omeprazole 20 mg delayed release capsules | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0541 | Created | OME Puren-AWB | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Fedder M | [6 empty] | No | OME Puren-AWB | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0608 | Protoc. Summary Approved | Observational, prospective and naturalistic study to evaluat | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Pradillo S | [6 empty] | No | Observational, prospective and naturalistic study to evaluate "Test-and-Treat" Strategy in ulcer like dyspepsia. (Tetra) |  |  |  | 2000-06-09 | 2000-06-09 | [17 empty] | 125 | 0 | 0 | 1272 | 1272 | 1272 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0621 | Created | Pilot bioavailablity of omeprazole 20 mg capsules vs Prilos | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Kastenholz K | [6 empty] | No | Pilot bioavailablity of omeprazole 20 mg capsules vs Prilosec | [22 empty] | 1 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0624 | Created | Food effect bioavailability of omeprazole 20 mg capsules vs | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Food effect bioavailability of omeprazole 20 mg capsules vs Prilosec | [22 empty] | 1 | 0 | 0 | 21 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0689 | Final TFLs released | Effect of applesauce on omeprazole bioavailability in health | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | A pharmacokinetic study to assess the effect of applesauce on the single dose bioavailability of a 20 mg formulation of SPUS 830 and a reference product |  |  |  | 2001-11-21 | 2001-11-21 |  | 2010-08-11: 2001-12-18; 2010-11-23: 2002-01-20; 2012-04-02: 2002-01-20; 2012-10-22: 2002-03-14 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 21 | 0 | 0 | 21
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0752 | Final TFLs released | Bioequivalence of omeprazole 40 mg fasted vs Prilosec | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to evaluate the bioequivalence of a test 40 mg omeprazole (KUDCO) delayed-release capsule, compared to a marketed 40 mg Prilosec (R) (Omeprazole, AstraZeneca, LP) delayed-release capsule when given in the fasted state |  |  |  | 2003-05-01 | 2003-05-01 |  | 2010-08-11: 2003-05-27; 2010-11-23: 2003-07-05; 2012-04-02: 2003-07-05; 2012-06-29: 2003-07-14; 2012-10-22: 2003-08-14 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 48 | 48 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0775 | CSR Approved | Bioequivalence of Omeprazole 40 mg vs Prilosec 40 mg, addend | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to evaluate the bioequivalence of a test 40 mg omeprazole (KUDCO) delayed-release capsule, compared to a marketed 40 mg Prilosec (R) (omeprazole, AstraZeneca, LP) delayed-release capsule when given in the fasted state |  |  |  | 2003-08-27 | 2003-08-27 |  | 2013-06-11: 2009-01-01 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 12 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0809 | Created | Pilot-Omeprazole 20mg OTC single dose bioequivalence | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pilot study to assess the bioavailability of two test 20 mg Omeprazole (KUDCO) delayed-release OTC capsules and to compare the potential bioequivalence of the test formulations compared to the marketed 20 mg Prilosec OTC (Omeprazole Magnesium, Procter & Gamble) delayed-release OTC tablet when giv en in the fasted state. | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0838 | Created | Pilot-Bioequivalence food effect of omeprazole, 20 mg, singl | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Papke A | [6 empty] | No | A pharmacokinetic study to assess the bioequivalence of a test 20 mg Omeprazole (KUDCO) delayed-release OTC capsule compared to the marketed 20 mg Prilosec OTC (Omeprazole Magnesium, Procter & Gamble) delayed-release OTC tablet when administered to healthy adult subjects in the fed state | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0839 | Created (Cancelled) | Pivotal--Bioequivalence of omeprazole OTC, 20 mg, single dos | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Papke A | [6 empty] | No | Long Title to be entered | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Omeprazole | not defined | SP0840 | Created (Cancelled) | Pivotal--Bioequivalence of omeprazole OTC, 20mg, single dose | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Papke A | [6 empty] | No | Long Title to be entered | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Oxybutynine | not defined | SP0488 | Created | Oxybutynin Phase I (PHAKI 1001) | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Pilot study to evaluate the pharmacokinetics of oxybutynin during a multiple dose application of a new oxybutynin patch in comparison with a multiple oral dose of oxybutynin in helthy male subjects. | [19 empty] | Germany | Germany (Created) |  | 1 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Oxybutynine | not defined | SP0495 | Created | Oxybutynin phase I trial (PHAKI 1002/1998) | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Double-blind multiple-dose randomized two-way cross-over study to evaluate the tolerance and plasma concentration following ascending doses of a new Oxybutynin TDS in comparison with oxybutynin hydrochloride tablets and with their respective placebos. | [19 empty] | Germany | Germany (Created) |  | 1 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 12
Yes | Not assigned | Managing Type | 1 | Oxybutynine | not defined | SP0496 | Created | Oxybutynin (PHAKI 1003) | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Double-blind single dose randomized two-way cross-over study to investigate the skin tolerance and adhesive properties of two transdermal therapeutic systems (Oxybutynin TDS, Type OB 0469 and Oxybutynin TDS, Type OB 0496) in comparision with their respective placebos and with a placebo of a register ed and marketed transdermal therapeutic system. | [19 empty] | Germany | Germany (Created) |  | 1 | 0 | 0 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0 | 0 | 26
Yes | Not assigned | Managing Type | 1 | Oxybutynine | not defined | SP0501 | CSR Approved | Proof of principle oxybutynin patch IIa Europe | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Auer S | [6 empty] | No | Proof of principle oxybutynin patch IIa Europe |  |  |  | 1999-02-16 | 1999-02-16 |  | 2010-08-11: 1999-03-15; 2010-11-23: 1999-05-31; 2012-04-02: 1999-12-16; 2012-06-29: 2000-02-08; 2012-10-22: 2000-04-28; 2013-06-11: 2000-12-05 | Belgium, France, Germany, Netherlands, United Kingdom | Belgium (Created), France (Created), Germany (Created), Netherlands (Created), United Kingdom (Created) |  | 28 | 0 | 0 | 190 | 174 | 150 | 0 | 0 | 0 | 60 | 7 | 12 | 41
Yes | Not assigned | Managing Type | 1 | Oxybutynine | not defined | SP0521 | Created (Cancelled) | Oxybutynin efficacy | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Auer S | [6 empty] | No | Oxybutynin efficacy | [22 empty] | 0 | 0 | 0 | 1200 | 1100 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Oxybutynine | not defined | SP0522 | Created (Cancelled) | Oxybutynin | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Auer S | [6 empty] | No | Oxybutynin | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Oxybutynine | not defined | SP0532 | Created | Oxybutynin -Phase I (PHAKI 1004/98) | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | not available (DMCD) | [19 empty] | Germany | Germany (Created) |  | 1 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 0 | 15 | 0 | 0 | 15
Yes | Not assigned | Managing Type | 1 | Oxybutynine | not defined | SP0539 | Created | Oxybutynin Phase I trial (PHAKI 1005) | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Pilot study to evaluate the adhesiveness and skin tolerability of Oxybutynin (OB) following two administrations of a new OB patch in comparison to 3 different placebo patches. | [22 empty] | 1 | 0 | 0 | 48 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Oxybutynine | not defined | SP0554 | Created (Cancelled) | Oxybutynin-Phase I (PHAKI 1007) | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | not available (DMCD) | [19 empty] | Germany | Germany (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | Padsevonil | Central Nervous System | EP0028 | Created (Cancelled) | Phase 2 Long Term Open Label Efficacy and Safety | Phase II |  | Clinical Development USA | CNS | Clinical Development USA | Smit R | Kime J | PRA | PRA |  |  |  | No |  |  |  |  | 2012-04-25 | [18 empty] | 60 | 0 | 0 | 400 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Padsevonil | Central Nervous System | EP0069 | Study Archived | Focal Epilepsy POC lite study | Phase II | Double Blind | GED | Neurology | UCB Pharma Global | Lelij G | Tillery N | PRA | SPI PRA | No | Yes | adults | No | A DOUBLE-BLIND, RANDOMIZED, PLACEBO-CONTROLLED STUDY OF THE EFFICACY, SAFETY/TOLERABILITY, AND PHARMACOKINETIC PROFILE OF UCB0942 IN ADULT PATIENTS WITH HIGHLY DRUG-RESISTANT FOCAL EPILEPSY | Epilepsy | Central Nervous System | EP0069 is a parent study of EP0073 |  | 2014-11-18 |  | 2015-03-18 | 2015-05-30 | 2015-08-28 | 2016-03-16 | 2016-10-04 | 2016-07-18 | 2017-07-18 | 2016-08-15 | 2017-07-31 | 2016-09-03 | 2017-08-10 | 2016-11-30 | 2017-10-05 | Belgium, Bulgaria, Germany, Hungary, Netherlands, Spain | Belgium (LPLV), Bulgaria (LPLV), Germany (LPLV), Hungary (LPLV), Italy (1st Site Initiation (Cancelled)), Netherlands (LPLV), Spain (LPLV) | Belgium, Bulgaria, Germany, Hungary, Netherlands, Spain | 10 | 23 | 18 | 46 | 46 | 46 | 66 | 0 | 11 | 55 | 0 | 5 | 50
Yes | Not assigned | Managing Type | 1 | Padsevonil | Central Nervous System | EP0073 | Study Archived | An open-label multicenter follow-up study ref. EP0069 | Phase II | Open | GCSO | Neurology | UCB Pharma Global | Namgoong K | Beinhauer-Zellenka U | PRA | PRA | No | Yes | adults | No | An open-label, multicenter, extension study to evaluate the long-term safety, tolerability, and efficacy of UCB0942 when used as adjunctive therapy for partial-onset seizures in adult subjects with highly drug-resistant focal epilepsy Phase 2 | Epilepsy | Central Nervous System | EP0073 is an extension of EP0069 and is a feeder study of EP0136 | 2015-04-14 | 2015-04-03 |  | 2015-06-11 | 2015-09-14 | 2015-12-03 17:01 | 2016-07-19 | 2016-12-07 | 2021-12-28 | 2020-11-24 11:00 | 2022-01-25 | 2020-12-21 | 2022-02-08 | 2021-01-15 | 2022-05-05 | 2021-03-22 | Belgium, Bulgaria, Germany, Hungary, Netherlands, Spain | Belgium (LPLV), Bulgaria (LPLV), Germany (LPLV), Hungary (LPLV), Netherlands (LPLV), Spain (LPLV) | Belgium, Bulgaria, Germany, Hungary, Netherlands, Spain | 32 | 17 | 15 | 42 | 17 | 17 | 45 | 0 | 3 | 42 | 0 | 42 | 0
Yes | Not assigned | Managing Type | 1 | Padsevonil | Central Nervous System | N01360 | CSR Approved | FIM-Safety/Tolerability/PK study | Phase I | Single Blind | GED |  | R & D | Hill P, Mccabe S | [6 empty] | Yes | A RANDOMIZED, SUBJECT-BLIND, INVESTIGATOR-BLIND, PLACEBO-CONTROLLED, SINGLE ASCENDING DOSE STUDY TO INVESTIGATE THE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF UCB1415943 000 IN HEALTHY MALE SUBJECTS |  |  |  | 2010-08-19 |  |  | 2010-09-09 | 2010-11-16 | 2010-12-14 | 2011-01-26 | 2011-01-04 | 2011-02-23 | 2011-02-25 | 2011-03-21 | 2011-03-22 | 2011-06-30 | 2011-07-01 | 2011-07-28 | 2011-11-23 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 24 | 24 | 24 | 48 | 32 | 0 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | Padsevonil | Central Nervous System | N01383 | Study Archived | PPSI - 11C Flumazenil PET study | Phase I | Open | GED |  | GED | Bosteels M | Mccabe S | N/A | Marc Bosteels (external EPM) |  |  | adults | Yes | A SINGLE CENTER, OPEN LABEL, POSITRON EMISSION TOMOGRAPHY STUDY TO EVALUATE GABAA RECEPTOR OCCUPANCY OF UCB0942 IN THE BRAINS OF HEALTHY MALE VOLUNTEERS |  |  |  | 2012-01-17 | 2012-01-17 |  | 2012-02-13 | 2012-03-27 | 2012-05-29 |  | 2012-06-25 |  | 2012-08-03 |  | 2012-10-17 |  | 2012-10-31 |  | 2013-02-14 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 8 | 8 | 8 | 29 | 22 | 0 | 7 | 0 | 0 | 7
Yes | Not assigned | Managing Type | 1 | Padsevonil | Central Nervous System | N01384 | Created (Cancelled) | Phase 2a/b Proof of concept and Dose Ranging Study | Phase II |  | Clinical Development USA | CNS | Clinical Development USA | Smit R | Kime J | PRA | PRA |  |  |  | No |  | Epilepsy | Central Nervous System |  | 2012-07-20 | [18 empty] | 60 | 0 | 0 | 500 | 450 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Padsevonil | Central Nervous System | N01386 | Study Archived | SIM | Phase I |  | GED |  | R & D | Mccabe S, Valgaeren A | Mccabe S | N/A |  |  |  |  | Yes | A SINGLE-SITE, RANDOMIZED, SUBJECT-BLIND, INVESTIGATOR-BLIND, PLACEBO-CONTROLLED, MULTIPLE ASCENDING DOSE STUDY TO INVESTIGATE THE SAFETY, TOLERABILITY, PHARMACOKINETICS, AND PHARMACODYNAMICS OF UCB1415943-000 IN HEALTHY MALE AND FEMALE SUBJECTS | Epilepsy | Central Nervous System |  | 2011-02-03 | 2011-02-16 |  | 2011-03-28 |  | 2011-05-25 | 2011-06-24 | 2011-10-27 | 2011-11-23 | 2011-11-23 | 2011-12-21 | 2011-12-21 | 2012-02-28 | 2012-06-24 | 2012-05-31 | 2012-12-05 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 96 | 48 | 48 | 108 | 3 | 57 | 48 | 0 | 5 | 43
Yes | Not assigned | Managing Type | 1 | Padsevonil | Central Nervous System | UP0001 | Study Archived | Bioavailability and food effect study | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Bosteels M | Mccabe S | N/A |  |  |  | adults | Yes | SINGLE CENTER, RANDOMIZED, OPEN LABEL, 2-PART, SEQUENTIAL STUDY TO COMPARE BIOAVAILABILITY (SINGLE DOSE ONLY), SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF UCB0942 AFTER SINGLE AND MULTIPLE DOSE ADMINISTRATION AS ORAL LIQUID FORMULATION AND ORAL TABLET, WITH ASSESSMENT OF FOOD EFFECT IN HEALTHY MALE AND FEMALE SUBJECTS |  |  |  |  | 2011-09-28 |  | 2011-12-07 | 2012-02-04 | 2012-01-18 | 2012-02-07 | 2012-01-31 | 2012-03-08 | 2012-03-19 | 2012-05-01 | 2012-04-30 | 2012-06-26 | 2012-07-20 | 2012-11-07 | 2012-11-20 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 36 | 24 | 24 | 82 | 0 | 54 | 24 | 0 | 4 | 20
Yes | Not assigned | Managing Type | 1 | Padsevonil | Central Nervous System | UP0002 | Study Archived | A Multi Center, open label, parallel group study, to investi | Phase I | Open | GED |  | UCB Pharma Global | Bosteels M | Mccabe S | N/A | PXL |  |  | adults | No | A Multi Centre, open label, parallel group study, to investigate the effect of stable doses of concomitant antiepileptic drugs on the PK and safety profile of single oral dose of UCB0492, in epilepsy patients. | Epilepsy | Central Nervous System |  | 2011-09-03 | 2012-01-13 |  | 2010-08-11: 2012-05-02; 2010-11-23: 2012-08-29; 2012-04-02: 2013-01-17; 2012-06-29: 2013-03-04; 2012-08-16: 2013-03-26; 2012-10-22: 2013-05-17; 2013-06-11: 2013-07-02 | Bulgaria, Germany, Netherlands | Bulgaria (LPLV), Germany (LPLV), Netherlands (LPLV) | Bulgaria, Germany, Netherlands | 4 | 3 | 3 | 20 | 20 | 20 | 32 | 0 | 12 | 20 | 0 | 1 | 19
Yes | Not assigned | Managing Type | 1 | Padsevonil | Central Nervous System | UP0010 | Study Archived | A single center study of excretion balance,PK and metabolism | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Soranson J | Grose-Hodge R |  |  |  |  | adults | Yes | A single centre open-label study of excretion balance, pharmacokinetics and metabolism of 14Carbon-Labelled UCB0942 after 100mg single oral dose administration in healthy male subjects. | Epilepsy | Central Nervous System |  | 2011-10-01 |  |  | 2011-11-09 |  | 2011-12-19 | 2012-01-14 | 2012-01-06 | 2012-01-25 | 2012-01-16 | 2012-02-17 | 2012-02-29 | 2012-05-08 | 2012-06-15 | 2012-09-18 | 2012-12-11 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 0 | 1 | 15 | 6 | 6 | 15 | 0 | 9 | 6 | 0 | 0 | 6
Yes | Not assigned | Managing Type | 1 | Padsevonil | Central Nervous System | UP0013 | Study Archived | Drug/Drug Interaction study (DDI) with volunteers | Phase I | Open | GED |  | GED | Bosteels M | Mccabe S | N/A | SPI-PXL |  |  | adults | Yes | A SINGLE CENTER, OPEN LABEL, 2-PART, SEQUENTIAL DESIGN STUDY TO EVALUATE THE DRUG INTERACTION POTENTIAL OF STEADY-STATE ORAL DOSES OF UCB0942 IN HEALTHY SUBJECTS RECEIVING A 5 PROBE COCKTAIL OR STABLE DOSES OF VALPROIC ACID | Epilepsy | Central Nervous System |  | 2012-02-03 | 2012-02-03 |  | 2012-03-16 | 2012-04-09 | 2012-05-21 |  | 2012-10-20 |  | 2013-01-08 |  | 2013-01-31 |  | 2013-04-17 |  | 2013-06-04 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 132 | 36 | 18 | 139 | 0 | 103 | 36 | 0 | 6 | 30
Yes | Not assigned | Managing Type | 1 | Padsevonil | Central Nervous System | UP0036 | Study Archived | A single-center, open-label, single-dose positron emission t | Phase I | Open | GED | Neurology | GED | Lelij G | Tillery N | Parexel | SPI PXL | No | Yes | adults | Yes | A SINGLE-CENTER, ADAPTIVE, OPEN-LABEL, SINGLE-DOSE POSITRON EMISSION TOMOGRAPHY STUDY WITH [11C]UCB-J TO EVALUATE THE SYNAPTIC VESICLE GLYCOPROTEIN 2A OCCUPANCY OF UCB0942 IN HEALTHY VOLUNTEERS | Epilepsy | Central Nervous System |  | 2016-02-29 | 2016-03-09 |  | 2016-06-09 | 2016-09-09 | 2016-11-02 | 2016-11-04 | 2017-03-22 | 2016-11-18 | 2017-05-22 | 2016-12-16 | 2017-06-19 | 2017-01-27 | 2017-07-28 | 2017-06-07 | 2018-02-16 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 15 | 10 | 10 | 29 | 0 | 12 | 17 | 0 | 2 | 15
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0073 | Created | Rifun-bei Patienten mit geheilter Refluxösophagitis II/III | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Plum C | [6 empty] | No | Rifun-bei Patienten mit geheilter Refluxösophagitis II/III | [22 empty] | 0 | 0 | 0 | 280 | 210 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0267 | Created | RIFUN - bei Patienten mit peptischen Erkrankungen | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Fedder M | [6 empty] | No | Durch die vorliegende Anwendungsbeobachtung sollen die Wirksamkeit und die Verträglichkeit von Rifun bei Patienten mit peptischen Erkrankungen (Ulkus duodeni, Ulkus ventrikuli, Refluxösophagitis) in Klinik und Praxis erfaßt werden. | [22 empty] | 0 | 0 | 0 | 8745 | 7953 | 7953 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0354 | Created | RIFUN - bei Patienten mit peptischen Erkrankungen | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Fedder M | [6 empty] | No | RIFUN - bei Patienten mit peptischen Erkrankungen | [22 empty] | 0 | 0 | 0 | 20000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0359 | Created | RIFUN - bei Patienten mit peptischen Erkrankungen | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | RIFUN - bei Patienten mit peptischen Erkrankungen | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0435 | Created | RIFUN - im Rahmen der zugelassenen Indikation | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Gaida-Schmidt G | [6 empty] | No | RIFUN - im Rahmen der zugelassenen Indikation | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0479 | Protoc. Summary Approved | Rifun- im Rahmen der zugelassenen Indikation | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Hamm G | [6 empty] | No | Rifun- im Rahmen der zugelassenen Indikation |  |  |  | 1998-06-03 | 1998-06-03 | [17 empty] | 0 | 0 | 0 | 600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0500 | Created | Rifun 20 mg Langzeit - Patienten mit einer Refluxkrankheit | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Hamm G | [6 empty] | No | Rifun 20 mg Langzeit - Patienten mit einer Refluxkrankheit | [22 empty] | 0 | 0 | 0 | 15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0612 | Created (Cancelled) | Pantoprazole PH-Metrie | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Hamm G | [6 empty] | No | gdfgdfgdfg | [22 empty] | 1 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0764 | Protocol Approved | Behandlung von Patienten, die unter Refluxösophagitis leiden | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Wendl M | [6 empty] | No | Postmarketing surveillance of rifun 40 mg in patients with refluxoesophagitis under special consideriation of nighttime heartburn | Reflux Esophagitis | Immunology |  |  |  |  | 2010-08-11: 2003-08-20 |  |  |  | 100 | 0 | 0 | 600 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0779 | Created | Nightime Heartburn | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Wendl M | [6 empty] | No | Postmarketing surveillance of rifun 40 mg in patients with refluxoesophagitis under special consideriation of nighttime heartburn | Reflux Esophagitis | Immunology | [20 empty] | 640 | 0 | 0 | 3840 | 3840 | 3840 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0796 | Created | Bioequivalence of Pantoprazole 40 mg fasted vs Protonix 40 m | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to evaluate the bioequivalence of a test 40 mg pantoprazole delayed-release capsule, compared to a marketed 40 mg Protonix® (pantoprazole, Wyeth-Ayerst) delayed-release capsule when given in the fasted state | [22 empty] | 1 | 0 | 0 | 40 | 40 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0797 | Created | Bioequivalence of pantoprazole 40 mg fed to Protonix 40 mg | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to evaluate the bioequivalence of a test 40 mg pantoprazole delayed-release capsule, compared to a marketed 40 mg Protonix® (pantoprazole, Wyeth-Ayerst) delayed-release capsule when given in the fed state | [22 empty] | 1 | 0 | 0 | 40 | 40 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0807 | Created (Cancelled) | Short Title to be entered, Max. Length of Title is 100 Chara | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | Long Title to be entered | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0808 | Created | Pilot-Bioequivalence of pantoprazole 40mg fed to Protonix 40 | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to investigate the pharmacokinetics of a test 40mg Pantoprazole sodium delayed-relase tablet and a marketed 40mg Pantoprazole sodium delayed-release tablet (Protonix (R), Wyeth Pharmaceuticals) when administered to healthy adult subjects in the fed state | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0859 | Created | Pilot Bioequivalence of 2 formulations 40 mg Pantoprazole De | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to assess the bioequivalence of two test 40 mg pantoprazole delayed-release tablets, compared to a marketed 40 mg pantoprazole delayed-release tablet (Protonix®, Wyeth Pharmaceuticals) when administered to healthy adult subjects in the fed state | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0860 | Created | Pilot Bioequivalence of 2 formulations 40mg Pantoprazole Del | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to assess the bioequivalence of two test 40 mg pantoprazole delayed-release tablets, compared to a marketed 40 mg pantoprazole delayed-release tablet (Protonix®, Wyeth Pharmaceuticals) when administered to healthy adult subjects in the fasted state | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0872 | Created | Bioequivalence of 40 mg pantoprazole to 40 mg Protonix in fe | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | Long Title to be entered | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pantoprazole | not defined | SP0907 | Created (Cancelled) | Nighttime heartburn in patients with erosive GERD | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Tapella C | [6 empty] | No | Nighttime heartburn in patients with erosive GERD | Reflux Esophagitis | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Penbutolol | not defined | SP0544 | Created | Levatol (SPMFG) to 20 mg Levatol Current Product) in the Fas | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Levatol (SPMFG) to 20 mg Levatol (Current Product) in the Fasting State | Mild to Moderate Hypertension | Immunology | [20 empty] | 1 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pentaerithryl Tetranitrate | not defined | SP0358 | Created | Drug Safety Trial Data. Study drug: PENTALONG |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PENTALONG | [22 empty] | 0 | 0 | 0 | 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pentaerithryl Tetranitrate | not defined | SP0373 | Created | Drug Safety Trial Data. Study drug: PENTALONG |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Drug Safety Trial Data. Study drug: PENTALONG | [22 empty] | 0 | 0 | 0 | 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pentaerithryl Tetranitrate | not defined | SP0375 | Created | Drug Safety Trial Data. Study drug: PENTALONG |  |  | UCB Pharma Global |  | UCB Pharma Global | Stalleicken D | [6 empty] | No | Drug Safety Trial Data. Study drug: PENTALONG | [22 empty] | 0 | 0 | 0 | 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pentaerithryl Tetranitrate | not defined | SP0466 | Created | PETN - ergometrische Belastungstoleranz bei KHK-Patienten |  |  | UCB Pharma Global |  | UCB Pharma Global | Stoeter M | [6 empty] | No | Doppelblinde, placebokontrollierte Pilotstudie zur Wirksamkeit einer einmal täglichen Gabe von PETN im Vergleich zur dreimaligen täglichen Gabe auf die ergometrische Belastungstoleranz bei KHK-Patienten | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 108 | 108 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pentaerithryl Tetranitrate | not defined | SP0520 | Created | Pentalong-in healthy volunteers (Bioverfügbarkeit) | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Open, randomized, two-way cross-over study to evaluate the relative bioavailability of Pentalong 80 mg Pentaerythriol Tetranitrate suspension in 24 healthy male volunteers. | [22 empty] | 0 | 0 | 0 | 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Pentoxyverine | Immunology | 9834 | CSR Approved | Adult project - Germany - polysomnography | Phase I | Double Blind | Affiliates - Germany | Clinical Pharmaco | Affiliates - Germany | Hess G | [6 empty] | Yes | A double-blind crossover, placebo controlled, randomized study : evaluation of the safety of a single dose of one pentox supository of 50 mg, measured by polysomnography and pharmacokinitics in healthy adult volunteers | Indication for Internal Medicine | Immunology |  |  |  |  | 2010-08-11: 1999-05-20; 2010-11-23: 1999-09-27; 2012-06-29: 2000-08-09; 2012-08-16: 2004-03-23; 2013-06-11: 2006-07-10 | Germany | Germany (LPLV) | Germany | 1 | 0 | 1 | 32 | 32 | 0 | 36 | 0 | 0 | 36 | 0 | 4 | 32
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0013 | Created | Moex/HCTZ versus components - in hypertensive patients | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Koch B | [6 empty] | No | A randomized, multicenter, double-blind, parallel study to evaluate the safety, efficacy and tolerability of two combinations of moexipril and hydrochlorothiazide and to compare these agents to each agent given alone during an 8-week treatment period in hypertensive patients | Moderate Hypertension | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0014 | Final TFLs released | Low dose Moex/HCTZ versus Placebo - in patients with mild to | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Koch B | [6 empty] | No | A randomized, multicenter, double-blind, parallel study to evaluate the safety, efficacy and tolerability of a low dose combination of Moexipril and HCTZ compared to placebo during a 12-week treatment period in patients with mild to moderate hypertension | Mild to Moderate Hypertension | Immunology |  | 1994-02-21 | 1994-02-21 |  | 2010-08-11: 1994-04-18; 2010-11-23: 1994-06-21; 2012-04-02: 1994-11-04; 2012-06-29: 1995-03-02; 2012-10-22: 1995-06-15 | United States of America | United States of America (Created) |  | 22 | 0 | 0 | 320 | 224 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0015 | Created | Moex/HCTZ versus Metoprolol/HCTZ - in patients with mild to | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Koch B | [6 empty] | No | A randomized, double-blind, multicenter, parallel study to compare the safety and efficacy of the combination of moexipril and HCTZ with the combination of metoprolol and HCTZ during a 12-week treatment period in patients with mild to moderate hypertension | Mild to Moderate Hypertension | Immunology | [17 empty] | United Kingdom | United Kingdom (Created) |  | 10 | 0 | 0 | 160 | 135 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0035 | Created | Dose finding study moexipril/HCTZ | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Koch B | [6 empty] | No | A randomized , double-blind, placebo-controlled, multicenter, parallel study to determine the optimal dose combinations of moexipril and hydrochlorothiazide, to evaluate the safety and efficacy of the combination of moexipril and hydrochlorothiazide and to compare specific combinations of these agen ts to each agent given alone during a 12-week treatment period in patients with mild to moderate hypertension | Mild to Moderate Hypertension | Immunology | [17 empty] | United Kingdom, United States of America | United Kingdom (Created), United States of America (Created) |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0036 | Created | Moexipril Study; Evaluation the safety and antihypertensive | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | Syntex Moexipril Study; Evaluation the safety and antihypertensive efficacy of Moexipril (dose titration) | Mild to Moderate Hypertension | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0037 | Created | Evaluation of the antihypertensive effectiveness and the saf |  | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | Double-blind, Placebo-controlled, parallel-design evaluation of various dosages of Moexipril (RS-10085), an ACE inhibitor, in patients with essential hypertension | Mild to Moderate Hypertension | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 15 | 0 | 0 | 300 | 203 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0038 | Created | Moexipril-not available (DMCD) |  |  | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | not available (DMCD) | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0039 | Created | Evaluation of the safety and efficacy of long-term Moexipril | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | Evaluation of Moexipril (RS-10085) an ACE Inhibitor, in long-term treatment of hypertension | Mild to Moderate Hypertension | Immunology | [20 empty] | 16 | 0 | 0 | 170 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0040 | Created | Dose-response of Moexipril + compare a specific combination | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A randomized, double-blind, multicenter, Placebo-controlled, parallel Study to evaluate the safety, efficacy and dose-response relationship of Moexipril and to compare a specific combination of Moexipril and Hydrochlorothiazide to each agent given alone during an eight-week treatment period followed by a two-year Open-Label Treatment period in patients with mild to moderate Hypertension | Mild to Moderate Hypertension | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 25 | 0 | 0 | 360 | 360 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0041 | Created | Evaluation of the effects of Moexipril versus Placebo on blo | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A phase II, randomized, double-blind, placebo-controlled, parallel study to compare the safety and hemodynamic effects of Moexipril to Placebo in patients with mild to moderate essential hypertension | Mild to Moderate Hypertension | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0042 | Created | To compare the safety and efficacy of two dose levels of Moe | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A randomized, double-blind, multicenter, Placebo-controlled, parallel study to compare the safety and efficacy of two dose levels of Moexipril, Hydrochlorothiazide and Placebo during an eight-week treatment period followed by a two-year, open-label treatment period in elderly patients with mild to m oderate hypertension. | Mild to Moderate Hypertension | Immunology | [17 empty] | United Kingdom | United Kingdom (Created) |  | 15 | 0 | 0 | 200 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0043 | Created | Moexipril added to HCTZ in patients whose blood pressure can | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A phase II, open-label, dose titration study to evaluate the safety and efficacy of Moexipril in patients with moderate to severe hypertension despite Hydrochlorothiazide | Moderate to Severe Hypertension | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 2 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0044 | Created | To compare the safety and efficacy of two dose levels of Moe | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A randomized, double-blind, multicenter, placebo-controlled, parallel study to compare the safety and efficacy of two dose levels of Moexipril, Hydrochlorothiazide and Placebo during a 12-week treatment period followed by one-year open-label treatment period in patients with mild to moderate hyperte nsion | Mild to Moderate Hypertension | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 15 | 0 | 0 | 160 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0045 | Created | Evaluation of the safety, tolerability and efficacy of two d | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A randomized, double-blind, multicenter, parallel, withdrawal study to evaluate the safety and efficacy of two dose levels of Moexipril during a 12-week treatment period followed by a 12-week placebo-controlled withdrawal period in patients with mild to moderate essential hypertension. | Mild to Moderate Hypertension | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 15 | 0 | 0 | 300 | 240 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0046 | Created | Evaluation of the efficacy and safety of three dose levels o | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A randomized, double-blind, multicenter, parallel study to compare the safety and efficacy of three dose levels of Moexipril versus Placebo as add-on therapy to Hydrochlorothiazide during an eight-week treatment period in patiets with moderate to severe hypertension. | Moderate to Severe Hypertension | Immunology | [17 empty] | United Kingdom | United Kingdom (Created) |  | 16 | 0 | 0 | 281 | 200 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0047 | Created | Evaluation of the safety, efficacy and tolerability of Moexi | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A randomized, double-blind, multicenter, parallel study to evaluate the safety, efficacy and tolerability of Moexipril compared to sustained release Verapamil in patients with mild to moderate hypertension | Mild to Moderate Hypertension | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 15 | 0 | 0 | 225 | 180 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0048 | Created | Evaluation of the efficacy, safety and tolerability of titra | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | Original: A randomized, double-blind, multicenter, placebo-controlled, dose titration study to evaluate the safety, efficacy and tolerability of Moexipril during a ten-week treatment period in patients with mild to moderate hypertension with impaired renal function. Modified: An open-label, multicen ter, dose titration study to evaluate the safety, efficacy and tolerability of Moexipril during a ten-week treatment period in patients with mild to moderate hypertension with impaired renal function | Mild to Moderate Hypertension | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 19 | 0 | 0 | 120 | 100 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0049 | Created | Evaluation of the efficacy, safety and tolerability of Moexi | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A randomized, double-blind, multicenter, parallel, dose titration study to evaluate the safety, efficacy and tolerability of Moexipril compared to sustained release Verapamil as add-on therapy to Hydrochlorothiazide during a 12-week treatment period in patients with moderate to severe essential hype rtension | Moderate to Severe Hypertension | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 11 | 0 | 0 | 147 | 100 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0050 | Created | Evaluation of the safety, efficacy and tolerability of Moexi | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A randomized, double-blind, multicenter, parallel study to evaluate the safety, efficacy and tolerability of Moexipril compared to captopril in patients with mild to moderate hypertension | Mild to Moderate Hypertension | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 15 | 0 | 0 | 240 | 180 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0051 | Created | Evaluation of the efficacy and safety of three dose levels o | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A randomized, double-blind, multicenter, parallel study to compare the safety and efficacy of three dose levels of Moexipril versus Placebo as add-on therapy to Nifedipine retard during an eight-week treatment period in patients with moderate to severe hypertension | Moderate to Severe Hypertension | Immunology | [17 empty] | United Kingdom | United Kingdom (Created) |  | 18 | 0 | 0 | 253 | 203 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0052 | Created | Blood pressure monitoring, safety of two dose levels of Moex | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A phase II, randomized, double-blind, multicenter, placebo-controlled, parallel study to evaluate the safety and antihypertensive effect of Moexipril as determined by ambulatory blood pressure monitoring duration an eight-week treatment period in patients with mild to moderate essential hypertension | Mild to Moderate Hypertension | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 3 | 0 | 0 | 60 | 55 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0060 | CSR Approved | Long-term effect (12 months) of moexipril on lung function ( | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Baxter T | [6 empty] | No | An open study to assess the effect of long-term therapy with moexipril hydrochloride (Perdix) 7.5mg or 15mg for 12 months on pulmonary function in patients with mild to moderate hypertension | Mild to Moderate Hypertension | Immunology |  | 1996-06-28 | 1996-06-28 |  | 2010-08-11: 1996-11-14; 2010-11-23: 1997-03-04; 2012-04-02: 1998-01-16; 2012-06-29: 1999-01-22; 2013-06-11: 1999-07-15 | United Kingdom | United Kingdom (Created) |  | 15 | 0 | 0 | 160 | 52 | 52 | 0 | 0 | 0 | 50 | 10 | 24 | 16
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0062 | Final TFLs released | Moexipril and arterial compliance in postmenopausal women wi | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Lecocq B | [6 empty] | No | Pilot study of the effects of hormone replacement therapy (HRT) on the moexipril (15mg)-induced changes of arterial compliance in postmenopausal hypertensive women | Mild to Moderate Hypertension | Immunology |  | 1995-06-01 | 1995-06-01 |  | 2010-08-11: 1995-09-04; 2010-11-23: 1995-10-26; 2012-04-02: 1996-10-31; 2012-06-29: 1996-11-27; 2012-10-22: 1997-04-01 | France | France (Created) |  | 1 | 0 | 0 | 60 | 60 | 40 | 0 | 0 | 0 | 45 | 0 | 0 | 45
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0063 | LPLV | Moexipril 15mg in patients with mild to moderate ess. hypert | Phase III | Single Blind | UCB Pharma Global |  | UCB Pharma Global | Delgado A | [6 empty] | No | The effect of moexipril on left ventricular hypertrophy in patients with mild to moderate essential hypertension | Mild to Moderate Hypertension | Immunology |  | 1998-01-07 | 1998-01-07 |  | 2010-08-11: 1998-01-07; 2010-11-23: 1998-03-16; 2012-06-29: 2000-02-29 | France, Portugal | France (Created), Portugal (Created) |  | 3 | 0 | 0 | 420 | 30 | 30 | 0 | 0 | 0 | 11 | 10 | 1 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0064 | Created | Moexipril versus Atenolol in postmenopausal women | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Koch B | [6 empty] | No | A randomized, double-blind, parallel, multicenter, comparative trial of moexipril versus atenolol in obese postmenopausal women | Mild to Moderate Hypertension | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 14 | 0 | 0 | 177 | 116 | 104 | 0 | 0 | 0 | 104 | 0 | 0 | 104
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0065 | Created | moexipril versus HCTZ in postmenopausal women | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A randomized, double-blind, parallel, multicenter study to compare safety and efficacy of moexipril and hydrochlorothiazide in postmenopausal hypertensive women | Mild to Moderate Hypertension | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 9 | 0 | 0 | 136 | 97 | 84 | 0 | 0 | 0 | 84 | 0 | 0 | 84
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0066 | Created | moexipril versus nitrendipine in postmenopausal women | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A randomized, double-blind, two parallel groups, multicenter study of moexipril versus nitrendipine in postmenopausal hypertensive women with or without hormone replacement therapy | Mild to Moderate Hypertension | Immunology | [20 empty] | 12 | 0 | 0 | 96 | 93 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0083 | Created | Moexipril in patients with mild to moderate hypertension. |  |  | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | A pilot-study to evaluate the safety and efficacy, using ABPM, of moexipril in patients with mild to moderate hypertension | Mild to Moderate Hypertension | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0084 | Created | moexipril mild to moderate hypertension |  |  | UCB Pharma Global |  | UCB Pharma Global | Moldenhauer U | [6 empty] | No | A randomized, double-blind, placebo-controlled, parallel, multicenter study of moexipril in postmenopausal hypertensive women who are using hormone replacement therapy | Mild to Moderate Hypertension | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0085 | Created | moexipril in postmenopausal hypertensive women |  |  | UCB Pharma Global |  | UCB Pharma Global | Pruesse D | [6 empty] | No | A randomized, double-blind, placebo-controlled, parallel, multicenter study of moexipril in postmenopausal hypertensive women who are using hormone replacement therapy | Mild to Moderate Hypertension | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0130 | Created | Drug Safety Trial Data. Study drug: MOEXIPRIL |  |  | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | Drug Safety Trial Data. Study drug: MOEXIPRIL | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0131 | Created | Drug Safety Trial Data. Study drug: MOEXIPRIL |  |  | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | Drug Safety Trial Data. Study drug: MOEXIPRIL | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0132 | Created | Drug Safety Trial Data. Study drug: MOEXIPRIL |  |  | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | Drug Safety Trial Data. Study drug: MOEXIPRIL | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0133 | Created | Drug Safety Trial Data. Study drug: MOEXIPRIL |  |  | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | Drug Safety Trial Data. Study drug: MOEXIPRIL | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0134 | Created | Drug Safety Trial Data. Study drug: MOEXIPRIL |  |  | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | Drug Safety Trial Data. Study drug: MOEXIPRIL | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0262 | Created | MOEXIPRIL - with uncomplicated essentieal hypertension |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | not available (DMCD) | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0337 | Created | MOEXIPRIL - in postmenopausal female hypertensives and the g |  |  | UCB Pharma Global |  | UCB Pharma Global | Pruesse D | [6 empty] | No | A single-blind study to compare the cost effectiveness, efficacy and safety of Moexipril either as monotherapy or in combination with felodipine e.r. in postmenopausal female hypertensives and the general hypertensive population | [22 empty] | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0365 | Created | Bioverfügbarkeit von Moexipril/HCTZ - Kombinationsformulieru |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Bioverfügbarkeit von Moexipril/HCTZ - Kombinationsformulierung | [22 empty] | 0 | 0 | 0 | 36 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0380 | Created | Drug Safety Trial Data. Study drug: MOEXIPRIL |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Drug Safety Trial Data. Study drug: MOEXIPRIL | [22 empty] | 0 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0383 | Created | Drug Safety Trial Data. Study drug: MOEXIPRIL |  |  | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | Drug Safety Trial Data. Study drug: MOEXIPRIL | [22 empty] | 0 | 0 | 0 | 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0386 | Created | Evaluation of The Bioavailability of Moexipril in Healthy V |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Evaluation of The Bioavailability of Moexipril Under Fasting and Nonfasting Conditions in Healthy Volunteers | [22 empty] | 0 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0389 | Created | Moexpril - bioequivalence of two different formulations |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | An open-laben, phase I, three-way cross-over study to investigate the bioequivalence of two different formulations of moexipril in healthy volunteers | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0390 | Created | Bioequivalence of two different formulatons of Moexipril in |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | An open label, phase I, two-way cross-over study to investigate the bioequivalence of two different formulations of moxipril in 37 healthy volunteers | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0392 | Created | Phase II open label study - moexipril - healthy volunteers - |  |  | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | A Phase II, open-label study to investigate the pharmacokinetics of multiple doses ofmoexipril in patients and healthy volunteers with different levels of renal function and to provide additional information on the safety and toleration of moexipril | [22 empty] | 0 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0415 | Created | FEMPRESS PMS study | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Stoeter M | [6 empty] | No | not available (DMCD) | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0446 | Created (Cancelled) | moexipril in postmenopausal women with mild to moderate hype |  |  | UCB Pharma Global |  | UCB Pharma Global | Pruesse D | [6 empty] | No | Single centre, randomized, double-blind, placebo-controlled cross-over study comparing the effect of moexipril and placebo on insulin sensitivity and forearm vascular function in postmenopausal women with essential hypertension already controlled on a thiazide diuretic and/or a ß-blocker | Mild to Moderate Hypertension | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0448 | Created | Drug Safety Trial Data. Study drug: MOEXIPRIL |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: MOEXIPRIL | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0451 | Created | Drug Safety Trial Data. Study drug: MOEXIPRIL |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: MOEXIPRIL | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0462 | Created | Moexipril - hypertension - to a new antihypertensive agent |  |  | UCB Pharma Global |  | UCB Pharma Global | Amar H | [6 empty] | No | Hypertension: Epidemiology Study of the French Female Population and of factors prediciting the response to a new antihypertensive agent | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0487 | Protoc. Summary Approved | Moexipril phase IV, patients with chronic heart failure | Phase IV | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Schmidt S | [6 empty] | No | Single Centre, randomized, Double-Blind, Controlled Cross-Over Study Studying the Effect of Moexipril on Insulin sensitivity and Exercise Tolerance in Patients with Chronic Heart Failure |  |  |  | 1998-09-08 | 1998-09-08 | [17 empty] | 1 | 0 | 0 | 24 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0498 | Protoc. Summary Approved | Moexipril trial (phase IV) - in postmenopausal women with an | Phase IV | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Schmidt S | [6 empty] | No | Single-centre, randomized, double-blind trial comparing the effect of Moexipril and Metoprolol on endothelial function in postmenopausal women with high cardiovascular risk with and without hormone replacement therapy. | Mild to Moderate Hypertension | Immunology |  | 1998-09-04 | 1998-09-04 | [17 empty] | 0 | 0 | 0 | 180 | 140 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0505 | Final TFLs released | Moexipril phase I trial | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | A Two-Period Open-Label Randomized Single Dose Cross-Over Study in Fifty-Two Healthy Male Volunteers to Investigate the bioequivalence of Two 15 mg Moexipril Tablets |  |  |  | 1998-10-14 | 1998-10-14 |  | 2010-08-11: 1999-01-01; 2010-11-23: 1999-01-11; 2012-06-29: 1999-03-24; 2012-10-22: 1999-05-31 |  |  |  | 1 | 0 | 0 | 52 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0519 | Final TFLs released | Moexipril/HCTZ site change (Uniretic) | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | A Two Period Open-label Randomized Single Dose Cross-Over Study in Thirty-Eight Helathy Male Volunteers to Investigate the Bioequivalence of Two 15 mg Moexipril Hydrochloride/25 mg Hydrochloride Tablets |  |  |  | 1999-01-15 | 1999-01-15 |  | 2010-08-11: 1999-03-09; 2010-11-23: 1999-04-30; 2012-06-29: 1999-06-15; 2012-10-22: 1999-07-31 |  |  |  | 1 | 0 | 0 | 38 | 38 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0538 | Final TFLs released | Poland trial (Oxycardil and Moexipril 7,5 15) | Phase IV | Single Blind | UCB Pharma Global |  | UCB Pharma Global | Mastej M | [6 empty] | No | Time of administration , morning versus evening, of antihypertensive drugs and influence on 24 hours blood pressure. | Hypertension | Immunology |  | 1999-06-01 | 1999-06-01 |  | 2010-08-11: 2000-02-20; 2010-11-23: 2000-04-02; 2012-04-02: 2001-01-02; 2012-06-29: 2001-03-15; 2012-10-22: 2001-09-30 |  |  |  | 3 | 0 | 0 | 160 | 140 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0699 | Final TFLs released | Moexipril bioavailability when crushed in applesauce | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | A pharmacokinetic study to compare the single dose bioavailability of moexipril administered as a 15 mg Univasc (Schwarz Pharma, Inc.) tablet taken intact or crushed in applesauce |  |  |  | 2002-03-28 | 2002-03-28 |  | 2010-08-11: 2002-05-07; 2010-11-23: 2002-05-18; 2012-04-02: 2002-05-18; 2012-06-29: 2002-06-10; 2012-10-22: 2002-08-12 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 32 | 32 | 28 | 0 | 0 | 0 | 32 | 0 | 0 | 32
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0719 | CSR Approved | Moexipril in patients with left ventricular hypertrophy with | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Lebedeva N | [6 empty] | No | Evaluation of efficacy and tolerability of Moexipril in patients with left ventricular hypertrophy - with mild and moderate arterial hypertension | Mild to Moderate Hypertension | Immunology |  | 2002-09-15 | 2002-09-15 |  | 2010-08-11: 2002-10-01; 2010-11-23: 2002-11-01; 2012-04-02: 2003-02-03; 2012-06-29: 2004-02-20; 2012-08-16: 2004-08-05; 2013-06-11: 2005-11-10 | Russian Federation | Russian Federation (Created) |  | 4 | 0 | 0 | 140 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0720 | Final TFLs released | Moexipril pilot food effect study | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pilot study to assess the bioavailability of a moexipril HCl 15 mg tablet test formulation and to compare the potential bioequivalence of the test formulation administered after a high-fat meal compared to the marketed 15 mg Univasc (moexipril, Schwarz Pharma, Inc) tablet under fed and fasted con ditions |  |  |  | 2002-09-13 | 2002-09-13 |  | 2010-08-11: 2002-09-27; 2010-11-23: 2003-07-11; 2012-04-02: 2003-07-11; 2012-06-29: 2003-07-28; 2012-10-22: 2003-09-05 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0868 | Created (Cancelled) | Single dose bioequivalence of moexipril 15 mg caps. (whole & | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | Long Title to be entered | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PERDIX | not defined | SP0869 | Created (Cancelled) | Single dose bioequivalence of moexipril 15 mg capsule vs moe | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | Long Title to be entered | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Polyethylene Glycol | not defined | SP0078 | Created | SPM-4757 - in patients with CAD |  |  | UCB Pharma Global |  | UCB Pharma Global | Stepien J | [6 empty] | No | Controlled acute study with SPM 4757 in a dose of 80 mg versus placebo in patients with CAD. Assessment of the antiischemic properties. Double-blind two period cross-over study. | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 24 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Polyethylene Glycol 3350 | not defined | SP0698 | Final TFLs released | Gas production with four flavored Colyte formulations | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Kastenholz K | [6 empty] | No | Gas production with four flavored Colyte formulations |  |  |  | 2002-04-24 | 2002-04-24 |  | 2010-08-11: 2002-05-08; 2010-11-23: 2002-05-22; 2012-04-02: 2002-05-22; 2012-06-29: 2002-05-22; 2012-10-22: 2002-07-03 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 5
Yes | Not assigned | Managing Type | 1 | Polysaccharide Iron Complex | Immunology | SP0523 | Created | Niferex with Ferrous succinate in hemodialysis patients | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | Multicenter, controlled trial to prove the efficacy and safety of Niferex in chronic renal failure patients with dialysis treatment. | [22 empty] | 0 | 0 | 0 | 180 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | PRESERVEX | Immunology | G01012 | Study Archived | Aceclofenac WALK study | Phase IV |  | Clinical Development Europe | TA Allergology / Respiratory | R & D | Picciolato M | [6 empty] | No | [6 empty] | 2000-10-30 | 2000-11-30 | 2001-02-01 | 2001-05-25 |  | 2002-07-08 | 2002-01-31 | 2002-08-22 | 2002-03-31 | 2003-05-09 |  | 2003-07-18 | 2002-05-31 |  | Austria, Belgium, Finland, Germany, Netherlands, United Kingdom | Austria (LPLV), Belgium (LPLV), Finland (LPLV), Germany (LPLV), Netherlands (LPLV), United Kingdom (LPLV) | Austria, Belgium, Finland, Germany, Netherlands, United Kingdom | 40 | 0 | 7 | 600 | 0 | 0 | 321 | 0 | 26 | 295 | 0 | 56 | 239
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0016 | Created | Prostaglandin E1 in chronic erectile dysfunction (I - III fo | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Albrecht D | [6 empty] | No | International multicenter study on the clinical efficacy and tolerability of self-medication by injection of prostaglandin E1 into the corpus cavernosum in patients with chronic erectile dysfunction in 5 centers (48 month) | Erectyle Dysfunction | Immunology | [17 empty] | Czech Republic, Denmark, France, Germany, Netherlands | Czech Republic (Created), Denmark (Created), France (Created), Germany (Created), Netherlands (Created) |  | 0 | 0 | 0 | 369 | 306 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0017 | Created | Prostavasin ED - Doppler Ultrasound | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Albrecht D | [6 empty] | No | Open-label study of intracavernous injections of Alprostadil Alfadex for use in the diagnosis of erectile dysfunction by doppler ultrasound | Erectyle Dysfunction | Immunology | [17 empty] | Netherlands, United States of America | Netherlands (Created), United States of America (Created) |  | 0 | 0 | 0 | 106 | 88 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0018 | Created | Prostavasin ED - Dynamic Pharmacocavernosometry | Phase II | Single Blind | UCB Pharma Global |  | UCB Pharma Global | Albrecht D | [6 empty] | No | Single-blind study of intracavernous injections of placebo versus Alprostadil alphadex for use in the diagnosis of erectile dysfunction by dynamic pharmacocanernousometry | Erectyle Dysfunction | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 51 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0019 | Created | Prostavasin ED in erectile dysfunction | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Albrecht D | [6 empty] | No | A placebo-controlled safety and efficacy study of Alprostadil alfadex (PGE1 Cyclodextrin) in the treatment of erectile dysfunction followed by 48 weeks of open-label treatment | Erectyle Dysfunction | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 117 | 49 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0020 | Created | Prostavasin ED in erectile dysfunction | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Albrecht D | [6 empty] | No | A placebo-controlled safety and efficacy study of Alprostadil Alfadex (PGE1 Cyclodextrin) in the treatment of erectile dysfunction in diabetic and non-diabetic patients followed by 48 weeks of open-label treatment | Erectyle Dysfunction | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 233 | 89 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0021 | Created | Prostavasin ED in erectile dysfunction | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Albrecht D | [6 empty] | No | A dose-titration safety and efficacy study of Alprostadil Alfadex (PGE1 Cyclodextrin) in the treatment of erectile dysfunction in diabetic and non-diabetic patients followed by 48 weeks of open-label treatment | Erectyle Dysfunction | Immunology | [17 empty] | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 567 | 197 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0022 | Created | Pilot study kinetic / prostavasin in patients with erectile | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Albrecht D | [6 empty] | No | a pilot study of plasma concentrations of PGE1, PGEo, 15-keto-PGEo after intracavernous injection of PGE1 in patients with erectile dysfunction of various origins | Erectyle Dysfunction | Immunology | [17 empty] | Germany | Germany (Created) |  | 0 | 0 | 0 | 19 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0023 | Created | PGE1/ED vs. Moxicylyte (France) | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Stegmann B | [6 empty] | No | controlled multicenter study alprostadil alfadex versus moxicylyte chlorhydrate by intracaversonal injection in the treatment of chronic erectile dysfunction | Erectyle Dysfunction | Immunology | [17 empty] | France | France (Created) |  | 0 | 0 | 0 | 154 | 154 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0024 | Created | PGE1/ED, follow up therapy (F) | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Stegmann B | [6 empty] | No | Open multicenter study of intracavernous injections of Alprostadil Alphadex in the treatment of erectile dysfunction | [19 empty] | France | France (Created) |  | 0 | 0 | 0 | 210 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0025 | Created | PGE1/ED vs. Placebo (Italy) | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Auer S | [6 empty] | No | Controlled multicenter study of Alpostradil Alphadex versus placebo by intracavernous injection in patients with chronic erectile dysfunction | [19 empty] | Italy | Italy (Created) |  | 0 | 0 | 0 | 122 | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0027 | Created | PDE1/ED, ease of use/handling | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Teichmann R | Tillery N | [5 empty] | No | A multicenter, phase III open study of intracavernous injections of Alprostadil Alphadex in the treatment of erectile dysfunction | Erectyle Dysfunction | Immunology | [17 empty] | United Kingdom | United Kingdom (Created) |  | 0 | 0 | 0 | 123 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0032 | Final TFLs released | Alprostadil ED in patients with insulin dependent diabetes m | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Auer S | [6 empty] | No | Treatment of erectile dysfunction with Alprostadil alfadex in patients with insulin dependent diabetes mellitus for 12 months | Erectyle Dysfunction | Immunology |  | 1995-10-01 | 1995-10-01 |  | 2010-08-11: 1996-03-08; 2010-11-23: 1996-07-01; 2012-04-02: 1996-12-31; 2012-06-29: 1997-09-16; 2012-10-22: 1997-12-23 | United States of America | United States of America (Created) |  | 17 | 0 | 0 | 150 | 100 | 100 | 0 | 0 | 0 | 61 | 0 | 0 | 61
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0053 | Final TFLs released | Intracavernous Alprostadil alfadex for ED | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Auer S | [6 empty] | No | A multicenter, phase IIIB, open-label study of intracavernous injections of alprostadil alfadex in the treatment of erectile dysfunction in patients following radical prostatectomy or cystoprostatectomy | Erectyle Dysfunction | Immunology |  | 1995-10-01 | 1995-10-01 |  | 2010-08-11: 1996-03-08; 2010-11-23: 1996-06-21; 2012-04-02: 1997-04-01; 2012-06-29: 1997-12-18; 2012-10-22: 1998-05-04 | France, Germany, Italy, Turkey | France (Created), Germany (Created), Italy (Created), Turkey (Created) |  | 13 | 0 | 0 | 110 | 70 | 70 | 0 | 0 | 0 | 56 | 0 | 0 | 56
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0054 | Final TFLs released | Intracavernous Alprostadil alfadex for ED in patients with s | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Auer S | [6 empty] | No | A multicenter, phase IIIB, open-label study of intracavernous injections of alprostadil alfadex in the treatment of erectile dysfunction in patients with spinal cord injury | Erectyle Dysfunction | Immunology |  | 1995-10-01 | 1995-10-01 |  | 2010-08-11: 1996-03-08; 2010-11-23: 1996-10-18; 2012-04-02: 1997-06-30; 2012-06-29: 1998-01-20; 2012-10-22: 1998-06-05 | France, Germany, Italy | France (Created), Germany (Created), Italy (Created) |  | 10 | 0 | 0 | 75 | 50 | 50 | 0 | 0 | 0 | 30 | 0 | 0 | 30
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0072 | Final TFLs released | German multicenter trial with Alprostadil alfadex in ED pati | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Gundlach C | [6 empty] | No | A multicenter, phase IIIb open-label trial to evaluate the efficacy and safety of intracavernous injections of Alprostadil Alfadex by means of the new injector duoject in subjects with erectile dysfunction. | Erectyle Dysfunction | Immunology |  | 1997-07-02 | 1997-07-02 |  | 2010-08-11: 1997-08-22; 2010-11-23: 1997-11-25; 2012-04-02: 1998-07-01; 2012-06-29: 1999-02-11; 2012-10-22: 1999-09-15 | Germany | Germany (Created) |  | 50 | 0 | 0 | 400 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0075 | Created | PROSTAVASIN bei Patienten mit schwerer Claudicatio |  |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Doppelblinde, placebokontrollierte multizentrische Studie zur Wirksamkeit einer stationären 4wöchigen intravenösen Behandlung mit Prostavasin und bewegungstherapeutischen Übungen bei Patienten mit schwerer Claudicatio (Stadium IIb nach Fontaine) | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0076 | Created | PROSTAVASIN(ED) bei femoro-cruralem Venenbypass |  |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Doppelblinde, placebokontrollierte mulitzentrische Dosisfindungs-Studie zum Einfluß von PGE1 auf den intraoperativ gemessenen Widerstand bei femoro-cruralem Venenbypass | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0077 | Created | PROSTAVASIN in the clinical outcome of patients with CLI |  |  | UCB Pharma Global |  | UCB Pharma Global | Sabia R | [6 empty] | No | To verify whether a stable prostaglandin E1 (PGE1), alprostadil alfadex cyclodextrine, added to the usual therapeutic pratcices (either invasive or not), improves in the medium term (6 months) the clinical outcome of patients with CLI | [22 empty] | 0 | 0 | 0 | 1560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0081 | Created | PROSTAVASIN in PAOD patients with advanced functional impair |  |  | UCB Pharma Global |  | UCB Pharma Global | Sabia R | [6 empty] | No | Randomized mulitcenter study on the short (4 weeks) and medium term (12 months) evolution of PAOD following alprostadil or usual standard infusional treatment in patients at stage IIb + III of Fontaine's classification | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0096 | Created | PROSTAVASIN PAOD |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | Doppelblinder, randomisierter, crossover, placebokontrollierter Vergleich des akuten Ausmaßes und Dauer der Wirkung zwei verschiedener galenischer Zubereitungen von PGE1 auf die Mikrozirkulation bei Patienten mit AVK, Stadium IIb | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0097 | Created | PROSTAVASIN in patients with PAOD and CHF |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | The tolerance of Prostaglandin E1 (PGE1) as a short time infusion (dose finding) in patients with peripheral arterial occlusive disease (PAOD) and chronic heart failure (CHF) | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0101 | Created | PROSTAVASIN to patients affected by peripheral obstructive d |  |  | UCB Pharma Global |  | UCB Pharma Global | Sabia R | [6 empty] | No | A randomized parallel group comparative study on the pharmacodynamic effect of two alprostadil doses after acute and chornic administration (4 weeks) to patients affected by peripheral obstructive disease (PAOD) at stage IIb of Fontaine's classification | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0106 | Created | Übersicht der Phase-I-Studien zu Alprostadil |  |  | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | A phase I, randomized, open-label, three-way rossover study to determine the possible interaction of alprostadil (prostaglandin E1) with acetylsalicylic acid in healthy volunteers | [22 empty] | 0 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0107 | Created | Prostavasin - Pharmacokinetics - PGE1, PGE0, 15-keto-PGE0 - |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Evaluation of the Pharmacokinetics of Prostaglandin E1 and its Main Metabolites Prostaglandin E0 and 15-keto-Prostaglanding E0 Following A | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0108 | Created | Prostaglandin - Warfarin - Alprostadil - Healthy Volunteers |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | A Phase 1, Open-Label Study to Determine the Possible Interaction of Alprostadil (Prostaglandin E1) With Warfarin in Healthy Volunteers | [22 empty] | 0 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0109 | Created | Alprostadil - Prostaglandin - Diogoxin - Healthy Volunteers |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | A Phase I, Open-Label Study to Determine the Possible Interaction of Alprostadil (Prostaglandin E1) on Digoxin in Healthy Volunteers | [22 empty] | 0 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0110 | Created | Prostavasin - Alprostadil - PGE1 - intravenous |  |  | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | Examinations of Dose Linearity of Alprostadil (Prostaglandin E1) in Healthy Volunteers Following Intravenous Dosing | [22 empty] | 0 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0111 | Created | Prostavasin - intravenous - pharmacokinetics |  |  | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | Pharmacokinetics of pge1, pge0 and 15-keto-pge0 and after intravenous infusion of pge1 | [22 empty] | 0 | 0 | 0 | 13 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0112 | Created | PROSTAVASIN in patients with type II diabetes mellitus and a |  |  | UCB Pharma Global |  | UCB Pharma Global | Veitinger K | [6 empty] | No | Double-blind placebo-controlled study of the efficacy of i.v. Prostavasin in patients with type II diabetes mellitus and arterial occlusive disease, stage IV according to Fontaine | [22 empty] | 0 | 0 | 0 | 15 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0116 | Created | PROSTAVASIN in patients with PAOD Fontaine stage IIb |  |  | UCB Pharma Global |  | UCB Pharma Global | Hartlieb C | [6 empty] | No | Double-blind, placebo-controlled, multicenter study to assess efficacy of PGE1 in patients with PAOD fontaine stage IIb | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 110 | 94 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0117 | Created | PROSTAVASIN in patients with peripheral occlusive arterial d |  |  | UCB Pharma Global |  | UCB Pharma Global | Puzic S | [6 empty] | No | Efficacy and tolerability of intravenous prostavasin treatment in patients with fontaine stage III/IV occlusive arterial disease | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 40 | 39 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0118 | Created | PROSTAVASIN - PAOD |  |  | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E | [6 empty] | No | Pilotstudie zum Einfluß von Prostavasin-Infusionen auf das Blutstillungssystem | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0120 | Created | PROSTAVASIN - in patients with PAOD |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | Double-blind (double-dummy), randomized, cross-over, placebo-controlled comparison of the acute extent and duration of the effect of four different galenic preparations of PGE1 on hemodynamics and microcirculation in patients with peripheral arterial occlusive disease (PAOD), Fontaine stage IIb | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0135 | Created | PROSTAVASIN (Crash II) - in patients with congestive heart f |  |  | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E | [6 empty] | No | A randomised, double-blind, placebo-controlled, parallel-group phase III study to evaluate the safety and the effects on haemodynamc and pulmonary parameters of a single infusion of Prostavasin in patients with congestive heart failure | Congestive Heart Failure | Immunology | [20 empty] | 0 | 0 | 0 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0136 | Created | PROSTAVASIN (Crash II) in patients with with Fontaine stage |  |  | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E | [6 empty] | No | Double-blind, randomized, placebo-controlled, mulitcenter, inpatient plus open lable outpatient assessment of the cardiac effects of Prostaglandin E1 in patients with Fontaine stage III or IV peripheral arterial occlusive disease (PAOD) and chronic NYHA II/III congestive heart failure (CHF) stabiliz ed on digitalis and/or diuretic and/or vasodilator (e.g. angiotensin converting enzyme inhibitor) | [22 empty] | 0 | 0 | 0 | 61 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0137 | Created | PROSTAVASIN (Crash II) - in patients with severe peripheral |  |  | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E | [6 empty] | No | A randomised, double-blind, controlled, parallel-group phase-III study to evaluate the tolerability and the effects on haemodynamic parameters of daily intravenous infusions of Prostavasin versus Buflomedil administered over a 21-Day treatment period in patients with severe peripheral arterial occlu sive disease | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0138 | Created | PROSTAVASIN (Crash II) - in patients with congestive heart f |  |  | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E | [6 empty] | No | A randomised, double-blind, placebo-controlled, parallel-group phase-III study to evaluate the safety and the effects on haemodynamic parameters of a single infusion of Prostavasin in patients with congestive heart failure (NYHA Class II / III) | Congestive Heart Failure | Immunology | [20 empty] | 0 | 0 | 0 | 21 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0139 | Created | PROSTAVASIN -PAOD |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | Interaction study proving the safety of a single-dose intravenous infusion of prostaglandin E1 60 µg over 2 hours in PAOD stage III - IV patients, in addition to an isosorbide mononitrate retard 50 mg, (once a day), in steady state conditions for treatment of chronic stable angina, cross-over, doubl e-blind, placebo controlled, phase IIIa study | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0140 | Created | PROSTAVASIN (Crash II) in patients with central aortic clamp |  |  | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E | [6 empty] | No | A randomized, double-blind, placebo-controlled, parallel-group phase III study to evaluate the tolerability and the effects on the reperfusion syndrome of a single infusion of Prostavasin in patients with central aortic clamping | [22 empty] | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0141 | Created | PROSTAVASIN - on glomerular hemodynamics and perm-selectivit |  |  | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E | [6 empty] | No | A double-blind, cross-over study to assess the acute effects of alprostadil on glomerular hemodynamics and perm-selectivity in proteinuric chronic nephropathy | [22 empty] | 0 | 0 | 0 | 20 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0142 | Created | PROSTAVASIN in patients with stable angina pectoris |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | A randomized, double-blind, placebo-controlled, cross-over phase III study to evaluate the safety and the effects on exercise capacity of a single infusion of PGE1 in patients with stable angina pectoris | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0143 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN(ED) |  |  | UCB Pharma Global |  | UCB Pharma Global | Albrecht D | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN(ED) | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0146 | Created | PROSTAVASIN in patients with PAOD and CHF |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | The tolerance and efficacy of Prostaglandin E1 (PGE1) as an intravenous bolus application (dose finding) in patients with peripheral arterial occlusion disease (PAOD) and chronic heart failure (CHF) | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0147 | Created | PROSTAVASIN to healthy male volunteers | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E | [6 empty] | No | A randomized, double-blind, placebo-controlled, parallel-group phase-I study to evaluate the tolerance and the effects on pulmonary function of single ascending doses of two different Prostaglandin E1 formulations given as intravenous bolus injection to healthy male volunteers. | [22 empty] | 0 | 0 | 0 | 24 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0148 | Created | PROSTAVASIN on cardiac electrophysiological status of patien |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | A randomized, double-blind, cross-over, placebo-controlled phase IIa study to evaluate the tolerability and effect on electrophysiological status of patients with stable angina pectoris giving a single ascending dose of PGE1 as intravenous short injection (bolus of 5 minutes duration) followed by op en label phase with 60 µg PGE1 injected in 2 minutes | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0149 | Created | PROSTAVASIN - PAOD |  |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | A double-blind evaluation of the clinical efficacy and safety of i.v. Alprostadil alfadex compared to placebo in patients with peripheral arterial occlusive disease (fontaine stage IV) in a multicenter trial | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 205 | 130 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0150 | Created | PROSTAVASIN bei therapieresistenten venösen Ulcera |  |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Prospektive placebo-kontrollierte doppelblinde Studie zur Prüfung der klinischen Wirksamkeit von i.v. Prostavasin bei therapieresistenten venösen Ulcera | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0151 | Created | PROSTAVASIN (Crash II) bei therapieresistenten venösen Ulcer |  |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Prospektive placebo-kontrollierte doppelblinde Studie zur Prüfung der klinischen Wirksamkeit von i.v. Prostavasin bei therapieresistenten venösen Ulcera | [22 empty] | 0 | 0 | 0 | 93 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0152 | Created (Cancelled) | PROSTAVASIN (Crash II) - in patients with severe peripheral |  |  | UCB Pharma Global |  | UCB Pharma Global | Pruesse D | [6 empty] | No | A randomized, double-blind, multicenter, placebo-controlled, parallel group study to evaluate the safety and efficacy of daily intravenous infusions of prostavasin, administered over a 28-day treatment period in patients with severe peripheral arterial occlusive disease (PAOD) | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0153 | Created | PROSTAVASIN - PAOD |  |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Doppelblinde, kontrollierte Pilot-Studie zum Einfluß einer intraarteriellen und intravenösen Prostaglandin E1-Infusion auf die fluoreszenzmikroskopischen Befunde bei Patienten mit arterieller Verschlußkrankheit im Stadium IV | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0155 | Created | PROSTAVASIN (Crash II) in patients with PAOD |  |  | UCB Pharma Global |  | UCB Pharma Global | Diede H | [6 empty] | No | Clinical efficacy of intravenous PGE1 (Prostavasin) in patients with peripheral arterial occlusive disease (Fontaine stage III / IV), in an open label multicentre trial | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 115 | 73 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0156 | Created | PROSTAVASIN (Crash II) - in patients with intermittent claud |  |  | UCB Pharma Global |  | UCB Pharma Global | Kubbutat S | [6 empty] | No | Clinical effects of regular physical training and additional i.v. PGE1 (Prostavasin) therapy versus placebo in patients with intermittent claudication | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0159 | Created | PROSTAVASIN (Crash II) to percutaneous transluminal coronar |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | Intravenous PGE1 as adjuvant therapy to percutaneous transluminal coronary angioplasty (PTCA) - Dose titration pilot study - | [22 empty] | 0 | 0 | 0 | 48 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0160 | Created | PROSTAVASIN - on early occlusions of venous bypasses of the |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | The effectg of PGE1 on early occlusions of venous bypasses of the lower extremities | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0161 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0162 | Created | PROSTAVASIN - bei PAVK Stadium IV |  |  | UCB Pharma Global |  | UCB Pharma Global | Rogatti W | [6 empty] | No | PROSTAVASIN - bei PAVK Stadium IV | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0163 | Created | PROSTAVASIN gegen ATP im Stadium III/IV der AVK |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | PROSTAVASIN gegen ATP im Stadium III/IV der AVK | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0164 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0165 | Created | PROSTAVASIN bei PAVK |  |  | UCB Pharma Global |  | UCB Pharma Global | Rogatti W | [6 empty] | No | PROSTAVASIN bei PAVK | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0166 | Created | PROSTAVASIN - bei peripherer arterieller Verschlußkrankheit |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | PROSTAVASIN - bei peripherer arterieller Verschlußkrankheit (IIb) | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0167 | Created | PROSTAVASIN - im Stadium IIb der AVK |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | PROSTAVASIN - im Stadium IIb der AVK | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 50 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0168 | Created | PROSTAVASIN - bei AVK Stadium III |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | PROSTAVASIN - bei AVK Stadium III | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0169 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0170 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0171 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0172 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0173 | Created | PROSTAVASIN - bei austrainierten Patienten mit Claudicatio i |  |  | UCB Pharma Global |  | UCB Pharma Global | Rogatti W | [6 empty] | No | PROSTAVASIN - bei austrainierten Patienten mit Claudicatio intermittens | [22 empty] | 0 | 0 | 0 | 48 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0174 | Created | PROSTAVASIN - zur Wirkung auf kortikale evozierte Potentiale |  |  | UCB Pharma Global |  | UCB Pharma Global | Rogatti W | [6 empty] | No | PROSTAVASIN - zur Wirkung auf kortikale evozierte Potentiale und spontanes EEG | [22 empty] | 0 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0175 | Created | PROSTAVASIN - not available (DMCD) |  |  | UCB Pharma Global |  | UCB Pharma Global | Dommaschk J | [6 empty] | No | not available (DMCD) | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0176 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0177 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0178 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0179 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0180 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0181 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0182 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0183 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0184 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0185 | Created | PROSTAVASIN - bei Patienten mit AVK |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | PROSTAVASIN - bei Patienten mit AVK | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 195 | 146 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0186 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0187 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0188 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0189 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0190 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0191 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0192 | Created | PROSTAVASIN in patients with stage IV PAOD |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | Single-blind randomized mulitcenter comparative study on alprostadil i.v. vs. pentoxifylline i.v. in patients with stage IV (Fontaine) peripheral occlusive arterial disease. | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0193 | Created | PROSTAVASIN bei Patienten mit AVK im Stadium IV |  |  | UCB Pharma Global |  | UCB Pharma Global | Rogatti W | [6 empty] | No | PROSTAVASIN bei Patienten mit AVK im Stadium IV | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 85 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0194 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0195 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0196 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0197 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0198 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0199 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0200 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0201 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0202 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0203 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0204 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0205 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0206 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0207 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0208 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0209 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0210 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0230 | Created | PROSTAVASIN bei Patienten mit AVK Stadium II |  |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Lebensqualität nach i.v. Prostavasin-Therapie bei Patienten mit AVK Stadium II - Pilotstudie | [22 empty] | 0 | 0 | 0 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0231 | Created | PROSTAVASIN - Bestimmung des Einflusses auf die Lebensqualit |  |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Lebensqualität nach i.v. Prostavasin-Therapie bei Patienten mit AVK Stadium IV - Pilotstudie | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0240 | Created | Interaktionen zwischen PROSTAVASIN und anderen Medikamenten |  |  | UCB Pharma Global |  | UCB Pharma Global | Dommaschk J | [6 empty] | No | Pilotstudie zur Erfassung des Einflusses von Interaktionen zwischen Prostavasin und anderen Medikamenten auf das Blutstillungssystem | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0241 | Created | PROSTAVASIN - two different PGE1 formulations |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | A randomised, double-blind, placebo-controlled, parallel-group phase-I-study to evaluate the tolerance and the effects on pulmonary function of single ascending doses of two different Prostaglandin E1 formulations given as intravenous bolus injection to healthy male volunteers | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0243 | Created | PROSTAVASIN in patients with coronary heart disease and posi |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | Exclusion of coronary steal with PGE1- two identical open-single rising dose tolerance phase IIa studies with PGE1 given i.v. over 5 min. in patient with coronary heart disease and positive and negative dipyridamole testing | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0244 | Created | PROSTAVASIN bei Patienten mit kritischer Etremitätenischämi |  |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Pilot-Studie zum Einfluß einer intravenösen Prostaglandin E1-Infusion auf die Thromboxan- und Prostazyklin-Synthese bei Patienten mit kritischer Extremitätenischämie | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0245 | Created | PROSTAVASIN bei Patienten mit chronisch kritischer Ischämie |  |  | UCB Pharma Global |  | UCB Pharma Global | Baumgartner (Mig. From Sports) U | [6 empty] | No | Studie über den Einfluss von Prostaglandin E1 (PGE1) i.v. bei Patienten mit chronisch kritischer Ischämie auf mikro-/makrozirkulatorische Parameter | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0247 | Created | PROSTAVASIN - not available (DMCD) |  |  | UCB Pharma Global |  | UCB Pharma Global | Dommaschk J | [6 empty] | No | not available (DMCD) | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0249 | Created | PROSTAVASIN - not available (DMCD) |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | not available (DMCD) | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0250 | Created | PROSTAVASIN - in patients with Fontaine stage III and IV PAO |  |  | UCB Pharma Global |  | UCB Pharma Global | Weiss M | [6 empty] | No | Efficacy and tolerability of intravenous Prostavasin therapy in patients with Fontaine stage III and IV occlusive arterial disease | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0251 | Created | PROSTAVASIN - PAOD |  |  | UCB Pharma Global |  | UCB Pharma Global | Rogatti W | [6 empty] | No | Wirksamkeit und Verträglichkeit der intravenösen Prostavasin-Therapie bei Patienten mit arterieller Verschlußkrankheit im Stadium III nach Fontaine | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0252 | Created | PROSTAVASIN - Veränderungen des tcPO2 bei Patienten mit AVK, |  |  | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E | [6 empty] | No | Randomisierte, kontrollierte Studie im cross-over Design zur Wirkung von i.a. und i.v. Prostavasin auf die kutane Mikrozirkulation bei AVK, Stadium IV | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0253 | Created | PROSTAVASIN - PAOD |  |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Doppelblinde, placebokontrollierte Studie zur Wirksamkeit einer ambulanten, 4wöchigen i.v. Behandlung mit Prostavasin (60 µg PGE1) bei Patienten mit schwerer Claudicatio (Stadium IIb nach Fontaine) | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 228 | 186 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0254 | Created | PROSTAVASIN - Muskelstoffwechsel der unteren Extremität (hea |  |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Pilot-Studie zum Einfluß einer intravenösen Prostaglandin E1-Infusion auf den Muskelstoffwechsel der unteren Extremität bei Probanden | [22 empty] | 0 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0283 | Created | PROSTAVASIN - bei Patienten mit AVK Stadium III und IV |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | PROSTAVASIN - bei Patienten mit AVK Stadium III und IV | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0287 | Created | PROSTAVASIN bei PAVK |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | PROSTAVASIN bei PAVK | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0288 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Rogatti W | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0290 | Created | PROSTAVASIN - bei geriatrischen Patienten mit AVK |  |  | UCB Pharma Global |  | UCB Pharma Global | Rogatti W | [6 empty] | No | PROSTAVASIN - bei geriatrischen Patienten mit AVK | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 20 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0295 | Created | PROSTAVASIN - bei erektiler Dysfunktion |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | PROSTAVASIN - bei erektiler Dysfunktion | Erectyle Dysfunction | Immunology | [20 empty] | 0 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0297 | Created | PROSTAVASIN - auf die Hämodynamik u. die Prostaglandin E1-Me |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | PROSTAVASIN - auf die Hämodynamik u. die Prostaglandin E1-Metaboliten | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0298 | Created | PROSTAVASIN - bei Patienten im Stadium IIb der AVK |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | PROSTAVASIN - bei Patienten im Stadium IIb der AVK | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0305 | Created | PROSTAVASIN - in patients with severe PAOD |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | A randomized, double-blind, multicenter, placebo-controlled parallel group study to evaluate the safety and efficacy of daily intravenous infusions of prostavasin administered over a 28-day treatment period in patients with severe peripheral arterial occlusive disease (PAOD) | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 145 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0308 | Created | ALPROSTADIL-RENAL in patients at risk induced by intravascul |  |  | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E | [6 empty] | No | A randomized, double-blind, placebo-controlled, parallel group study to evaluate the efficacy and safety of short-term administration of i.v. PGE1 for the prevention of transient or permanent renal dysfunction in patients at risk induced by intravascular radiocontrast media andministration - pilot s tudy | [22 empty] | 0 | 0 | 0 | 31 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0309 | Created | Prostaglandin - Prostavasin, Erectyle Dysfunction - 24 Volun |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Pharmacokinetic Comparison of Prostaglandin E1 (Prostavasin) after Intravenous and Intracavernous Administration in 24 Volunteers with Erectile Dysfunction | [22 empty] | 0 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0314 | Created | PROSTAVASIN - on indicators of the adequacy of microcirculat |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | A randomized, double-blind, mulitcenter, placebo-controlled, parallel group study to evaluate the effect of two doses of prostavasin on indicators of the adequacy of microcirculation in patients with severe peripheral arterial occlusive disease (PAOD) | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 69 | 67 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0315 | Created | PROSTAVASIN - bei Patienten mit arterieller Verschlußkrankhe |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | not available (DMCD) | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 20 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0319 | Created | PROSTAVASIN -PAOD |  |  | UCB Pharma Global |  | UCB Pharma Global | Dommaschk J | [6 empty] | No | A double-blind, placebo-controlled study to evaluate the efficacy and safety of vasoprost (alprostadil) in the treatment of patients with severe intermittent claudication due to peripheral arterial occlusive disease (PAOD) | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 330 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0320 | Created | PROSTAVASIN in patients requiring cardiopulmonary bypass ope |  |  | UCB Pharma Global |  | UCB Pharma Global | Dommaschk J | [6 empty] | No | A randomized, double-blind, placebo-controled, parallel group study to evaluate the efficacy and safety of short-term administration of i.v. SPM-633 for the prevention of transient or permanent renal dysfunction in patients requiring cardiopulmonary bypass operation - pilot study - | [22 empty] | 0 | 0 | 0 | 45 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0321 | Created | PROSTAVASIN in patients at risk induced by intravascular rad |  |  | UCB Pharma Global |  | UCB Pharma Global | Dommaschk J | [6 empty] | No | A randomized, double-blind, placebo-controled, parallel group study to evaluate the efficacy and safety of short-term administration of i.v. SPM-633 for the prevention of transient or permanent renal dysfunction in patients at risk induced by intravascular radiocontrast media administration - pilot study - | [22 empty] | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0322 | Created | ALPROSTADIL-ALPHADEX(RENAL) in patients requiring cardiopulm |  |  | UCB Pharma Global |  | UCB Pharma Global | Schollmayer E | [6 empty] | No | A randomized, double-blind, placebo-controlled, parallel group study to evaluate the efficacy and safety of short-term administration of i.v. SPM-633 for the prevention of transient or permanent renal dysfunction in patients requiring cardiopulmonary bypass operation - a pilot study - | [22 empty] | 0 | 0 | 0 | 32 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0323 | Created | PROSTAVASIN in patients at risk undergoing vascular surgery |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | A randomized, double-blind, placebo-controlled, parallel group study to evaluate the efficacy and safety of short-term administration of i.v. SPM-633 for the prevention of transient or permanent renal dysfunction in patients at risk undergoing vascular surgery requiring suprarenal clamping - a pilo t study - | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0324 | Created | PROSTAVASIN in patients at risk undergoing vascular surgery |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | A randomized, double-blind, placebo-controlled, parallel group study to evaluate the efficacy and safety of short-term administration of i.v. SPM-633 for the prevention of transient or permanent renal dysfunction in patients at risk undergoing vascular surgery requiring infrarenal clamping - a pilo t study - | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0330 | Created | PROSTAVASIN ED with a new self-injector |  |  | UCB Pharma Global |  | UCB Pharma Global | Auer S | [6 empty] | No | A single-center, phase II open-label pilot study of intracavernous injections of alprostadil alfadex in the treatment of erectile dysfunction with a new self-injector | Erectyle Dysfunction | Immunology | [20 empty] | 0 | 0 | 0 | 31 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0332 | Created | PROSTAVASIN - bei femorocruralem Venenbypass im Stadium III/ |  |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Kontrollierte, offene Studie zum Einfluß einer präsintra- und postoperativen Gabe von Prostavasin auf die Verschlußrate bei femorocruralem Venenbypass im Stadium III/IV der AVK | [22 empty] | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0333 | Created | PROSTAVASIN - im Stadium II der AVK |  |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Kontrollierte, randomisierte Studie zur Wirksamkeit und Verträglichkeit einer 1stündigen gegenüber einer 2stündigen Prostavasin-Infusionstherapie im Stadium II der AVK | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0334 | Created | PROSTAVASIN - Muskelstoffwechsel bei Patienten mit Claudicat |  |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Pilotstudie zur Wirkung einer 4wöchigen intravenösen PGE1-Therapie auf den mittels NMR gemessenen Muskelstoffwechsel bei Patienten mit Claudicatio | [22 empty] | 0 | 0 | 0 | 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0343 | Created | PROSTAVASIN - on blood flow through newly inserted infra-ing |  |  | UCB Pharma Global |  | UCB Pharma Global | Dommaschk J | [6 empty] | No | A randomized, double-blind, placebo-controlled pilot study to evaluate the effects of Prostaglandin E1 (alprostadil alfadex) on blood flow through newly inserted infra-inguinal vein bypass grafts | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0370 | Created | pharmacokinetic study of alprostadil |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Pharmacokinetic study of alprostadil in volunteers with an end-stage ofrenal impairment compared to a control group of healthy volunteers with matched pair technic | [22 empty] | 0 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0371 | Created | Pharmacokinetic - Alprostadil - Hepatic Impairment - Healthy |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Pharmacokinetic study of alprostadil in volunteers with hepatic impairment compared to control group of healthy volunteers with matched pair technik | [22 empty] | 0 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0384 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 | 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0420 | Created | Pharmacokinetic study with Alprostadil in patients suffering |  |  | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | Pharmacokinetic study with Alprostadil in patients suffering from PAOD stage III/IV compared to control group of healthy volunteers with matched pair technique | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0437 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN-ED |  |  | UCB Pharma Global |  | UCB Pharma Global | Dommaschk J | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN-ED | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0438 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Dommaschk J | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0456 | Created | Drug Safety Trial Data. Study drug: ALPROSTADIL-ALFADEX |  |  | UCB Pharma Global |  | UCB Pharma Global | Dommaschk J | [6 empty] | No | Drug Safety Trial Data. Study drug: ALPROSTADIL-ALFADEX | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0458 | Created | VIRIDAL in patients with erectile dysfunction |  |  | UCB Pharma Global |  | UCB Pharma Global | Baxter T | [6 empty] | No | A multicentre, randomized, cross-over trial to investigate patient preference between two different presentations of alprostadil: the Viridal cartridge system and caverject, in patients with erectile dysfunction | Erectyle Dysfunction | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0465 | Created | VASOPROST - not available (DMCD) | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | not available (DMCD) | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0467 | Created | EDEX vs MUSE in male patients with erectile dysfunction |  |  | UCB Pharma Global |  | UCB Pharma Global | Dommaschk J | [6 empty] | No | A prospective, randomized, open-label, cross-over, comparative study of the efficacy and safety of EDEX vs MUSE in male patients with erectile dysfunction | Erectyle Dysfunction | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0469 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0470 | Created | Drug Safety Trial Data. Study drug: PROSTAVASIN |  |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Drug Safety Trial Data. Study drug: PROSTAVASIN | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0477 | Protoc. Summary Approved | AWB /Viridal 98 - erektile Dysfunktion | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Gundlach C | [6 empty] | No | AWB /Viridal 98 - erektile Dysfunktion | Erectyle Dysfunction | Immunology |  | 1998-05-04 | 1998-05-04 | [17 empty] | 0 | 0 | 0 | 1800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0489 | Final TFLs released | Viagra non-responder trial | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Auer S | [6 empty] | No | A prospective, open-label trial of the efficacy and safety of EDEX (VIRIDAL) in patients unsuccessfully treated with VIAGRA | Erectyle Dysfunction | Immunology |  | 1998-02-25 | 1998-02-25 |  | 2010-08-11: 1998-08-28; 2010-11-23: 1998-10-21; 2012-04-02: 1999-01-08; 2012-06-29: 1999-03-25; 2012-10-22: 1999-06-14 | United States of America | United States of America (Created) |  | 6 | 0 | 0 | 350 | 50 | 50 | 0 | 0 | 0 | 84 | 0 | 20 | 64
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0507 | Created | Vasoprost in patients with severe peripheral arterial occlus | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | An open-label, multicenter study to evaluate the safety and efficacy of 28 intravenous infusions of Vasoprost (Alprostadil), administered to patients with severe peripheral arterial occlusive disease. (PAOD) | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0510 | Created | Prostavasin in patients of Fontaine stage II,III and IV | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Multicenter, open-label trial to proof the efficacy in reducing the pain symptoms of peripheral arterial occlusive disease and safety of Prostavasin in patients of Fontaine stage II, III and IV. | Peripheral Arterial Occlusive Disease | Immunology | [20 empty] | 0 | 0 | 0 | 60 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0543 | LPLV | Prostavasin bei Spalthaut-transplantierten Patienten mit Ulc | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Sohn M | [6 empty] | No | The Effect of Prostavasin on the healing of meshgraft on patients with venous ulcers and postthrombotic syndrome | Chronic Venous insufficiency | Immunology |  | 1999-05-21 | 1999-05-21 |  | 2010-08-11: 1999-12-08; 2010-11-23: 2000-03-28; 2012-04-02: 2002-09-18; 2012-06-29: 2002-09-18 | Germany | Germany (Created) |  | 1 | 0 | 0 | 48 | 44 | 40 | 0 | 0 | 0 | 17 | 0 | 0 | 17
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0548 | LPLV | Periphere und Kardiopulmonare Leistungsfähigkeit nach PgE1-T | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Peripheral and Cardiopulmonary performance after additive Prostaglandin E1 therapy while exercise program | Peripheral Arterial Occlusive Disease | Immunology |  | 1999-04-27 | 1999-04-27 |  | 2010-08-11: 1999-12-03; 2010-11-23: 2000-02-25; 2012-06-29: 2002-09-19 | Germany | Germany (Created) |  | 3 | 0 | 0 | 50 | 45 | 40 | 0 | 0 | 0 | 18 | 6 | 0 | 12
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0580 | Study Archived | Intravenous prostaglandin E1 treatment in outpatients with i | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Nilius S | Beinhauer-Zellenka U | [5 empty] | No | Intravenous prostaglandin E1 treatment in outpatients with intermittent claudication | Claudicatio Intermittens | Immunology |  | 2000-06-01 | 2000-06-01 |  | 2000-11-30 | 2001-01-18 | 2001-04-17 | 2010-12-13 | 2010-09-08 | 2011-07-28 | 2011-04-26 | 2011-08-11 | 2011-09-06 | 2011-09-22 | 2012-03-12 | 2011-12-15 | 2012-03-26 | Germany | Germany (LPLV) | Germany | 40 | 56 | 45 | 558 | 558 | 0 | 617 | 0 | 56 | 561 | 0 | 104 | 457
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0617 | Created (Cancelled) | Prostavasin bei primärem Raynaud Syndrom | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Wilberz S | [6 empty] | No | Prostavasin bei primärem Raynaud Syndrom | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0777 | Study Archived | Prostavasin-in patients with critical limb ischemia (Fontain | Phase IV | Double Blind | UCB Pharma Global | GMA Neurology / Psychiatry | UCB Pharma Global | Webers T | Bonny M | N/A | CRO AptivSolutions, Cologne, Germany |  |  | adults | No | Multinational, prospective, randomized, double-blind, placebo-controlled, parallel groups study to assess the efficacy and safety of Prostavasin in patients with critical limb ischemia (Fontaine stage IV) | Peripheral Arterial Occlusive Disease | Immunology |  | 2004-03-12 |  |  | 2003-11-28 | 2004-03-26 | 2004-03-26 | 2012-06-30 | 2013-01-16 |  | 2013-07-30 |  | 2013-10-23 |  | 2014-01-13 |  | 2014-05-19 | Czech Republic, Germany, Mexico, Poland, Russian Federation, Ukraine | Czech Republic (LPLV), Germany (LPLV), Mexico (LPLV), Poland (LPLV), Russian Federation (LPLV), Ukraine (LPLV) | Czech Republic, Germany, Mexico, Poland, Russian Federation, Ukraine | 60 | 100 | 78 | 1500 | 840 | 0 | 1483 | 0 | 643 | 840 | 0 | 272 | 568
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0878 | Study Archived | ALPROSTADIL IN MACULOPATHY STUDY | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Nilius S | Beinhauer-Zellenka U | [5 empty] | No | Confirmatory, prospective, randomized, double-blind, placebo-controlled, parallel groups study to assess the efficacy and safety of prostaglandin e1 in subjects with dry age-related macular degeneration | Age-related Maculopathy | Immunology |  | 2005-09-02 | 2005-09-02 |  | 2006-02-20 | 2006-07-11 | 2006-07-11 | 2010-05-25 | 2009-11-03 | 2010-12-01 | 2010-02-25 | 2010-06-23 | 2010-06-30 | 2010-09-15 | 2010-08-05 | 2010-11-15 | 2010-11-15 | Austria, Germany | Austria (LPLV), Germany (LPLV) | Austria, Germany | 8 | 9 | 6 | 54 | 54 | 26 | 40 | 0 | 4 | 36 | 0 | 1 | 35
Yes | Not assigned | Managing Type | 1 | Prostavasin, Viridal | not defined | SP0884 | CSR Approved | PIKASSO | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Ney U | [6 empty] | No | Integation of therapy in hospital and outpatient treatment Investigation of the medical care of patients with Prostavasin in advanced occlusive arterial disease |  |  |  | 2006-04-12 | 2006-04-12 |  | 2010-08-11: 2006-04-12; 2010-11-23: 2006-06-02; 2012-04-02: 2007-01-22; 2012-06-29: 2008-01-30; 2013-06-11: 2011-12-31 |  |  |  | 50 | 0 | 0 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | RADIPRODIL | Central Nervous System | UP0027 | Study Archived | Open-label Exploratory PK/Safety of UCB3491 in Healthy Volun | Phase I | Single Blind | GED | Neurology | GED | Mollet M | Mccabe S | PRA | SPI PRA | Yes | Yes | adults | Yes | A SINGLE ORAL DOSE STUDY OF THE SAFETY, TOLERABILITY, AND PHARMACOKINETIC PROFILE OF RADIPRODIL IN ADULT HEALTHY VOLUNTEERS | Epilepsy | Central Nervous System |  | 2015-09-24 | 2015-06-18 |  | 2015-11-10 | 2016-01-06 | 2016-01-11 | 2016-01-22 | 2016-01-21 |  | 2016-02-03 |  | 2016-03-17 |  | 2016-04-15 |  | 2016-06-29 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 10 | 10 | 10 | 17 | 0 | 7 | 10 | 0 | 0 | 10
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0723 | Study Archived (Stopped) | SPM 969/RBx 2258: Single dose escalation with capsules | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | Randomized, double-blind, placebo-controlled, group-comparison, dose escalation trial to investigate safety, tolerability and pharmacokinetics of RBx 2258 after single oral dosing of 1, 2, 3, 4.5 and 6 mg in young healthy male subjects |  |  |  | 2002-12-05 | 2002-12-05 |  | 2010-08-11: 2003-01-07; 2010-11-23: 2003-03-31; 2012-04-02: 2003-05-07; 2012-06-29: 2003-05-21; 2012-08-16: 2003-07-28; 2012-10-22: 2003-09-05 | Germany | Germany (Created) |  | 1 | 0 | 0 | 50 | 50 | 40 | 67 | 17 | 0 | 50 | 0 | 2 | 48
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0724 | Study Archived | SPM 969/RBx 2258: Multiple dose escalation + food interactio | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | Randomized, double-blind, placebo-controlled, group-comparison, dose escalation trial to investigate safety, tolerability and pharmacokinetics of RBx 2258 after multiple oral dosing once daily for 7 days in young healthy male subjects |  |  |  | 2003-01-14 | 2003-01-14 |  | 2010-08-11: 2003-02-21; 2010-11-23: 2003-08-20; 2012-04-02: 2003-10-27; 2012-06-29: 2003-11-24; 2012-08-16: 2004-01-27; 2012-10-22: 2005-03-03 | Germany | Germany (Created) |  | 1 | 0 | 0 | 30 | 30 | 24 | 37 | 12 | 0 | 25 | 0 | 2 | 23
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0725 | Study Archived | SPM 969/RBx 2258: Single dose PK in young and elderly men | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL-GROUP TRIAL TO EVALUATE THE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF SINGLE DOSE ORAL TREATMENT OF RBx 2258 IN YOUNG MALE AND ELDERLY MALE SUBJECTS |  |  |  | 2003-07-07 | 2003-07-07 |  | 2010-08-11: 2003-09-02; 2010-11-23: 2003-11-03; 2012-04-02: 2003-11-20; 2012-06-29: 2003-12-18; 2012-08-16: 2004-01-22; 2012-10-22: 2005-04-01 | Germany | Germany (Created) |  | 1 | 0 | 0 | 32 | 32 | 32 | 62 | 30 | 0 | 32 | 0 | 0 | 32
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0726 | Study Archived | SPM 969/RBx 2258: Multiple dose PK in elderly men | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL GROUP TRIAL TO EVALUATE THE SAFETY, TOLERABILITY AND PHARMACOKINETICS OF MULTIPLE DOSE TREATMENTS OF 7.5MG OR 10MG RBX 2258 VERSUS PLACEBO IN 50 TO 80-YEAR-OLD MALE SUBJECTS |  |  |  | 2003-10-15 | 2003-10-15 |  | 2010-08-11: 2003-12-15; 2010-11-23: 2004-01-09; 2012-04-02: 2004-02-23; 2012-06-29: 2004-04-13; 2012-08-16: 2004-06-14; 2012-10-22: 2005-03-07 | Netherlands | Netherlands (Created) |  | 1 | 0 | 0 | 36 | 36 | 36 | 135 | 99 | 0 | 36 | 0 | 0 | 36
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0727 | Study Archived | SPM 969/RBx 2258: PK in ethnic groups | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL GROUP TRIAL TO EVALUATE THE SAFETY, TOLERABILITY AND PHARMACOKINETICS OF SINGLE DOSE ORAL TREATMENT OF 7.5mg RBX 2258 IN HEALTHY MALE WHITE AND BLACK SUBJECTS |  |  |  | 2004-02-06 | 2004-02-06 |  | 2010-08-11: 2004-04-05; 2010-11-23: 2004-07-13; 2012-04-02: 2004-08-19; 2012-06-29: 2004-09-08; 2012-08-16: 2004-10-15; 2012-10-22: 2005-03-23 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 32 | 32 | 32 | 135 | 100 | 0 | 33 | 1 | 1 | 31
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0737 | Final TFLs released (Stopped) | Dose-finding trial of the efficacy and tolerability of RBx 2 | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Thomas D | [6 empty] | No | A multisite, multinational, double-blind, double dummy, parallel group, randomized, placebo-controlled, dose-finding comparator trial of the efficacy, safety and tolerability of 4 different oral doses of sustained release RBx 2258 tablets in comparison to tamsulosin 0.4mg in male subjects with Lower Urinary Tract Symptoms due to Benign Prostatic Hyperplasia | Lower Urin Tract symps assoc with BPH | Immunology |  | 2004-05-27 | 2003-03-04 |  | 2010-08-11: 2004-02-05; 2010-11-23: 2004-07-01; 2012-04-02: 2004-11-04; 2012-06-29: 2004-12-10; 2012-08-16: 2005-01-31; 2012-10-22: 2005-03-02 | Belgium, France, Germany, Lithuania, Netherlands, Poland, Russian Federation, South Africa, Spain, United Kingdom | Belgium (Created), France (Created), Germany (Created), Lithuania (Created), Netherlands (Created), Poland (Created), Russian Federation (Created), South Africa (Created), Spain (Created), United Kingdom (Created) |  | 45 | 0 | 0 | 450 | 300 | 255 | 213 | 56 | 0 | 79 | 0 | 18 | 61
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0763 | Study Archived | SPM 969/RBx 2258: Single dose escalation with x mg tablet | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | Randomized, double-blind, placebo-controlled, group-comparison, dose escalation trial to investigate safety, tolerability and pharmacokinetics of RBx 2258 after single oral administration of ascending doses in young healthy male subjects |  |  |  | 2003-06-11 | 2003-06-11 |  | 2010-08-11: 2003-06-27; 2010-11-23: 2003-08-05; 2012-04-02: 2003-10-15; 2012-06-29: 2003-10-28; 2012-08-16: 2003-12-12; 2012-10-22: 2005-03-08 | Germany | Germany (Created) |  | 1 | 0 | 0 | 40 | 40 | 40 | 85 | 29 | 0 | 56 | 0 | 0 | 56
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0770 | Study Archived | SPM 969/RBx 2258: Interaction | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | SINGLE-CENTER, TWO-FOLD-CROSSOVER, RANDOMIZED, DOUBLE-BLIND COCKTAIL PHENOTYPING TRIAL TO INVESTIGATE THE IN VIVO POTENTIAL OF 10MG OF RBX 2258 ADMINISTERED IN STEADY STATE TO INHIBIT CYP1A2, CYP2C9, CYP2C19, CYP2D6, INTESTINAL AND HEPATIC CYP3A4 IN 16 HEALTHY MALE SUBJECTS |  |  |  | 2004-06-21 | 2004-06-21 |  | 2010-08-11: 2004-06-07; 2010-11-23: 2004-07-02; 2012-04-02: 2004-07-20; 2012-06-29: 2004-09-06; 2012-08-16: 2004-11-13; 2012-10-22: 2005-05-18; 2013-06-11: 2005-09-02 | Germany | Germany (Created) |  | 1 | 0 | 0 | 16 | 16 | 16 | 30 | 13 | 0 | 17 | 0 | 1 | 16
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0771 | Protocol Approved (Cancelled) | SPM 969/RBx 2258: Interaction with ketoconazole | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | No | Randomized, non-blind, two-fold crossover study to investigate the influence of a pre-and co-administration of ketoconazole on the safety, tolerability and pharmacokinetics of a single oral dose administration of 2.5mg RBx 2258 in 12 healthy male subjects |  |  |  | 2004-07-16 | 2004-07-16 |  | 2010-08-11: 2004-09-07 | Germany | Germany (Created) |  | 1 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0772 | Created (Cancelled) | SPM 969/RBx 2258: Relative BA current vs. new formulation | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | No | Randomized, non blind, 2-fold crossover trial to investigate the relative bioavailability of a newly developed 2.5mg SR formulation of RBx 2258 after single dose administration in comparison to the current 2.5mg tablets in 12 healthy, male subjects. | [22 empty] | 1 | 0 | 0 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0773 | Created (Cancelled) | SPM 969/RBx 2258: Food effect | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | No | SPM 969/RBx 2258: Food effect | [22 empty] | 1 | 0 | 0 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0806 | Created (Cancelled) | Human ADME trial | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | No | OPEN, NON-RANDOMIZED, NON-CONTROLLED STUDY TO INVESTIGATE THE METABOLISM, EXCRETION PATTERN AND BALANCE OF RBX 2258 AFTER SINGLE DOSE ORAL ADMINISTRATION OF [14C] RBX 2258 IN SIX HEALTHY, MALE SUBJECTS | Lower Urin Tract symps assoc with BPH | Immunology |  | 2004-06-18 | [15 empty] | United Kingdom | United Kingdom (Created) |  | 1 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0827 | Created (Cancelled) | phase 2 long term safety trial | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Thomas D | [6 empty] | No | Long Title to be entered | Lower Urin Tract symps assoc with BPH | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0844 | Created (Cancelled) | Interaction PDE5-Inhibitor | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | No | Long Title to be entered | Lower Urin Tract symps assoc with BPH | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0845 | Created (Cancelled) | Interaction Antihypertensiva | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | No | Long Title to be entered | Lower Urin Tract symps assoc with BPH | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | RBx 2258 | not defined | SP0846 | Created (Cancelled) | Interaction CYP 3A4 Inducer | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | No | Long Title to be entered | Lower Urin Tract symps assoc with BPH | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Recombinant Human Alpha 2b interferon | not defined | SP0526 | Protocol Approved (Cancelled) | The efficacy and safety study for Bioferon in HBV patients. | Phase IV | Single Blind | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | not available (DMCD) | Viral Hepatitis B | Immunology |  | 1999-09-01 | 1999-09-01 |  | 2010-08-11: 2001-01-16 | China | China (Created) |  | 4 | 0 | 0 | 144 | 144 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Recombinant Human Erythropoietin | not defined | SP0524 | Final TFLs released (Stopped) | The efficacy and safety for Hemax in dialysis patients | Phase IV | Single Blind | UCB Pharma Global |  | UCB Pharma Global | Li Z | [6 empty] | No | not available (DMCD) | Renal Anemia | Immunology |  | 2001-08-06 | 1999-09-01 |  | 2010-08-11: 2001-04-15; 2010-11-23: 2001-08-23; 2012-04-02: 2001-12-22; 2012-06-29: 2002-03-15; 2012-10-22: 2002-04-15 | China | China (Created) |  | 4 | 0 | 0 | 144 | 144 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Reviparin Sodium | not defined | SP0753 | Created | Clivarina trial SP Italy |  |  | UCB Pharma Global |  | UCB Pharma Global | Sanguini M | [6 empty] | No | Further knowledge on Clivarina risk/benefit profile in cardioverted patients suffering from atrial fibrillation: short anti coagulation management vs conventional therapy. | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Rystiggo | Central Nervous System | PV0002 | Created (Cancelled) | Phase 2a POC Study of UCB7665 Pts w/ Pemphigus Vulgaris | Phase II |  | GCSO | Neurology | GCSO |  |  | Parexel |  |  |  |  | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2020-05-20 | [18 empty] | 25 | 0 | 0 | 72 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Rystiggo | Central Nervous System | TP0001 | Study Archived | POC study of UCB7665 in idiopathic thrombocytopenic purpura | Phase II | Open | GCSO | Neurology | GCSO | Grasses T | Tillery N | Parexel | PAREXEL | No | Yes | adults | No | A multi-center, open-label, multiple dose study to evaluate the safety, tolerability and efficacy of UCB7665 in subjects with primary immune thrombocytopenia. Phase 2 | Idiopathic Thrombocytopenic Purpura | Immunology |  | 2015-11-17 | 2015-09-09 |  | 2015-11-09 | 2016-02-29 | 2016-03-02 | 2017-02-27 | 2018-11-26 | 2017-06-22 | 2019-02-04 | 2017-07-20 | 2019-03-05 | 2017-08-03 | 2019-03-22 | 2017-11-06 | 2019-06-11 | Australia, Bulgaria, Czech Republic, Georgia, Germany, Italy, Moldavia, Poland, Romania, Spain, United Kingdom | Australia (LPLV), Belgium (1st Site Initiation (Cancelled)), Bulgaria (LPLV), Czech Republic (LPLV), Georgia (LPLV), Germany (LPLV), Italy (LPLV), Lithuania (1st Site Initiation (Cancelled)), Moldavia (LPLV), Poland (LPLV), Romania (LPLV), Spain (LPLV), United Kingdom (LPLV) | Australia, Bulgaria, Czech Republic, Georgia, Germany, Italy, Moldavia, Poland, Romania, Spain, United Kingdom | 15 | 38 | 29 | 90 | 57 | 55 | 127 | 0 | 61 | 66 | 0 | 1 | 65
Yes | Not assigned | Managing Type | 1 | Rystiggo | Central Nervous System | UP0018 | Study Archived | First in Human Study | Phase I | Double Blind | GED | Neurology | GED | Watanabe S | Cain D | Parexel | SPI PXL | No | No | adults | Yes | A SUBJECT-BLIND, INVESTIGATOR-BLIND, RANDOMIZED, PLACEBO-CONTROLLED, FIRST-IN-HUMAN STUDY EVALUATING THE SAFETY, PHARMACOKINETICS, AND PHARMACODYNAMICS OF SINGLE ASCENDING INTRAVENOUS AND SUBCUTANEOUS DOSES OF UCB7665 IN HEALTHY SUBJECTS | Idiopathic thrombocytopenic purpura; Myasthenia gravis | Central Nervous System; Central Nervous System |  | 2014-02-27 | 2014-02-27 |  | 2014-04-29 | 2014-07-03 | 2014-07-28 | 2014-10-01 | 2015-06-18 |  | 2015-09-24 |  | 2015-10-27 |  | 2015-12-21 |  | 2016-04-05 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 36 | 24 | 24 | 184 | 0 | 135 | 49 | 0 | 1 | 48
Yes | Not assigned | Managing Type | 1 | Sabalis Serulatae | not defined | SP0421 | Created | SITA - bei Patienten mit benigner Prostatahyperplasie | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | SITA - bei Patienten mit benigner Prostatahyperplasie | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | SECTRAL | not defined | SP0636 | Final TFLs released | Efficacy and tolerability of a new slow release formulation | Phase IV | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Mastej M | [6 empty] | No | Double blind randomized crossed-over study on efficancy and tolerability of a new slow release formulation of acebutolol in primary hypertension. | Hypertension | Immunology |  | 2000-09-04 | 2000-09-04 |  | 2010-08-11: 2000-02-08; 2010-11-23: 2001-02-22; 2012-04-02: 2001-05-07; 2012-06-29: 2001-07-10; 2012-10-22: 2002-01-31 | Poland | Poland (Created) |  | 2 | 0 | 0 | 50 | 50 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Seletalisib | Immunology | APD001 | Study Archived | OPEN-LABEL EXPLORATORY STUDY IN SUBJECTS WITH ACTIVATED PHOS | Phase I | Open | GED | Immunology | GED | Akintola J, Soranson J | Grose-Hodge R | Parexel | SPI PXL | No | No | paediatrics | No | An open-label exploratory study of UCB5857 in subjects with activated phosphoinositide 3 kinase (PI3K) delta syndrome (APDS). | Clinical Pharmacology; Activated PI3K Delta Syndrome | Immunology; Immunology | APD001 is a parent study of APD003 | 2015-06-03 | 2015-06-03 |  | 2015-10-19 | 2016-02-02 | 2016-05-23 | 2016-04-26 | 2017-07-10 | 2016-08-20 | 2018-01-23 | 2016-09-17 | 2018-02-20 | 2016-10-03 | 2018-03-14 | 2016-12-28 | 2018-05-16 | France, Germany, Italy, Spain | France (LPLV), Germany (LPLV), Italy (LPLV), Spain (LPLV) | France, Germany, Italy, Spain | 4 | 4 | 4 | 6 | 6 | 6 | 8 | 0 | 1 | 7 | 0 | 2 | 5
Yes | Not assigned | Managing Type | 1 | Seletalisib | Immunology | APD003 | Study Archived | Open label follow up study for parent trial APD001 Phase 1b | Phase III | Open | GCSO | Immunology | GCSO | Akintola J | Grose-Hodge R | Parexel | PAREXEL | No | No | paediatrics | No | AN OPEN-LABEL, EXPLORATORY, MULTICENTER, EXTENSION STUDY TO EVALUATE THE LONG-TERM SAFETY, TOLERABILITY, PHARMACOKINETICS AND EFFICACY OF UCB5857 IN SUBJECTS WITH ACTIVATED PHOSPHOINOSITIDE 3 KINASE (PI3K) DELTA SYNDROME (APDS) | Activated PI3K Delta Syndrome | Immunology | APD003 is a follow up of APD001 and is a parent study of APD002 | 2015-11-25 | 2015-11-12 |  | 2016-01-06 | 2016-05-17 | 2017-01-11 | 2016-11-01 | 2017-10-26 | 2018-12-20 | 2018-12-13 | 2019-01-15 | 2019-01-23 | 2019-02-20 | 2019-02-08 | 2019-04-03 | 2019-04-03 | France, Germany, Italy, Spain | France (LPLV), Germany (LPLV), Italy (LPLV), Spain (LPLV) | France, Germany, Italy, Spain | 5 | 4 | 4 | 6 | 6 | 6 | 5 | 0 | 1 | 4 | 0 | 1 | 3
Yes | Not assigned | Managing Type | 1 | Seletalisib | Immunology | PS0001 | Study Archived | Phase1 Placebo controlled ascending single & multiple dose | Phase I | Double Blind | GED |  | GED | Garratt H | Mccabe S | Parexel | Appledown |  | No | adults | No | A RANDOMISED, DOUBLE-BLIND, PLACEBO-CONTROLLED, SINGLE AND MULTIPLE ASCENDING DOSE STUDY EVALUATING THE SAFETY/TOLERABILITY, PHARMACOKINETIC AND PHARMACODYNAMIC EFFECTS OF UCB5857 IN HEALTHY AND MILD-TO-MODERATE PSORIATIC SUBJECTS | Osteoarthritis | Immunology |  | 2013-03-26 | 2013-03-27 |  | 2013-06-13 | 2013-07-23 | 2013-08-05 | 2014-01-09 | 2014-01-23 |  | 2014-02-25 |  | 2014-05-12 |  | 2014-07-07 |  | 2014-09-03 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 57 | 57 | 57 | 253 | 0 | 191 | 62 | 0 | 6 | 56
Yes | Not assigned | Managing Type | 1 | Seletalisib | Immunology | RA0102 | Created (Cancelled) | PK in adults with RA and inadequate response to MTX | Phase II |  | Clinical Development USA | Immunology | Clinical Development Europe | Bretschneider M | Tillery N | PRA | PRA |  |  |  | No |  | Indication for Rheumato GI | Immunology |  | 2016-12-29 | [18 empty] | 40 | 0 | 0 | 120 | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Seletalisib | Immunology | SS0004 | Study Archived | POC in primary sjogrens syndrome | Phase II | Double Blind | GED | Immunology | GED | Akintola J | Grose-Hodge R | PRA | SPI PRA | No | Yes | adults | No | A randomised, double-blind, placebo-controlled, prrof of concept study to evaluate the efficacy and safety of UCB5857 over 12 weeks in subjects with Primary Sjogren's Syndrome. | Sjogren's Syndrome | Immunology |  | 2014-07-07 | 2014-07-07 |  | 2015-02-18 | 2015-06-15 | 2015-10-28 | 2016-06-20 | 2017-08-17 | 2016-10-22 | 2017-12-05 | 2016-11-11 | 2018-07-10 | 2016-12-23 | 2018-08-15 | 2017-05-03 | 2018-09-12 | France, Greece, Italy, Spain, Sweden, United Kingdom | France (LPLV), Greece (1st Site Initiation), Italy (LPLV), Spain (LPLV), Sweden (LPLV), United Kingdom (LPLV) | France, Greece, Italy, Spain, Sweden, United Kingdom | 22 | 22 | 15 | 107 | 64 | 64 | 51 | 0 | 24 | 27 | 0 | 7 | 20
Yes | Not assigned | Managing Type | 1 | Seletalisib | Immunology | UP0021 | Study Archived | Combined SAD/MAD ascending dose UCB5857 in Healthy Volunteer | Phase I | Single Blind | GED |  | R & D | Bosteels M | Mccabe S | Parexel | SPI PXL | No | Yes | adults | Yes | A RANDOMIZED, INVESTIGATOR- AND SUBJECT-BLIND, PLACEBO-CONTROLLED, COMBINED SINGLE AND MULTIPLE ASCENDING DOSE STUDY TO EVALUATE THE SAFETY, TOLERABILITY, PHARMACOKINETIC AND PHARMACODYNAMIC PROFILES OF UCB5857 IN HEALTHY SUBJECTS | Indication for Rheumato GI | Immunology |  |  | 2014-05-16 |  | 2014-06-17 | 2014-08-04 | 2014-08-04 | 2014-09-10 | 2015-01-20 |  | 2015-02-28 |  | 2015-04-20 |  | 2015-04-29 |  | 2015-07-30 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 72 | 36 | 36 | 156 | 0 | 96 | 60 | 0 | 7 | 53
Yes | Not assigned | Managing Type | 1 | Seletalisib | Immunology | UP0022 | Study Archived | Open lable SD study to eval. comparative BA of 2 formulation | Phase I | Open | GED |  | GED | Garratt H | Mccabe S | PRA | SPI PRA | No | Yes | adults | Yes | An Open-Label, Single Dose Study to assess the relative bioavailability of 2 new formulations of UCB5857 versus the reference formulation, and to evaluate the mass balance recovery and the absolute bioavailability of UCB5857 using intravenous and oral microtracers in healthy subjects | Nonspecific | Immunology |  |  |  |  | 2015-01-19 | 2015-03-04 | 2015-03-04 | 2015-03-13 | 2015-03-16 |  | 2015-04-17 |  | 2015-11-06 |  | 2015-12-02 |  | 2016-01-26 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 16 | 16 | 12 | 24 | 0 | 12 | 12 | 0 | 0 | 12
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01126 | CSR Approved | FIM 44212 | Phase I | Double Blind | Clinical Development USA | Clinical Pharmaco | R & D | Salas V | [6 empty] | Yes | Randomized, Monocenter, Double-Blind, Placebo-Controlled, 3 Alternating-Panel, Single Rising Oral Dose (up to 800 mg), Safety, Tolerability, Pharmacokinetic and Pharmacodynamic Study of ucb 44212 in 27 Healthy Male Volunteers (Part A), and Open-Label, Food Interaction Study in 8 Healthy Male Volunteers (Part B). | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2004-01-19 | 2004-01-27 | 2004-04-15 | 2004-03-18 | 2004-06-23 | 2004-06-23 | 2004-08-10 | 2004-06-29 | 2004-10-05 | 2004-09-08 |  | 2004-12-21 | 2005-03-11 | 2005-04-18 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 40 | 35 | 35 | 65 | 0 | 37 | 28 | 0 | 3 | 25
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01126B | CSR Approved | FIM 44212 - food interaction | Phase I | Open | Clinical Development USA | Clinical Pharmaco | R & D | Salas V | [6 empty] | Yes | Randomized, Monocenter, Double-Blind, Placebo-Controlled, 3 Alternating-Panel, Single Rising Oral Dose (up to 800 mg), Safety, Tolerability, Pharmacokinetic and Pharmacodynamic Study of ucb 44212 in 27 Healthy Male Volunteers (Part A), and Open-Label, Food Interaction Study in 8 Healthy Male Volunteers (Part B). | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 2004-01-27 |  | 2004-06-21 |  | 2004-07-09 |  | 2004-07-30 |  | 2004-10-12 |  | 2005-05-02 | 2005-04-07 | 2005-07-18 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 12 | 8 | 8 | 38 | 0 | 30 | 8 | 0 | 1 | 7
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01157 | CSR Approved | ucb 4412 oral rising dose study | Phase I | Double Blind | Clinical Development USA | Clinical Pharmaco | R & D | Salas V | [6 empty] | Yes | Randomized, Single Center, Double-Blind, Placebo Controlled, Sequential Group, 2 Weeks Repeated Oral Rising Dose, Safety, Tolerability, Pharmacokinetic and Pharmacodynamic Study of ucb 44212 Administered as 20 mg, 60 mg and 200 mg Twice Daily in 36 Healthy Male Volunteers. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2004-08-30 | 2004-08-30 | 2004-09-23 | 2004-09-20 | 2004-11-16 | 2004-11-16 | 2004-12-24 | 2004-12-24 | 2005-02-21 | 2005-02-21 | 2005-04-11 | 2005-07-25 | 2005-09-01 | 2006-04-25 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 90 | 36 | 36 | 79 | 0 | 43 | 36 | 0 | 3 | 33
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01179 | Study Archived | 44212 C14 oral | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A | [6 empty] | Yes | Open label, monocenter, excretion balance, pharmacokinetics and metabolism study of 14C-labeled ucb 44212 after 100 mg single oral dose administration in healthy male subjects. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 2010-08-11: 2004-11-15; 2010-11-23: 2005-01-09; 2012-04-02: 2005-01-09; 2012-06-29: 2005-01-24; 2012-08-16: 2005-02-24; 2012-10-22: 2005-05-10; 2013-06-11: 2005-09-13 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 6 | 6 | 6 | 8 | 0 | 2 | 6 | 0 | 0 | 6
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01180 | Study Archived | UCB 44212 oral contraceptive interaction | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | De Smedt F | [6 empty] | Yes | Randomized, monocenter, double-blind, placebo-controlled, two-way crossover, multiple oral dose interaction study between seletracetam, 20 mg twice daily and oral contraceptive (ethinylestradiol 30 µg, levonorgestrel 150 µg) in 24 healthy female volunteers. | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2004-10-13 | 2005-02-04 | 2005-02-04 | 2005-03-21 | 2005-03-23 | 2005-05-02 | 2005-05-09 | 2005-09-30 | 2005-09-21 | 2005-11-09 | 2005-11-25 | 2006-01-06 | 2006-03-29 | 2006-03-31 | 2006-10-20 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 48 | 24 | 24 | 42 | 0 | 18 | 24 | 0 | 3 | 21
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01184 | Study Archived | UCB44212 PPR | Phase I | Single Blind | Clinical Development Europe | Clinical Pharmaco | R & D | De Smedt F, Hollis A, Mccabe S |  |  | FR : CRO, US : UCB |  |  |  | No | A multicenter, single-blind, exploratory study on the pharmacodynamic effect of ucb 44212 in photosensitive epileptic subjects; evaluation of the photoparoxysmal responses (PPRs) after single oral dose (0.5 to 40 mg) administration of ucb 44212 capsules. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2004-11-01 | 2004-10-28 | 2005-01-10 | 2005-01-28 | 2005-07-25 | 2005-07-06 | 2005-08-20 | 2005-08-18 | 2005-10-08 | 2006-02-15 | 2005-11-30 | 2006-03-31 | 2006-05-15 | 2006-08-31 | France, United States of America | France (LPLV), United States of America (LPLV) | France, United States of America | 6 | 6 | 6 | 40 | 30 | 30 | 40 | 0 | 3 | 37 | 0 | 0 | 37
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01189 | Study Archived | Intellisite 44212 | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S, Perreaux A |  |  | PP/UCB |  |  |  | Yes | Pharmacoscintigraphic investigation of the regional drug absorption of ucb 44212 (50 mg) delivered using the EnterionTM capsule in 3 different sites of the GI tract in comparison with the 50 mg immediate release oral capsule: open-label, randomized, four-way cross-over, single dose study, in 9 healthy adult male volunteers. | Indication for Neuro Psychiatry | Central Nervous System |  |  |  | 2004-09-06 | 2004-09-07 | 2004-10-16 | 2004-10-22 | 2004-11-01 | 2004-11-01 | 2005-12-06 | 2004-12-06 | 2005-02-15 | 2005-02-18 | 2005-04-11 | 2005-07-26 | 2005-06-07 | 2006-02-21 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 18 | 9 | 6 | 24 | 0 | 15 | 9 | 0 | 3 | 6
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01191 | Study Archived | UCB 44212 Dose Escalation | Phase II | Open | Clinical Development USA | CNS | R & D | Climo K |  |  | Contract CRAs |  |  |  | No | an open-label, exploratory,multi-center, dose escalation study, examining the efficacy, safety, and tolerability of UCB44212 used at doese of 10, 20, 40, and 80 mg b.i.d. (total daily dose of 20 to 160 mg) in adult subjects (18-65 yrs) with refractory epilepsy suffering from partial onset seizures (whether or not secondarily generalized) and treated with 1, 2, or 3 approved antiepileptic drugs. | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-01-07 | 2004-12-20 | 2005-01-07 | 2004-12-20 | 2005-04-29 | 2005-05-19 | 2006-01-16 | 2006-01-06 | 2006-05-15 | 2007-01-29 |  | 2006-05-25 | 2006-08-18 | 2006-06-21 | 2006-10-06 | 2007-04-27 | United States of America | United States of America (LPLV) | United States of America | 8 | 7 | 7 | 40 | 30 | 30 | 36 | 0 | 5 | 31 | 0 | 4 | 27
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01192 | CSR Approved | PD Dose Escalation | Phase II | Open | Clinical Development USA | CNS | R & D |  |  |  | To be done by the CRAs from PPD |  |  |  | No | An open label, exploratory, dose-escalation, multicenter study examining the safety, tolerability and efficacy of ucb 44212 (seletracetam) used at doses of 10, 20, 40, and 80 mg b.i.d. (total daily doses of 20 - 160 mg) administration (oral capsules) in adult subjects (18 - 65 years) with refractory epilepsy suffering from partial onset seizures who are currently receiving levetiracetam (LEV) but still experiencing seizures | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-04-01 | 2005-04-01 | 2005-05-27 | 2005-06-03 | 2005-08-19 | 2005-08-31 | 2006-01-06 | 2006-01-16 | 2006-05-19 | 2007-01-31 | 2006-06-27 |  | 2006-07-18 |  | 2006-11-17 | 2007-11-15 | Canada, United States of America | Canada (LPLV), United States of America (LPLV) | Canada, United States of America | 23 | 25 | 22 | 80 | 60 | 60 | 72 | 0 | 13 | 59 | 0 | 4 | 55 |  |  |  | 2006-07-16
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01196 | Created (Cancelled) | Safety SR vs IR | Phase II |  | UCB Pharma Global | Neurology | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-06-15 | [18 empty] | 15 | 0 | 0 | 90 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01197 | Protoc. Summary Approved (Cancelled) | LTFU | Phase II | Open | Clinical Development USA | CNS | R & D | [7 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-08-05 | 2005-08-05 | 2005-09-09 | 2010-11-03: 2006-01-16; 2011-09-27: 2009-12-25; 2012-06-29: 2009-12-25; 2012-08-13: 2010-03-31; 2012-10-09: 2010-09-05; 2013-03-26: 2010-10-15 |  |  |  | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01212 | Protocol Approved (Cancelled) | Open Label Safety study to include PGS and POS patients | Phase II | Open | Clinical Development USA | CNS | R & D | Delobelle K, Sykes D | [6 empty] | No | Open label, multicenter study of the safety and efficacy of oral treatment with immediate release seletracetam (ucb 44212) at individualized doses up to 160mg/day in patients with refractory epilepsy. | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-08-05 | 2005-08-05 | 2005-09-30 | 2010-08-11: 2005-10-11; 2010-11-03: 2006-01-16; 2011-09-27: 2006-12-01; 2012-06-29: 2007-07-02; 2012-08-13: 2007-09-10; 2012-10-09: 2007-11-13; 2013-03-26: 2007-12-21 | Canada, United States of America | Canada (Created), United States of America (Created) |  | 0 | 0 | 0 | 556 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01213 | CSR Approved | 44212-Elderly PK | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Mccabe S | [6 empty] | Yes | Monocenter, open label, pharmacokinetic, safety and tolerability study of a single dose followed by a 7 day 20 mg b.i.d. dosing regimen of seletracetam administered orally in healthy elderly volunteers | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-07-04 | 2005-07-01 | 2005-09-15 | 2005-09-09 | 2005-11-15 | 2005-11-15 | 2005-12-19 | 2005-12-09 | 2006-02-28 | 2005-12-22 | 2006-04-07 | 2006-04-20 | 2006-05-31 | 2006-08-07 | 2006-08-01 | 2007-01-19 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 24 | 24 | 24 | 47 | 0 | 23 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01214 | CSR Approved | Renal Impairment | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A |  |  | Monitoring: SGS |  |  |  | No | Open-label, muticenter, parallel group, not randomized, pharmacokinetic study of single oral administration of seletracetam in subjects with normal renal function and with impaired renal function | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-07-01 | 2005-07-01 | 2005-09-29 | 2005-09-29 | 2006-05-08 | 2006-05-05 | 2006-07-10 | 2006-09-11 | 2006-07-31 | 2006-09-18 | 2006-08-28 | 2006-10-27 | 2006-11-27 | 2007-01-24 | 2007-01-22 | 2007-05-11 | Poland | Poland (LPLV) | Poland | 1 | 1 | 1 | 48 | 24 | 24 | 31 | 0 | 7 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01215 | CSR Approved | PK Pilot Study SR vs IR | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | De Smedt F | [6 empty] | Yes | A single dose open-label pilot study to compare the pharmacokinetics of four prolonged release test formulations (seletracetam 20 mg pellets in capsules oral dose) using the immediate release formulation (seletracetam 10 mg pellets in capsules oral dose) as reference, in 18 healthy male volunteers and to assess the influence of food on one of the prolonged release formulations. | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-07-15 | 2005-07-01 | 2005-09-01 | 2005-08-04 | 2005-10-24 | 2005-11-07 | 2005-11-04 | 2005-11-10 | 2005-12-16 | 2005-12-21 | 2006-02-01 | 2006-02-21 | 2006-03-15 | 2006-03-30 | 2006-04-20 | 2006-06-27 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 18 | 12 | 12 | 32 | 0 | 14 | 18 | 0 | 0 | 18
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01225 | CSR Approved | End Stage renal disease / hemodialysis | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A |  |  | Monitoring: SGS |  |  |  | No | Open-label, monocenter, single dose pharmacokinetic study of seletracetam, orally administered in subjects with end stage renal disease undergoing hemodialysis | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2005-07-01 | 2005-09-16 | 2005-09-13 | 2005-11-10 | 2005-11-10 | 2005-11-17 | 2005-11-25 | 2005-12-05 | 2005-12-05 | 2006-01-30 | 2006-02-08 | 2006-06-21 | 2006-07-12 | 2006-08-01 | 2006-09-25 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 12 | 6 | 6 | 7 | 0 | 1 | 6 | 0 | 0 | 6
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01234 | CSR Approved | QT/Qtc Study | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A |  |  | Monitoring: Covance |  |  |  | Yes | Four-way crossover, randomized, placebo- and moxifloxacin-controlled study of the effect of seletracetam on cardiac repolarization in 52 healthy male and female subjects. | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-01-06 | 2006-01-06 | 2006-02-23 | 2006-02-24 | 2006-04-20 | 2006-04-21 | 2006-05-02 | 2006-07-25 | 2006-06-19 | 2006-08-21 | 2006-08-25 | 2006-12-14 | 2006-12-01 | 2007-03-06 | 2007-01-26 | 2007-05-11 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 120 | 52 | 52 | 117 | 0 | 65 | 52 | 0 | 1 | 51
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01244 | Created (Cancelled) | Pop PK Seletracetam | Meta-analysis |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01246 | CSR Approved | BE study | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Achour M, Mccabe S |  |  | Fabienne Eggermont outsourced by ATC |  |  |  | Yes | Randomized four-way crossover, open label bioequivalence study between three sustained release (SR) capsules of seletracetam with different drug loads, in a single oral dose and the immediate release (IR) capsule of seletracetam as a reference, administered twice a day in 20 healthy fasting male and female volunteers | [6 empty] | 2006-08-07 | 2006-11-14 | 2006-11-14 | 2006-11-22 | 2006-11-22 |  | 2006-12-23 |  | 2007-02-08 |  | 2007-07-10 |  | 2007-08-06 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 20 | 20 | 20 | 35 | 0 | 15 | 20 | 0 | 1 | 19
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01251 | Created (Cancelled) | META - Seletracetam | Meta-analysis |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01272 | Protocol Approved (Cancelled) | Phase 2b/3 | Phase II | Double Blind | Clinical Development USA | CNS | R & D | [7 empty] | No | A phase IIb/III, double-blind, parallel-group, placebo-controlled, randomized study: evaluation of the efficacy and safety of seletracetam as adjunctive treatment in subjects (_> 16 to 70 years old) with refractory partial onset seizures. | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-12-12 | 2006-11-16 |  | 2010-08-11: 2006-11-16 |  |  |  | 50 | 0 | 0 | 625 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Seletracetam | Central Nervous System | N01273 | Created (Cancelled) | Pivotal 2 | Phase III |  | Clinical Development Europe | CNS | R & D | Picciolato M | [6 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System | [20 empty] | 50 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | SOMATOSTATIN | Immunology | 9135 | Study Archived | Oesophageal variceal bleeding and in the prevention of early | Phase II |  | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | [7 empty] | No | Somatostatin-UCB in combination with sclerotherapy in the emergency control of oesophageal variceal bleeding and in the prevention of early rebleeding. (A randomized, double-blind, placebo-controlled, multicenter trial). | [6 empty] | 2010-08-11: 1992-04-17; 2010-11-23: 1992-08-23; 2012-06-29: 1996-03-22; 2012-08-16: 2000-05-24; 2013-06-11: 2001-02-08 | Belgium, Greece, Netherlands | Belgium (LPLV), Greece (LPLV), Netherlands (LPLV) | Belgium, Greece, Netherlands | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | SOMATOSTATIN | Immunology | 9330 | CSR Approved | Somato Tchéquie | Phase III | Double Blind | Global Medical Affairs Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Daubresse M | [6 empty] | No | Somatostatin in the control of early rebleeding after sclerotherapy for acute bleeding from oesophageal varices : a multicentre, double blind, randomised, placebo-controlled study. | Indication for Internal Medicine | Immunology |  |  |  |  | 2010-08-11: 1994-02-14; 2010-11-23: 1994-12-15; 2012-06-29: 1996-11-21; 2012-08-16: 2001-04-02; 2012-10-22: 2001-05-20; 2013-06-11: 2006-08-22 | Czech Republic | Czech Republic (LPLV) | Czech Republic | 6 | 0 | 1 | 200 | 200 | 0 | 234 | 0 | 34 | 200 | 0 | 36 | 164
Yes | Not assigned | Managing Type | 1 | SOMATOSTATIN | Immunology | 9439 | CSR Approved | Exocrine pancreatic secreting reduction - GOUILLAT | Phase II | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | Affiliates - France | Daubresse M | [6 empty] | No | Etude clinique pilote multicentrique, en double aveugle contrôlée par un placbo, de l'efficacité et de la tolérence de la somatostatine sur la réduction des sécrétions pancréatiques exocrines | Indication for Internal Medicine | Immunology |  |  |  |  | 2010-08-11: 1995-07-18; 2010-11-23: 1995-10-31; 2012-06-29: 1996-12-10; 2012-08-16: 2001-08-01; 2013-06-11: 2008-08-28 | France | France (LPLV) | France | 8 | 0 | 1 | 48 | 48 | 0 | 75 | 0 | 0 | 75 | 0 | 27 | 48
Yes | Not assigned | Managing Type | 1 | SOMATOSTATIN | Immunology | 9526 | CSR Approved | Varices oesophagiennes - ambulances | Phase II | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | Affiliate - Hungary | Daubresse M | [6 empty] | No | Early administration of Somatostatine-UCB, in bolus injection followed by infusion, as add-on therapy to routine standard treatment, in the emergency treatment of oesophageal variceal bleeding : a multicenter, DB, rando, plc-controle, exploratory study | Indication for Internal Medicine | Immunology |  |  |  |  | 2010-08-11: 1996-07-18; 2010-11-23: 1997-03-24; 2012-06-29: 1997-07-22; 2013-06-11: 2008-08-26 | Hungary | Hungary (LPLV) | Hungary | 1 | 0 | 1 | 100 | 100 | 0 | 0 | 0 | 0 | 6 | 0 | 2 | 4
Yes | Not assigned | Managing Type | 1 | SOMATOSTATIN | Immunology | 9823 | CSR Approved | PUB | Phase II | Double Blind | Clinical Development Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Martin L |  |  | Parexell |  |  |  | No | A multicenter, randomised, double-blind, placebo controlled trial to study the efficacy and the safety of the early administration of Somatostatin (UCB) 12 mg/24h iv infusion and 2 iv boluses of 250 µg during 72 hours in the treatment of patients with acute severe upper gastrointestinal bleeding with suspicion of Peptic Ulcer Bleeding [the PUB study] | Indication for Internal Medicine | Immunology |  |  |  |  | 1999-01-27 | 1999-06-15 | 2000-09-08 | 2003-11-30 | 2005-09-26 | 2001-06-15 | 2005-10-21 | 2004-06-30 | 2005-12-16 |  | 2006-02-17 | 2001-12-15 | 2008-06-02 | Belgium, France, Greece, Hungary, Poland, Spain | Austria (1st Site Initiation (Cancelled)), Belgium (LPLV), France (LPLV), Greece (LPLV), Hungary (LPLV), Poland (LPLV), Spain (LPLV), Switzerland (1st Site Initiation (Cancelled)) | Belgium, France, Greece, Hungary, Poland, Spain | 30 | 36 | 31 | 500 | 500 | 0 | 0 | 0 | 0 | 444 | 6 | 29 | 355
Yes | Not assigned | Managing Type | 1 | SPM14221 | not defined | SP0865 | Protoc. Summary Approved (Cancelled) | Pilot dose escalation trial | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | No | Single site randomized double-blind placebo-controlled dose escalation trial to investigate the safety and tolerability and pharmacokinetic of SPM14221 after single dose administration in an ascending order in young healthy male subjects | Osteoarthritis | Immunology |  | 2005-05-01 | 2005-05-11 | [17 empty] | 1 | 0 | 0 | 72 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | SPM924 | not defined | SP0576 | Protocol Approved (Cancelled) | Phase IIa trial of SPM 924 in prostate cancer | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Puttick R | [6 empty] | No | A Phase IIa, randomised, double-blind, placebo-controlled, parallel group trial of CEP-701/SPM 924 as neoadjuvant treatment in subjects with localised prostatic cancer undergoing radical prostatectomy. | Prostatic cancer | Oncology |  | 2000-03-31 | 2000-03-31 |  | 2010-08-11: 2000-06-14 | Austria, Belgium, Germany, Ireland, Netherlands, United Kingdom | Austria (Created), Belgium (Created), Germany (Created), Ireland (Created), Netherlands (Created), United Kingdom (Created) |  | 14 | 0 | 0 | 80 | 66 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | SPM924 | not defined | SP0635 | Created (Cancelled) | Pilot trial of SPM924 in hormone-independent prostate cancer | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Puttick R | [6 empty] | No | Pilot trial of SPM924 in hormone-independent prostate cancer | Prostatic cancer | Oncology | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | SPW-5186 | not defined | SP0344 | Created | Biodesign/Innovex - Pharmacodynamic - nitrate - capsules - h |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Pharmacodynamic study with three different doses of spw 5186, a new organic nitrate, given as capsules to healthy male volunteers | [22 empty] | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | SPW-5186 | not defined | SP0351 | Created | Innovex/Biodesign - nitrate - SPW 5186 - 60 and 120 mg - cap |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Multiple dose study with SPW 5186, a new organic nitrate, given 60 and 120 mg T.I.D. as capsules to healthy male volunteers | [22 empty] | 0 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | SPW-5186 | not defined | SP0356 | Created | Drug Safety Trial Data. Study drug: SPW-5186 (PS) |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Drug Safety Trial Data. Study drug: SPW-5186 (PS) | [22 empty] | 0 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | SPW-5186 | not defined | SP0372 | Created | SPW 5186 - IS5MN - double-blind - placebo-controlled, cross |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Double-blind, randomized, placebo-controlled cross-over study for the evaluation of the hemodynamic effects of single oral doses of the new organic nitrate SPW-5186 150 mg in cimparison with Isosorbide-5-mononitrate 20 mg in healthy volunteers | [22 empty] | 0 | 0 | 0 | 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | SPW-5186 | not defined | SP0377 | Created | SPW-5186 (Listings) (PS) in patients with coronary artery di |  |  | UCB Pharma Global |  | UCB Pharma Global | Stimpel M | [6 empty] | No | Controlled dose finding study with SP/W 5186 versus placebo in patients with coronary artery disease (CAD). Assessment of antiischemic and antiplatelet properties | Coronary Heart Disease | Immunology | [20 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | SPW-5186 | not defined | SP0385 | Created | SPW5186 - Capsules - healthy volunteers |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | single dose tolerance study with ascendingn doses of SPW 5186 a new organic nitrate, given as capsules to healthy male volunteers | [22 empty] | 0 | 0 | 0 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | SPW-5186 | not defined | SP0401 | Created | Drug Safety Trial Data. Study drug: SPW-5186 (Listings) (PS) |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Drug Safety Trial Data. Study drug: SPW-5186 (Listings) (PS) | [22 empty] | 0 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | SPW-5186 | not defined | SP0419 | Created | Drug Safety Trial Data. Study drug: SPW5186 |  |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | Drug Safety Trial Data. Study drug: SPW5186 | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Staccato Alprazolam | Central Nervous System | EP1062 | Created (Cancelled) | Bad data record, archived |  |  | UCB Pharma Global |  | UCB Pharma Global | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | THEO24 | not defined | A00274 | Created (Cancelled) | THEO 24 | Phase I |  | Clinical Development USA | Clinical Pharmaco | R & D | Meeus M | [6 empty] | No |  |  |  |  | 2007-10-15 |  | 2007-09-11 | 2010-11-03: 2007-11-05; 2011-09-27: 2007-11-04; 2012-06-29: 2007-12-23; 2012-08-13: 2008-02-01; 2012-10-09: 2008-04-04; 2013-03-26: 2008-05-23 |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0560 | Final TFLs released | SPM 907/Fesoterodine: healthy Caucasian volunteers | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | First dose in man IR study 001 |  |  |  | 2000-04-01 | 2000-04-01 |  | 2010-08-11: 2000-06-16; 2010-11-23: 2000-07-18; 2012-04-02: 2000-09-06; 2012-06-29: 2000-10-13; 2012-10-22: 2001-02-16 | Germany | Germany (Created) |  | 1 | 0 | 0 | 65 | 65 | 64 | 0 | 0 | 0 | 64 | 0 | 0 | 64
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0561 | Final TFLs released | SPM 907/Fesoterodine:in healthy Caucasian volunteers | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | md/food effect IR study 002 |  |  |  | 2000-05-30 | 2000-05-30 |  | 2010-08-11: 2000-08-11; 2010-11-23: 2000-09-07; 2012-04-02: 2000-10-01; 2012-06-29: 2000-10-23; 2012-10-22: 2001-01-11 | France | France (Created) |  | 1 | 0 | 0 | 44 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0562 | Final TFLs released | SPM 907/Fesoterodine: Single dose PK of two SR formulations | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | single dose PK of two SR formulation |  |  |  | 2000-08-01 | 2000-08-01 |  | 2010-08-11: 2000-09-18; 2010-11-23: 2000-10-18; 2012-04-02: 2000-10-18; 2012-06-29: 2000-11-30; 2012-10-22: 2000-12-12 | Germany | Germany (Created) |  | 1 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 12
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0563 | Protoc. Summary Approved (Cancelled) | SPM 907/Fesoterodine: PK of final SR formulaton sd | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | PK of final SR formulation sd study |  |  |  | 2001-03-01 | 2001-03-01 | [17 empty] | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0564 | Final TFLs released | SPM 907/Fesoterodine: Fesoterodine SR 8 mg interaction study | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Sachse R | [6 empty] | No | Randomized, non-blind, two-fold crossover trial to investigate the influence of a pre- and co-administration of ketoconazole on the safety, tolerability and pharmacokinetics of a single oral dose administration of 8 mg fesoterodine in 18 healthy male subjects |  |  |  | 2001-11-27 | 2001-11-27 |  | 2010-08-11: 2001-11-21; 2010-11-23: 2002-01-15; 2012-04-02: 2002-03-04; 2012-06-29: 2002-04-03; 2012-10-22: 2002-08-20 | Germany | Germany (Created) |  | 1 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 18 | 0 | 0 | 18
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0565 | Final TFLs released | SPM 907/Fesoterodine: in healthy volunteers with different s | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Auer S | [6 empty] | No | food effect final study 006 |  |  |  | 2000-12-18 | 2000-12-18 |  | 2010-08-11: 2001-01-19; 2010-11-23: 2001-03-20; 2012-04-02: 2001-04-13; 2012-06-29: 2001-05-19; 2012-10-22: 2001-05-29 | Germany | Germany (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0566 | Final TFLs released | SPM 907/Fesoterodine: MTD final SR (4-40 mg) Fesoterodine in | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Auer S | [6 empty] | No | MTD final SR study 007 |  |  |  | 2000-12-19 | 2000-12-19 |  | 2010-08-11: 2001-02-02; 2010-11-23: 2001-03-11; 2012-04-02: 2001-04-08; 2012-06-29: 2001-04-13; 2012-10-22: 2001-05-28 | Germany | Germany (Created) |  | 1 | 0 | 0 | 54 | 54 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0567 | Study Archived | SPM 907/Fesoterodine: Absolute BA | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | Sequential, randomized, non-blinded trial to investigate the absolute bioavailability of fesoterodine after oral administration of fesoterodine and i.v. administration of fesoterodine and SPM 7605 to healthy male subjects |  |  |  | 2003-01-23 | 2003-01-23 |  | 2010-08-11: 2003-04-17; 2010-11-23: 2003-05-22; 2012-04-02: 2003-10-20; 2012-06-29: 2003-12-08; 2012-08-16: 2004-05-26; 2012-10-22: 2005-03-11 | Germany | Germany (Created) |  | 1 | 0 | 0 | 16 | 16 | 16 | 38 | 6 | 0 | 32 | 0 | 6 | 26
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0568 | Study Archived | SPM 907/Fesoterodine: Fesoterodine - renal impairment | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | Investigation of pharmacokinetics, safety and tolerability of 4 mg fesoterodine in male and female patients with renal impairment and in male and female healthy subjects following single-dose administration |  |  |  | 2002-06-28 | 2002-07-10 |  | 2010-08-11: 2002-09-11; 2010-11-23: 2003-06-03; 2012-04-02: 2003-12-01; 2012-06-29: 2003-12-16; 2012-08-16: 2004-05-13; 2012-10-22: 2005-04-01 | Germany | Germany (Created) |  | 2 | 0 | 0 | 32 | 32 | 32 | 33 | 5 | 0 | 32 | 0 | 0 | 32
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0569 | Study Archived | SPM 907/Fesoterodine: PK of 8 mg fesoterodine SR in hepatic | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | Yes | Open, group-comparison, single dose trial to evaluate the influence of liver impairment on the pharmacokinetics, safety and tolerability of 8 mg fesoterodine sustained release oral administration in healthy and hepatic impaired male Caucasian subjects |  |  |  | 2002-03-14 | 2002-03-14 |  | 2010-08-11: 2002-05-31; 2010-11-23: 2002-10-16; 2012-04-02: 2003-02-25; 2012-06-29: 2003-03-04; 2012-08-16: 2003-07-11; 2012-10-22: 2005-01-11 | Bulgaria | Bulgaria (Created) |  | 2 | 0 | 0 | 16 | 16 | 16 | 0 | 0 | 0 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0570 | Final TFLs released | SPM 907/Fesoterodine: Pharmacokinetics | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Auer S | [6 empty] | No | elderly subjects study 011 |  |  |  | 2001-03-07 | 2001-03-07 |  | 2010-08-11: 2001-05-15; 2010-11-23: 2001-06-20; 2012-04-02: 2001-08-06; 2012-06-29: 2001-08-13; 2012-10-22: 2001-08-31 | Germany | Germany (Created) |  | 1 | 0 | 0 | 48 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0571 | Protoc. Summary Approved (Cancelled) | SPM 907/Fesoterodine: Bioequivalence of Fesoterodine in heal | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Auer S | [6 empty] | No | dose proportionality study 012 |  |  |  | 2002-03-01 | 2002-03-01 | [14 empty] | Germany | Germany (Created) |  | 1 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0577 | Final TFLs released | SPM 8272 in subjects with confirmed detrusor instability | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Wuerth G | [6 empty] | No | A phase II, parallel cross-over, randomized, double-blind, placebo controlled pilot trial to determine pharmacodynamics and tolerability of immediate release SPM 8272 2 and 4 mg in subjects with confirmed detrusor instability | Bladder Overactivity | Immunology |  | 2000-09-26 | 2000-09-26 |  | 2010-08-11: 2000-10-30; 2010-11-23: 2000-12-18; 2012-04-02: 2001-07-02; 2012-06-29: 2001-08-31; 2012-10-22: 2001-11-01 | France | France (Created) |  | 1 | 0 | 0 | 48 | 32 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0582 | Study Archived | 3 doses of SPM 8272 vs. placebo subjects with non-neurogenic | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Steinert A | [6 empty] | No | A phase II, parallel group, randomized, double-blind, placebo-controlled dose-ranging trial to determine the optimal dose and the tolerability of sustained release SPM 8272 in subjects with non-neurogenic bladder overactivity | Bladder Overactivity | Immunology |  | 2001-01-02 | 2001-01-02 |  | 2010-08-11: 2001-06-08; 2010-11-23: 2001-10-01; 2012-04-02: 2002-10-16; 2012-06-29: 2002-12-31; 2012-08-16: 2003-01-31; 2012-10-22: 2003-04-03 | Czech Republic, Denmark, Estonia, France, Germany, Hungary, Israel, Italy, Poland, Russian Federation, South Africa, Spain, Sweden, Ukraine, United Kingdom | Czech Republic (Created), Denmark (Created), Estonia (Created), France (Created), Germany (Created), Hungary (Created), Israel (Created), Italy (Created), Poland (Created), Russian Federation (Created), South Africa (Created), Spain (Created), Sweden (Created), Ukraine (Created), United Kingdom (Created) |  | 99 | 0 | 0 | 800 | 720 | 696 | 0 | 0 | 0 | 729 | 18 | 97 | 614
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0583 | CSR Approved | European phase 3 trial SPM 8272 in overactive bladder syndr | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Steinert A | [6 empty] | No | A Phase 3, Parallel Group, Randomized, Double-blind, Double-dummy, Placebo and Active-controlled Multicenter Trial to Investigate the Efficacy and Safety of Fesoterodine in Subjects with Overactive Bladder Syndrome | Bladder Overactivity | Immunology |  | 2003-03-28 | 2003-03-28 |  | 2010-08-11: 2003-09-11; 2010-11-23: 2004-01-31; 2012-04-02: 2004-11-12; 2012-06-29: 2005-02-25; 2012-08-16: 2005-04-06; 2012-10-22: 2005-06-07; 2013-06-11: 2005-09-01 | Australia, Belgium, Bulgaria, Czech Republic, Estonia, France, Germany, Hungary, Italy, Netherlands, New Zealand, Poland, Romania, Russian Federation, South Africa, Spain, Sweden, Ukraine, United Kingdom | Australia (Created), Belgium (Created), Bulgaria (Created), Czech Republic (Created), Estonia (Created), France (Created), Germany (Created), Hungary (Created), Italy (Created), Netherlands (Created), New Zealand (Created), Poland (Created), Romania (Created), Russian Federation (Created), South Africa (Created), Spain (Created), Sweden (Created), Ukraine (Created), United Kingdom (Created) |  | 163 | 0 | 0 | 1400 | 1080 | 870 | 1464 | 55 | 0 | 1135 | 0 | 143 | 992
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0584 | CSR Approved | US phase III trial in treating bladder overactivity with fes | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Derby B | Christopher K | [5 empty] | No | A phase 3, parallel group, randomized, double-blind, placebo controlled multicenter trial to investigate the efficacy, tolerability and safety of fesoterodine in subjects with overactive bladder syndrome. | Bladder Overactivity | Immunology | SP0584 is a parent study of SP0739 | 2003-04-30 | 2003-04-25 |  | 2010-08-11: 2003-09-11; 2010-11-23: 2003-10-30; 2012-04-02: 2004-10-19; 2012-06-29: 2005-02-10; 2012-08-16: 2005-03-29; 2012-10-22: 2005-06-21; 2013-06-11: 2005-10-14 | United States of America | United States of America (Created) |  | 80 | 0 | 0 | 1200 | 810 | 810 | 1894 | 304 | 0 | 835 | 0 | 155 | 680
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0585 | Created (Cancelled) | Efficacy phase II/III trial in detrusor hyperreflexia | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Schulz A | [6 empty] | No | Efficacy phase II/III trial in detrusor hyperreflexia | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0648 | Protoc. Summary Approved (Cancelled) | SPM 907/Fesoterodine: Other interaction trial (if necessary) | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | SPM 907/Fesoterodine: Other interaction trial (if necessary) |  |  |  | 2001-02-13 | 2001-02-13 | [14 empty] | Germany | Germany (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0649 | CSR Approved | SPM 907/Fesoterodine: Pharmacokinetics of Fesoterodine (SPM | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Sachse R | [6 empty] | No | Randomized, double-blind, placebo-controlled, parallel group trial to evaluate the pharmacokinetics, safety and tolerability following single dose oral treatment of 8 mg SPM 8272 in Caucasian, Black A |  |  |  | 2001-04-04 | 2001-04-04 |  | 2010-08-11: 2001-06-26; 2010-11-23: 2001-10-03; 2012-04-02: 2001-10-12; 2012-06-29: 2001-10-22; 2012-10-22: 2002-01-25; 2013-06-11: 2002-09-24 | South Africa, United Kingdom | South Africa (Created), United Kingdom (Created) |  | 2 | 0 | 0 | 48 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0668 | CSR Approved | SPM 8272 by urodynamics in subjects with non-neurogenic blad | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Derby B | Christopher K | [5 empty] | No | A phase II, parallel group, stratified, randomized, double blind, placebo-controlled trial to investigate the efficacy and safety of three different dosages of sustained release DRUG X in subjects with non-neurogenic bladder overactivity showing either involuntary detrusor contractions or normal fin dings during the baseline urodynamic assessment. | Bladder Overactivity | Immunology |  | 2001-10-18 | 2001-10-18 |  | 2010-11-23: 2002-06-19; 2012-04-02: 2003-05-12; 2012-06-29: 2003-07-23; 2012-10-22: 2003-09-19; 2013-06-11: 2006-02-19 | United States of America | United States of America (Created) |  | 25 | 0 | 0 | 250 | 168 | 160 | 0 | 0 | 0 | 261 | 2 | 120 | 139
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0669 | Study Archived | open-label extension trial of SP668 | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Derby B | Christopher K | [5 empty] | No | A double-blind extension and open-label follow-up trial of trial SP668 to determine long-term subject treatment satisfaction, tolerability, safety and efficacy of sustained release fesoterodine in subjects with overactive bladder | Bladder Overactivity | Immunology |  | 2002-07-23 | 2002-08-05 |  | 2010-08-11: 2002-08-05; 2010-11-23: 2003-07-07; 2012-04-02: 2004-02-12; 2012-06-29: 2007-06-15; 2012-08-16: 2007-08-03; 2012-10-22: 2007-09-07; 2013-06-11: 2007-12-19 | United States of America | United States of America (Created) |  | 25 | 0 | 0 | 250 | 190 | 100 | 192 | 46 | 0 | 76 | 28 | 48 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0677 | Study Archived | SPM 907/Fesoterodine: 8 mg SR interaction with oral contrace | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Auer S | [6 empty] | Yes | Randomized, double-blind, placebo-controlled, crossover, multiple dose trial to investigate the influence of 8 mg fesoterodine sustained release for 14 days on the suppression of ovulation by oral hormonal contraception in healthy female subjects |  |  |  | 2001-11-27 | 2001-11-27 |  | 2010-08-11: 2002-01-09; 2010-11-23: 2002-03-04; 2012-04-02: 2002-06-20; 2012-06-29: 2002-08-14; 2012-08-16: 2002-10-11; 2012-10-22: 2003-02-05 | France | France (Created) |  | 1 | 0 | 0 | 30 | 30 | 20 | 0 | 0 | 0 | 30 | 0 | 4 | 26
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0678 | Created (Cancelled) | SPM 907/Fesoterodine: Interaction with antacids | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | SPM 907/Fesoterodine: Interaction with antacids | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0679 | Created (Cancelled) | SPM 907/Fesoterodine: Interaction with CYP 3A4 substrate | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | SPM 907/Fesoterodine: Interaction with CYP 3A4 substrate | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0680 | Created (Cancelled) | SPM 907/Fesoterodine: CYP 2D6 inhibitor | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | SPM 907/Fesoterodine: CYP 2D6 inhibitor | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0681 | Study Archived | SPM 907/Fesoterodine: Confirmative BE Phase 2b vs. Phase 3 f | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | Randomized, non blind, two-fold crossover trial to investigate the bioequivalence of 8 mg fesoterodine after single dose administration of two different formulations in 16 healthy, male subjects |  |  |  | 2002-12-15 | 2002-12-15 |  | 2010-08-11: 2003-01-10; 2010-11-23: 2003-02-10; 2012-04-02: 2003-02-10; 2012-06-29: 2003-04-03; 2012-08-16: 2003-06-30; 2012-10-22: 2003-09-05 | Germany | Germany (Created) |  | 2 | 0 | 0 | 16 | 16 | 16 | 23 | 7 | 0 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0682 | Created (Cancelled) | SPM 907/Fesoterodine: Mass balance | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | SPM 907/Fesoterodine: Mass balance | [22 empty] | 1 | 0 | 0 | 20 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0683 | Study Archived | SPM 907/Fesoterodine: Interaction with CYP 3A4 inducer | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | Non-blind, two period sequential trial to investigate the influence of a pre- and coadministration of rifampicin on the safety, tolerability and pharmacokinetics of a single oral dose administration of 8mg fesoterodine in 12 healthy male subjects |  |  |  | 2003-11-26 | 2003-11-26 |  | 2010-08-11: 2004-02-20; 2010-11-23: 2004-03-09; 2012-04-02: 2004-04-07; 2012-06-29: 2004-05-13; 2012-08-16: 2004-06-16; 2012-10-22: 2005-03-24 | United Kingdom | United Kingdom (Created) |  | 1 | 0 | 0 | 20 | 18 | 18 | 24 | 10 | 0 | 12 | 0 | 0 | 12
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0684 | Study Archived | SPM 907/Fesoterodine: Interaction with 200mg bid ketoconazol | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | RANDOMIZED, NON-BLIND, TWO-FOLD CROSSOVER TRIAL TO INVESTIGATE THE INFLUENCE OF A PRE- AND CO-ADMINISTRATION OF KETOCONAZOLE ON THE SAFETY, TOLERABILITY AND PHARMACOKINETICS OF A SINGLE ORAL DOSE ADMINISTRATION OF 8MG FESOTERODINE IN 18 HEALTHY MALE SUBJECTS |  |  |  | 2003-10-13 | 2003-10-13 |  | 2010-08-11: 2003-11-18; 2010-11-23: 2004-01-12; 2012-04-02: 2004-01-29; 2012-06-29: 2004-03-05; 2012-08-16: 2004-05-27; 2012-10-22: 2005-02-16 | Germany | Germany (Created) |  | 1 | 0 | 0 | 18 | 18 | 18 | 27 | 9 | 0 | 18 | 0 | 1 | 17
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0685 | Study Archived | SPM 907/Fesoterodine: Comparative BA phase 2b vs. phase 3 fo | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | Randomized, non blind, three-fold crossover trial to investigate the absorption and relative bioavailability of two newly developed 8 mg SR formulations of fesoterodine after single oral dose administration in comparison to two 4 mg SR tablets in twelve healthy, male subjects |  |  |  | 2002-04-10 | 2002-04-10 |  | 2010-08-11: 2002-04-19; 2010-11-23: 2002-06-16; 2012-04-02: 2002-06-16; 2012-06-29: 2002-07-15; 2012-08-16: 2002-08-20; 2012-10-22: 2002-09-26 | Germany | Germany (Created) |  | 1 | 0 | 0 | 12 | 12 | 12 | 25 | 8 | 0 | 12 | 0 | 0 | 12
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0686 | Study Archived | SPM 907/Fesoterodine: Thorough QTc | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | A double-blind, single-site, randomized, placebo- and positive-controlled, parallel-design trial of the electrocardiographic effects of 4mg and 28mg per day of fesoterodine administered orally to steady state to healthy male and female subjects: a thorough QT trial |  |  |  | 2003-10-17 | 2003-10-17 |  | 2010-08-11: 2004-04-02; 2010-11-23: 2004-07-30; 2012-04-02: 2004-11-10; 2012-06-29: 2004-12-05; 2012-08-16: 2005-02-07; 2012-10-22: 2005-03-07 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 256 | 256 | 256 | 623 | 363 | 0 | 260 | 0 | 4 | 256
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0687 | Study Archived | SPM 907/Fesoterodine: Food effect final formulation | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | Randomized, non blind, two-fold crossover trial to investigate the influence of food on the pharmacokinetics of fesoterodine after single oral dose administration of 8 mg fesoterodine in 16 healthy, male subjects |  |  |  | 2002-12-12 | 2002-12-12 |  | 2010-08-11: 2003-01-30; 2010-11-23: 2003-03-06; 2012-04-02: 2003-03-06; 2012-06-29: 2003-04-11; 2012-08-16: 2003-07-17; 2012-10-22: 2004-12-02 | Germany | Germany (Created) |  | 1 | 0 | 0 | 16 | 16 | 16 | 20 | 4 | 0 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0728 | Created (Cancelled) | SPM 907/Fesoterodine: Renal impairment 4 mg | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | No | Sequential investigation of pharmacokinetics, safety and tolerability of 4 mg fesotero-dine in male and female patients with renal impairment and in male and female healthy subjects following single-dose administration | [19 empty] | Bulgaria | Bulgaria (Created) |  | 1 | 0 | 0 | 32 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0736 | Protoc. Summary Approved (Cancelled) | 8272 in subjects with non-neurogenic bladder overactivity. | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Derby B | Christopher K | [5 empty] | No | Two phase extension trial of SP668 to investigate the safety and tolerability of sustained release fesoterodine in subjects with overactive bladder: a double-blind phase followed by an open-label extension phase. | Bladder Overactivity | Immunology |  | 2002-07-23 | 2002-07-23 | [14 empty] | United States of America | United States of America (Created) |  | 25 | 0 | 0 | 160 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0738 | Study Archived | SP583 Open Label Extension | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Steinert A | [6 empty] | No | Long-term open-label extension trial for subjects completing the phase 3 trial of Fesoterodine (SP583) for the treatment of overactive bladder syndrome | Bladder Overactivity | Immunology |  | 2003-09-03 | 2003-09-03 |  | 2010-08-11: 2004-02-13; 2010-11-23: 2004-07-03; 2012-04-02: 2005-02-25; 2012-06-29: 2007-06-27; 2012-08-16: 2007-08-09; 2012-10-22: 2007-10-12; 2013-06-11: 2007-12-13 | Australia, Belgium, Bulgaria, Czech Republic, Estonia, France, Germany, Italy, Netherlands, New Zealand, Poland, Romania, South Africa, Spain, Sweden, Ukraine, United Kingdom | Australia (Created), Belgium (Created), Bulgaria (Created), Czech Republic (Created), Estonia (Created), France (Created), Germany (Created), Italy (Created), Netherlands (Created), New Zealand (Created), Poland (Created), Romania (Created), South Africa (Created), Spain (Created), Sweden (Created), Ukraine (Created), United Kingdom (Created) |  | 100 | 0 | 0 | 500 | 500 | 200 | 0 | 0 | 0 | 417 | 66 | 155 | 196
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0739 | Study Archived | OL trial to SP584 for treatment of overactive bladder syndro | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Derby B | Christopher K | [5 empty] | No | Long-Term Open-Label Extension Trial for Subjects Completing the Phase 3 Trial of Fesoterodine (SP584) for the Treatment of Overactive Bladder Syndrome | Bladder Overactivity | Immunology | SP0739 is an extension of SP0584 | 2004-02-11 | 2004-02-11 |  | 2010-08-11: 2004-02-13; 2010-11-23: 2004-04-20; 2012-04-02: 2005-01-31; 2012-06-29: 2007-06-28; 2012-08-16: 2007-08-10; 2012-10-22: 2007-10-16; 2013-06-11: 2007-12-19 | United States of America | United States of America (Created) |  | 70 | 0 | 0 | 450 | 450 | 154 | 0 | 0 | 0 | 150 | 0 | 0 | 150
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0842 | Study Archived | Bioequivalence Trial | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | Yes | RANDOMIZED, NON-BLINDED, TWO-FOLD CROSSOVER TRIAL TO INVESTIGATE THE BIOEQUIVALENCE OF 8MG FESOTERODINE AFTER SINGLE DOSE ADMINISTRATION OF TWO DIFFERENT TABLETS IN 32 HEALTHY, MALE SUBJECTS | Bladder Overactivity | Immunology |  | 2004-10-20 | 2004-10-20 |  | 2010-08-11: 2004-11-17; 2010-11-23: 2005-05-17; 2012-04-02: 2005-06-15; 2012-06-29: 2005-07-12; 2012-08-16: 2005-07-18; 2012-10-22: 2005-08-12; 2013-06-11: 2005-09-07 | Germany | Germany (Created) |  | 1 | 0 | 0 | 32 | 32 | 32 | 48 | 14 | 0 | 34 | 0 | 2 | 32
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0857 | Study Archived | Single dose escalation trial in healthy male Japanese subjec | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | Yes | RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, SINGLE-SITE, DOSE ESCALATION TRIAL TO INVESTIGATE SAFETY, TOLERABILITY AND PHARMACOKINETICS OF FESOTERODINE AFTER SINGLE ORAL ADMINISTRATION OF 4, 8, AND 16MG DOSES IN 12 YOUNG HEALTHY MALE JAPANESE SUBJECTS | Bladder Overactivity | Immunology |  | 2005-03-21 | 2005-03-21 |  | 2010-08-11: 2005-05-19; 2010-11-23: 2005-09-06; 2012-04-02: 2005-09-08; 2012-06-29: 2005-10-19; 2012-08-16: 2005-12-14; 2012-10-22: 2006-04-27; 2013-06-11: 2006-05-18 | Japan | Japan (Created) |  | 1 | 0 | 0 | 12 | 12 | 12 | 22 | 10 | 0 | 12 | 0 | 0 | 12
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0858 | Created (Cancelled) | Multiple dose in middle-aged subjects | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Lueck H | [6 empty] | No | RANDOMIZED, NON-CONTROLLED, NON-BLINDED TRIAL TO CHARACTERIZE THE FLUCTUATION INDEX OF SPM 7605 PLASMA LEVELS AT STEADY STATE AFTER ONCE DAILY ADMINISTRATION OF 4MG OR 8MG FESOTERODINE OVER 5 DAYS TO 72 HEALTHY MALE AND FEMALE SUBJECTS | Bladder Overactivity | Immunology | [20 empty] | 1 | 0 | 0 | 72 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0866 | Created (Cancelled) | Short Title to be entered, Max. Length of Title is 100 Chara | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Steinert A | [6 empty] | No | Long Title to be entered | Bladder Overactivity | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0877 | Study Archived | Dose-proportionality of 4 mg Fesoterodine | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | Yes | Single-site, randomized ,non-blind two-fold crossover trial to investigate the dose proportionality of Fesoterodine administered as single dose administration of one 4 mg or one 8 mg tablet in 24 healthy male subjects | Bladder Overactivity | Immunology |  | 2006-01-04 | 2005-12-21 |  | 2010-08-11: 2006-02-09; 2010-11-23: 2006-05-24; 2012-04-02: 2006-06-06; 2012-06-29: 2006-06-27; 2012-08-16: 2006-07-21; 2012-10-22: 2006-09-12; 2013-06-11: 2006-10-16 | Germany | Germany (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TOVIAZ | not defined | SP0928 | Created (Cancelled) | *Pfizer study A0221007: Fesoterodine on OAB treatment satisf | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Moeltgen H | Russell R | [5 empty] | No | *Pfizer study A0221007: A 12-WEEK, MULTICENTER, OPEN-LABEL, SINGLE-ARM STUDY TO EVALUATE THE EFFECTS OF FESOTERODINE ON TREATMENT SATISFACTION AND SYMPTOM RELIEF IN OVERACTIVE BLADDER PATIENTS | Bladder Overactivity | Immunology | [20 empty] | 80 | 0 | 0 | 400 | 360 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Tozadenant | Central Nervous System | PD0026 | Study Archived | Tozadenant 14C mass balance study | Phase I | Open | GED |  | R & D | Bosteels M | Mccabe S | PRA | SPI PRA |  |  | adults | Yes | A SINGLE-CENTER, OPEN-LABEL STUDY OF EXCRETION BALANCE, PHARMACOKINETICS, AND METABOLISM OF 14C-LABELED TOZADENANT AFTER 240MG SINGLE ORAL DOSE ADMINISTRATION IN HEALTHY MALE SUBJECTS | Parkinson's disease | Central Nervous System |  | 2013-06-06 | 2013-06-06 |  | 2013-08-15 | 2013-09-10 | 2013-09-16 | 2013-09-26 | 2013-09-16 |  | 2013-10-14 |  | 2013-12-11 |  | 2014-01-30 |  | 2014-05-07 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 6 | 6 | 6 | 13 | 0 | 7 | 6 | 0 | 0 | 6
Yes | Not assigned | Managing Type | 1 | Tozadenant | Central Nervous System | UP0015 | Created (Cancelled) | A2A Tozadenant SPECT Study | Phase I |  | R & D |  | R & D |  |  | N/A | Parexel |  |  | adults | No |  |  |  |  | 2013-12-03 | [15 empty] | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 12 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Trapidil | Immunology | 9731 | Study Archived | ISDN | Phase IV | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | Affiliates - Germany | Hess G |  |  | PSI, Vujaklija |  |  |  | No | A multinational, multicenter, double-blind, randomised, 2 parallel-group, non-inferiority study of trapidil 200mg t.i.d versus ISDN 20mg b.i.d. in patients with chronic stable angina pectoris | Indication for Internal Medicine | Immunology |  |  |  |  | 2010-08-11: 1998-03-13; 2010-11-23: 1998-07-01; 2012-06-29: 2001-11-02; 2012-08-16: 2002-03-21; 2013-06-11: 2003-05-07 | Russian Federation | Russian Federation (LPLV) | Russian Federation | 31 | 0 | 1 | 2000 | 2000 | 0 | 726 | 0 | 78 | 648 | 0 | 111 | 537
Yes | Not assigned | Managing Type | 1 | Trospium Chloride | not defined | SP0639 | Final TFLs released | Spasmo-lyt Dragees/Spasmo-lyt 10 mg Anwendungsbeobachtung | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Geerke H | [6 empty] | No | Spasmo-lyt Dragees/Spasmo-lyt 10 mg Anwendungsbeobachtung | Bladder Overactivity | Immunology |  |  |  |  | 2012-10-22: 2002-02-28 |  |  |  | 446 | 0 | 0 | 3000 | 2553 | 2553 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Trospium Chloride | not defined | SP0730 | Protoc. Summary Approved | Spasmolyt Dosierung und Verträglichkeit | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Geerke H | [6 empty] | No | Spasmolyt Dosierung und Verträglichkeit | Bladder Overactivity | Immunology |  | 2002-11-30 | 2002-11-30 | [17 empty] | 1000 | 0 | 0 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TUSSIONEX | Immunology | C10401 | CSR Approved | Bioequivalence | Phase I |  | Clinical Development USA | Clinical Pharmaco | R & D | Salas V | [6 empty] | Yes | A 3-period, randomized, crossover, single-dose bioavailability study of hydrocodone and dexchlorpheniramine administered as extended-release suspensions, and as an immediate-release reference formulation in healthy volunteers | Indication for Dermato Allergo | Immunology |  | 2006-01-06 |  | 2006-06-27 | 2006-06-23 | 2006-07-31 | 2006-07-25 | 2006-08-22 | 2006-07-31 | 2006-08-22 | 2006-08-19 | 2006-10-13 | 2006-10-10 | 2006-11-20 |  | 2007-01-11 | 2007-03-07 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 20 | 20 | 20 | 49 | 0 | 25 | 24 | 0 | 1 | 23
Yes | Not assigned | Managing Type | 1 | TUSSIONEX | Immunology | C10402 | Protocol Approved (Cancelled) | Multiple Dose | Phase I |  | Clinical Development USA | Clinical Pharmaco | R & D | [7 empty] | Yes |  | Indication for Dermato Allergo | Immunology |  | 2007-03-30 |  | 2006-08-24 | 2010-08-11: 2007-07-16 |  |  |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TUSSIONEX | Immunology | C10403 | Created (Cancelled) | Food Effect and IVIVC | Phase I |  | Clinical Development USA | Clinical Pharmaco | R & D | [7 empty] | Yes |  | Indication for Dermato Allergo | Immunology |  | 2007-09-03 |  | 2006-08-31 | [16 empty] | 1 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | TUSSIONEX | Immunology | C10404 | Created (Cancelled) | IVIVC | Phase I |  | Clinical Development USA | Clinical Pharmaco | R & D | Salas V |  |  | ICON |  |  |  | No |  | Indication for Dermato Allergo | Immunology |  | 2007-11-02 | [15 empty] | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB0660 | Immunology | UP0014 | Created (Cancelled) | FIM | Phase I |  | GED |  | GED | Watanabe S | Cain D | [5 empty] | No |  |  |  |  | 2013-03-27 | [18 empty] | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB101264 | Immunology | G01049 | Study Archived | FIM urnary incontinence | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A | [6 empty] | Yes | Randomized, monocenter, double blind, placebo controlled, 3 alternating-panel, 3-period single rising oral dose (0.5 to 50 mg) study of the safety, tolerability and pharmacokinetics of ucb-101264-1 oral solution in 27 healthy male volunteers. | Indication for Dermato Allergo | Immunology |  |  | 2005-03-29 | 2005-06-03 | 2005-04-05 | 2005-06-24 | 2005-07-26 | 2005-08-15 | 2005-08-31 | 2005-10-21 | 2005-10-13 | 2005-11-25 | 2006-10-04 | 2006-02-22 | 2006-11-24 | 2006-03-17 | 2007-01-19 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 27 | 27 | 0 | 51 | 0 | 24 | 27 | 0 | 0 | 27
Yes | Not assigned | Managing Type | 1 | UCB101264 | Immunology | G01050 | Created (Cancelled) | Multiple dose Young | Phase I | Double Blind | Clinical Development USA | Clinical Pharmaco | R & D | Salas V | [6 empty] | Yes |  | Indication for Dermato Allergo | Immunology |  | 2006-01-13 | [18 empty] | 1 | 0 | 0 | 120 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB101264 | Immunology | G01052 | Created (Cancelled) | Multiple dose Elderly | Phase I |  | Clinical Development USA | Clinical Pharmaco | R & D | Salas V | [6 empty] | Yes |  | Indication for Dermato Allergo | Immunology |  | 2006-02-10 | [18 empty] | 1 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB101264 | Immunology | G01053 | Created (Cancelled) | 101264 - 14C | Phase I | Open | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No |  | Indication for Dermato Allergo | Immunology | [20 empty] | 1 | 0 | 0 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB101264 | Immunology | G01054 | Created (Cancelled) | POC | Phase II | Open | UCB Pharma Global | TA Allergology / Respiratory | R & D | [7 empty] | Yes |  | Indication for Dermato Allergo | Immunology | [20 empty] | 5 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB101264 | Immunology | G01055 | Created (Cancelled) | Bioequivalence capsules PIB + Food effect | Phase I | Open | Clinical Development USA | Clinical Pharmaco | R & D | Salas V | [6 empty] | Yes |  | Indication for Dermato Allergo | Immunology |  | 2006-02-03 | [18 empty] | 1 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB103493 | Central Nervous System | N01255 | Created (Cancelled) | FIM Study | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A | [6 empty] | No |  |  |  |  | 2007-12-31 | [18 empty] | 0 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB106607 | Central Nervous System | N01201 | Study Archived | Single ascending dose, safety, and tolerability of FIH admin | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S | [6 empty] | Yes | A Phase I, double-blind, placebo-controlled, randomized, alternating-panel crossover design, dose escalating study to assess the safety, tolerability and pharmacokinetics of single oral doses of ucb-106607-8 in healthy male and female subjects at up to 8 dose levels. | Indication for Neuro Psychiatry | Central Nervous System |  | 2006-03-31 | 2006-04-03 | 2006-05-09 | 2006-05-09 | 2006-07-03 | 2006-07-17 | 2006-07-17 | 2006-08-07 | 2006-09-25 | 2006-10-30 | 2006-10-25 | 2006-12-08 | 2006-12-30 | 2007-03-15 | 2007-03-30 | 2007-05-30 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 36 | 36 | 36 | 71 | 0 | 35 | 36 | 0 | 24 | 12
Yes | Not assigned | Managing Type | 1 | UCB106607 | Central Nervous System | N01271 | Created (Cancelled) | PET Scan / PD1 | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S | [6 empty] | Yes |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2007-04-06 | [18 empty] | 0 | 0 | 0 | 20 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB1412892 | Central Nervous System | N01352 | Study Archived | FIM | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Valgaeren A | Mccabe S | [5 empty] | Yes | A RANDOMIZED, SUBJECT-BLIND, INVESTIGATOR-BLIND, PLACEBO-CONTROLLED, SINGLE ASCENDING DOSE STUDY TO INVESTIGATE THE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF UCB1412892-000 IN HEALTHY MALE SUBJECTS | Epilepsy | Central Nervous System |  | 2009-08-17 | 2009-05-07 | 2009-09-22 | 2009-11-09 | 2009-12-01 | 2009-11-30 | 2009-12-22 | 2009-12-04 | 2010-03-23 | 2010-02-05 | 2010-04-20 | 2010-03-23 | 2010-06-17 | 2010-04-13 | 2010-08-10 | 2010-09-20 | France | France (LPLV) | France | 1 | 1 | 1 | 16 | 16 | 16 | 28 | 0 | 12 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | UCB1412892 | Central Nervous System | N01381 | CSR Approved (Stopped) | SIM | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Valgaeren A | Mccabe S | [5 empty] | Yes | A RANDOMIZED, SUBJECT- AND INVESTIGATOR-BLIND, PLACEBO-CONTROLLED, MULTIPLE ASCENDING DOSE, CROSSOVER, SINGLE-CENTER STUDY TO INVESTIGATE THE SAFETY, TOLERABILITY, PHARMACOKINETICS, AND PHARMACODYNAMICS OF UCB1412892-000 IN HEALTHY MALE SUBJECTS |  |  |  | 2010-02-27 |  |  | 2010-04-21 | 2010-08-04 | 2010-07-23 | 2010-08-11 | 2010-09-21 |  | 2011-01-05 |  | 2011-03-07 |  | 2011-04-28 |  | 2011-10-19 | France | France (LPLV (Stopped)) | France | 1 | 1 | 1 | 40 | 24 | 24 | 52 | 0 | 28 | 24 | 0 | 24 | 0
Yes | Not assigned | Managing Type | 1 | UCB1430721 | Central Nervous System | UP0003 | Protoc. Summary Approved (Cancelled) | FIM | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Valgaeren A | Mccabe S | [5 empty] | No |  |  |  |  | 2011-05-27 | 2011-05-18 | [17 empty] | 1 | 0 | 0 | 170 | 88 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB1430721 | Central Nervous System | UP0007 | Study Archived | Pet Ligand Validation Study | Phase I |  | R & D |  | R & D | Bosteels M, Valgaeren A | Mccabe S | N/A | Marc Bosteels (contract EPM) |  |  | adults | Yes | A SINGLE CENTRE STUDY TO INVESTIGATE THE WHOLE-BODY DOSIMETRY AND CENTRAL KINETICS OF NOVEL PET LIGAND [18F]UCB-H IN HEALTHY MALE VOLUNTEERS | Epilepsy | Central Nervous System |  | 2011-08-17 | 2011-10-10 |  | 2010-08-11: 2011-11-08; 2010-11-23: 2012-05-07; 2012-04-02: 2012-07-02; 2012-06-29: 2012-07-05; 2012-08-16: 2012-09-18; 2012-10-22: 2012-10-31; 2013-06-11: 2013-04-11 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 12 | 8 | 8 | 22 | 13 | 0 | 9 | 0 | 0 | 9
Yes | Not assigned | Managing Type | 1 | UCB1430721 | Central Nervous System | UP0012 | CSR Approved | Effects of Donepezil on Scopolamine induced deficits | Phase I |  | GED |  | GED | Mollet M, Valgaeren A | Mccabe S | N/A |  |  |  | adults | Yes | A Randomised, Subject and Investigator-Blinded, Active and Placebo-Controlled, Crossover Study to Evaluate the Deficits in Psychomotor and Cognitive Function Induced after 30 hours of Sleep Deprivation and Scopolamine Administration in Healthy Male Subjects | Epilepsy | Central Nervous System |  | 2011-11-15 |  |  | 2010-08-11: 2011-12-22; 2010-11-23: 2012-03-05; 2012-04-02: 2012-04-05; 2012-06-29: 2012-05-22; 2012-08-16: 2012-07-25; 2012-10-22: 2012-09-29; 2013-06-11: 2013-04-17 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 24 | 24 | 20 | 132 | 108 | 0 | 24 | 0 | 2 | 22
Yes | Not assigned | Managing Type | 1 | UCB34742 | Immunology | A00359 | Protoc. Summary Approved (Cancelled) | FIM 34742 | Phase I | Double Blind | Clinical Development Europe |  | R & D | Daoust A | [6 empty] | Yes | PTC combined with A00368. Randomized, monocenter, double blind, placebo controlled, two alternating-panel, single rising oral dose (25-800 mg), safety, tolerability, pharmacokinetic and pharmacodynamic study of ucb 34742 (oral capsule) in 18 healthy male volunteers. | Indication for Dermato Allergo | Immunology |  |  | 2003-09-17 | [17 empty] | 1 | 0 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB34742 | Immunology | A00368 | Protoc. Summary Approved (Cancelled) | ucb 34742 - Food effect | Phase I | Open | Clinical Development Europe |  | R & D | Daoust A | [6 empty] | Yes | PTC combined with A00359. Randomized, monocenter, open label, two-way cross-over, food interaction pilot study of a single oral dose (xxx mg) of ucb 34742 (oral capsule) in 8 healthy male volunteers. | Indication for Dermato Allergo | Immunology |  |  | 2003-09-17 | [17 empty] | 1 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB34742 | Immunology | A00369 | Protoc. Summary Approved (Cancelled) | ucb 34742 - EIB (exercice induced bronchoconstriction) | Phase I | Double Blind | Clinical Development Europe |  | R & D | Daoust A | [6 empty] | No | Randomized, double blind, one center, placebo controlled, 4-way cross-over exercise-induced bronchoconstriction trial after single oral dose (xx mg and xx mg expressed as base) of ucb 34742 and one dose of ucb 35440 in male subjcets with mild asthma with a known exercise-induced bronchoconstriction |  |  |  |  | 2003-09-22 | [17 empty] | 0 | 0 | 0 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB34742 | Immunology | A00370 | Created (Cancelled) | ucb 34742 - repeated dose tolerance | Phase I |  | Clinical Development Europe |  | R & D | Daoust A | [6 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB35440 | Immunology | A00313 | Study Archived | FIM + food interaction | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A |  |  | SGS |  |  |  | Yes | randomized, monocenter, DB, placebo controlled, 3 alternative-panel, 3-period single rising oral dose (25 to 2000 mg), safety, tolerability, pharmacokinetic and pharmacodynamic study of ucb-35440-3 oral capsule in 27 healthy male volunteers (Part A), open label, food interaction study in 8 healthy.. | Indication for Dermato Allergo | Immunology |  |  |  | 2002-04-05 | 2002-04-10 | 2002-05-02 | 2002-05-02 | 2002-08-23 | 2002-07-25 | 2002-08-23 | 2002-08-28 | 2002-10-22 | 2003-01-29 |  | 2003-06-18 | 2003-01-21 | 2003-10-28 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 35 | 35 | 35 | 63 | 0 | 28 | 35 | 0 | 0 | 35
Yes | Not assigned | Managing Type | 1 | UCB35440 | Immunology | A00327 | Study Archived | Multiple Dose Tolerance Study | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Bendahmane S |  |  | SGS/UCB |  |  |  | Yes | Randomized, monocenter, double blind, placebo controlled, parallel group, single dose followed by 2-week multiple oral dose, safety, tolerability, pharmacokinetic and pharmacodynamic study of ucb-35440-3 (200 mg capsules), 200 mg, 400 mg and 800 mg twice daily in 36 healthy male volunteers. | Indication for Dermato Allergo | Immunology |  |  |  | 2002-10-21 | 2002-10-23 | 2002-11-12 | 2002-11-12 | 2003-01-21 | 2003-01-21 | 2003-03-07 | 2003-03-10 | 2003-04-30 | 2003-05-07 |  | 2004-12-15 | 2003-08-30 | 2005-05-03 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 70 | 36 | 36 | 62 | 0 | 26 | 36 | 0 | 12 | 24
Yes | Not assigned | Managing Type | 1 | UCB35440 | Immunology | A00328 | Study Archived | exercise induced asthma | Phase II | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | R & D | Pinelli M, Roobaert S | [6 empty] | No | Randomized, double blind, two centers, placebo controlled, 4-way cross-over exercise-induced bronchoconstriction trial after multiple oral dose (62.5 mg, 125 mg and 312.5 mg expressed as base) of ucb-35440-3 in male subjects with mild asthma with a known exercise-induced bronchoconstriction (EIB) | Indication for Dermato Allergo | Immunology |  |  | 2002-12-02 |  | 2003-03-20 | 2003-06-02 | 2003-07-24 |  | 2004-01-07 | 2003-09-30 | 2004-02-24 | 2003-11-17 | 2004-04-05 | 2003-11-24 | 2004-11-03 | 2004-02-27 | 2005-01-11 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 2 | 2 | 2 | 16 | 16 | 16 | 29 | 15 | 0 | 14 | 14 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB35440 | Immunology | A00329 | Protoc. Summary Approved (Cancelled) | C14 Oral | Phase I |  | Clinical Development Europe |  | R & D | Daoust A, Riethuisen J | [6 empty] | Yes | [5 empty] | 2003-01-27 | [17 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB35440 | Immunology | A00344 | Created (Cancelled) | 35440- CYP inhibition | Phase I |  | Clinical Development Europe |  | R & D | [7 empty] | No | [6 empty] | 2002-11-15 | 2010-11-03: 2003-06-01; 2012-06-29: 2003-10-31; 2012-08-13: 2004-03-31; 2013-03-26: 2004-06-30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB35440 | Immunology | A00345 | Created (Cancelled) | 35440 - OC interaction | Phase I |  | Clinical Development Europe |  | R & D | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCB35440 | Immunology | A00346 | CSR Approved | Histamine challenge | Phase II | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | R & D | Gerard D, Pinelli M | [6 empty] | No | Randomized, monocenter, 4 way cross-over histamine-induced bronchoconstriction trial to assess the protective effect of multiple oral dose of ucb-35440-3 (312.5 mg bid expressed as base), versus Levocetirizine (5 mg), Montelukast (10 mg) and Placebo, in 16 male subjects suffering from mild to modera | Indication for Dermato Allergo | Immunology |  | 2003-01-22 | 2003-01-22 | 2003-04-11 | 2003-04-23 | 2003-07-16 | 2003-08-02 | 2003-09-12 | 2004-01-15 | 2003-12-09 | 2004-04-07 | 2004-02-27 | 2004-06-10 | 2004-03-26 | 2004-11-04 | 2004-04-22 | 2005-02-17 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 20 | 16 | 12 | 23 | 0 | 11 | 12 | 0 | 3 | 9
Yes | Not assigned | Managing Type | 1 | UCB4019 | Immunology | UP0028 | Study Archived | UP0028 FIH | Phase I | Double Blind | GED | NewMeds | GED | Watanabe S | Cain D | Parexel | PAREXEL | No | Yes | adults | Yes | A SUBJECT-BLIND, INVESTIGATOR-BLIND, RANDOMIZED, PLACEBO-CONTROLLED, FIRST-IN-HUMAN STUDY EVALUATING THE SAFETY, PHARMACOKINETICS, AND PHARMACODYNAMICS OF SINGLE ASCENDING SUBCUTANEOUS DOSES OF UCB4019 IN HEALTHY SUBJECTS | All Indications; Healthy Volunteers | Immunology; Immunology |  |  | 2016-01-15 |  | 2016-04-27 | 2016-08-04 | 2016-07-28 | 2016-10-28 | 2016-12-08 | 2017-01-13 | 2017-02-08 | 2017-02-14 | 2017-03-07 | 2017-03-21 | 2017-06-14 | 2017-06-27 | 2017-10-27 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 80 | 32 | 32 | 97 | 0 | 65 | 32 | 0 | 0 | 32
Yes | Not assigned | Managing Type | 1 | UCB6352 | not defined | PF0001 | Protoc. Summary Approved (Cancelled) | Safety/Tolerability in Adults with Idiopathic Pulmon Fibrosi | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Vandendriessche A | Beaman M | Parexel | PXL SPI |  |  | adults | No |  |  |  |  | 2014-06-02 | 2014-06-02 | [17 empty] | 0 | 0 | 0 | 60 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | UCERAX | Central Nervous System | N01108 | CSR Approved | Premedication | Phase III | Double Blind | Clinical Development Europe | GMA Neurology / Psychiatry | Affiliates - France | Benkaci D |  |  | Quintiles |  |  |  | No | A double-blind, placebo controlled, randomized, parallel groups, multicenter phase IV trial : Evaluation of the efficacy and of the safety of hydroxyzine dihydrochloride 100mg oral tablet (single dose) in treatment of preoperative anxiety on subjects undergoing a premedication before general anesthe | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 2002-10-03 | 2002-10-01 | 2002-12-12 |  | 2003-08-06 | 2003-06-30 | 2003-08-18 |  | 2004-01-27 |  | 2003-10-16 |  | 2008-08-21 | France | France (LPLV) | France | 40 | 0 | 36 | 330 | 300 | 300 | 354 | 0 | 49 | 300 | 0 | 0 | 300
Yes | Not assigned | Managing Type | 1 | Valsartan | not defined | SP0594 | Created (Cancelled) | PROBAT Pilot-Studie | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Babst H | [6 empty] | No | PROBAT Pilot-Studie | Essential Hypertension | Immunology | [20 empty] | 60 | 0 | 0 | 180 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Valsartan | not defined | SP0652 | Created | Ermittlung der Lebensqualität (QoL) unter Provas | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Babst H | [6 empty] | No | Ermittlung der Lebensqualität (QoL) unter Provas | [22 empty] | 0 | 0 | 0 | 3000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Valsartan | not defined | SP0721 | LPLV (Stopped) | ADMITEN Study: Adherence to treatment among hypertensive pat | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Bravo J | [6 empty] | No | ADMITEN Study:Adherence to treatment among hypertensive patients | Hypertension | Immunology |  | 2001-10-22 | 2001-04-04 |  | 2010-08-11: 2001-07-01; 2010-11-23: 2001-09-10; 2012-04-02: 2002-12-30; 2012-06-29: 2003-01-29 |  |  |  | 3505 | 0 | 0 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Valsartan | not defined | SP0778 | Created | Provas PMS essential hypertension | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Wendl M | [6 empty] | No | Provas PMS essential hypertension | Essential Hypertension | Immunology | [20 empty] | 2500 | 0 | 0 | 12500 | 12500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Valsartan | not defined | SP0916 | Created | Short Title to be entered, Max. Length of Title is 100 Chara | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Jansen T | [6 empty] | No | Long Title to be entered | Hypertension | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Verapamil | not defined | SP0434 | Created | Drug Safety Trial Data. Study drug: VERAPAMIL |  |  | UCB Pharma Global |  | UCB Pharma Global | Cawello W | [6 empty] | No | Drug Safety Trial Data. Study drug: VERAPAMIL | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Verapamil | not defined | SP0455 | Created | Drug Safety Trial Data. Study drug: VERAPAMIL |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: VERAPAMIL | [22 empty] | 0 | 0 | 0 | 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Verapamil | not defined | SP0459 | Created | Drug Safety Trial Data. Study drug: VERAPAMIL |  |  | UCB Pharma Global |  | UCB Pharma Global | Nelsen L | [6 empty] | No | Drug Safety Trial Data. Study drug: VERAPAMIL | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Verapamil HCL | not defined | SP0556 | Final TFLs released | The C.H.R.O.N.O. Trial, VERELAN PM | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Pollock S | [6 empty] | No | The C.H.R.O.N.O. Trial, VERELAN PM | Mild to Moderate Hypertension | Immunology |  | 1999-08-12 | 1999-08-12 |  | 2010-08-11: 1999-10-04; 2010-11-23: 1999-11-15; 2012-06-29: 2000-10-12; 2012-10-22: 2001-04-09 | United States of America | United States of America (Created) |  | 2000 | 0 | 0 | 6000 | 6000 | 6000 | 0 | 0 | 0 | 2039 | 0 | 0 | 2039
Yes | Not assigned | Managing Type | 1 | Verapamil HCL | not defined | SP0700 | Final TFLs released | Verapamil bioavailability when sprinkled on applesauce | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | A pharmacokinetic study to compare the single dose bioavailability of verapamil administered as a 300 mg Verelan PM capsule (manufactured by Elan Pharmaceuticals for Schwarz Pharma, Inc) taken intact or sprinkled in applesauce |  |  |  | 2002-03-29 | 2002-03-29 |  | 2010-08-11: 2002-04-10; 2010-11-23: 2002-05-04; 2012-04-02: 2002-05-04; 2012-06-29: 2002-05-13; 2012-10-22: 2002-06-26 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 36 | 36 | 32 | 0 | 0 | 0 | 36 | 0 | 0 | 36
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0002 | Protocol Approved (Cancelled) | VIMPAT NONINTERVENTIONAL STUDY POST MARKETING SURVEILLANCE | Non Interventional Study - Prospective | Open | Affiliates | GMA Neurology / Psychiatry | Affiliates | Lee J | Matsuoka K | N/A | Dream CIS |  |  | adults | No | POST MARKETING SURVEILLANCE STUDY FOR VIMPAT® (LACOSAMIDE) SOLUTION FOR INFUSION IN KOREAN SUBJECTS | Epilepsy | Central Nervous System |  | 2011-11-30 | 2013-09-06 |  | 2010-08-11: 2013-09-06; 2010-11-03: 2014-10-30; 2011-09-27: 2015-09-10 | South Korea | South Korea (Regulatory Approval) | South Korea | 50 | 0 | 0 | 3300 | 3300 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0004 | Created (Cancelled) | Retrospective Multicenter NIS Study on OCT data in Spain | Non Interventional Study - Retrospective |  | Affiliates - Spain |  | Affiliates - Spain | Alcazar J | [6 empty] | No | [23 empty] | 15 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0008 | Study Archived | Double blind, multicenter study | Phase III | Double Blind | GCSO | Neurology | GCSO | Sasamoto H | Matsuo T | Parexel | PXL | Yes | Yes | adults | No | A MULTICENTER, DOUBLE-BLIND, RANDOMIZED, PLACEBO-CONTROLLED, PARALLEL-GROUP STUDY TO EVALUATE THE EFFICACY AND SAFETY OF LACOSAMIDE AS ADJUNCTIVE THERAPY IN JAPANESE AND CHINESE ADULTS WITH UNCONTROLLED PARTIAL-ONSET SEIZURES WITH OR WITHOUT SECONDARY GENERALIZATION. | Epilepsy | Central Nervous System | EP0008 is a parent study of EP0009 | 2011-05-06 | 2011-05-06 |  | 2012-03-06 | 2012-10-17 | 2012-09-28 | 2014-05-10 | 2014-01-28 |  | 2014-08-06 |  | 2014-10-01 |  | 2014-10-20 |  | 2015-02-28 | China, Japan | China (LPLV), Japan (LPLV) | China, Japan | 76 | 76 | 72 | 676 | 540 | 540 | 693 | 0 | 105 | 588 | 123 | 94 | 371
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0009 | Study Archived | Open-label, multicenter study | Phase III | Open | GCSO | Neurology | GCSO | Horn K |  | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, OPEN-LABEL, UNCONTROLLED, LONG-TERM, EXTENSION STUDY TO EVALUATE THE SAFETY AND EFFICACY OF LACOSAMIDE AS ADJUNCTIVE THERAPY IN JAPANESE AND CHINESE ADULTS WITH PARTIAL-ONSET SEIZURES WITH OR WITHOUT SECONDARY GENERALIZATION | Epilepsy | Central Nervous System | EP0009 is a follow up of EP0008 | 2011-07-11 | 2011-07-14 |  | 2012-03-06 | 2013-03-29 | 2013-03-26 | 2013-11-30 | 2014-07-30 | 2019-07-31 | 2019-07-29 | 2019-08-28 | 2019-08-29 | 2019-09-25 | 2019-09-26 | 2019-11-25 | 2020-01-14 | China, Japan | China (LPLV), Japan (LPLV) | China, Japan | 76 | 76 | 67 | 378 | 378 | 378 | 474 | 0 | 0 | 474 | 0 | 220 | 254
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0012 | Study Archived | Phase III (PGTCS) OLE | Phase III | Open | GCSO | Neurology | GCSO | Conrath P, Gao L, Yokoyama T | Copetti C, Guo J, Shimizu S | ICON | ICON | No | Yes | other | No | AN OPEN-LABEL, MULTICENTER EXTENSION STUDY TO EVALUATE THE LONG-TERM SAFETY AND EFFICACY OF LACOSAMIDE AS ADJUNCTIVE THERAPY FOR UNCONTROLLED PRIMARY GENERALIZED TONIC-CLONIC SEIZURES IN SUBJECTS WITH IDIOPATHIC GENERALIZED EPILEPSY PHASE 3 | Epilepsy | Central Nervous System | EP0012 is an extension of SP0982 | 2011-08-31 | 2011-08-31 |  | 2012-10-18 | 2014-12-26 | 2015-08-03 | 2018-01-02 | 2019-05-23 23:00 | 2024-02-08 | 2023-03-30 | 2018-07-24 | 2023-05-03 | 2019-10-21 | 2023-06-09 | 2019-04-25 | 2023-08-22 | Australia, Brazil, Bulgaria, China, Czech Republic, France, Germany, Hungary, Israel, Italy, Japan, Mexico, Poland, Portugal, Romania, Russian Federation, Slovakia, South Korea, Spain, Taiwan, United States of America | Australia (LPLV), Belgium (1st Site Initiation (Cancelled)), Brazil (LPLV), Bulgaria (LPLV), China (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Israel (LPLV), Italy (LPLV), Japan (LPLV), Mexico (LPLV), Poland (LPLV), Portugal (LPLV), Romania (LPLV), Russian Federation (LPLV), Slovakia (LPLV), South Korea (LPLV), Spain (LPLV), Taiwan (LPLV), Turkey (1st Site Initiation (Cancelled)), United States of America (LPLV) | Australia, Brazil, Bulgaria, China, Czech Republic, France, Germany, Hungary, Israel, Italy, Japan, Mexico, Poland, Portugal, Romania, Russian Federation, Slovakia, South Korea, Spain, Taiwan, United States of America | 196 | 195 | 87 | 240 | 240 | 240 | 240 | 0 | 0 | 240 | 0 | 85 | 155
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0013 | Study Archived | Lacosamide Warfarin Interaction Study | Phase I |  | GED |  | GED | Mollet M | Mccabe S | N/A |  |  |  | adults | Yes | SINGLE-CENTER, OPEN-LABEL, RANDOMIZED 2-WAY CROSSOVER STUDY OF THE EFFECT OF LACOSAMIDE 200MG TWICE DAILY ON THE SINGLE-DOSE PHARMACOKINETICS AND PHARMACODYNAMICS OF WARFARIN (25 MG) IN HEALTHY MALE VOLUNTEERS |  |  |  |  | 2011-09-29 |  | 2011-11-29 | 2012-01-11 | 2012-01-18 | 2012-01-31 | 2012-02-15 | 2012-03-31 | 2012-03-27 | 2012-05-02 | 2012-04-20 | 2012-07-04 | 2012-10-03 | 2012-11-12 | 2012-12-03 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 20 | 20 | 16 | 53 | 0 | 37 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0014 | Protocol Approved (Cancelled) | NIS-LCM in pts/POS routine clinical practise | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Haraszti Z | [6 empty] | No | OPEN-LABEL, PROSPECTIVE, NON-INTERVENTIONAL MULTICENTER STUDY TO EVALUATE EFFECTIVENESS AND SAFETY OF ADJUNCTIVE VIMPAT® IN PATIENTS WITH PARTIAL-ONSET SEIZURES IN ROUTINE CLINICAL PRACTICE IN HUNGARY | Epilepsy | Central Nervous System |  |  | 2011-08-04 |  | 2010-08-11: 2011-08-04 | Hungary | Hungary (Created) |  | 60 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0024 | Study Archived | Open Label, Multicenter Study | Phase III | Open | Clinical Development Japan | Clinical Development Japan | Clinical Development Japan | Okagaki T, Sasamoto H, Soma T | Matsuo T, Tsujii A | Parexel | SPI PXL | No | Yes | adults | No | A MULTICENTER, OPEN-LABEL STUDY TO EVALUATE THE SAFETY AND TOLERABILITY OF INTRAVENOUS LACOSAMIDE AS REPLACEMENT FOR ORAL LACOSAMIDE IN JAPANESE ADULTS WITH PARTIAL-ONSET SEIZURES WITH OR WITHOUT SECONDARY GENERALIZATION | Epilepsy | Central Nervous System |  | 2013-01-17 | 2013-01-16 |  | 2014-03-17 | 2014-07-11 | 2014-07-06 | 2014-11-21 | 2014-10-26 |  | 2014-11-01 |  | 2015-01-30 |  | 2015-02-13 |  | 2015-07-21 | Japan | Japan (LPLV) | Japan | 10 | 6 | 5 | 12 | 10 | 10 | 9 | 0 | 0 | 9 | 0 | 0 | 9
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0034 | Study Archived | Long Term ext study to assess safety of Vimpat in a ped popu | Phase III | Open | GCSO | Neurology | GCSO | Bullock E | Grose-Hodge R | PRA | PRA | No | Yes | paediatrics | No | A MULTICENTER, OPEN-LABEL, LONG-TERM EXTENSION STUDY TO INVESTIGATE THE EFFICACY AND SAFETY OF LACOSAMIDE AS ADJUNCTIVE THERAPY IN PEDIATRIC SUBJECTS WITH EPILEPSY WITH PARTIAL ONSET SEIZURES | Epilepsy | Central Nervous System | EP0034 is an extension of SP0967, SP0969 and is a feeder study of EP0151 | 2012-08-27 08:00 | 2012-08-27 |  | 2013-06-03 | 2014-03-28 | 2014-08-13 | 2017-03-15 | 2020-04-09 09:00 | 2022-06-24 | 2022-04-13 | 2022-07-22 | 2022-05-14 | 2022-08-05 | 2022-05-27 | 2022-11-01 | 2022-08-09 | Argentina, Australia, Belgium, Brazil, Bulgaria, China, Colombia, Croatia, Czech Republic, Estonia, France, Georgia, Greece, Hungary, Israel, Italy, Latvia, Lithuania, Mexico, Moldavia, Montenegro, Philippines, Poland, Portugal, Romania, Russian Federation, Serbia, Slovakia, Slovenia, South Korea, Taiwan, Thailand, Ukraine, United Kingdom, United States of America | Argentina (LPLV), Australia (LPLV), Belgium (LPLV), Brazil (LPLV), Bulgaria (LPLV), China (LPLV), Colombia (LPLV), Croatia (LPLV), Czech Republic (LPLV), Estonia (LPLV), France (LPLV), Georgia (LPLV), Greece (LPLV), Hungary (LPLV), Israel (LPLV), Italy (LPLV), Latvia (LPLV), Lithuania (LPLV), Mexico (LPLV), Moldavia (LPLV), Montenegro (LPLV), Philippines (LPLV), Poland (LPLV), Portugal (LPLV), Romania (LPLV), Russian Federation (LPLV), Serbia (LPLV), Slovakia (LPLV), Slovenia (LPLV), South Korea (LPLV), Taiwan (LPLV), Thailand (LPLV), Ukraine (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Argentina, Australia, Belgium, Brazil, Bulgaria, China, Colombia, Croatia, Czech Republic, Estonia, France, Georgia, Greece, Hungary, Israel, Italy, Latvia, Lithuania, Mexico, Moldavia, Montenegro, Philippines, Poland, Portugal, Romania, Russian Federation, Serbia, Slovakia, Slovenia, South Korea, Taiwan, Thailand, Ukraine, United Kingdom, United States of America | 209 | 143 | 141 | 544 | 544 | 544 | 11 | 0 | 0 | 540 | 0 | 152 | 388 |  |  | 2020-05-07 08:00 | 2020-05-07 |  |  | 2020-11-06 08:00 | 2020-11-06
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0036 | Study Archived | VIMPAT BA Study (tablets vs IV) | Phase I | Open | GED |  | GED | Watanabe S | Cain D | Parexel | SPI PXL |  |  | adults | No | A SINGLE-CENTER, OPEN-LABEL, RANDOMIZED, SINGLE DOSE, 3-WAY CROSSOVER STUDY TO COMPARE THE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF LACOSAMIDE ADMINISTERED AS ORAL TABLET OR INTRAVENOUS INFUSION IN HEALTHY JAPANESE SUBJECTS | Epilepsy | Central Nervous System |  | 2012-07-30 | 2012-07-17 |  | 2013-08-14 | 2013-11-06 | 2013-11-01 | 2013-11-21 | 2013-11-27 |  | 2013-12-30 |  | 2014-04-01 |  | 2014-06-25 |  | 2014-08-11 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 48 | 24 | 24 | 40 | 0 | 14 | 26 | 0 | 2 | 24
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0042 | Protocol Approved (Cancelled) | EU NIS wirh LCM as single add-on | Non Interventional Study - Prospective |  | Affiliates | GMA Neurology / Psychiatry | Global Medical Affairs Europe | Awedikian R | Baukens C | PRA | PRA |  |  |  | No | A NONINTERVENTIONAL STUDY EVALUATING THE EFFECTIVENESS OF VIMPAT® (LACOSAMIDE) AS ADJUNCTIVE TREATMENT TO 1 BASELINE ANTIEPILEPTIC DRUG THERAPY IN PATIENTS WITH PARTIAL-ONSET SEIZURES WITH OR WITHOUT SECONDARY GENERALIZATION IN ROUTINE CLINICAL PRACTICE (VIMPRO) |  |  |  | 2012-12-18 |  |  | 2010-08-11: 2012-12-17; 2010-11-03: 2014-04-29; 2011-09-27: 2016-04-28 | Austria, France, Italy, Spain, Sweden, United Kingdom | Austria (Created), France (Created), Italy (Created), Spain (Created), Sweden (Created), United Kingdom (Created) |  | 75 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0044 | Study Archived | retrospective assessment of effectiveness | Non Interventional Study - Retrospective | Open | Global Medical Affairs Europe | GMA Neurology / Psychiatry | Affiliates |  |  | N/A | NA (Acromion) |  |  | other | No | A multi-center, retrospective, post-marketing authorization assessment of epilepsy patients with partial onset seizures treated with either VImpat (Lacosamide) or LAmotrigine as adjunctive therapy in daily clinical pRActice to explore treatment effectiveness (VILARA) | Epilepsy | Central Nervous System |  | 2012-07-20 | 2012-08-07 |  | 2010-08-11: 2012-08-07; 2010-11-23: 2012-11-14; 2012-04-02: 2013-03-31; 2012-06-29: 2013-03-31; 2012-08-16: 2013-05-14; 2012-10-22: 2013-06-26; 2013-06-11: 2013-12-13 | Germany | Germany (LPLV) | Germany | 25 | 16 | 16 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 813 | 0 | 0 | 813
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0045 | Study Archived | Vimpat (Laco) Added to One Anti Epileptic Drug Brain Tum | Non Interventional Study - Prospective | Open | GCSO | Neurology | UCB Pharma Global | Bretschneider M | Tillery N | PRA | PRA | No | Hybrid | adults | No | A NONINTERVENTIONAL STUDY OF VIMPAT® (LACOSAMIDE) AS ADJUNCTIVE ANTIEPILEPTIC DRUG THERAPY IN PATIENTS WITH BRAIN TUMOR RELATED EPILEPSY (VIBES) | Epilepsy | Central Nervous System |  | 2014-03-18 | 2014-06-25 |  | 2014-06-25 | 2014-11-07 | 2014-11-27 | 2015-11-11 | 2017-06-19 |  | 2017-12-04 04:00 |  | 2018-01-17 |  | 2018-02-23 |  | 2018-05-10 | France, Germany, Italy, Netherlands, Spain, United Kingdom | France (LPLV), Germany (LPLV), Italy (LPLV), Netherlands (LPLV), Spain (LPLV), United Kingdom (LPLV) | France, Germany, Italy, Netherlands, Spain, United Kingdom | 28 | 28 | 24 | 100 | 100 | 100 | 93 | 0 | 0 | 93 | 0 | 14 | 79
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0049 | Study Archived | Vimpat retrospective trial Russia | Non Interventional Study - Retrospective | Open | Clinical Development Europe |  | Affiliates | Webers T | Bonny M | N/A | N/A | No | No | adults | No | OBSERVATIONAL PLAN STUDY EP0049 A MULTICENTER, RETROSPECTIVE POSTMARKETING AUTHORIZATION STUDY IN PATIENTS WITH UNCONTROLLED EPILEPSY TREATED WITH VIMPAT IN DAILY CLINICAL PRACTICE IN RUSSIA RETROSPECTIVE CHART REVIEW | Epilepsy | Central Nervous System |  | 2014-09-17 | 2014-09-17 |  | 2014-10-16 | 2015-01-07 | 2014-12-25 | 2015-04-15 | 2015-03-06 |  | 2015-03-06 |  | 2015-04-30 |  | 2015-06-09 |  | 2015-09-04 | Russian Federation | Russian Federation (LPLV) | Russian Federation | 20 | 14 | 14 | 190 | 171 | 171 | 181 | 0 | 0 | 181 | 0 | 0 | 181
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0057 | Study Archived | Lacosamide Mono Safety Study in Japan | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Ikeda K | Matsuo T | Parexel | PAREXEL | Yes | Yes | adults | No | A multicenter, open-label, Long-term study to investigate the safety of conversion to Lacosamide at doses up to 600mg/day as monotherapy in Japanese Adults with partial-onset seizures with or without secondary generalization. | Epilepsy | Central Nervous System |  | 2013-06-19 | 2013-06-28 |  | 2013-10-14 | 2014-01-22 | 2014-04-21 | 2014-12-18 | 2015-01-14 | 2017-07-04 | 2017-11-21 | 2017-10-13 | 2017-12-25 | 2018-01-10 | 2018-01-23 | 2018-05-21 | 2018-03-16 | Japan | Japan (LPLV) | Japan | 10 | 13 | 11 | 20 | 15 | 15 | 20 | 0 | 0 | 20 | 0 | 7 | 13
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0059 | Study Archived | Bioequivalence Tablet vs Dry Syrup | Phase I | Open | GED | NewMeds | UCB Pharma Global | Watanabe S | Cain D | PRA | SPI PRA | No | Yes | adults | Yes | A single-CENTER, open-label, randomized, single-ORAL dose, 2-way cross-over study to INVESTIGATE THE BIOEQUIVALENCE BETWEEN LACOSAMIDE TABLET AND DRY SYRUP IN healthy male Japanese subjects | Epilepsy | Central Nervous System |  | 2016-04-29 | 2016-05-24 |  | 2016-07-14 | 2016-11-24 | 2016-10-31 | 2017-02-09 | 2017-02-15 | 2017-03-21 | 2017-03-04 | 2017-04-19 | 2017-04-03 | 2017-06-07 | 2017-05-23 | 2017-09-06 | 2017-07-26 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 36 | 24 | 24 | 32 | 0 | 8 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0063 | Study Archived | Vimpat Taiwan Post-commitment approval NIS | Non Interventional Study - Prospective | Open | GCSO | Neurology | UCB Pharma Global | Guo J | Grose-Hodge R | PRA | PRA | No | No | adults | No | Multicenter observational study in Taiwan to evaluate the safety of Lacosamide in clinical practice for the treatment of (1) complex partial seizures and (2) simple or complex partial seizures with secondary generalization in patients with epilepsy aged 16 years and older | Epilepsy | Central Nervous System |  | 2014-09-01 | 2014-12-04 |  | 2014-12-04 | 2015-08-13 | 2016-11-24 05:00 | 2016-08-11 | 2017-05-16 05:00 |  | 2018-06-07 07:06 |  | 2018-07-05 |  | 2018-07-19 |  | 2018-10-11 | Taiwan | Taiwan (LPLV) | Taiwan | 10 | 8 | 7 | 170 | 170 | 170 | 172 | 0 | 0 | 172 | 0 | 33 | 139
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | EP0068 | Study Archived | LACOSAMIDE (LCM;Vimpal) Monotherapy in clinical practice | Non Interventional Study - Retrospective |  | GCSO | Neurology | UCB Pharma Global | Sacre J | Copetti C | N/A | N/A | No | No | adults | No | MULTICENTER, NON-INTERVENTIONAL, RETROSPECTIVE CHART REVIEW OF LACOSAMIDE MONOTHERAPY IN CLINICLA PRACTICE IN PATIENTS AGED 16 YEARS OR OLDER SHOWING PARTIAL-ONSET SEIZURES WITH OR WITHOUT SECONDARY GENERALIZATION | Epilepsy | Central Nervous System |  |  |  |  | 2015-07-02 | 2015-09-19 | 2015-11-25 | 2016-01-22 | 2016-04-26 |  | 2016-04-26 |  | 2016-06-16 |  | 2016-08-01 | 2016-08-13 | 2016-11-16 | Italy, Netherlands, Spain | Italy (LPLV), Netherlands (LPLV), Spain (LPLV) | Italy, Netherlands, Spain | 40 | 25 | 25 | 450 | 450 | 400 | 439 | 0 | 0 | 439 | 0 | 0 | 439
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0586 | Final TFLs released | Harkoseride Phase II proof of concept in Adjunctive patients | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Schmitt L | [6 empty] | No | A Phase II multicenter, Ascending Dose Assesment of the Safety a, Tolerability, Compatibility, Efficacy and Pharmacokinetics of Harkoseride (ADD 234037 as Asjunctive Therapy in Patients with Partial Seizures. | Epilepsy | Central Nervous System |  | 1999-07-20 08:00 | 1999-01-01 |  | 2010-08-11: 1999-03-30; 2010-11-23: 1999-06-01; 2012-06-29: 2000-03-06; 2012-10-22: 2000-08-20 | United States of America | United States of America (Created) |  | 4 | 0 | 0 | 13 | 13 | 13 | 0 | 0 | 0 | 13 | 0 | 0 | 13
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0587 | Final TFLs released | SPM 927: Single rising dose tolerance | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | SPM 927: Single rising dose tolerance |  |  |  | 2000-04-20 | 2000-04-20 |  | 2010-08-11: 2000-06-07; 2010-11-23: 2000-07-31; 2012-04-02: 2000-09-04; 2012-06-29: 2000-09-08; 2012-10-22: 2000-12-01 | Germany | Germany (Created) |  | 1 | 0 | 0 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0588 | Final TFLs released | SPM 927: Multiple dose tolerance | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | SPM 927: Multiple dose tolerance |  |  |  | 2000-04-20 | 2000-04-20 |  | 2010-08-11: 2000-06-16; 2010-11-23: 2000-09-16; 2012-04-02: 2000-11-06; 2012-06-29: 2000-11-25; 2012-10-22: 2001-04-29 | Germany | Germany (Created) |  | 1 | 0 | 0 | 33 | 33 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0597 | Protoc. Summary Approved (Cancelled) | Harkoseride/Epilepsy/Add-on Therapy/Phase IIb | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Moldenhauer U | [6 empty] | No | A Multicenter, Double-blind, Randomized, Placebo-controlled, Parallel Group Trial to Investigate the Efficacy and Safety of SPM 927 (600 mg/day) as Add-on Therapy in Patients with Partial Seizures with or without Secondary Generalization " | Epilepsy | Central Nervous System |  | 2000-04-13 | 2000-04-13 | [14 empty] | France, Germany, Hungary, Lithuania, Poland, Sweden, Switzerland, United Kingdom, United States of America | France (Created), Germany (Created), Hungary (Created), Lithuania (Created), Poland (Created), Sweden (Created), Switzerland (Created), United Kingdom (Created), United States of America (Created) |  | 60 | 0 | 0 | 250 | 212 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0598 | CSR Approved | Harkoseride as adjunctive therapy in patients with partial s | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Schmitt L | [6 empty] | No | AN OPEN-LABEL EXTENSION STUDY OF THE SAFETY, TOLERABILITY AND COMPATIBILITY OF THE CONTINUED ADMINSTRATION OF HARKOSERIDE (ADD 234037) AS ADJUNCTIVE THERAPY IN PATIENTS WITH PARTIAL SEIZURES | Epilepsy | Central Nervous System |  | 1999-06-12 | 1999-06-12 |  | 2010-08-11: 1999-09-10; 2010-11-23: 1999-12-16; 2012-04-02: 2000-03-25; 2012-06-29: 2001-09-15; 2012-10-22: 2005-09-08; 2013-06-11: 2005-12-19 | United States of America | United States of America (Created) |  | 3 | 0 | 0 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0599 | Final TFLs released | SPM 927: Interaction effect of harkoseride on OCs | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | SPM 927: Interaction effect of harkoseride on OCs |  |  |  | 2000-08-02 | 2000-08-02 |  | 2010-08-11: 2000-10-02; 2010-11-23: 2000-11-17; 2012-04-02: 2001-04-04; 2012-06-29: 2001-06-12; 2012-10-22: 2001-12-08 | Germany | Germany (Created) |  | 1 | 0 | 0 | 40 | 40 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0600 | Final TFLs released | SPM 927: Interaction: Food Effect | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | SPM 927: Interaction: Food Effect |  |  |  | 2000-07-21 | 2000-07-21 |  | 2010-08-11: 2000-09-22; 2010-11-23: 2001-02-12; 2012-04-02: 2001-02-12; 2012-06-29: 2001-03-12; 2012-10-22: 2001-04-15 | Germany | Germany (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0601 | Final TFLs released | SPM 927: Interaction effect of harkoseride on valproic acid | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | SPM 927: Interaction effect of harkoseride on valproic acid |  |  |  | 2000-09-01 | 2000-09-01 |  | 2010-08-11: 2000-10-06; 2010-11-23: 2000-11-08; 2012-04-02: 2000-11-09; 2012-06-29: 2000-12-15; 2012-10-22: 2001-04-06 | Germany | Germany (Created) |  | 1 | 0 | 0 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0602 | Final TFLs released | SPM 927: Interaction effect of valproic acid on harkoseride | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | SPM 927: Interaction effect of valproic acid on harkoseride |  |  |  | 2000-09-01 | 2000-09-01 |  | 2010-08-11: 2000-10-06; 2010-11-23: 2001-01-05; 2012-04-02: 2001-01-15; 2012-06-29: 2001-01-06; 2012-10-22: 2001-06-12 | Germany | Germany (Created) |  | 1 | 0 | 0 | 16 | 16 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0603 | Final TFLs released | SPM 927: Interaction effect of carbamazepine on harkoseride | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | SPM 927: Interaction effect of carbamazepine on harkoseride |  |  |  | 2000-09-12 | 2000-09-12 |  | 2010-08-11: 2000-10-13; 2010-11-23: 2000-11-14; 2012-04-02: 2000-11-26; 2012-06-29: 2000-12-21; 2012-10-22: 2001-06-25 | Germany | Germany (Created) |  | 1 | 0 | 0 | 20 | 20 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0607 | Final TFLs released | Harkoseride/Epilepsy/MaximumToleratedDose/Phase II | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | An open label, dose titration trial to determine tolerability and efficacy of oral SPM 927 as adjunctive therapy in patients with partial seizures with or without secondary generalization | Epilepsy | Central Nervous System |  | 2000-04-13 | 2000-04-13 |  | 2010-08-11: 2001-03-01; 2010-11-23: 2001-05-29; 2012-04-02: 2002-01-23; 2012-06-29: 2002-05-15; 2012-10-22: 2002-09-03 | United States of America | United States of America (Created) |  | 16 | 0 | 0 | 100 | 80 | 80 | 0 | 0 | 0 | 90 | 6 | 13 | 71
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0615 | CSR Approved | Open label continuation to all Phase II SPM 927/epilepsy | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Heinzen L | Smit R | [5 empty] | No | An open-label extension trial to determine tolerability and efficacy of long-term oral SPM 927 as adjunctive therapy in patients with partial seizures | Epilepsy | Central Nervous System | SP0615 is a follow up of SP0616, SP0745 | 2000-04-13 | 2000-04-13 |  | 2010-08-11: 2001-04-05; 2010-11-03: 2001-08-30; 2012-04-02: 2004-05-07; 2012-08-16: 2010-04-21; 2012-10-22: 2010-06-08; 2013-06-11: 2010-11-01 | France, Germany, Hungary, Lithuania, Poland, Sweden, Switzerland, United Kingdom, United States of America | France (Created), Germany (Created), Hungary (Created), Lithuania (Created), Poland (Created), Sweden (Created), Switzerland (Created), United Kingdom (Created), United States of America (Created) |  | 65 | 0 | 0 | 360 | 160 | 86 | 0 | 0 | 0 | 371 | 95 | 236 | 40
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0616 | CSR Approved | Double-blind trial of iv SPM 927 | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Whitesides J | [6 empty] | No | Multicenter, double-blind, double-dummy, randomized trial comparing 60-minute and 30-minute infusion of iv SPM 927 and oral SPM 927 | Epilepsy | Central Nervous System | SP0616 is a feeder study of SP0615 | 2003-09-08 | 2003-09-08 |  | 2010-08-11: 2003-12-03; 2010-11-23: 2004-03-04; 2012-04-02: 2004-06-08; 2012-06-29: 2004-06-16; 2012-08-16: 2004-08-03; 2012-10-22: 2005-04-18; 2013-06-11: 2005-09-20 | Lithuania, Sweden, United States of America | Lithuania (Created), Sweden (Created), United States of America (Created) |  | 8 | 0 | 0 | 60 | 60 | 60 | 60 | 0 | 0 | 60 | 0 | 1 | 59
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0618 | Final TFLs released | SPM 927: Interaction effect of harkoseride on carbamazepine | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | SPM 927: Interaction effect of harkoseride on carbamazepine |  |  |  | 2000-09-12 | 2000-09-12 |  | 2010-08-11: 2000-12-20; 2010-11-23: 2001-01-17; 2012-04-02: 2001-01-20; 2012-06-29: 2001-03-09; 2012-10-22: 2001-07-12 | Germany | Germany (Created) |  | 1 | 0 | 0 | 20 | 20 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0619 | CSR Approved | SPM 927: Human ADME harkoseride 100 mg oral or i. v. single | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | SPM 927: Human ADME harkoseride 100 mg oral or i. v. single dose |  |  |  | 2001-02-08 | 2001-02-08 |  | 2010-08-11: 2001-06-08; 2010-11-23: 2001-07-02; 2012-04-02: 2001-07-18; 2012-06-29: 2001-07-26; 2012-10-22: 2001-09-19; 2013-06-11: 2002-09-02 | United Kingdom | United Kingdom (Created) |  | 1 | 0 | 0 | 10 | 10 | 10 | 10 | 0 | 0 | 10 | 0 | 0 | 10
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0620 | Final TFLs released | SPM 927: Age and gender harkoseride 100 mg bid | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | SPM 927: Age and gender harkoseride 100 mg bid |  |  |  | 2001-05-04 | 2001-05-04 |  | 2010-08-11: 2001-05-25; 2010-11-23: 2001-06-28; 2012-04-02: 2001-08-05; 2012-06-29: 2001-08-31; 2012-10-22: 2001-11-14 | Germany | Germany (Created) |  | 1 | 0 | 0 | 51 | 51 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0640 | Study Archived | SPM 927: Thorough QTc | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Goldammer N | Beinhauer-Zellenka U | [5 empty] | Yes | A DOUBLE-BLIND, SINGLE-SITE, RANDOMIZED, PLACEBO- AND POSITIVE-CONTROLLED, PARALLEL-DESIGN TRIAL OF THE ELECTROCARDIOGRAPHIC EFFECTS OF 400 AND 800MG PER DAY OF LACOSAMIDE IN HEALTHY MALE AND FEMALE SUBJECTS: A THOROUGH QT TRIAL |  |  |  | 2005-03-31 | 2005-03-31 |  | 2010-08-11: 2005-05-25; 2010-11-23: 2005-06-27; 2012-04-02: 2005-10-04; 2012-06-29: 2005-10-27; 2012-08-16: 2005-12-20; 2012-10-22: 2006-03-06; 2013-06-11: 2006-05-22 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 216 | 216 | 216 | 489 | 242 | 0 | 247 | 0 | 27 | 220
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0641 | Study Archived | Lacosamide/SPM 927: PK renal impairment | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Goldammer N | Beinhauer-Zellenka U | [5 empty] | Yes | Open, non-randomized, sequential group comparison to investigate the pharmacokinetics, safety and tolerability of 100mg SPM 927 in male and female subjects with renal impairment including subjects requiring hemodialysis compared to male and female healthy subjects following single-dose administratio n |  |  |  | 2003-09-17 | 2003-09-17 |  | 2010-08-11: 2003-11-24; 2010-11-23: 2004-06-24; 2012-04-02: 2004-10-27; 2012-06-29: 2004-11-22; 2012-08-16: 2004-12-21; 2012-10-22: 2005-08-12; 2013-06-11: 2005-12-21 | Germany | Germany (Created) |  | 2 | 0 | 0 | 40 | 40 | 40 | 71 | 31 | 0 | 40 | 0 | 0 | 40
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0642 | Study Archived | Lacosamide/SPM 927: PK liver impaired subjects | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Mueller-Voessing C | [6 empty] | Yes | Open, non-randomized, group comparison to investigate the pharmacokinetics, safety, and tolerability of 100mg SPM 927 twice daily in male and female subjects with hepatic impairment compared with male and female healthy subjects following multiple-dose administration |  |  |  | 2003-06-24 | 2003-06-24 |  | 2010-08-11: 2003-10-21; 2010-11-23: 2004-04-05; 2012-04-02: 2004-05-14; 2012-06-29: 2004-06-04; 2012-08-16: 2004-09-13; 2012-10-22: 2004-12-16 | Bulgaria, Hungary | Bulgaria (Created), Hungary (Created) |  | 2 | 0 | 0 | 16 | 16 | 16 | 43 | 27 | 0 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0643 | Study Archived | SPM 927: PK in poor metabolizers CYP 2C19 | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Mueller-Voessing C | [6 empty] | No | Randomized, open-label, two-way crossover trial to investigate the pharmaco-kinetics and bioavailability of SPM 927 in poor and extensive metabolizers (CYP2C19). |  |  |  | 2002-04-15 | 2002-04-15 |  | 2010-08-11: 2002-05-16; 2010-11-23: 2002-07-27; 2012-04-02: 2002-09-04; 2012-06-29: 2002-10-07; 2012-08-16: 2002-10-25; 2012-10-22: 2002-11-19 | Germany | Germany (Created) |  | 1 | 0 | 0 | 36 | 36 | 36 | 0 | 0 | 0 | 50 | 2 | 1 | 47
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0644 | CSR Approved | Lacosamide/SPM 927: Interaction with digoxin | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Mueller-Voessing C | [6 empty] | Yes | Double-blind, placebo-controlled, randomized crossover Phase 1 trial to investigate a possible influence of SPM 927 on the steady state pharmacokinetics, pharmacodynamics, safety and tolerability of digoxin in healthy male Caucasian subjects |  |  |  | 2003-07-30 | 2003-07-30 |  | 2010-08-11: 2003-09-15; 2010-11-23: 2003-10-27; 2012-04-02: 2003-11-12; 2012-06-29: 2004-01-05; 2012-08-16: 2004-03-04; 2012-10-22: 2005-08-29; 2013-06-11: 2005-12-19 | Germany | Germany (Created) |  | 1 | 0 | 0 | 20 | 20 | 16 | 38 | 15 | 0 | 20 | 0 | 0 | 20
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0645 | Study Archived | Equivalence of iv infusion and tablet. | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Goldammer N | Beinhauer-Zellenka U | [5 empty] | Yes | Randomized, open-label, single-dose, two-way crossover trial to compare the pharmacokinetics of SPM 927 when given as intravenous solution or as oral tablet in healthy male subjects. | Epilepsy | Central Nervous System |  | 2003-01-09 | 2003-01-09 |  | 2010-08-11: 2003-01-27; 2010-11-23: 2003-03-25; 2012-04-02: 2003-05-07; 2012-06-29: 2003-07-21; 2012-08-16: 2003-08-13; 2012-10-22: 2004-01-14; 2013-06-11: 2005-09-02 | Germany | Germany (Created) |  | 1 | 0 | 0 | 24 | 24 | 16 | 50 | 26 | 0 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0656 | Created (Cancelled) | Lacosamide/SPM 927: Dose equivalence: High versus low dosage | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Mueller-Voessing C | [6 empty] | No | Lacosamide/SPM 927: Dose equivalence: High versus low dosage strength |  |  |  | 2005-03-01 | [18 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0657 | Study Archived | Lacosamide/SPM 927: Equivalence capsules vs. syrup | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Goldammer N | Beinhauer-Zellenka U | [5 empty] | Yes | Randomized, open, 2-period crossover trial to show bioequivalence following single oral dosing of a tablet and of a liquid of 200mg SPM 927 each in healthy subjects. |  |  |  | 2004-07-16 | 2004-07-16 |  | 2010-08-11: 2004-08-24; 2010-11-23: 2004-11-10; 2012-04-02: 2004-11-25; 2012-06-29: 2005-01-04; 2012-08-16: 2005-02-22; 2012-10-22: 2005-06-09; 2013-06-11: 2005-09-05 | Germany | Germany (Created) |  | 1 | 0 | 0 | 16 | 16 | 16 | 20 | 4 | 0 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0658 | Study Archived | Lacosamide/SPM 927: Equivalence i.v. vs. oral formulation | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Mueller-Voessing C | [6 empty] | Yes | Randomized, open-label, single-dose, three-way crossover trial to compare the pharmacokinetics of SPM 927 when given as intravenous solution or as oral tablet in 24 healthy male subjects |  |  |  | 2003-08-08 | 2003-08-08 |  | 2010-08-11: 2003-09-18; 2010-11-23: 2003-10-16; 2012-04-02: 2003-11-14; 2012-06-29: 2003-12-17; 2012-08-16: 2004-02-23; 2012-10-22: 2004-07-30; 2013-06-11: 2005-04-13 | Germany | Germany (Created) |  | 1 | 0 | 0 | 24 | 24 | 20 | 42 | 15 | 0 | 27 | 0 | 5 | 22
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0659 | Created (Cancelled) | SPM 927: PK in children | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | SPM 927: PK in children | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0661 | Study Archived | SPM 927: Pharmacokinetics and tolerability in ethnic groups | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Goldammer N | Beinhauer-Zellenka U | [5 empty] | Yes | Randomized, Double-Blind, Placebo-Controlled, prallel-group phase 1 trial to evaluate the pharmacokinetics, safety and tolerability following multiple dose oral treatment of 200mg SPM 927 in helathy male white, black and asian subjects |  |  |  | 2004-02-24 | 2004-02-24 |  | 2010-08-11: 2004-04-21; 2010-11-23: 2004-08-14; 2012-04-02: 2004-09-05; 2012-06-29: 2004-10-01; 2012-08-16: 2004-12-03; 2012-10-22: 2005-06-22; 2013-06-11: 2005-10-24 | South Africa | South Africa (Created) |  | 1 | 0 | 0 | 48 | 48 | 48 | 59 | 11 | 0 | 48 | 0 | 0 | 48
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0664 | Created (Cancelled) | SPM 927: Bioequivalence: Capsules versus tablets | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Mueller-Voessing C | [6 empty] | No | SPM 927: Bioequivalence: Capsules versus tablets | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0667 | Study Archived | SPM 927/Epilepsy/ Add-On Therapy/Phase IIb | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Hackenson M | [6 empty] | No | A Multicenter, Double-blind, Randomized, Placebo-controlled, Parallel Group Trial to Investigate the Efficacy and Safety of SPM 927 (200, 400, 600 mg/day) as adjunctive therapy in subjects with Partial Seizures with or without Secondary Generalization | Epilepsy | Central Nervous System |  | 2001-07-03 | 2001-07-03 |  | 2010-08-11: 2001-09-24; 2010-11-23: 2002-02-11; 2012-04-02: 2003-10-22; 2012-06-29: 2004-05-07; 2012-08-16: 2004-06-21; 2012-10-22: 2005-02-02 | France, Germany, Hungary, Lithuania, Poland, Sweden, Switzerland, United Kingdom, United States of America | France (Created), Germany (Created), Hungary (Created), Lithuania (Created), Poland (Created), Sweden (Created), Switzerland (Created), United Kingdom (Created), United States of America (Created) |  | 60 | 0 | 0 | 500 | 400 | 400 | 0 | 0 | 0 | 421 | 43 | 65 | 313
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0754 | CSR Approved | Double-blind Study SPM927 Safety/Effic (400+600 mg/d) as Adj | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Beaman M | Kime J | [5 empty] | No | A multicenter, double-blind, randomized, placebo-controlled, parallel-group trial to investigate the efficacy and safety of SPM 927 (400 and 600 mg/day) as adjunctive therapy in subjects with partial seizures with or without secondary generalization. | Epilepsy | Central Nervous System |  | 2003-05-15 | 2003-05-15 |  | 2010-08-11: 2003-12-19; 2010-11-23: 2004-03-18; 2012-04-02: 2006-01-31; 2012-06-29: 2006-08-16; 2012-08-16: 2006-10-18; 2012-10-22: 2006-11-30; 2013-06-11: 2007-03-01 | United States of America | United States of America (Created) |  | 85 | 0 | 0 | 500 | 400 | 300 | 561 | 47 | 0 | 408 | 89 | 77 | 242
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0755 | CSR Approved | D-B Study of SPM 927 Safety/Efficacy (200 and 400mg/day) as | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Hoepken B | [6 empty] | No | A Multicenter, Double-blind, Randomized, Placebo-controlled, Parallel-group Trial to Investigate the Efficacy and Safety of SPM 927 (200 and 400mg/day) as Adjunctive Therapy in Subjects with Partial Seizures with or without Secondary Generalization | Epilepsy | Central Nervous System |  | 2003-05-15 | 2003-05-15 |  | 2010-08-11: 2003-12-19; 2010-11-23: 2004-05-28; 2012-04-02: 2005-07-15; 2012-06-29: 2006-01-24; 2012-08-16: 2006-03-22; 2012-10-22: 2006-05-17; 2013-06-11: 2006-09-08 | Australia, Croatia, Czech Republic, Finland, France, Germany, Hungary, Lithuania, Poland, Russian Federation, Spain, Sweden, United Kingdom | Australia (Created), Croatia (Created), Czech Republic (Created), Finland (Created), France (Created), Germany (Created), Hungary (Created), Lithuania (Created), Poland (Created), Russian Federation (Created), Spain (Created), Sweden (Created), United Kingdom (Created) |  | 80 | 0 | 0 | 577 | 462 | 370 | 585 | 0 | 0 | 485 | 0 | 86 | 399
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0756 | Study Archived | Long-term safety of SPM 927 as Adjunctive Therapy in Subject | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Hackenson M | [6 empty] | No | An open label extension trial to determine safety and efficacy of Long-term oral SPM 927 in patients with partial seizures. | Epilepsy | Central Nervous System |  | 2004-03-23 | 2004-03-23 |  | 2004-05-05 | 2004-10-04 | 2004-10-04 |  | 2006-08-16 |  | 2009-10-28 |  | 2010-01-14 |  | 2010-03-02 |  | 2010-06-23 | United States of America | United States of America (Created) |  | 80 | 0 | 0 | 305 | 305 | 135 | 0 | 0 | 0 | 311 | 170 | 141 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0757 | Study Archived | Open-label IV SPM 927 trial in patients with partial seizure | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Brock M | [6 empty] | No | A multicenter open-label trial to investigate the safety and tolerability of intravenous SPM 927 as replacement for oral SPM 927 in subjects with partial seizures with or without secondary generalization | Epilepsy | Central Nervous System |  | 2004-06-24 | 2004-06-24 |  | 2010-08-11: 2004-08-24; 2010-11-23: 2005-02-03; 2012-04-02: 2006-05-02; 2012-06-29: 2006-05-05; 2012-08-16: 2006-06-27; 2012-10-22: 2006-08-18; 2013-06-11: 2006-12-07 | Czech Republic, Germany, Lithuania, Sweden, United States of America | Czech Republic (Created), Germany (Created), Lithuania (Created), Sweden (Created), United States of America (Created) |  | 31 | 0 | 0 | 160 | 160 | 158 | 160 | 0 | 0 | 159 | 0 | 3 | 156
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0758 | Protoc. Summary Approved (Cancelled) | Open-label IV SPM 927 trial in patients with partial seizure | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Whitesides J | [6 empty] | No | A multicenter open-label trial to investigate the safety and tolerability of 400mg SPM 927 administered by intravenous infusion following titration with oral SPM 927 | Epilepsy | Central Nervous System |  | 2004-08-31 | 2004-08-31 | [17 empty] | 30 | 0 | 0 | 175 | 175 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0774 | Study Archived | Open-label extension for European Phase 3 | Phase III | Open | Clinical Development Europe | CNS | UCB Pharma Global | Esch M | Copetti C | [5 empty] | No | An international Open-label extension trial to determine safety and efficacy of long-term oral SPM 927 in patients with partial seizures. | Epilepsy | Central Nervous System |  | 2004-03-19 | 2004-03-19 |  | 2004-05-05 | 2004-12-05 | 2004-12-21 |  | 2006-01-24 |  | 2010-08-05 |  | 2010-09-29 |  | 2011-01-23 |  | 2011-04-13 | Australia, Croatia, Czech Republic, Finland, France, Germany, Hungary, Lithuania, Poland, Russian Federation, Spain, Sweden, United Kingdom | Australia (1st Site Initiation), Croatia (1st Site Initiation), Czech Republic (1st Site Initiation), Finland (1st Site Initiation), France (1st Site Initiation), Germany (1st Site Initiation), Hungary (1st Site Initiation), Lithuania (1st Site Initiation), Poland (1st Site Initiation), Russian Federation (1st Site Initiation), Spain (1st Site Initiation), Sweden (1st Site Initiation), United Kingdom (1st Site Initiation) | Australia, Croatia, Czech Republic, Finland, France, Germany, Hungary, Lithuania, Poland, Russian Federation, Spain, Sweden, United Kingdom | 71 | 71 | 0 | 376 | 376 | 125 | 0 | 0 | 0 | 376 | 0 | 216 | 160
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0828 | Created (Cancelled) | SPM 927/Epilepsy/ Add-On Therapy/Phase IIb | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Hackenson M | [6 empty] | No | A Multicenter, Double-blind, Randomized, Placebo-controlled, Parallel Group Trial to Investigate the Efficacy and Safety of SPM 927 (200, 400, 600 mg/day) as adjunctive therapy in subjects with Partial Seizures with or without Secondary Generalization | Epilepsy | Central Nervous System | [17 empty] | France, Germany, Hungary, Lithuania, Poland, Sweden, Switzerland, United Kingdom, United States of America | France (Created), Germany (Created), Hungary (Created), Lithuania (Created), Poland (Created), Sweden (Created), Switzerland (Created), United Kingdom (Created), United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0847 | Study Archived | O-L trial to invest. safety, tolerability and PK of ADJ LCM | Phase II | Open | UCB Pharma Global | Neurology | UCB Pharma Global |  |  | N/A | IQVIA;UCB |  |  | paediatrics | No | A MULTICENTER, OPEN-LABEL TRIAL TO INVESTIGATE THE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF LACOSAMIDE (LCM) SYRUP AS ADJUNCTIVE THERAPY IN CHILDREN WITH UNCONTROLLED EPILEPSIES WITH PARTIAL SEIZURES | Epilepsy | Central Nervous System | SP0847 is a feeder study of EP0060, SP0848 | 2008-09-25 | 2009-03-02 |  | 2009-03-02 | 2011-10-25 | 2009-11-04 | 2009-11-30 | 2014-07-09 | 2014-08-26 | 2014-08-26 |  | 2014-10-02 |  | 2014-11-05 |  | 2014-12-09 | Belgium, Mexico, United States of America | Belgium (LPLV), Mexico (LPLV), United States of America (LPLV) | Belgium, Mexico, United States of America | 25 | 30 | 16 | 42 | 42 | 42 | 59 | 0 | 12 | 47 | 0 | 23 | 24
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0848 | Study Archived | O-L-E trial to invest. safety, tol., and efficacy of LCM syr | Phase II | Open | GCSO | Neurology | UCB Pharma Global | Matsuo T, Thierault S | Beinhauer-Zellenka U, Driver D | PRA | UCB;IQVIA;PRA | No | No | paediatrics | No | An open-label study to determine safety, tolerability, and efficacy of long-term Oral lacosamide (LCM) as adjunctive therapy in children with epilepsy | Epilepsy | Central Nervous System | SP0848 is an extension of EP0060, SP0847, SP0966 and is a feeder study of EP0060, EP0151 | 2008-12-19 | 2009-03-02 |  | 2009-03-02 | 2009-07-31 | 2009-12-09 | 2010-02-11 | 2019-06-28 | 2021-06-29 | 2021-05-18 | 2021-07-27 | 2021-07-21 | 2021-08-24 | 2021-08-03 | 2021-11-23 | 2021-10-04 | Belgium, China, France, Germany, Hungary, Italy, Japan, Mexico, Poland, Ukraine, United States of America | Belgium (LPLV), China (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Japan (LPLV), Mexico (LPLV), Poland (LPLV), Ukraine (LPLV), United States of America (LPLV) | Belgium, China, France, Germany, Hungary, Italy, Japan, Mexico, Poland, Ukraine, United States of America | 25 | 97 | 69 | 392 | 367 | 294 | 391 | 0 | 25 | 366 | 0 | 114 | 252 |  |  | 2019-09-26 | 2019-09-24 |  |  | 2020-04-22 | 2020-04-23 |  |  | 2020-09-15 | 2020-09-29
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0863 | Study Archived | Lacosamide Omeprazole Interaction | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Goldammer N | Beinhauer-Zellenka U | [5 empty] | Yes | Open-label multiple dose trial to evaluate the pharmacokinetic effect of Lacosamide on Omeprazole and vice versa in healthy male white subjects | Epilepsy | Central Nervous System |  | 2005-05-06 | 2005-04-28 |  | 2010-08-11: 2005-06-13; 2010-11-23: 2005-08-22; 2012-04-02: 2005-08-23; 2012-06-29: 2005-10-20; 2012-08-16: 2005-12-05; 2012-10-22: 2006-02-17; 2013-06-11: 2006-03-31 | Germany | Germany (Created) |  | 1 | 0 | 0 | 34 | 34 | 34 | 44 | 8 | 0 | 36 | 0 | 2 | 34
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0887 | CSR Approved | Proof of Concept Trial to Assess Efficacy and Safety of 400m | Phase II | Double Blind | UCB Pharma Global | Neurology | UCB Pharma Global | Derby B | Christopher K | [5 empty] | No | A Parallel, Randomized, Double-Blind, Placebo Controlled Multicenter Trial to Assess the Efficacy and Safety of 400mg/day Lacosamide in Subjects with Signs and Symptoms Associated with Fibromyalgia Syndrome | Fibromyalgia | Immunology |  | 2006-06-21 | 2006-06-21 |  | 2010-08-11: 2006-09-20; 2010-11-23: 2006-10-24; 2012-04-02: 2007-11-16; 2012-06-29: 2008-02-29; 2012-08-16: 2008-05-13; 2012-10-22: 2008-08-06; 2013-06-11: 2008-10-13 | United States of America | United States of America (Created) |  | 20 | 0 | 0 | 160 | 160 | 120 | 0 | 0 | 0 | 163 | 24 | 52 | 87
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0902 | Study Archived | Lacosamide Monotherapy Epilepsy Trial | Phase III | Double Blind | Clinical Development USA | CNS | UCB Pharma Global | Thierault S | Driver D | N/A | Chiltern International |  |  | adults | No | A Historical-controlled, Multicenter, Double-blind, Randomized Trial to Assess the Efficacy and Safety of Conversion to Lacosamide 400mg/day Monotherapy in Subjects with Partial-onset Seizures | Indication for Neuro Psychiatry | Central Nervous System | SP0902 is a parent study of SP0904 |  | 2006-09-26 |  | 2007-04-23 | 2007-06-15 | 2007-08-02 | 2012-04-16 | 2012-05-18 |  | 2012-12-06 |  | 2013-02-28 |  | 2013-04-01 |  | 2013-06-13 | Australia, Austria, Canada, Denmark, France, Germany, Ireland, Italy, Poland, Spain, United Kingdom, United States of America | Australia (LPLV), Austria (LPLV), Canada (LPLV), Denmark (LPLV), France (LPLV), Germany (LPLV), Ireland (LPLV), Italy (LPLV), Poland (LPLV), Spain (LPLV), Switzerland (1st Site Initiation (Cancelled)), United Kingdom (LPLV), United States of America (LPLV) | Australia, Austria, Canada, Denmark, France, Germany, Ireland, Italy, Poland, Spain, United Kingdom, United States of America | 130 | 213 | 160 | 451 | 451 | 215 | 819 | 0 | 392 | 427 | 0 | 164 | 263
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0903 | Study Archived | Evaluation of drug abuse potential of lacosamide | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | Yes | Single-site, randomized, double-blind, placebo and active comparator-controlled crossover study to evaluate the drug abuse potential of lacosamide in healthy subjects with a history of recreational CNS depressant use | Epilepsy | Central Nervous System |  | 2006-08-25 | 2006-08-28 |  | 2010-08-11: 2006-09-27; 2010-11-23: 2006-11-06; 2012-04-02: 2007-01-09; 2012-06-29: 2007-03-05; 2012-08-16: 2007-03-21; 2012-10-22: 2007-04-25; 2013-06-11: 2007-06-15 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0904 | Study Archived | Lacosamide Monotherapy Epilepsy Trial - Open-label-Extension | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Thierault S | Driver D | N/A | Chiltern International |  |  | adults | No | A Multicenter, Open-Label Extension Trial to Assess the Long-term Use of Lacosamide Monotherapy and Safety of Lacosamide Monotherapy and Adjunctive Therapy in Subjects with Partial-Onset Seizures | Indication for Neuro Psychiatry | Central Nervous System | SP0904 is an extension of SP0902 |  | 2007-03-16 |  | 2007-04-23 | 2007-10-24 | 2008-02-20 | 2012-11-30 | 2012-12-06 |  | 2014-12-10 |  | 2015-01-23 |  | 2015-02-05 |  | 2015-04-29 | Australia, Canada, Denmark, Germany, Italy, Poland, Spain, United Kingdom, United States of America | Australia (LPLV), Canada (LPLV), Denmark (LPLV), Germany (LPLV), Italy (LPLV), Poland (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Canada, Denmark, Germany, Italy, Poland, Spain, United Kingdom, United States of America | 130 | 122 | 108 | 294 | 294 | 200 | 322 | 0 | 0 | 322 | 0 | 111 | 211
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0905 | CSR Approved | A Proof of Concept Trial of 400mg/day LCM in Subjects with O | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Hoepken B | [6 empty] | No | A multi-centre, randomized, double-blind, placebo controlled trial to assess the efficacy and safety of 400mg/day Lacosamide in subjects with osteoarthritis of the knee | Osteoarthritis | Immunology |  | 2006-10-05 | 2006-10-05 |  | 2010-08-11: 2006-11-20; 2010-11-23: 2007-03-29; 2012-04-02: 2007-07-04; 2012-06-29: 2007-11-23; 2012-08-16: 2008-02-26; 2012-10-22: 2008-06-24; 2013-06-11: 2008-09-18 | Czech Republic, Germany, Hungary, Poland, Romania, Sweden, United Kingdom | Czech Republic (1st Site Initiation), Germany (1st Site Initiation), Hungary (1st Site Initiation), Poland (1st Site Initiation), Romania (1st Site Initiation), Sweden (1st Site Initiation), United Kingdom (1st Site Initiation) | Czech Republic, Germany, Hungary, Poland, Romania, Sweden, United Kingdom | 31 | 31 | 0 | 235 | 194 | 194 | 194 | 0 | 45 | 149 | 0 | 6 | 143
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0906 | CSR Approved | Lacosamide for Migraine Prophylaxis | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Kenney P | [6 empty] | No | A multi-centre, randomized, double-blind, placebo controlled trial to assess the efficacy and safety of 100mg/day and 300mg/day Lacosamide for migraine prophylaxis | Migraine prophylaxis | Central Nervous System |  | 2006-10-03 | 2006-10-03 |  | 2006-11-14 | 2007-02-15 | 2007-02-15 |  | 2008-01-18 |  | 2008-07-17 |  | 2008-09-29 |  | 2008-11-21 |  | 2009-05-12 | United States of America | United States of America (Created) |  | 20 | 0 | 0 | 252 | 192 | 192 | 394 | 0 | 0 | 218 | 1 | 55 | 162
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0923 | Created (Cancelled) | Short Title to be entered, Max. Length of Title is 100 Chara | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Beaman M | Kime J | [5 empty] | No | Long Title to be entered | Epilepsy | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0924 | Created (Cancelled) | Short Title to be entered, Max. Length of Title is 100 Chara | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Beaman M | Kime J | [5 empty] | No | Long Title to be entered | Epilepsy | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0925 | Study Archived | Safety of Adjunctive IV Followed by Oral Lacosamide in Subje | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Yates T | Bonny M | [5 empty] | No | A Multicenter, Open-Label Trial to Assess the Safety and Tolerability of a Single Intravenous Loading Dose of Lacosamide Followed by Oral Lacosamide Maintenance as Adjunctive Therapy in Subjects with Partial-Onset Seizures |  |  | SP0925 is a parent study of SP0926 |  | 2007-06-21 |  | 2010-08-11: 2007-10-21; 2010-11-23: 2008-04-08; 2012-04-02: 2009-09-11; 2012-06-29: 2009-09-23; 2012-08-16: 2009-11-18; 2012-10-22: 2010-01-29; 2013-06-11: 2010-05-26 | United States of America | United States of America (LPLV) | United States of America | 10 | 10 | 8 | 100 | 100 | 100 | 118 | 0 | 18 | 100 | 0 | 8 | 92
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0926 | Study Archived | Long-term Safety of Lacosamide as Adjunctive Therapy in Subj | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Yates T | Bonny M | [5 empty] | No | A Multicenter, Open-Label Extension Trial to Assess the Long-Term Safety and Tolerability of Lacosamide as Adjunctive Therapy in Subjects with Partial-Onset Seizures | Epilepsy | Central Nervous System | SP0926 is an extension of SP0925 |  | 2007-07-25 |  | 2007-11-01 | 2008-03-31 | 2008-04-22 | 2009-08-25 | 2009-09-23 | 2010-06-30 | 2010-06-15 | 2010-08-11 | 2010-08-10 | 2010-10-06 | 2010-10-07 | 2011-01-21 | 2011-01-24 | United States of America | United States of America (LPLV) | United States of America | 10 | 9 | 7 | 100 | 100 | 100 | 0 | 0 | 0 | 97 | 0 | 28 | 69
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0940 | Study Archived | Effect of LCM on CYP 3A4 activity | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | Yes | SINGLE SITE, OPEN-LABEL, NON-RANDOMIZED, PHASE 1 TRIAL TO INVESTIGATE THE INFLUENCE OF SINGLE AND REPEATED ADMINISTRATIONS OF LACOSAMIDE ON THE PHARMACOKINETICS OF MIDAZOLAM IN HEALTHY MALE SUBJECTS | Epilepsy | Central Nervous System |  |  |  |  | 2010-08-11: 2008-03-06; 2010-11-23: 2008-05-27; 2012-04-02: 2008-06-10; 2012-06-29: 2008-07-08; 2012-08-16: 2008-08-26; 2012-10-22: 2008-11-13; 2013-06-11: 2009-01-28 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0942 | Study Archived | Non-Interventional PASS to evaluate long-term safety | Non Interventional Study - Prospective | Open | Clinical Development Europe |  | Clinical Development Europe | Baukens C, Wuiame D | Baukens C, Tillery N | N/A | Monitoring CRO: PRA International GmbH | No | No | other | No | Post-authorization safety study to evaluate the long-term safety and tolerability of Vimpat as add-on therapy in epilepsy patients with partial-onset seizures who are uncontrolled on current therapy | Indication for Neuro Psychiatry | Central Nervous System |  | 2008-07-06 | 2008-07-06 | 2008-08-14 | 2008-08-14 | 2008-10-01 | 2008-09-26 | 2009-10-04 | 2011-03-09 | 2010-04-04 | 2012-03-09 | 2010-05-24 | 2012-04-27 | 2010-07-27 | 2012-06-08 | 2010-10-04 | 2012-12-13 | France, Germany, Netherlands, Spain, United Kingdom | France (LPLV), Germany (LPLV), Netherlands (LPLV), Spain (LPLV), United Kingdom (LPLV) | France, Germany, Netherlands, Spain, United Kingdom | 60 | 86 | 71 | 1000 | 1000 | 1000 | 0 | 0 | 0 | 1005 | 6 | 492 | 506
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0944 | Created (Cancelled) | Long-term safety and tolerability evaluation of LCM as add-o | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Beaman M | Kime J | [5 empty] | No |  |  |  |  | 2016-08-19 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0945 | Created (Cancelled) | VELCOME (Vimpat: Non Interventional Study with Lacosamide in | Phase IV |  | Affiliates |  | Affiliates | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0952 | CSR Approved | Multiple dose trial to evaluate the pharmacokinetics and tol | Phase I | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Kim C | [6 empty] | Yes | Single-site, randomized, double-blind, placebo-controlled, parallel-group, repeated dose trial to evaluate the pharmacokinetics and safety/tolerability of lacosamide in 3 dosages (50/100/200mg) in healthy Korean subjects | Epilepsy | Central Nervous System |  | 2008-04-30 |  |  | 2008-07-25 | 2008-09-30 | 2008-11-10 |  | 2009-01-08 |  | 2009-02-02 |  | 2009-04-02 |  | 2009-06-06 |  | 2009-10-19 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0954 | Study Archived | Open-label trial evaluating efficacy of LCM as first add-on | Phase IV | Open | UCB Pharma Global | GMA Neurology / Psychiatry | Global Medical Affairs | Smit R | Kime J | N/A | PAREXEL |  |  | other | No | A Multi-center, Open-label, Trial to Assess the Efficacy of Lacosamide as First Add-on Treatment in Subjects with Partial-onset Seizures (FILAE) | Epilepsy | Central Nervous System | SP0954 is a parent study of EP0020 | 2009-02-20 | 2009-02-20 |  | 2009-04-23 | 2009-07-30 | 2009-08-05 | 2011-02-02 | 2012-12-20 |  | 2013-08-09 |  | 2013-09-16 |  | 2014-01-15 |  | 2014-01-20 | Austria, Bulgaria, Czech Republic, Denmark, Finland, France, Greece, Italy, Mexico, Romania, Russian Federation, Spain, Turkey, United States of America | Austria (LPLV), Bulgaria (LPLV), Czech Republic (LPLV), Denmark (LPLV), Finland (LPLV), France (LPLV), Germany (1st Site Initiation (Cancelled)), Greece (LPLV), Hungary (1st Site Initiation (Cancelled)), Italy (LPLV), Mexico (LPLV), Romania (LPLV), Russian Federation (LPLV), Spain (LPLV), Switzerland (1st Site Initiation (Cancelled)), Turkey (LPLV), United States of America (LPLV) | Austria, Bulgaria, Czech Republic, Denmark, Finland, France, Greece, Italy, Mexico, Romania, Russian Federation, Spain, Turkey, United States of America | 130 | 152 | 97 | 656 | 656 | 522 | 513 | 0 | 52 | 461 | 0 | 140 | 321
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0955 | Study Archived | BE trial | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Strauss B | [6 empty] | Yes | Single-site, randomized, open label, 2 period crossover trial to investigate the bioequivalence between 2 different formulations of 200mg lacosamide given as one 200mg tablet and two 100mg tablets in healthy male subjects | Epilepsy | Central Nervous System |  | 2008-05-19 |  |  | 2010-08-11: 2008-06-12; 2010-11-23: 2008-07-25; 2012-04-02: 2008-07-31; 2012-06-29: 2008-08-18; 2012-08-16: 2008-09-19; 2012-10-22: 2008-10-20; 2013-06-11: 2008-11-20 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0956 | Created (Cancelled) | Lacosamide Registration Study in India | Phase III | Open | Affiliates |  | Affiliates | Ambarkhane S | Weinsberg F | [5 empty] | No |  |  |  |  | 2009-01-29 | [15 empty] | India | India (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0958 | Created (Cancelled) | None | Phase IV |  | UCB Pharma Global |  | UCB Pharma Global | Hummel F | [6 empty] | No | Non-interventional multi-center study to evaluate the retention rate of Lacosamide (LCM) as add-on therapy in epilepsy patients with partial onset seizures with and without secondary generalization up to 2 years after treatment initiation. | Epilepsy | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0961 | Study Archived | Open label pilot study | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global |  |  | N/A | PRA |  |  | other | No | An open-label pilot study to assess the safety of oral lacosamide as adjunctive therapy for uncontrolled primary generalized tonic-clonic seizures in subjects with idiopathic generalized epilepsy | Epilepsy | Central Nervous System | SP0961 is a parent study of SP0962 | 2009-03-05 | 2009-03-03 |  | 2009-08-31 | 2010-05-14 | 2010-05-17 | 2010-11-17 | 2011-05-31 | 2011-09-20 | 2011-08-30 | 2011-11-15 | 2011-11-11 | 2012-01-10 | 2012-01-09 | 2012-04-03 | 2012-08-31 | United States of America | United States of America (LPLV) | United States of America | 10 | 27 | 20 | 60 | 45 | 45 | 68 | 0 | 19 | 49 | 0 | 9 | 40
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0962 | Study Archived | Open label extension study | Phase II | Open | Clinical Development USA | CNS | Clinical Development USA |  |  | N/A | PRA |  |  | other | No | An Open-Label Extension Study to Assess the Safety and Seizure Frequency Associated with Long-Term Oral Lacosamide for Uncontrolled Primary Generalized Tonic-Clonic Seizures in Subjects with Idiopathic Generalized Epilepsy | Epilepsy | Central Nervous System | SP0962 is an extension of SP0961 | 2009-07-24 | 2009-07-30 |  | 2009-09-24 | 2010-08-18 | 2010-08-18 | 2011-03-09 | 2011-08-30 |  | 2012-10-25 |  | 2012-12-11 |  | 2013-02-15 |  | 2013-06-05 | United States of America | United States of America (LPLV) | United States of America | 10 | 19 | 19 | 45 | 45 | 45 | 0 | 0 | 0 | 39 | 0 | 10 | 29
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0963 | Created (Cancelled) | Investigate LCM safety & efficacy profile | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Baukens C | Tillery N | [5 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2010-04-22 |  | 2010-01-15 | 2010-11-03: 2010-08-03; 2011-09-27: 2012-02-02; 2012-06-29: 2012-11-29; 2012-08-13: 2012-10-04; 2012-10-09: 2012-11-29; 2013-03-26: 2013-03-21 |  |  |  | 120 | 0 | 0 | 655 | 522 | 470 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0966 | Study Archived | A multi-center, open label, exploratory study to investigate | Phase II | Open | GCSO | Neurology | GCSO | Bullock E | Grose-Hodge R | PRA | PRA | Yes | No | paediatrics | No | A MULTI-CENTER, OPEN-LABEL, EXPLORATORY STUDY TO INVESTIGATE THE SAFETY AND EFFICACY OF LACOSAMIDE AS ADJUNCTIVE THERAPY IN SUBJECTS >=1 MONTH TO <18 YEARS WITH EPILEPSY SYNDROMES ASSOCIATED WITH GENERALIZED SEIZURES | Epilepsy | Central Nervous System | SP0966 is a feeder study of EP0060, SP0848 | 2012-03-02 | 2012-02-24 |  | 2012-05-31 | 2014-02-13 | 2014-02-13 | 2016-02-06 | 2017-12-04 23:00 |  | 2017-12-19 23:00 |  | 2018-05-25 |  | 2018-06-14 |  | 2018-08-27 | France, Hungary, Mexico, Poland, United States of America | France (LPLV), Germany (1st Site Initiation (Cancelled)), Hungary (LPLV), Mexico (LPLV), Poland (LPLV), United States of America (LPLV) | France, Hungary, Mexico, Poland, United States of America | 31 | 31 | 18 | 70 | 55 | 55 | 70 | 0 | 15 | 55 | 0 | 11 | 44
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0967 | Study Archived | Study of LCM as Adj. tx subjects>=1 mo to <4 yrs in POS | Phase III | Double Blind | GCSO | Neurology | GCSO | Moeltgen H | Russell R | PRA | PRA | Yes | Yes | paediatrics | No | A Multicenter, Double-blind, Randomized, Placebo-controlled, Parallel-group Study to Investigate the Efficacy and Safety of Lacosamide as Adjunctive Therapy in Subjects with Epilepsy >=1 month to <4 years of Age with Partial-onset Seizures | Epilepsy | Central Nervous System | SP0967 is a "sister" study of SP0969 and is a feeder study of EP0034 | 2013-04-29 | 2013-05-01 |  | 2014-05-29 | 2014-10-17 | 2015-06-05 | 2017-02-28 | 2020-02-21 11:00 | 2018-01-19 | 2020-05-28 10:00 | 2018-02-28 | 2020-06-12 | 2018-03-20 | 2020-06-24 | 2018-06-15 | 2020-08-24 | Argentina, Brazil, Bulgaria, China, Croatia, Czech Republic, France, Georgia, Greece, Hungary, Israel, Italy, Lithuania, Mexico, Moldavia, Philippines, Poland, Portugal, Romania, Russian Federation, Serbia, Slovakia, South Korea, Taiwan, Thailand, Ukraine, United States of America | Argentina (LPLV), Australia (1st Site Initiation (Cancelled)), Belgium (1st Site Initiation (Cancelled)), Brazil (LPLV), Bulgaria (LPLV), Chile (1st Site Initiation (Cancelled)), China (LPLV), Colombia (1st Site Initiation (Cancelled)), Croatia (LPLV), Czech Republic (LPLV), Finland (1st Site Initiation (Cancelled)), France (LPLV), Georgia (LPLV), Germany (1st Site Initiation (Cancelled)), Greece (LPLV), Hungary (LPLV), Israel (LPLV), Italy (LPLV), Lithuania (LPLV), Mexico (LPLV), Moldavia (LPLV), Philippines (LPLV), Poland (LPLV), Portugal (LPLV), Romania (LPLV), Russian Federation (LPLV), Serbia (LPLV), Slovakia (LPLV), South Korea (LPLV), Spain (1st Site Initiation (Cancelled)), Taiwan (LPLV), Thailand (LPLV), Turkey (1st Site Initiation (Cancelled)), Ukraine (LPLV), United States of America (LPLV) | Argentina, Brazil, Bulgaria, China, Croatia, Czech Republic, France, Georgia, Greece, Hungary, Israel, Italy, Lithuania, Mexico, Moldavia, Philippines, Poland, Portugal, Romania, Russian Federation, Serbia, Slovakia, South Korea, Taiwan, Thailand, Ukraine, United States of America | 170 | 180 | 89 | 364 | 244 | 244 | 355 | 0 | 100 | 255 | 0 | 13 | 242
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0969 | Study Archived | Multi DB Placebo Control Paral Study of LCM POS age 4 to 16 | Phase III | Double Blind | GCSO | Neurology | GCSO | Webers T | Bonny M | PRA | SPI PRA | Yes | Yes | paediatrics | No | A MULTICENTER, DOUBLE-BLIND, RANDOMIZED, PLACEBO-CONTROLLED, PARALLEL-GROUP STUDY TO INVESTIGATE THE EFFICACY AND SAFETY OF LACOSAMIDE AS ADJUNCTIVE THERAPY IN SUBJECTS WITH EPILEPSY >=4 YEARS TO <17 YEARS OF AGE WITH PARTIAL-ONSET SEIZURES | Epilepsy | Central Nervous System | SP0969 is a feeder study of EP0034, EP0060 | 2011-09-19 | 2011-09-19 |  | 2013-05-23 | 2013-08-22 | 2013-08-29 | 2016-05-21 | 2016-09-06 | 2016-12-26 | 2017-01-24 | 2017-02-18 | 2017-02-13 | 2017-04-17 | 2017-03-31 | 2017-06-26 | 2017-06-16 | Argentina, Australia, Belgium, Bulgaria, Colombia, Croatia, Czech Republic, Estonia, Georgia, Hungary, Israel, Italy, Latvia, Lithuania, Mexico, Montenegro, Poland, Romania, Russian Federation, Serbia, Slovakia, Slovenia, South Korea, Taiwan, Thailand, Ukraine, United Kingdom, United States of America | Argentina (LPLV), Australia (LPLV), Belgium (LPLV), Bulgaria (LPLV), Colombia (LPLV), Croatia (LPLV), Czech Republic (LPLV), Estonia (LPLV), France (1st Site Initiation (Cancelled)), Georgia (LPLV), Hungary (LPLV), Israel (LPLV), Italy (LPLV), Latvia (LPLV), Lithuania (LPLV), Mexico (LPLV), Montenegro (LPLV), Poland (LPLV), Romania (LPLV), Russian Federation (LPLV), Serbia (LPLV), Slovakia (LPLV), Slovenia (LPLV), South Korea (LPLV), Spain (1st Site Initiation (Cancelled)), Sweden (1st Site Initiation (Cancelled)), Taiwan (LPLV), Thailand (LPLV), Turkey (1st Site Initiation (Cancelled)), Ukraine (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Argentina, Australia, Belgium, Bulgaria, Colombia, Croatia, Czech Republic, Estonia, Georgia, Hungary, Israel, Italy, Latvia, Lithuania, Mexico, Montenegro, Poland, Romania, Russian Federation, Serbia, Slovakia, Slovenia, South Korea, Taiwan, Thailand, Ukraine, United Kingdom, United States of America | 155 | 153 | 115 | 370 | 308 | 250 | 405 | 0 | 62 | 343 | 1 | 40 | 302
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0978 | Study Archived | VICTOR- multicenter, open-label, single-arm study | Phase III | Open | UCB Pharma Global | GMA Neurology / Psychiatry | UCB Pharma Global | Bare S | Baukens C | N/A | PRA | No | No | adults | No | A MULTICENTER, OPEN-LABEL, SINGLE-ARM STUDY TO EVALUATE HORMONE AND LIPID LEVELS IN MALE SUBJECTS WITH PARTIAL-ONSET SEIZURES AFTER A SWITCH OF TREATMENT FROM CARBAMAZEPINE AS ADJUNCTIVE TREATMENT TO LEVETIRACETAM TO LACOSAMIDE AS ADJUNCTIVE TREATMENT TO LEVETIRACETAM | Indication for Neuro Psychiatry | Central Nervous System |  | 2010-07-26 | 2010-08-20 | 2010-09-16 | 2010-10-24 | 2011-02-15 | 2011-07-14 | 2011-08-15 | 2013-04-09 | 2011-12-15 | 2013-04-23 | 2012-02-24 | 2014-08-15 | 2012-04-16 | 2014-09-11 | 2012-07-02 | 2014-11-25 | Austria, Germany, Spain | Austria (LPLV), Germany (LPLV), Spain (LPLV) | Austria, Germany, Spain | 15 | 11 | 5 | 35 | 28 | 28 | 13 | 0 | 2 | 11 | 0 | 1 | 10
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0980 | Study Archived | Optimising Combination Therapy on POS (OCTOPOS) | Phase III | Open | Clinical Development USA | GMA Neurology / Psychiatry | UCB Pharma Global | Doggett K | Smit R | N/A | PRA |  |  | adults | No | A Prospective, Multinational, Open-Label, Singel-Arm, Explorative Study To Evaluate The Tolerability and Efficacy Of Lacosamide When Added To Levetiracetam With Withdrawal Of The Concomitant Sodium Channel Blocking Antiepileptic Drug In Subjects With Uncontrilled Partial-Onset Seizures | Epilepsy | Central Nervous System |  |  | 2011-05-06 |  | 2011-07-25 | 2011-12-30 | 2011-12-20 | 2012-10-20 | 2013-06-28 |  | 2014-01-10 |  | 2014-03-10 |  | 2014-09-08 |  | 2014-12-08 | Australia, Bulgaria, Denmark, France, Germany, Romania, Spain, Sweden, United States of America | Australia (LPLV), Austria (1st Site Initiation (Cancelled)), Bulgaria (LPLV), Canada (1st Site Initiation (Cancelled)), Denmark (LPLV), France (LPLV), Germany (LPLV), Hungary (1st Site Initiation (Cancelled)), Romania (LPLV), Spain (LPLV), Sweden (LPLV), Switzerland (1st Site Initiation (Cancelled)), United States of America (LPLV) | Australia, Bulgaria, Denmark, France, Germany, Romania, Spain, Sweden, United States of America | 140 | 101 | 54 | 300 | 300 | 300 | 147 | 0 | 27 | 120 | 0 | 27 | 93
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0982 | Study Archived | Phase III (PGTCS) | Phase III | Double Blind | GCSO | Neurology | GCSO | Conrath P | Copetti C | PRA | PRA | Yes | Yes | other | No | A DOUBLE-BLIND, RANDOMIZED, PLACEBO-CONTROLLED, PARALLEL-GROUP, MULTICENTER STUDY TO EVALUATE THE EFFICACY AND SAFETY OF LACOSAMIDE AS ADJUNCTIVE THERAPY FOR UNCONTROLLED PRIMARY GENERALIZED TONIC-CLONIC SEIZURES IN SUBJECTS WITH IDIOPATHIC GENERALIZED EPILEPSY PHASE 3 | Epilepsy | Central Nervous System | SP0982 is a parent study of EP0012 | 2012-02-15 | 2012-02-15 |  | 2012-09-27 | 2014-11-28 | 2015-04-23 | 2017-11-28 |  | 2019-06-05 |  | 2019-06-19 | 2019-06-21 | 2019-07-01 | 2019-08-01 | 2019-08-30 | 2019-09-11 | Australia, Belgium, Brazil, Bulgaria, China, Czech Republic, France, Germany, Hungary, Israel, Italy, Japan, Mexico, Poland, Portugal, Romania, Russian Federation, Slovakia, South Korea, Spain, Taiwan, United States of America | Australia (LPLV), Belgium (LPLV), Brazil (LPLV), Bulgaria (LPLV), China (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Israel (LPLV), Italy (LPLV), Japan (LPLV), Mexico (LPLV), Poland (LPLV), Portugal (LPLV), Romania (LPLV), Russian Federation (LPLV), Slovakia (LPLV), South Korea (FPFV), Spain (LPLV), Taiwan (LPLV), Turkey (1st Site Initiation (Cancelled)), United States of America (LPLV) | Australia, Belgium, Brazil, Bulgaria, China, Czech Republic, France, Germany, Hungary, Israel, Italy, Japan, Mexico, Poland, Portugal, Romania, Russian Federation, Slovakia, South Korea, Spain, Taiwan, United States of America | 195 | 196 | 115 | 329 | 242 | 242 | 226 | 2 | 72 | 152 | 46 | 27 | 79
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0983 | Study Archived | Adult adjunctive_Vimpat | Phase I | Open | Affiliate China | CNS | Affiliate China |  |  | Parexel | PXL SPI |  |  | adults | Yes | An Open Label, Single Dose Study to Investigate the Pharmacokinetics as well as Safety and Tolerability of Lacosamide Tablets in Healthy Male and Female Chinese Subjects | Epilepsy | Central Nervous System |  |  | 2010-06-07 |  | 2012-12-06 | 2014-02-18 | 2014-02-19 | 2014-02-28 | 2014-02-26 |  | 2014-03-11 |  | 2014-05-13 |  | 2014-08-13 |  | 2014-09-09 | China | China (LPLV) | China | 1 | 1 | 1 | 12 | 12 | 12 | 21 | 0 | 9 | 12 | 0 | 0 | 12
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0984 | Protoc. Summary Approved (Cancelled) | Placebo st. in Chinese subj. w/ epilepsy of partial seiz. | Non Interventional Study - Prospective |  | UCB Pharma Global |  | UCB Pharma Global | Wang L | [6 empty] | No |  |  |  |  | 2010-05-26 | 2010-06-08 | [14 empty] | China | China (Created) |  | 6 | 0 | 0 | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0991 | Study Archived | Compassionate Use Program (F.U. of SP0774) | Compassionate Use | Open | Clinical Development Europe | CNS | UCB Pharma Global | Esch M | Copetti C | N/A | UCB |  |  | adults | No | Local/National Compassionate Use Program for access to adjuntive lacosamide in patients with partial-onset seizures prior to launch in Croatia | Indication for Neuro Psychiatry | Central Nervous System |  |  |  |  | 2010-08-11: 2010-01-25; 2010-11-23: 2010-03-16; 2011-09-27: 2010-04-29; 2012-04-02: 2010-04-16; 2012-06-29: 2014-05-30 | Croatia | Croatia (LPLV) | Croatia | 3 | 0 | 3 | 15 | 15 | 0 | 15 | 0 | 0 | 15 | 0 | 6 | 9
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0993 | Study Archived | EU Monotherapy trial, double blind, double dummy | Phase III | Double Blind / Double Dummy | GCSO | Neurology | UCB Pharma Global | Esch M, Ikeda K, Jensen L | Copetti C, Driver D, Matsuo T | N/A | PXL | Yes | Yes | other | No | A multicenter, double blind, double dummy, randomized, positive controlled study comparing the efficacy and safety of lacosamide (200 to 600mg/day) to controlled release carbamazepine (400 to 1200mg/day), used as monotherapy in subjects (>=16 years) newly or recently diagnosed with epilepsy and experiencing partial onset or generalized tonic clonic seizures | Epilepsy | Central Nervous System | SP0993 is a parent study of SP0994 | 2009-09-30 | 2010-03-02 |  | 2010-07-07 | 2010-11-17 | 2011-04-27 | 2012-11-14 | 2014-09-10 |  | 2015-08-07 |  | 2015-09-17 |  | 2015-09-30 |  | 2015-12-30 | Australia, Belgium, Bulgaria, Canada, Czech Republic, Finland, France, Germany, Greece, Hungary, Italy, Japan, Latvia, Lithuania, Mexico, Philippines, Poland, Portugal, Romania, Russian Federation, Slovakia, South Korea, Spain, Sweden, Switzerland, Thailand, Ukraine, United Kingdom, United States of America | Australia (LPLV), Belgium (LPLV), Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Greece (LPLV), Hungary (LPLV), Italy (LPLV), Japan (LPLV), Latvia (LPLV), Lithuania (LPLV), Mexico (LPLV), Philippines (LPLV), Poland (LPLV), Portugal (LPLV), Romania (LPLV), Russian Federation (LPLV), Slovakia (LPLV), South Korea (LPLV), Spain (LPLV), Sweden (LPLV), Switzerland (LPLV), Thailand (LPLV), Ukraine (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Belgium, Bulgaria, Canada, Czech Republic, Finland, France, Germany, Greece, Hungary, Italy, Japan, Latvia, Lithuania, Mexico, Philippines, Poland, Portugal, Romania, Russian Federation, Slovakia, South Korea, Spain, Sweden, Switzerland, Thailand, Ukraine, United Kingdom, United States of America | 200 | 241 | 185 | 1000 | 878 | 790 | 1035 | 0 | 147 | 888 | 0 | 336 | 552
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0994 | Study Archived | EU Monotherapy trial, dble blind, dble dummy f/u from SP0993 | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Bullock E, Ikeda K | Grose-Hodge R, Matsuo T | N/A | PXL | Yes | Yes | other | No | A MULTICENTER, DOUBLE-BLIND, DOUBLE-DUMMY, FOLLOW-UP STUDY EVALUATING THE LONG-TERM SAFETY OF LACOSAMIDE (200 TO 600MG/DAY) IN COMPARISON WITH CONTROLLED-RELEASE CARBAMAZEPINE (400 TO 1200MG/DAY), USED AS MONOTHERAPY IN SUBJECTS WITH PARTIAL-ONSET OR GENERALIZED TONIC-CLONIC SEIZURES >=16 YEARS OF AGE COMING FROM THE SP0993 STUDY | Epilepsy | Central Nervous System | SP0994 is a follow up of SP0993 and is a parent study of SP1042 | 2010-04-08 | 2010-04-08 |  | 2010-08-03 | 2011-06-17 | 2012-05-16 | 2014-03-19 | 2015-08-05 |  | 2017-01-03 |  | 2017-04-04 |  | 2017-04-20 |  | 2017-06-26 | Australia, Belgium, Bulgaria, Canada, Czech Republic, Finland, France, Germany, Greece, Hungary, Italy, Japan, Latvia, Lithuania, Mexico, Philippines, Poland, Portugal, Romania, Russian Federation, Slovakia, South Korea, Spain, Sweden, Switzerland, Thailand, Ukraine, United Kingdom, United States of America | Australia (LPLV), Belgium (LPLV), Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Greece (LPLV), Hungary (LPLV), Italy (LPLV), Japan (LPLV), Latvia (LPLV), Lithuania (LPLV), Mexico (LPLV), Philippines (LPLV), Poland (LPLV), Portugal (LPLV), Romania (LPLV), Russian Federation (LPLV), Slovakia (LPLV), South Korea (LPLV), Spain (LPLV), Sweden (LPLV), Switzerland (LPLV), Thailand (LPLV), Ukraine (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Belgium, Bulgaria, Canada, Czech Republic, Finland, France, Germany, Greece, Hungary, Italy, Japan, Latvia, Lithuania, Mexico, Philippines, Poland, Portugal, Romania, Russian Federation, Slovakia, South Korea, Spain, Sweden, Switzerland, Thailand, Ukraine, United Kingdom, United States of America | 200 | 158 | 150 | 527 | 527 | 316 | 553 | 0 | 0 | 553 | 0 | 162 | 391
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP0998 | Study Archived | Comparing neuropsychological effects of LCM and CBZ IR | Phase I | Double Blind / Double Dummy | GCSO | Neurology | UCB Pharma Global | Dedeken P, Forbis K | Beaman M, Laranjo S | N/A | UCB |  |  | adults | No | A multicenter, randomized, double-blind, double-dummy, 2-period crossover study of neuropsychological effects of lacosamide and carbamazepine immediate release in healthy subjects | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2010-08-10 |  | 2011-06-01 | 2012-01-30 | 2012-05-10 | 2013-05-09 | 2013-08-23 |  | 2014-01-21 |  | 2014-05-29 |  | 2014-10-06 |  | 2014-12-03 | United States of America | United States of America (LPLV) | United States of America | 2 | 2 | 2 | 70 | 50 | 40 | 182 | 0 | 122 | 60 | 0 | 16 | 44
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP1007 | Study Archived | SELF- Open-label study of LCM(flexible dosing)in POS (France | Phase IV | Open | Affiliates - France |  | Affiliates - France | Coulbaut S, Friedel C |  | N/A |  |  |  | adults | No | A multicenter, open label study to evaluate the tolerability, safety and efficacy of Lacosamide (200mg-400mg/day) as add-on therapy for patients with partial onset epilepsy using a flexible dose-escalation schedule and individualized maintenance doses |  |  |  | 2009-12-30 | 2010-02-11 |  | 2010-03-16 | 2010-07-06 | 2010-06-29 | 2011-05-31 | 2011-05-31 |  | 2011-12-19 |  | 2012-03-15 |  | 2012-10-23 |  | 2012-10-26 | France | France (LPLV) | France | 50 | 43 | 30 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP1021 | Study Archived | NIS of LCM in POS (Belgium) | Non Interventional Study - Prospective | Open | Affiliates | GMA Neurology / Psychiatry | Affiliates | Baukens C, Dedeken P | Laranjo S, Tillery N |  | CPM, Peter Dedeken |  |  | other | No | Multicenter observational drug utilization study in Belgium to evaluate the use of Vimpat in Clinical Practice as adjunctive treatment of Partial Onset Epilepsy in subjects aged 16 and older |  |  |  | 2010-01-14 | 2010-05-28 |  | 2010-05-28 | 2010-09-24 | 2010-09-24 | 2011-08-24 | 2011-08-24 |  | 2012-03-06 |  | 2012-04-30 |  | 2012-09-03 |  | 2012-09-04 | Belgium | Belgium (LPLV) | Belgium | 23 | 23 | 22 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP1023 | Protoc. Summary Approved (Cancelled) | RETROKID - Retrospective study of LCM in children (Germany) | Non Interventional Study - Prospective |  | Affiliates - Germany | GMA Neurology / Psychiatry | Affiliates - Germany | Joeres L |  | Parexel | SPI PXL |  |  |  | No |  |  |  |  | 2011-02-22 | 2011-02-21 | [14 empty] | Germany | Germany (Created) |  | 30 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP1029 | Created (Cancelled) | Epidemiological retrospective study | Non Interventional Study - Retrospective |  | Affiliates - Spain |  | UCB Pharma Global | Cara C | [6 empty] | No | Cross-sectional, epidemiological, multicenter study to analyze predictive factors related to DICE in patients with epilepsy. |  |  |  | 2010-05-12 | [15 empty] | Spain | Spain (Created) |  | 50 | 0 | 0 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP1031 | Study Archived | Multicenter Open Label. Effects on sleep in healthy subjects | Phase I | Open | GCSO |  |  | Collini E | Beaman M | N/A |  |  |  | adults | Yes |  | Epilepsy | Central Nervous System |  | 2011-05-05 | 2011-05-04 |  | 2011-08-25 |  | 2012-01-16 | 2012-06-30 | 2012-06-08 |  | 2012-07-16 |  | 2012-08-17 |  | 2012-10-12 |  | 2013-03-18 | United States of America | United States of America (LPLV) | United States of America | 4 | 4 | 3 | 31 | 25 | 25 | 55 | 0 | 28 | 27 | 0 | 2 | 25
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP1039 | Study Archived | PK characterization of LCM MR formulations | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Mccabe S | [6 empty] | Yes | SINGLE SITE, OPEN-LABEL, RANDOMIZED, SINGLE DOSE, 3-WAY CROSS-OVER, PILOT STUDY TO COMPARE THE PHARMACOKINETICS OF LACOSAMIDE WHEN GIVEN AS AN ORAL MODIFIED RELEASE OR IMMEDIATE RELEASE TABLET IN 12 HEALTHY MALE SUBJECTS |  |  |  | 2010-03-19 | 2010-03-23 |  | 2010-05-06 | 2010-07-12 | 2010-07-15 | 2010-07-28 | 2010-08-04 | 2010-09-08 | 2010-09-08 | 2010-10-06 | 2010-10-05 | 2010-11-19 | 2010-11-12 | 2011-01-12 | 2011-09-12 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 50 | 12 | 12 | 33 | 0 | 19 | 14 | 0 | 2 | 12
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP1042 | Study Archived | Long-term FU study evaluating safety/tolerability of LCM | Phase III | Open | GCSO | Neurology | GCSO | Dedeken P, Howerton C, Ikeda K | Laranjo S, Matsuo T, Smit R | Parexel | PAREXEL | No | Yes | adults | No | A MULTICENTER, OPEN-LABEL, FOLLOW-UP STUDY TO ASSESS THE LONG-TERM USE OF LACOSAMIDE (FLEXIBLE DOSE FROM 200 TO 600MG/DAY) USED AS MONOTHERAPY IN SUBJECTS WHO COMPLETED SP0994 AND RECEIVED LACOSAMIDE MONOTHERAPY TREATMENT | Epilepsy | Central Nervous System | SP1042 is a follow up of SP0994 | 2015-03-04 | 2015-03-04 |  | 2015-05-12 | 2015-09-29 | 2016-01-18 | 2016-04-08 | 2016-11-29 | 2019-11-29 | 2020-01-06 | 2020-02-04 | 2020-02-04 | 2020-02-07 | 2020-02-25 | 2020-05-05 | 2020-07-02 | Bulgaria, Finland, France, Germany, Japan, Latvia, Mexico, Philippines, Poland, Romania, Russian Federation, South Korea, Sweden, Switzerland, Ukraine | Bulgaria (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Japan (LPLV), Latvia (LPLV), Mexico (LPLV), Philippines (LPLV), Poland (LPLV), Romania (LPLV), Russian Federation (LPLV), South Korea (LPLV), Sweden (LPLV), Switzerland (LPLV), Ukraine (LPLV) | Bulgaria, Finland, France, Germany, Japan, Latvia, Mexico, Philippines, Poland, Romania, Russian Federation, South Korea, Sweden, Switzerland, Ukraine | 67 | 47 | 46 | 119 | 119 | 119 | 106 | 0 | 0 | 106 | 0 | 21 | 85
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP1046 | CSR Approved | Phase I PK Study with Tablet Adm in JPN and CHN subjects | Phase I |  | Clinical Development Japan | Clinical Pharmaco | R & D | Okagaki T, Watanabe S | Cain D, Tsujii A | [5 empty] | Yes | A PHASE 1, RANDOMIZED, DOUBLE-BLIND, PLACEBO CONTROLLED, SINGLE-CENTER, SINGLE DOSE, THREE-WAY CROSS-OVER STUDY TO EVALUATE THE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF LACOSAMIDE TABLETS IN HEALTHY MALE CHINESE AND JAPANESE SUBJECTS | Epilepsy | Central Nervous System |  | 2010-08-30 | 2010-09-06 |  | 2010-11-16 | 2011-03-01 | 2011-03-29 | 2011-05-09 | 2011-06-01 | 2011-06-29 | 2011-06-29 | 2011-08-19 | 2011-08-12 | 2011-09-29 | 2011-10-04 | 2012-02-07 | 2012-01-20 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 48 | 36 | 36 | 54 | 0 | 18 | 36 | 0 | 0 | 36
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP1047 | Study Archived | A multicenter, open‑label study to investigate the pharmacok | Phase I | Open | UCB Pharma Global | Neurology | UCB Pharma Global | Thierault S | Driver D | N/A | UCB |  |  | paediatrics | No | A multicenter, open-label study to investigate the pharmacokinetics of commercial lacosamide oral formulation as therapy in children (aged 1 month to 17 years) with epilepsy | Epilepsy | Central Nervous System |  | 2010-07-22 | 2010-07-13 | 2010-12-14 | 2010-12-14 | 2011-06-24 | 2011-04-11 | 2011-08-10 | 2014-07-29 | 2014-09-27 | 2014-07-29 | 2014-10-25 | 2014-10-24 | 2014-11-08 | 2014-11-05 | 2015-02-03 | 2014-12-18 | United States of America | United States of America (LPLV) | United States of America | 3 | 9 | 5 | 35 | 35 | 35 | 34 | 0 | 2 | 32 | 0 | 0 | 32
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP1053 | Protocol Approved (Cancelled) | Long Term Safety LCM in subjects W/Pos | Phase III |  | Affiliates |  | Affiliates | Epik G | Kasabaligil A | [5 empty] | No | OPEN-LABEL MULTICENTER EXTENSION STUDY TO ASSESS THE LONG-TERM SAFETY OF LACOSAMIDE AS ADJUNCTIVE THERAPY IN TURKISH SUBJECTS WITH PARTIAL-ONSET SEIZURES. PHASE 3B |  |  |  | 2011-01-17 | 2011-05-17 |  | 2015-05-12: 2011-05-17 | Turkey | Turkey (Created) |  | 9 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP1061 | Protocol Approved (Cancelled) | Retrospective study of LCM as first add-on in POS (Spain) | Non Interventional Study - Retrospective | Open | Affiliates - Spain | CNS | Affiliates - Spain | Alcazar J |  | N/A |  |  |  | adults | No |  |  |  |  | 2011-11-30 | 2011-11-21 |  | 2015-05-12: 2011-11-21 | Spain | Spain (Created) |  | 40 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | Central Nervous System | SP1065 | Study Archived | Influence of Vimpat on Dosing of Concomitant AEDs | Non Interventional Study - Prospective | Open | GCSO | Neurology | Affiliates | Webers T | Bonny M | PRA | SPI PRA | No | No | adults | No | A non-interventional, observational study evaluating changes in total drug load and seizure frequency using VIMPAT (Lacosamide) in daily clinical practice in Combination Therapy with sODium Channel-blocking AEDs or non Sodium channel blocking AEDs (VICTOS) | Epilepsy | Central Nervous System |  | 2011-11-26 | 2012-03-15 |  | 2012-03-15 | 2012-07-31 | 2012-07-11 | 2013-07-10 | 2014-12-22 |  | 2015-08-18 |  | 2015-08-19 |  | 2015-09-24 |  | 2016-04-12 | Austria, Germany | Austria (LPLV), Germany (LPLV) | Austria, Germany | 50 | 64 | 42 | 374 | 374 | 280 | 315 | 0 | 0 | 315 | 0 | 63 | 252
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0611 | Final TFLs released | phase IIa pilot trial of harkoseride in subjects with chroni | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Marshall S | [6 empty] | No | A phase IIa, single centre, open-label trial to assess the efficacy and safety of ascending doses of SPM 927 in subjects with chronic refractory neuropathic pain. | Neuropathic pain | Central Nervous System | SP0611 is a parent study of SP0647 | 2000-08-18 | 2000-08-18 |  | 2015-05-12: 2000-10-23; 2016-01-18: 2001-01-02; 2016-11-29: 2001-01-15; 2020-01-06: 2001-04-27; 2020-02-25: 2001-06-15 | Ireland | Ireland (Created) |  | 1 | 0 | 0 | 25 | 20 | 20 | 0 | 0 | 0 | 25 | 11 | 2 | 12
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0614 | Final TFLs released | Harkoseride in Diabetic Neuropathy/placebo controlled, doubl | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Simpson J | Driver D | [5 empty] | No | A Randomized, Double-Blind Placebo Controlled Trial to Investigate Safety and Efficacy of SPM 927 in Painful Diabetic Neuropathy | Neuropathic pain | Central Nervous System |  | 2000-11-10 | 2000-11-10 |  | 2015-05-12: 2001-03-08; 2016-01-18: 2001-06-03; 2016-11-29: 2002-10-11; 2020-01-06: 2003-01-22; 2020-02-25: 2003-04-29 | United States of America | United States of America (Created) |  | 25 | 0 | 0 | 140 | 120 | 100 | 0 | 0 | 0 | 119 | 0 | 25 | 94
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0647 | Study Archived | Open-label continuation trial of oral SPM 927 in Neuropathic | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Thierfelder S | Driver D |  | Axon Scandinavia, Copenhagen |  |  |  | No | An open-label continuation trial to assess the continued efficacy and safety of ascending doses of SPM 927 in subjects with chronic refractory neuropathic pain |  |  | SP0647 is a follow up of SP0611 |  | 2001-01-02 |  | 2001-02-28 |  | 2001-05-02 |  | 2001-07-09 | 2011-02-28 | 2011-03-10 | 2011-04-26 | 2011-05-27 | 2011-06-23 | 2011-12-20 | 2011-08-24 | 2012-03-01 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 24 | 24 | 24 | 7 | 0 | 0 | 7 | 0 | 3 | 4
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0655 | CSR Approved | PHN Pilot with SPM927 | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Bongardt S | [6 empty] | No | A multi center randomized double blind placebo controlled pilot trial to assess the efficacy, safety and tolerability of SPM 927 in subjects with postherpetic neuralgia (PHN) | Neuropathic pain | Central Nervous System |  | 2001-06-30 | 2001-06-30 |  | 2015-05-12: 2001-10-10; 2016-01-18: 2002-02-08; 2016-11-29: 2002-09-10; 2020-01-06: 2002-12-16; 2020-02-25: 2003-05-26; 2020-07-02: 2003-09-30 | Belgium, Denmark, France, Germany, United Kingdom | Belgium (Created), Denmark (Created), France (Created), Germany (Created), United Kingdom (Created) |  | 7 | 0 | 0 | 48 | 42 | 36 | 0 | 0 | 0 | 44 | 5 | 7 | 32
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0660 | Study Archived | SPM 929: Interaction with oral anti-diabetics | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Goldammer N | Beinhauer-Zellenka U | [5 empty] | Yes | Randomized, open-label, single and multiple dose trial to evaluate the pharmacokinetic effect as well as safety and tolerability of SPM 927 on metformin and vice versa in healthy male Caucasian subjects. |  |  |  | 2004-03-16 | 2004-03-16 |  | 2015-05-12: 2004-04-05; 2016-01-18: 2004-06-02; 2016-11-29: 2004-07-06; 2020-01-06: 2004-08-02; 2020-02-04: 2004-09-03; 2020-02-25: 2005-04-15; 2020-07-02: 2005-12-14 | Germany | Germany (Created) |  | 1 | 0 | 0 | 16 | 16 | 16 | 25 | 9 | 0 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0662 | Created (Cancelled) | SPM 929: Interaction with paracetamol | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | SPM 929: Interaction with paracetamol | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0663 | Created (Cancelled) | SPM 929: Interaction with tramadol | Phase I |  | UCB Pharma Global |  | UCB Pharma Global | Bonn R | [6 empty] | No | SPM 929: Interaction with tramadol | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0665 | Study Archived | Open label follow-up Diabetic Neuropathic Pain | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Simpson J | Driver D | [5 empty] | No | An open label follow-on trial to assess the long term safety and efficacy of oral SPM927 in subjects with diabetic neuropathy. | Neuropathic pain | Central Nervous System |  | 2001-05-15 | 2001-05-15 |  | 2015-05-12: 2002-02-22; 2016-01-18: 2002-04-30; 2016-11-29: 2003-03-31; 2020-01-06: 2004-12-28; 2020-02-04: 2005-03-23; 2020-02-25: 2005-08-15; 2020-07-02: 2005-11-15 | United States of America | United States of America (Created) |  | 30 | 0 | 0 | 100 | 100 | 100 | 0 | 0 | 0 | 69 | 17 | 18 | 34
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0690 | Study Archived | Open-label follow-on PHN | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Bongardt S | [6 empty] | No | An open-label follow-on trial to assess the long-term safety and efficacy of oral SPM 927 in subjects with postherpetic neuralgia | Neuropathic pain | Central Nervous System |  | 2001-12-27 | 2001-12-27 |  | 2015-05-12: 2002-05-15; 2016-01-18: 2002-11-26; 2016-11-29: 2003-02-05; 2020-01-06: 2005-01-06; 2020-02-04: 2005-03-31; 2020-02-25: 2005-05-30 | Germany | Germany (Created) |  | 6 | 0 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | 17 | 0 | 15 | 2
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0697 | Created (Cancelled) | Pilot Trial in Mononeuropathies / Radiculopathies | Phase II |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | Pilot Trial in Mononeuropathies / Radiculopathies | Neuropathic pain | Central Nervous System | [20 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0742 | Study Archived | SPM 927 dose finding trial in Painful Diabetic Neuropathy | Phase II | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Simpson J | Driver D | [5 empty] | No | A MULTI-CENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO CONTROLLED TRIAL TO ASSESS THE EFFICACY AND SAFETY OF 200, 400, AND 600MG/DAY SPM 927 IN SUBJECTS WITH PAINFUL DISTAL DIABETIC NEUROPATHY | Neuropathic pain | Central Nervous System |  | 2003-05-23 | 2003-05-23 |  | 2015-05-12: 2003-12-12; 2016-01-18: 2004-04-12; 2016-11-29: 2005-01-04; 2020-01-06: 2005-06-06; 2020-02-04: 2005-07-19; 2020-02-25: 2006-01-10; 2020-07-02: 2006-04-04 | United States of America | United States of America (Created) |  | 60 | 0 | 0 | 630 | 360 | 288 | 735 | 0 | 0 | 370 | 4 | 132 | 234
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0743 | CSR Approved | SPM 927 efficacy and safety trial in Painful Diabetic Neurop | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Bongardt S | [6 empty] | No | SPM 927 efficacy and safety trial in Painful Diabetic Neuropathy | Neuropathic pain | Central Nervous System |  | 2003-05-23 | 2003-05-23 |  | 2015-05-12: 2003-09-08; 2016-01-18: 2003-12-17; 2016-11-29: 2004-07-23; 2020-01-06: 2005-01-06; 2020-02-04: 2005-02-28; 2020-02-25: 2005-05-06; 2020-07-02: 2006-05-05 | Belgium, Czech Republic, France, Germany, Hungary, Italy, Netherlands, Poland, Romania, Russian Federation, Spain, United Kingdom | Belgium (Created), Czech Republic (Created), France (Created), Germany (Created), Hungary (Created), Italy (Created), Netherlands (Created), Poland (Created), Romania (Created), Russian Federation (Created), Spain (Created), United Kingdom (Created) |  | 55 | 0 | 0 | 471 | 330 | 230 | 513 | 0 | 0 | 357 | 0 | 110 | 247
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0744 | Protoc. Summary Approved (Cancelled) | SPM 927 mixed population trial with enriched trial design | Phase II |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | SPM 927 mixed population trial with enriched trial design | Neuropathic pain | Central Nervous System |  | 2003-10-21 | 2003-10-21 | [17 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0745 | CSR Approved | SPM 927 follow-on of dose finding trial in Painful Diabetic | Phase II | Open | UCB Pharma Global |  | UCB Pharma Global | Thierfelder S | Driver D | [5 empty] | No | A Multi-center, open-label, follow-on trial to assess the long-term safety and efficacy of SPM 927 in subjects with painful distal diabetic neuropathy | Neuropathic pain | Central Nervous System | SP0745 is a feeder study of SP0615 | 2003-05-23 | 2003-05-23 |  | 2015-05-12: 2004-01-12; 2016-01-18: 2004-09-13; 2016-11-29: 2006-01-11; 2020-01-06: 2008-07-25; 2020-02-04: 2008-10-29; 2020-02-25: 2008-12-19; 2020-07-02: 2009-06-09 | United States of America | United States of America (1st Site Initiation) | United States of America | 130 | 1 | 0 | 525 | 525 | 315 | 0 | 0 | 0 | 452 | 0 | 283 | 169
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0746 | Study Archived | SPM 927 follow-on of efficacy and safety trial in Painful Di | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Thierfelder S | Driver D | [5 empty] | No | A multi-center, open-label, follow-on trial to assess the long-term safety and efficacy of lacosamide in subjects with painful distal diabetic neuropathy including a double-blind randomized time point withdrawal subtrial | Neuropathic pain | Central Nervous System |  | 2003-05-23 | 2003-05-23 |  | 2003-09-08 | 2004-06-01 | 2004-05-26 | 2005-02-28 | 2007-11-26 | 2010-12-31 | 2011-01-05 | 2010-12-27 | 2011-03-04 | 2011-02-24 | 2011-05-20 | 2011-04-26 | 2011-12-20 | Austria, Belgium, Bulgaria, Czech Republic, Finland, France, Germany, Hungary, Italy, Poland, Romania, Russian Federation, Serbia, Spain, United Kingdom | Austria (LPLV), Belgium (LPLV), Bulgaria (LPLV), Czech Republic (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Poland (LPLV), Romania (LPLV), Russian Federation (LPLV), Serbia (LPLV), Spain (LPLV), United Kingdom (LPLV) | Austria, Belgium, Bulgaria, Czech Republic, Finland, France, Germany, Hungary, Italy, Poland, Romania, Russian Federation, Serbia, Spain, United Kingdom | 57 | 101 | 100 | 220 | 220 | 66 | 0 | 0 | 0 | 621 | 0 | 234 | 387
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0747 | Protoc. Summary Approved (Cancelled) | SPM 927 follow-on of mixed population trial with enriched tr | Phase II |  | UCB Pharma Global |  | UCB Pharma Global | Person (Migrated From Sports) U | [6 empty] | No | SPM 927 follow-on of mixed population trial with enriched trial design | Neuropathic pain | Central Nervous System |  | 2003-10-21 | 2003-10-21 | [17 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0768 | CSR Approved | A parallel group trial to assess the efficacy and safety of | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Simpson J | Driver D | [5 empty] | No | A DOSE FINDING TRIAL TO ASSESS THE EFFICACY AND SAFETY OF 200, 400, AND 600 MG/DAY OF SPM 927 IN SUBJECTS WITH PAINFUL DISTAL DIABETIC NEUROPATHY (SP742-like trial) | Neuropathic pain | Central Nervous System |  | 2004-04-02 | 2004-04-02 |  | 2015-05-12: 2004-06-21; 2016-01-18: 2004-10-18; 2016-11-29: 2005-07-28; 2020-01-06: 2005-12-28; 2020-02-04: 2006-02-10; 2020-02-25: 2006-04-05; 2020-07-02: 2006-08-14 | United States of America | United States of America (Created) |  | 90 | 0 | 0 | 650 | 455 | 364 | 1220 | 0 | 0 | 467 | 0 | 212 | 255
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0769 | Protoc. Summary Approved (Cancelled) | A MULTI-CENTER, OPEN-LABEL FOLLOW-ON TRIAL TO ASSESS THE LON | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Simpson J | Driver D | [5 empty] | No | A MULTI-CENTER, OPEN-LABEL FOLLOW-ON TRIAL TO ASSESS THE LONG-TERM SAFETY AND EFFICACY OF SPM 927 IN SUBJECTS WITH PAINFUL DISTAL DIABETIC NEUROPATHY (Follow-on trial of SP768) | Neuropathic pain | Central Nervous System |  | 2003-10-21 | 2003-10-21 | [17 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0830 | Study Archived | Open-label trial with SPM 927 in subjects with Diabetic Neur | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Thierfelder S | Driver D | [5 empty] | No | A MULTI-CENTER, OPEN-LABEL TRIAL TO ASSESS THE LONG-TERM SAFETY AND EFFICACY OF SPM 927 IN SUBJECTS WITH PAINFUL DIABETIC NEUROPATHY | Neuropathic pain | Central Nervous System |  | 2004-08-06 | 2004-08-06 |  | 2015-05-12: 2004-08-05; 2016-01-18: 2004-12-21; 2016-11-29: 2005-06-07; 2020-01-06: 2007-10-31; 2020-02-04: 2008-01-16; 2020-02-25: 2008-05-28; 2020-07-02: 2008-06-02 | Belgium, Bulgaria, Czech Republic, France, Germany, Hungary, Italy, Netherlands, Poland, Romania, Russian Federation, Serbia, Slovakia, South Africa, Spain, Ukraine, United Kingdom | Belgium (Created), Bulgaria (Created), Czech Republic (Created), France (Created), Germany (Created), Hungary (Created), Italy (Created), Netherlands (Created), Poland (Created), Romania (Created), Russian Federation (Created), Serbia (Created), Slovakia (Created), South Africa (Created), Spain (Created), Ukraine (Created), United Kingdom (Created) |  | 65 | 0 | 0 | 480 | 360 | 108 | 505 | 0 | 0 | 371 | 151 | 211 | 9
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0874 | CSR Approved | Onset of action of Lacosamide | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | Tzschaschel B | [6 empty] | No | A MULTI-CENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED TRIAL TO ASSESS THE EFFICACY AND SAFETY OF 400MG/DAY LACOSAMIDE IN SUBJECTS WITH PAINFUL DISTAL DIABETIC NEUROPATHY USING TWO DIFFERENT TITRATION SCHEMES | Neuropathic pain | Central Nervous System |  | 2005-11-09 | 2005-11-09 |  | 2015-05-12: 2006-01-24; 2016-01-18: 2006-06-30; 2016-11-29: 2007-02-01; 2020-01-06: 2007-06-29; 2020-02-04: 2007-08-22; 2020-02-25: 2007-10-22; 2020-07-02: 2008-01-09 | Austria, Bulgaria, Czech Republic, Finland, France, Germany, Hungary, Italy, Poland, Romania, Serbia, Spain, United Kingdom | Austria (Created), Bulgaria (Created), Czech Republic (Created), Finland (Created), France (Created), Germany (Created), Hungary (Created), Italy (Created), Poland (Created), Romania (Created), Serbia (Created), Spain (Created), United Kingdom (Created) |  | 92 | 0 | 0 | 537 | 537 | 376 | 778 | 0 | 227 | 551 | 20 | 100 | 431
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0875 | Created (Cancelled) | Efficacy of Lacosamide vs. Placebo and active comparator Pre | Phase III | Double Blind | UCB Pharma Global |  | UCB Pharma Global | [7 empty] | No |  |  |  |  | 2009-04-23 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0876 | Created (Cancelled) | Switch from Pregabalin or Gabpentin to Lacosamide in the tre | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Joeres L | [6 empty] | No |  |  |  |  | 2008-05-19 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0946 | Created (Cancelled) | VOICE (Vimpat: Non Interventional Study with Lacosamide in D | Phase IV |  | Affiliates |  | Affiliates | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0947 | Created (Cancelled) | Epidemiiologic study on the treatment of DMP in Germany | Phase IV |  | Affiliates |  | Affiliates | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | VIMPAT | not defined | SP0960 | Created (Cancelled) | A 26 week multicenter. rando. D.B. placebo control. study | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | Thierfelder S | Driver D | N/A | N/A |  |  |  | No |  |  |  |  | 2014-07-30 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XANAX | not defined | SP0691 | Final TFLs released | Alprazolam ODT single dose bioequivalence | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to evaluate the bioequivalence of a unique new formulation (test), orally disintegrating tablet (ODT) of alprazolam 1 mg, administered with and without water, to a marketed immediate release alprazolam 1 mg formulation (reference), Xanax, by Pharmacia |  |  |  | 2003-01-08 | 2003-01-08 |  | 2015-05-12: 2003-01-27; 2016-01-18: 2003-02-21; 2016-11-29: 2003-02-21; 2020-01-06: 2003-03-10; 2020-02-25: 2003-04-23 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 21 | 21 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XANAX | not defined | SP0765 | Final TFLs released | Alprazolam ODT 0.5 mg single dose bioequivalence | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to evaluate the bioequivalence of a unique new formulation (test), Orally Disintegrating Tablet (ODT), of Alprazolam 0.5 mg administered with and without water, compared to a marketed immediate release Alprazolam 0.5 mg tablet formulation (reference), Xanax (R), by Pharmacia and Upjohn |  |  |  | 2003-06-27 | 2003-06-27 |  | 2015-05-12: 2003-08-04; 2016-01-18: 2003-08-22; 2016-11-29: 2003-08-22; 2020-01-06: 2003-09-09; 2020-02-25: 2003-10-16 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 15 | 15 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XANAX | not defined | SP0766 | Final TFLs released | Alprazolam ODT 1 mg food effect | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A pharmacokinetic study to evaluate the effect of food on the bioavailability of a 1.0 mg Alprazolam Orally Disintegrating Tablet |  |  |  | 2003-07-28 | 2003-07-28 |  | 2015-05-12: 2003-08-04; 2016-01-18: 2003-08-22; 2016-11-29: 2003-08-22; 2020-01-06: 2003-09-01; 2020-02-25: 2003-10-09 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 16 | 16 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XANAX | not defined | SP0829 | Created | Alprazolam Orally Disintegrating Tablets preference study in | Phase III | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | A multicenter, open-label, randomized crossover trial to assess subject preference for alprazolam orally disintegrating tablets compared to conventional alprazolam tablets in subjects with anxiety disorders | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XANAX | not defined | SP0831 | Created | Interaction of Proton Pump Inhibitor with Alprazolam ODT pha | Phase I | Open | UCB Pharma Global |  | UCB Pharma Global | Witt P | [6 empty] | No | Long Title to be entered | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XANAX | not defined | SP0851 | Created | Alprazolam ODT Phase 4 study to compare time to response in | Phase IV | Open | UCB Pharma Global |  | UCB Pharma Global | Mccrary K | [6 empty] | No | A multicenter, randomized, open-label, parallel design trial to compare time to response in the symptoms of anxiety to concomitant treatment with NiravamÔ and an SSRI or SNRI to treatment with an SSRI or SNRI alone in subjects with Generalized Anxiety Disorder or Panic Disorder | [22 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYREM | Central Nervous System | C00301 | Study Archived | Xyrem Endocrine Study | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Mccabe S | [6 empty] | No | Single center, therapeuthic exploratory clinical trial to evaluate the safety of sodium oxybate (Xyrem) 500 mg/mL oral solution on potential endocrine change at currently labeled therapeutic dose regimens (4.5 - 9 g/day divided into two equal doses) during 12 weeks of treatment of cataplexy in adlut | Indication for Neuro Psychiatry | Central Nervous System |  | 2005-09-02 | 2005-09-02 | 2006-02-28 | 2006-02-07 | 2006-03-31 | 2006-04-10 | 2006-12-29 | 2007-10-23 | 2007-05-01 | 2008-01-22 | 2007-06-12 | 2008-04-29 | 2007-08-01 | 2008-06-27 | 2007-10-01 | 2008-08-14 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 25 | 25 | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 25
Yes | Not assigned | Managing Type | 1 | XYREM | Central Nervous System | C00302 | Study Archived | Xyrem - PMS Safety Study | Non Interventional Study - Prospective | Open | GCSO | Neurology | Affiliates | Reichel C | Anderson K | N/A | PAREXEL | No | No | adults | No | post marketing, non-interventional surveillance pharmacoepidemiology study (PMSS) to evaluate long-term safety, tolerability and compliance in administration of Xyrem oral solution in patients who receive treatment with this medication in regular clinical practice | Indication for Neuro Psychiatry | Central Nervous System |  |  | 2005-09-16 | 2005-10-31 | 2005-12-20 | 2006-03-30 | 2006-05-24 | 2008-03-30 | 2015-03-06 | 2009-09-30 | 2016-09-02 | 2009-11-30 | 2016-10-25 | 2010-02-15 | 2017-02-03 | 2010-06-30 | 2017-02-27 | Austria, Belgium, Czech Republic, Germany, Ireland, Italy, Spain, Switzerland, United Kingdom | Austria (LPLV), Belgium (LPLV), Czech Republic (LPLV), Germany (LPLV), Ireland (LPLV), Italy (LPLV), Spain (LPLV), Switzerland (LPLV), United Kingdom (LPLV) | Austria, Belgium, Czech Republic, Germany, Ireland, Italy, Spain, Switzerland, United Kingdom | 40 | 41 | 41 | 750 | 750 | 750 | 735 | 0 | 0 | 753 | 0 | 216 | 537
Yes | Not assigned | Managing Type | 1 | XYREM | Central Nervous System | C00303 | Created (Cancelled) | Paediatry studies | Phase III | Double Blind | UCB Pharma Global | GMA Neurology / Psychiatry | Global Medical Affairs | Baukens C | Tillery N | [5 empty] | No |  | Indication for Neuro Psychiatry | Central Nervous System |  | 2012-04-16 |  | 2008-04-30 | 2015-09-29: 2008-09-16; 2016-04-08: 2010-03-15; 2019-11-29: 2010-06-15; 2020-02-04: 2010-09-01; 2020-02-07: 2010-10-21; 2020-05-05: 2011-01-31 |  |  |  | 3 | 0 | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYREM | Central Nervous System | C00306 | Created (Cancelled) | Xyrem MOA | Phase I |  | UCB Pharma Global | Clinical Pharmaco | UCB Pharma Global | [7 empty] | No |  |  |  |  | 2012-06-15 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYREM | Central Nervous System | C00307 | Created (Cancelled) | Xyrem Dose Ranging Study plc 3g | Phase II |  | UCB Pharma Global | Neurology | UCB Pharma Global | [7 empty] | No |  |  |  |  | 2011-02-21 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00260 | Study Archived | Levocetirizine vs Placebo on CNS | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | Global Medical Affairs | Benzaquen S, Daoust A |  |  | BioTrial |  |  |  | Yes | Effect of LCTZ on cognitive and psychometric function in healthy male volunteers -a DB, placebo controlled, randomized, 3-way crossover study of 5 mg LCTZ, administred Orally in capsule form, od for 5 days, in single dose and repeated doses, using 50 mg diphenhydramine as positive control | Indication for Dermato Allergo | Immunology |  |  |  | 2000-03-27 | 2000-03-24 | 2000-05-03 | 2000-04-21 |  |  | 2000-07-07 | 2000-07-03 | 2000-08-30 | 2000-08-28 |  |  | 2000-10-01 | 2000-12-08 | France | France (LPLV) | France | 1 | 0 | 1 | 0 | 0 | 0 | 31 | 0 | 12 | 19 | 0 | 1 | 18
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00263 | Study Archived | QTc and other ECG characteristics | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Pigeolet E |  |  | Bio-pharma |  |  |  | Yes | A randomized, double blind, 1 centre, 2-way cross-over, placebo-controled study to assess the safety of 1 & multiple doses of Levoceterizine 30 mg od (5mg oral tab) on QTc & othe ECG characteristics, in healthy male and female subjects | Indication for Dermato Allergo | Immunology |  |  |  | 1999-12-31 | 1999-12-20 | 2000-01-19 | 2000-01-19 |  |  | 2000-03-06 | 2000-03-06 | 2000-03-24 | 2000-04-16 |  |  | 2000-06-15 | 2000-09-05 | Belgium | Belgium (LPLV) | Belgium | 1 | 0 | 1 | 0 | 0 | 0 | 48 | 0 | 12 | 36 | 0 | 0 | 36
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00264 | Study Archived | Long Term Persistent Allergic Rhinitis | Phase II | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | Segaut C |  |  | Biomedical; MDS Pharma Services; Ascopharm |  |  |  | No | Randomized, multicenter, double-blind, quality of life therapeutic exploratory trial, with two parallel groups, comparing effects on health-related quality of life of 5mg levocetirizine tab vs plc, administrated per os once daily in the evening, during 6 months, to adults suffering from persistent allergic rhinitis | Indication for Dermato Allergo | Immunology |  |  |  | 2000-05-31 | 2000-07-25 | 2001-01-01 | 2001-04-02 |  | 2001-09-21 | 2001-09-01 | 2002-04-29 |  | 2002-09-17 |  | 2002-11-20 | 2002-06-01 | 2003-02-04 | Belgium, France, Germany, Italy, Spain | Belgium (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Spain (LPLV) | Belgium, France, Germany, Italy, Spain | 63 | 63 | 59 | 520 | 500 | 0 | 724 | 0 | 173 | 551 | 0 | 130 | 421
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00265 | Study Archived | PAR Phase II plc Vs 2,5 mg Vs 5 mg Vs 10 mg | Phase II |  | Clinical Development Europe | TA Allergology / Respiratory | R & D | Liard A | [6 empty] | No | Randomised, double blind, placebo controlled, multicentre, phase II study of the efficacy and safety of 2.5 mg, 5 mg and 10 mg levocetirizine dihydrochloride (ucb 28556) tablets, administered once daily in the evening, for four weeks, to subjects sufferin rhinitis associated with house dust mites | [5 empty] | 2000-04-15 | 2000-04-13 | 2000-09-01 | 2000-09-08 |  |  | 2001-02-26 | 2001-02-05 | 2001-04-02 | 2001-05-07 |  |  | 2001-06-08 | 2002-05-08 | France, Germany | France (LPLV), Germany (LPLV) | France, Germany | 52 | 0 | 49 | 500 | 0 | 0 | 611 | 90 | 0 | 521 | 521 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00266 | Study Archived | PAR Phase III plc Vs 5 mg | Phase III |  | Clinical Development Europe | TA Allergology / Respiratory | R & D | Wajskop M | [6 empty] | No | Randomized, double blind, placebo-controlled, multi-centre, phase III study, of the efficacy and safety of 5 mg levocetirizine dihydrochloride (ucb 28566) tablets, administered once daily at bedtime, for 6 weeks, to patients suffering from perennial aller | [5 empty] | 2000-02-04 | 2000-02-08 | 2000-05-02 | 2000-06-13 |  |  | 2000-08-31 | 2000-09-08 | 2000-11-30 | 2001-02-14 |  | 2001-04-24 | 2001-04-30 | 2002-01-04 | South Africa | South Africa (LPLV) | South Africa | 30 | 0 | 27 | 250 | 0 | 0 | 368 | 74 | 0 | 294 | 294 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00268 | Study Archived | SAR Phase III plc vs 5 mg | Phase III | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | R & D | Le Gall M | [6 empty] | No | Randomised, double blind, placebo controlled, multicentre, phase III study, of the efficacy and safety of 5 mg levocetirizine dihydrochloride (ucb 28556) tablets, administered once daily in the evening, for two weeks, to subjects suffering from grass pollen allergic rhinitis | [5 empty] | 2000-06-30 | 2000-06-16 | 2000-10-01 | 2000-11-07 |  |  | 2001-02-01 | 2001-03-19 | 2001-06-30 | 2001-06-19 |  | 2001-10-02 | 2001-09-30 | 2002-01-08 | South Africa | South Africa (LPLV) | South Africa | 20 | 0 | 20 | 232 | 0 | 0 | 344 | 107 | 0 | 237 | 237 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00269 | Study Archived | CIU Phase III (plc vs 5 mg ) | Phase III | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | R & D | Voss G |  |  | Oestreich + Partner |  |  |  | No | Randomised, double blind, placebo controlled, multicentre, phase III study, of the efficacy and safety of 5mg levocetirizine dihydrochloride (ucb 28556) tablets, administered orally, once daily in the evening, for four weeks, to adults suffering from chronic idiopathic urticaria | Indication for Dermato Allergo | Immunology |  |  |  | 2000-09-30 | 2000-09-22 | 2001-02-20 | 2001-02-26 |  |  | 2001-09-30 | 2001-09-18 | 2001-11-30 | 2002-02-01 |  | 2002-06-12 | 2002-03-31 | 2002-09-25 | Germany, Switzerland | Germany (LPLV), Switzerland (LPLV) | Germany, Switzerland | 19 | 0 | 18 | 154 | 154 | 154 | 186 | 20 | 0 | 166 | 166 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00270 | Study Archived | CIU Phase II (2.5, 5 and 10 mg vs plc) | Phase II | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | R & D | Benzaquen S, Pinelli M | [6 empty] | No | Randomised, double blind, placebo controlled, multicentre, Phase II study, of the efficacy and safety of 2.5 mg, 5 mg and 10 mg Levocetirizine dihydrochloride (ucb 28556) tablets, administered orally once daily in the evening, for four weeks, to adults suffering from Chronic Idiopathic Urticaria. | Indication for Dermato Allergo | Immunology |  |  |  | 2000-06-12 | 2000-07-12 | 2001-02-20 | 2001-03-02 | 2000-08-18 |  | 2001-09-30 | 2002-03-15 | 2001-11-30 | 2002-06-11 |  | 2002-11-22 | 2002-03-30 | 2003-05-05 | France | France (LPLV) | France | 25 | 0 | 34 | 0 | 0 | 0 | 303 | 45 | 0 | 258 | 258 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00280 | Study Archived | Valorisation Wheal & Flare vs. descarboxyloratadine | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | Global Medical Affairs | Melac M | [6 empty] | Yes | Double-blind, randomized, placebo controlled, single oral dose, cross-over trial to compare levocetirizine (tablet 5mg) and desloratadine (tablet 5mg) on histamine induced wheal and flare during 24 hours in 18 healthy volunteers | Indication for Dermato Allergo | Immunology |  |  |  | 2001-04-10 | 2001-04-06 | 2001-06-11 | 2001-06-13 |  |  | 2001-08-15 | 2001-08-11 | 2001-10-15 | 2001-10-15 |  |  | 2002-01-15 | 2002-01-03 | France | France (LPLV) | France | 1 | 0 | 1 | 0 | 0 | 0 | 20 | 0 | 2 | 18 | 0 | 0 | 18
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00297 | Study Archived | Bioequivalence levo drops / Tablets in adults | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Moulaert B | [6 empty] | Yes | Randomized, monocenter, open label, cross-over, single dose bioequivalence study of levocetirizine dihydrochloride 5 mg tablet and levocetirizine dihydrochloride 1 mL oral drops formulation ( 5 mg/mL) in 24 healthy fasting male and femal subjects. | Indication for Dermato Allergo | Immunology |  |  |  | 2001-03-20 | 2001-03-29 | 2001-05-02 | 2001-06-15 |  |  | 2001-06-15 | 2001-07-31 | 2001-09-07 | 2001-09-14 |  |  | 2001-10-31 | 2001-12-05 | Germany | Germany (LPLV) | Germany | 1 | 0 | 1 | 24 | 24 | 24 | 41 | 0 | 17 | 24 | 0 | 1 | 23
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00299 | Study Archived | Levocetirizine in PAR - Taiwan | Phase III | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | R & D | Liard A | [6 empty] | No | A double-blind, multicenter, randomized, active comparator controlled study to evaluate the efficacy and safety of levocetirizine (oral capsules of 5 mg o.d.) at a dose of 5 mg/day compared to loratadine 10 mg daily in oral capsules in adults suffering from perennial allergic rhinitis and treated du ring 3 weeks. | Indication for Dermato Allergo | Immunology |  |  |  | 2001-03-07 | 2001-03-14 | 2001-10-01 | 2001-10-23 |  |  | 2002-01-20 | 2002-02-07 | 2002-03-22 | 2002-05-14 |  |  | 2002-05-31 | 2002-11-13 | Taiwan | Taiwan (LPLV) | Taiwan | 1 | 0 | 1 | 60 | 60 | 0 | 76 | 0 | 14 | 62 | 0 | 5 | 57
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00303 | Study Archived | SAR in Child 6 - 12 years old | Phase IV | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | Martin L | [6 empty] | No | A double-blind, placebo controlled, randomized multicenter, Phase IV trial : Evaluation of the efficacy and safety, for children from 6 to 12 years old, suffering from seasonal allergic rhinitis, of levocetirizine dihydrochloride (ucb 28556) 5 mg tablets, administered orally once daily in the evening, for 6 weeks | Indication for Dermato Allergo | Immunology |  |  | 2001-10-22 |  | 2001-12-20 | 2002-04-01 | 2002-04-09 | 2002-07-15 | 2002-08-17 | 2002-09-01 | 2002-09-04 | 2002-11-01 | 2003-05-15 | 2003-07-18 | 2003-07-18 | 2003-02-01 | 2003-11-14 | France, Germany | France (LPLV), Germany (LPLV) | France, Germany | 52 | 41 | 30 | 330 | 292 | 292 | 223 | 0 | 46 | 177 | 0 | 26 | 151
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00304 | Study Archived | PAR Pediatry (6-12 years) | Phase III | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | Le Gall M | [6 empty] | No | A double-blind placebo controlled randomized multicenter phase III trial: evaluation of the efficacy and safety on 6 to 12 years old children suffering from PAR due to house dust mites of levocetirizine dihydrochloride 5mg tablets administered orally once daily in the evening for four weeks | Indication for Dermato Allergo | Immunology |  |  |  | 2001-10-08 | 2001-10-08 | 2002-04-02 | 2002-04-23 | 2002-07-15 |  | 2002-08-31 | 2002-09-27 | 2002-11-04 | 2003-02-17 |  | 2003-04-22 | 2002-02-01 | 2003-11-27 | South Africa | South Africa (LPLV) | South Africa | 25 | 25 | 24 | 400 | 292 | 292 | 371 | 0 | 65 | 306 | 0 | 9 | 297
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00305 | Study Archived | Thermography - pilot | Phase IV | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | Martin L | [6 empty] | No | A pilot, randomized trial : Evaluation of the dose response effects of nasal histamine challenges (70 µg to 1120 µg) (Part A) and double-blind, placebo controlled, cross-over evaluation of the effects of levocetirizine (5mg) oral tablet in single dose versus desloratadine (5 mg) oral tablet or placebo (Part B), on nasal temperature, measured by facial thermography on healthy male adults stimulated by nasal histamine challenge <RPCE02A1103> | Indication for Dermato Allergo | Immunology |  |  | 2001-12-06 | 2002-08-01 | 2002-07-31 | 2002-09-16 | 2002-09-17 |  | 2002-10-09 | 2002-11-12 | 2002-11-07 |  | 2002-12-02 | 2003-03-15 | 2003-03-17 | 2003-04-10 | 2003-06-25 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 18 | 18 | 18 | 20 | 0 | 1 | 18 | 0 | 0 | 18
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00306 | Study Archived | Rhinitis-Asthma | Phase III | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | Pinelli M, Segaut C | [6 empty] | No | A double-blind, parallel, placebo controlled, 3 arms, randomized study: evaluation of the efficacy and safety of levocetirizine 5 mg oral tablets, administered during 8 weeks preceding and during 8 weeks following the anticipated onset of the grass pollen season, in subjects suffering from Seasonal Allergic Rhinitis associated with pollen-induced Asthma. | Indication for Dermato Allergo | Immunology |  | 2003-04-01 | 2003-04-01 | 2003-07-01 | 2003-08-27 | 2004-02-16 | 2004-02-21 | 2004-02-16 | 2004-04-17 | 2004-05-31 | 2004-07-31 |  | 2004-11-24 |  | 2004-12-20 |  | 2006-04-18 | Belgium, France, Italy | Belgium (LPLV), France (LPLV), Italy (LPLV) | Belgium, France, Italy | 80 | 53 | 53 | 300 | 300 | 0 | 435 | 0 | 1 | 461 | 8 | 67 | 386
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00307 | Created (Cancelled) | Asthma Levo + Montelukast vs placebo + Montelukast | Phase III | Double Blind | Clinical Development Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Favre-Bonte J | [6 empty] | No | A double-blind, placebo controlled, randomized study: evaluation of the efficacy and safety of Levocetirizine, 5mg tablets, administered orally once daily, given in combination with Montelukast, 10mg tablets, administered orally once daily, for the treatment of persistent asthmatic patients, aged 15 to 60 years, over 4 weeks. | Indication for Dermato Allergo | Immunology | [20 empty] | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00309 | Study Archived | Early Prevention of Asthma in Atopic Children | Phase III | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | R & D | Verkest (Health Care Interim) S, Wajskop M |  |  | UCB/Quintiles |  |  |  | No | The Early Prevention of Asthma in Atopic Children (EPAAC) study : A multi-country, double-blind, placebo controlled, randomized, parallel group trial : Evaluation of the efficacy and safety of levocetirizine (5 mg/ml oral drops - 0.125 mg/kg b.w. b.i.d.) administered for 18 months in preventing the onset of asthma in 12 to 24 months old children who suffer from atopic dermatitis and are sensitized to Grass Pollen and/or House Dust Mite allergens | Indication for Dermato Allergo | Immunology |  |  | 2001-05-14 | 2001-08-13 | 2001-08-29 | 2002-03-31 | 2002-03-20 | 2004-02-01 | 2004-03-09 | 2006-02-01 | 2006-03-15 | 2006-09-01 | 2006-06-08 |  | 2006-06-30 | 2006-12-31 | 2007-08-07 | Australia, Austria, Belgium, Czech Republic, France, Germany, Italy, Netherlands, Poland, South Africa, Spain, United Kingdom | Australia (LPLV), Austria (LPLV), Belgium (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Netherlands (LPLV), Poland (LPLV), South Africa (LPLV), Spain (LPLV), United Kingdom (LPLV) | Australia, Austria, Belgium, Czech Republic, France, Germany, Italy, Netherlands, Poland, South Africa, Spain, United Kingdom | 105 | 111 | 95 | 2500 | 500 | 486 | 2348 | 13 | 1821 | 514 | 0 | 80 | 434
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00315 | Study Archived | Ped 1-2y Pilot Cough PK/PD | Phase II | Open | Clinical Development Europe | TA Allergology / Respiratory | R & D | Moulaert B | [6 empty] | No | A non-controlled, pilot, multi-centric, open study of the efficacy and safety of LCTZ 5 mg/ml oral drops given 0.125 mg/kg bid during 90 days in the treatment of recurrent cough associated with other allergic symptoms, e.g. wheezing, in children aged 1-2 years | Indication for Dermato Allergo | Immunology |  |  |  |  | 2015-05-12: 2001-08-22; 2016-01-18: 2001-12-07; 2020-01-06: 2003-03-24; 2020-02-04: 2003-06-26; 2020-02-25: 2003-09-01; 2020-07-02: 2003-10-27 | Australia, Czech Republic | Australia (LPLV), Belgium (1st Site Initiation (Cancelled)), Czech Republic (LPLV), France (1st Site Initiation (Cancelled)) | Australia, Czech Republic | 4 | 3 | 2 | 24 | 24 | 24 | 18 | 0 | 3 | 15 | 0 | 1 | 14
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00318 | Study Archived | Bioequivalence solute vs tablets | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | De Smedt F |  |  | SGS Biopharma/UCB |  |  |  | Yes | Randomized, monocenter, open label, cross-over, single dose bioequivalence study of levocetirizine dihydrochloride 5 mg tablet and levocetirizine dihydrochloride 10 mL oral solution (0.5 mg/mL) in 24 healthy fasting male and female subjects. | Indication for Dermato Allergo | Immunology |  |  |  | 2002-08-19 | 2002-08-19 | 2002-08-23 | 2002-09-10 |  |  | 2002-09-20 | 2002-11-25 | 2002-10-18 | 2002-10-22 |  | 2002-10-29 | 2002-12-20 | 2003-01-13 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 40 | 24 | 24 | 43 | 0 | 19 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00324 | Study Archived | SAR pollen chamber | Phase IV | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | Voss G | [6 empty] | No | A randomized, double-blind, three way cross-over, placebo controlled trial to compare the efficacy and safety of levocetirizine 5 mg od (oral tablets) and fexofenadine 120 mg od (oral tablets) in reducing symptoms of seasonal allergic rhinitis in grass pollen sensitized adults exposed for 2 consecutive days during 4 and 6 hours respectively to this allergen in the Vienna Challenge Chamber <RPCE02C1103> | Indication for Dermato Allergo | Immunology |  |  |  | 2002-05-10 | 2002-05-17 | 2002-09-15 | 2002-09-23 |  | 2002-10-31 |  | 2002-12-07 |  | 2003-03-17 | 2003-05-12 | 2003-05-12 |  | 2003-07-18 | Austria | Austria (LPLV) | Austria | 1 | 1 | 1 | 120 | 100 | 84 | 120 | 0 | 26 | 94 | 0 | 9 | 85
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00331 | Study Archived | SAR - Ragweed sensitive subjects | Phase III | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | Gerard D |  |  | Out-sourced monitors (RPS): L. HOULE; N. BRISTOW |  |  |  | No | Double-Blind, Parallel, Placebo-controlled study of Levocetirizine 5 mg tablets q.d. vs. Desloratadine 5 mg tablets q.d. to determine clinical onset of action & efficacy in reducing symptoms of S.A.R. in ragweed sensitive subjects exposed to pollen challenge in an Environmental Exposure Unit (EEU) | Indication for Dermato Allergo | Immunology |  | 2002-01-22 | 2002-01-21 | 2002-01-28 | 2002-01-28 | 2002-03-25 | 2002-03-25 | 2002-04-08 | 2002-04-29 | 2002-05-30 | 2002-05-21 | 2002-07-16 | 2002-07-16 | 2002-09-17 | 2002-09-17 | 2002-10-31 | 2002-11-08 | Canada | Canada (LPLV) | Canada | 1 | 1 | 1 | 550 | 360 | 360 | 524 | 0 | 114 | 373 | 1 | 10 | 362
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00333 | Study Archived | Pre-marketing levocetirizine France | Phase IV | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | Affiliates - France | Segaut C | [6 empty] | No | A double-blind, placebo controlled, randomized, multicenter phase IV trial : Evaluation of the efficacy using the number of comfortable days, and of the safety of levocetirizine dihydrochloride 5 mg oral tablets, administered once daily in the evening, for 30 days to subjects suffering from perennial allergic rhinitis to house dust mites. | Indication for Dermato Allergo | Immunology |  |  |  | 2002-04-20 | 2002-04-15 | 2002-09-15 | 2002-09-09 |  | 2003-04-03 | 2003-04-30 | 2003-05-20 | 2003-07-30 | 2004-01-20 |  | 2004-03-11 | 2003-11-30 | 2004-06-30 | France | France (LPLV) | France | 100 | 0 | 74 | 490 | 490 | 450 | 562 | 108 | 3 | 454 | 0 | 59 | 395
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00334 | CSR Approved | CIU - Chronic Idiopatic Urticaria | Phase III | Open | Clinical Development Asia | Clinical Pharmaco | R & D | He G |  |  | KendleWits |  |  |  | No | A multicenter, randomised, investigator-blinded, active-control, parallel group study evaluating the efficacy and safety of 5 mg Levocetirizine Oral Tablets, once daily, versus 10 mg Loratadine Oral Tablets, once daily, for the treatment of Chronic idiopathic Urticaria | Indication for Dermato Allergo | Immunology |  | 2002-09-15 | 2002-09-15 | 2002-11-15 | 2002-11-27 | 2003-06-01 | 2003-08-01 |  | 2003-09-25 | 2003-10-31 | 2004-03-04 | 2004-03-31 | 2004-09-10 |  | 2004-10-11 | 2004-06-30 | 2004-11-26 | China | China (LPLV) | China | 2 | 0 | 2 | 144 | 120 | 120 | 143 | 0 | 9 | 134 | 0 | 12 | 122
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00340 | CSR Approved | LCTZ India Pharmacokinetic BE | Phase I | Open | Clinical Development Europe | TA Allergology / Respiratory | R & D | Bendahmane S |  |  | SPC |  |  |  | Yes | Randomised, two period corss-over, single dose BE study of Levocetirizine dihydrochloride 5 mg tablet manufactered by UCB India and Levocetirizine dihydrochloride 5 mg tablet manufactered by UCB Farchim S.A. in 16 healthy male subjects under fasting conditions. | Indication for Dermato Allergo | Immunology |  |  | 2002-09-23 | 2002-07-31 | 2002-10-31 | 2002-09-15 | 2002-12-28 |  |  | 2002-10-15 | 2003-01-17 | 2003-03-15 | 2003-05-08 |  |  | 2003-06-15 | 2006-03-15 | India | India (LPLV) | India | 1 | 0 | 1 | 16 | 16 | 16 | 16 | 0 | 0 | 16 | 0 | 0 | 16
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00348 | CSR Approved | SAR - Seasonal Allergic Rhinitis - China | Phase III | Open | Clinical Development Asia | TA Allergology / Respiratory | R & D | He G |  |  | KendleWits |  |  |  | No | A multi-center, randomised, investigator-blinded, active-control, parallel-group study evaluating the efficacy and safety of 5 mg Levocetirizine oral tablets, once daily, versus 10 mg Loratadine oral tablets, once daily, for the treatment of Seasonal Allergic Rhinitis. | Indication for Dermato Allergo | Immunology |  |  | 2002-09-15 | 2002-11-15 | 2002-11-27 | 2003-06-01 | 2003-08-29 |  | 2003-09-15 | 2003-10-31 | 2003-10-22 | 2004-01-31 | 2004-07-14 |  | 2004-10-11 | 2004-04-30 | 2004-11-26 | China | China (LPLV) | China | 2 | 0 | 2 | 72 | 60 | 60 | 76 | 0 | 8 | 68 | 0 | 2 | 66
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00349 | CSR Approved | PAR - Perennial Allergic Rhinitis - China | Phase III | Open | Clinical Development Asia | TA Allergology / Respiratory | R & D | He G |  |  | KendleWits |  |  |  | No | A multicenter, randomised, investigator-blinded, active control, parallel-group study evaluating the efficacy and safety of 5 mg Levocetirizine oral tablets, once daily, versus 10 mg Loratadine oral tablets, once daily, for the treatment of Perennial Allergic Rhinitis. | Indication for Dermato Allergo | Immunology |  |  | 2002-10-15 | 2002-11-15 | 2002-11-27 | 2003-04-01 | 2003-09-12 |  | 2004-02-06 | 2003-12-31 | 2004-02-24 | 2004-02-28 | 2004-08-19 |  | 2004-10-11 | 2004-05-31 | 2004-11-26 | China | China (LPLV) | China | 2 | 0 | 2 | 72 | 60 | 60 | 76 | 0 | 5 | 71 | 0 | 6 | 65
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00351 | Study Archived | Rhinitis, Nasal Challenge, Facial Thermagrophy | Phase IV | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | Gerard D, Pinelli M | [6 empty] | Yes | A randomized double blind, placebo control crossover trial in healthy male subjects: comparison of the efficacy of levocetirizine 5-mg tablet single oral dose and fexofenadine 120-mg tablet single oral dose on the changes in nasal skin temperature induced by histamine provocation, and measured by th | Indication for Dermato Allergo | Immunology |  | 2003-02-28 | 2003-03-21 | 2003-05-23 | 2003-05-27 | 2003-07-11 | 2003-07-21 |  | 2003-10-28 | 2003-10-03 | 2003-11-27 | 2003-11-17 | 2003-12-19 | 2004-01-10 | 2004-02-10 | 2004-03-10 | 2004-05-28 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 30 | 30 | 27 | 34 | 0 | 4 | 30 | 1 | 0 | 29
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00352 | Created (Cancelled) | COR-Protocol | Phase IV | Double Blind | Clinical Development Europe |  | Global Medical Affairs | Gerard D | [6 empty] | No | Randomized, double blind, placebo controlled, multicentre trial: Efficacy and safety of 5 mg Levocetirizine dihydrochloride oral tablets, administered once daily at bedtime, for four weeks, to patients suffering from allergic rhinitis due to house dust mites | Indication for Dermato Allergo | Immunology |  | 2002-12-20 |  | 2003-03-17 | 2015-09-29: 2003-09-08; 2016-04-08: 2004-02-20; 2019-11-29: 2004-03-29 | Belgium, France, Germany, Italy, Spain | Belgium (Created), France (Created), Germany (Created), Italy (Created), Spain (Created) |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00361 | Created (Cancelled) | ECP | Phase III |  | Clinical Development Europe |  | Affiliates - Italy | Liard A, Pinelli M | [6 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00366 | Protocol Approved (Cancelled) | Levo versus placebo and versus Montelukast | Phase III | Double Blind / Double Dummy | Clinical Development Europe |  | Global Medical Affairs | Liard A, Pinelli M | [6 empty] | No | A double blind placebo controlled randomized study: Evaluation of the efficacy and safety of levocetirizine 5 mg, and montelukast 10 mg, administered orally as capsules once daily over 4 weeks, for the treatment of subjects aged 15 to 65 years , suffering from Allergic Rhinitis with Asthma recrudescence. | Indication for Dermato Allergo | Immunology |  | 2003-11-28 | 2003-12-05 |  | 2015-05-12: 2004-01-20 |  |  |  | 100 | 0 | 0 | 900 | 900 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00367 | Created (Cancelled) | Asthma burden | Phase II | Double Blind | Clinical Development Europe |  | R & D | Le Gall M, Pinelli M | [6 empty] | No |  |  |  |  | 2004-09-15 | [18 empty] | 100 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00372 | Created (Cancelled) | XPERT Plus | Phase III |  | Clinical Development Europe |  | Global Medical Affairs | [7 empty] | No |  | Indication for Dermato Allergo | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00373 | Study Archived | W & F | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | Global Medical Affairs | Daoust A | [6 empty] | No | Randomized, monocenter, double blind, placebo-controlled, single oral dose, three-way cross over study, to compare levocetirizine (tablet 5 mg) and desloratadine (tablet 5 mg) on allergen-induced wheal and flare reaction during 24 hours in 18 adult allergic volunteers | Indication for Dermato Allergo | Immunology |  |  | 2004-09-02 |  | 2015-05-12: 2004-09-09; 2016-01-18: 2004-11-23; 2016-11-29: 2004-12-02; 2020-01-06: 2005-01-24; 2020-02-04: 2005-03-02; 2020-02-25: 2005-11-29; 2020-07-02: 2006-03-02 | France | France (LPLV) | France | 1 | 1 | 1 | 18 | 18 | 18 | 18 | 0 | 0 | 18 | 0 | 0 | 18
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00374 | Created (Cancelled) | Nasal congestion | Phase II |  | Clinical Development Europe |  | Global Medical Affairs | [7 empty] | No |  | Indication for Dermato Allergo | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00375 | Created (Cancelled) | CIU / Pruritus | Phase II |  | Clinical Development Europe |  | Global Medical Affairs | [7 empty] | No |  | Indication for Dermato Allergo | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00376 | Created (Cancelled) | "Fishing" - Anti-inflammatory | Phase I |  | Clinical Development Europe |  | Global Medical Affairs | [7 empty] | No |  | Indication for Dermato Allergo | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00377 | Created (Cancelled) | Facial Thermography | Phase II |  | Clinical Development Europe |  | Global Medical Affairs | Martin L, Pinelli M | [6 empty] | No |  | Indication for Dermato Allergo | Immunology | [20 empty] | 1 | 0 | 0 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00378 | Created (Cancelled) | Long term in children | Phase III |  | Clinical Development Europe |  | Global Medical Affairs | [7 empty] | No |  | Indication for Dermato Allergo | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00379 | Study Archived | EEU Levo vs Ceti | Phase III | Double Blind / Double Dummy | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | Pinelli M, Segaut C | [6 empty] | No | Double blind, double dummy, parallel groups, randomized, placebo-controlled exploratory clinical trial to compare the efficacy of a single dose of levocetirizine 5 mg tablets and cetirizine 10 mg tablets in reducing symptoms of seasonal allergic rhinitis in ragweed sensitive subjects exposed to poll | Indication for Dermato Allergo | Immunology |  | 2004-01-12 | 2004-01-12 | 2004-02-10 | 2004-02-06 | 2004-03-22 | 2004-04-20 | 2004-05-18 | 2004-05-29 | 2004-07-20 | 2004-07-11 | 2004-09-28 | 2004-09-28 | 2004-11-26 | 2004-10-29 | 2004-12-20 | 2006-01-25 | Canada | Canada (LPLV) | Canada | 1 | 0 | 1 | 825 | 540 | 540 | 721 | 0 | 118 | 570 | 0 | 8 | 562
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00380 | CSR Approved (Stopped) | CLAIRE (Thermography levo vs ceti) | Phase IV | Double Blind / Double Dummy | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | Martin L, Pinelli M | [6 empty] | Yes | A randomized, double-blind, double dummy, placebo controlled, cross-over exploratory trial in healthy male adult subjects: Comparison by means of infrared thermography of the anti-H1 potency of levocetirizine 5 mg and cetirizine 10 mg tablet single oral dose after nasal histamine provocation. | Indication for Dermato Allergo | Immunology |  | 2003-12-10 | 2003-12-10 |  | 2015-05-12: 2004-04-20; 2016-01-18: 2004-07-05; 2016-11-29: 2004-09-29; 2020-01-06: 2004-10-05; 2020-02-04: 2004-12-08; 2020-02-25: 2005-02-24; 2020-07-02: 2005-10-18 | Germany | Germany (LPLV (Stopped)) | Germany | 1 | 1 | 1 | 60 | 60 | 60 | 63 | 0 | 10 | 53 | 0 | 0 | 35
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00382 | Created (Cancelled) | DIOC in children |  |  | Clinical Development Europe |  | Clinical Development Europe | Le Gall M | [6 empty] | No | [23 empty] | 1 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00384 | Study Archived | Prolongation of the EPAAC Trial | Phase III | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | R & D | Verkest (Health Care Interim) S, Wajskop M |  |  | QUINTILES/UCB |  |  |  | No | The prolongation of te EPAAC trial ((Early Prevention of Asthma in Atopic Children), a multi country, double-blind, placebo controlled, follow-up trial with 3 parallel groups (LCTZ-LCTZ, LCTZ-PLC and PLC-PLC): Evaluating the long term efficacy and safety of levocetirizine (5 mg/mL oral drops - 0.125 mg/kg b.w. bid) administered for an additional 18-month period in preventing the onset of asthma in children coming from the EPAAC trial | Indication for Dermato Allergo | Immunology |  | 2003-12-31 |  |  | 2004-03-09 | 2004-05-15 | 2004-06-16 | 2005-09-15 | 2005-09-15 | 2007-03-15 | 2006-03-24 | 2007-05-02 | 2006-06-08 | 2007-05-26 | 2007-01-12 | 2007-07-14 | 2008-08-14 | Australia, Belgium, Czech Republic, France, Germany, Italy, Poland, South Africa, Spain, United Kingdom | Australia (LPLV), Belgium (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Poland (LPLV), South Africa (LPLV), Spain (LPLV), United Kingdom (LPLV) | Australia, Belgium, Czech Republic, France, Germany, Italy, Poland, South Africa, Spain, United Kingdom | 68 | 57 | 55 | 300 | 300 | 0 | 0 | 0 | 0 | 207 | 72 | 123 | 12
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00385 | Study Archived | safety 2-6y | Phase II | Open | Clinical Development Europe | TA Allergology / Respiratory | R & D | Segaut C | [6 empty] | No | A 4 weeks open, multi-center study evaluating the safety of levocetirizine 1.25 mg b.i.d. given as 0.5 mg/mL oral solution in 2 to 6 year old children suffering from allergic rhinitis | Indication for Dermato Allergo | Immunology |  |  |  |  | 2015-05-12: 2004-04-20; 2016-01-18: 2004-06-23; 2016-11-29: 2004-11-23; 2020-01-06: 2004-12-29; 2020-02-04: 2005-01-27; 2020-02-25: 2005-02-22; 2020-07-02: 2005-05-27 | France | France (LPLV) | France | 5 | 5 | 4 | 30 | 30 | 30 | 34 | 0 | 4 | 30 | 0 | 1 | 29
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00391 | Study Archived | Efficacy trial comparing Levo. 5 mg and Deslo. 5 mg in SAR | Phase III | Double Blind | Global Medical Affairs Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Roobaert S | [6 empty] | No | Pilot, double blind, randomized, two parallel groups, clinical efficacy trial comparing Levocetirizine 5 mg capsules and Desloratadine 5 mg capsules taken once a day in the morning over 3 weeks of treatment in patients suffering from Seasonal Allergic Rhinitis (SAR) due to grass pollen. | Indication for Dermato Allergo | Immunology |  |  |  |  | 2015-05-12: 2004-11-16; 2016-01-18: 2005-05-23; 2016-11-29: 2005-06-15; 2020-01-06: 2005-07-11; 2020-02-04: 2005-09-22; 2020-02-25: 2005-10-10; 2020-07-02: 2006-03-09 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 250 | 200 | 0 | 215 | 0 | 15 | 200 | 200 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00392 | Study Archived | Efficacy trial comparing continuous vs. on demand treatment | Phase IV | Open | Global Medical Affairs Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Conrath P | Copetti C | [5 empty] | No | A pilot, open, monocenter randomized two parallel groups, clinical efficacy trial: comparison continuous vs. on demand regimen of treatment with Levocetirizine 5 mg oral tablets, once a day, in adults suffering from PErsistent allergic Rhinitis (PER) over 6 months. | Indication for Dermato Allergo | Immunology |  | 2004-06-22 |  | 2004-10-30 | 2004-10-26 | 2005-03-31 | 2005-03-11 | 2005-11-30 | 2005-11-29 | 2006-06-15 | 2006-06-21 | 2006-09-30 | 2006-10-26 | 2006-11-13 | 2007-01-25 | 2006-11-30 | 2007-06-12 | Italy | Italy (LPLV) | Italy | 0 | 1 | 1 | 120 | 100 | 0 | 66 | 0 | 4 | 62 | 0 | 22 | 40
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00393 | Created (Cancelled) | A cross-over study evaluating effects of Levo. in PAR |  |  | Clinical Development Europe |  | Clinical Development Europe | [7 empty] | No | A pilot double-blind, placebo controlled, cross-over study evaluating clinical and anti-inflammatory short and long term treatment effects of Levocetirizine 5 mg once daily in patients suffering from Persistent Allergic Rhinitis as defined by ARIA classification sensitized to HDM and grass pollen. | Indication for Dermato Allergo | Immunology | [20 empty] | 1 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00394 | CSR Approved | Levo vs Deslo in CIU patients | Phase IV | Double Blind | Global Medical Affairs Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Conrath P | Copetti C | [5 empty] | No | A multicentre, double-blind, two parallel groups, randomized trial over four weeks of treatment to compare the clinical efficacy and safety of Levocetirizine 5 mg oral capsules once daily in the morning vs Desloratadine 5 mg oral capsules once daily in the morning in patients suffering from Chronic | Indication for Dermato Allergo | Immunology |  |  | 2005-01-14 | 2005-02-28 | 2005-03-08 | 2005-10-31 | 2005-12-01 | 2006-12-06 | 2006-11-28 | 2006-12-29 | 2007-01-03 | 2007-03-16 | 2007-04-19 | 2007-04-30 | 2007-06-05 | 2007-06-15 | 2007-10-01 | Belgium, France, Germany, Italy, Malaysia, Romania, South Africa, Spain, United Kingdom | Belgium (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Malaysia (LPLV), Romania (LPLV), South Africa (LPLV), Spain (LPLV), United Kingdom (LPLV) | Belgium, France, Germany, Italy, Malaysia, Romania, South Africa, Spain, United Kingdom | 0 | 83 | 118 | 816 | 816 | 0 | 972 | 2 | 86 | 888 | 1 | 42 | 845
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00401 | CSR Approved | Comparative trial LCTZ versus Desloratadine | Phase IV | Double Blind | Global Medical Affairs Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Liard A |  |  | Quintiles, C.R.A., Keyrus |  |  |  | No | A multicentre, double-blind, parallel, randomized, placebo-controlled study : Evaluation of the efficacy and safety of Levocetirizine 5 mg and Desloratadine 5 mg administered orally as capsules once daily, in the morning, over 2 weeks in patients suffering from Allergic Rhinitis (AR) | Indication for Dermato Allergo | Immunology |  | 2004-09-01 |  | 2004-10-04 | 2004-10-19 | 2005-04-01 | 2005-04-21 | 2005-08-01 | 2005-08-11 | 2005-08-23 | 2005-09-12 | 2005-12-08 | 2005-12-09 | 2006-01-06 | 2006-01-10 | 2006-04-01 | 2006-03-27 | France, Germany, Italy | France (LPLV), Germany (LPLV), Italy (LPLV) | France, Germany, Italy | 0 | 0 | 53 | 750 | 729 | 0 | 862 | 0 | 96 | 766 | 0 | 55 | 711
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00403 | Study Archived | Bioequivalence Desloratadine | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | Global Medical Affairs | Daoust A, Mccabe S |  |  | Biotrial |  |  |  | Yes | Randomized, monocenter, open label, two-way crossover, single dose comparative bioavailability study of desloratadine 5 mg oral dose (tablet) with desloratadine 5 mg oral dose (over encapsulated tablet) in 24 healthy male and female subjects. | Indication for Dermato Allergo | Immunology |  |  |  |  | 2005-03-16 | 2005-04-22 | 2005-04-18 | 2005-05-08 | 2005-04-22 | 2005-05-30 | 2005-05-28 | 2005-07-04 | 2005-07-15 | 2005-08-18 | 2005-11-21 | 2005-08-29 | 2006-01-11 | France | France (LPLV) | France | 1 | 0 | 1 | 47 | 24 | 24 | 47 | 0 | 23 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00410 | CSR Approved | Korean study for local registrational purposes | Phase III | Double Blind / Double Dummy | Affiliates | TA Allergology / Respiratory | Affiliates | Beh K |  |  | C&R Research Inc, Korea |  |  |  | No | A multi-center,double-blind, double-dummy, randomized, active-controlled phase III study to evaluate the efficacy and safety ox Xyzal 5mg vs Zyrtec 10mg od in adults patients with dermatitis and eczema. | Indication for Dermato Allergo | Immunology |  |  | 2005-05-10 | 2005-07-01 | 2005-06-27 | 2005-09-22 | 2005-09-22 | 2006-02-10 | 2006-05-22 | 2006-02-28 | 2006-05-30 | 2006-04-30 | 2006-06-07 | 2006-06-15 | 2006-06-20 | 2006-08-07 | 2006-07-07 | South Korea | South Korea (LPLV) | South Korea | 6 | 5 | 6 | 468 | 310 | 310 | 374 | 1 | 32 | 341 | 18 | 34 | 289
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00411 | Study Archived | Bioequivalence Montelukast versus over encapsulation | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | Global Medical Affairs | Daoust A | [6 empty] | Yes | Randomized, monocenter, open label, two-way crossover, single dose comparative bioavailability study of montelukast 10 mg oral dose (tablet) with montelukast 10 mg oral dose (over encapsulated tablet), in 24 healthy fasting male and female subjects. | Indication for Dermato Allergo | Immunology |  |  |  |  | 2005-06-20 | 2005-09-01 | 2005-09-05 | 2005-09-30 | 2005-09-26 | 2005-10-10 | 2005-10-24 | 2005-11-17 | 2005-12-01 | 2006-01-16 | 2006-01-24 | 2006-02-24 | 2006-04-19 | France | France (LPLV) | France | 1 | 1 | 1 | 31 | 24 | 24 | 31 | 0 | 7 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00412 | Study Archived | Ragweed - Pollen Chamber | Phase III | Double Blind / Double Dummy | Clinical Development Europe | TA Allergology / Respiratory | R & D | Conrath P | Copetti C | [5 empty] | No | Double blind, double-dummy, five parallel groups, randomized, exploratory clinical trial to compare the efficacy of single dose of levocetirizine 2.5 mg oral drops (5 mg/ml), levocetirizine 5 mg oral tablets, cetirizine 5 mg oral drops (10 mg/ml) and cetirizine 10 mg oral tablets to placebo n reducing symptoms of seasonal allergic rhinitis (SAR) in ragweed sensitive subjects exposed to ragweed pollen in an Environmental Exposure Unit (EEU) | Indication for Dermato Allergo | Immunology |  |  |  |  | 2005-11-22 | 2006-01-28 | 2006-01-31 | 2006-03-28 | 2006-03-30 | 2006-04-15 | 2006-04-15 |  | 2006-05-05 | 2006-05-30 | 2006-05-24 | 2006-06-15 | 2006-06-20 | Canada | Canada (LPLV) | Canada | 1 | 1 | 1 | 900 | 541 | 0 | 699 | 0 | 135 | 551 | 0 | 5 | 546
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00414 | Study Archived | Levocetirizine vs Montelukast EEU1 | Phase III | Double Blind | Global Medical Affairs Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Conrath P | Copetti C |  | Linda Houle & associates Inc |  |  |  | No | Double-blind, three parallel randomized groups, therapeutic confirmatory clinical trial to compare the efficacy of oral levocetirizine 5 mg and montelukast 10 mg to placebo in reducing symptoms of seasonal allergic rhinitis (SAR) in ragweed sensitive subjects exposed to ragweed pollen in an environmental exposure unit (EEU) | Indication for Dermato Allergo | Immunology |  | 2006-02-13 | 2006-02-10 | 2006-03-31 | 2006-04-03 | 2006-07-29 | 2006-07-29 | 2006-09-09 | 2006-09-07 | 2006-10-01 | 2006-10-01 | 2006-11-01 | 2006-12-11 | 2006-12-15 | 2007-02-23 | 2007-01-15 | 2007-05-11 | Canada | Canada (LPLV) | Canada | 1 | 1 | 1 | 600 | 403 | 0 | 500 | 0 | 82 | 418 | 0 | 7 | 411
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00415 | CSR Approved | Levocetirizine vs Montelukast EEU2 | Phase IV | Double Blind | Global Medical Affairs Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Conrath P | Copetti C |  | Linda Houle & Associates Inc. |  |  |  | No | Double-blind, three parallel randomized groups, therapeutic confirmatory clinical trial to compare the efficacy of oral levocetirizine 5 mg and montelukast 10 mg to placebo in reducing symptoms of seasonal allergic rhinitis (SAR) in ragweed sensitive subjects exposed to ragweed pollen in an environmental exposure chamber (EEC) | Indication for Dermato Allergo | Immunology |  | 2006-02-08 | 2006-03-24 | 2006-04-15 | 2006-05-09 | 2006-07-15 | 2006-07-15 | 2006-09-21 | 2006-10-14 | 2006-10-05 | 2006-10-23 | 2006-11-30 | 2007-02-02 | 2007-01-02 | 2007-03-22 | 2007-02-15 | 2007-09-26 | Canada | Canada (LPLV) | Canada | 1 | 1 | 1 | 860 | 403 | 0 | 611 | 0 | 208 | 403 | 0 | 6 | 397
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00417 | Created (Cancelled) | Levocetirizine vs Montelukast SAR 1 (EEU) | Phase IV |  | UCB Pharma Global | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | [7 empty] | No |  | Indication for Dermato Allergo | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00418 | Created (Cancelled) | Levocetirizine vs Montelukast SAR 2 (EEU) | Phase IV |  | UCB Pharma Global | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | [7 empty] | No |  | Indication for Dermato Allergo | Immunology | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00419 | CSR Approved | LCTZ-US QTc | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A |  |  | Clinical phase: ATC Monitoring : SGS |  |  |  | Yes | Four-way crossover, randomized, placebo- and moxifloxacin-controlled study of the effect of levocetirizine on cardiac repolarization in 52 healthy male and female subjects. | Indication for Dermato Allergo | Immunology |  |  |  | 2006-02-28 | 2006-03-03 | 2006-04-18 | 2006-04-19 | 2006-05-22 | 2006-05-31 | 2006-07-04 | 2006-07-04 | 2006-08-18 | 2006-08-31 | 2006-09-28 | 2006-10-03 | 2006-10-23 | 2006-10-20 | Belgium | Belgium (LPLV) | Belgium | 1 | 1 | 1 | 75 | 52 | 52 | 75 | 0 | 23 | 52 | 0 | 0 | 52
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00420 | Study Archived | Observational study | Non Interventional Study - Prospective |  | Global Medical Affairs Europe | GMA Allergy/Respiratory/Inflam | Global Medical Affairs | Conrath P | Copetti C | [5 empty] | No | Evaluation of the Treatment Satisfaction in Children suffering from an Allergy and who received an Antihistamine treatment. |  |  |  | 2006-11-15 | 2006-11-24 | 2006-12-15 | 2007-01-19 | 2007-03-26 | 2007-03-26 | 2008-01-29 |  | 2008-01-29 |  | 2008-03-10 | 2008-05-30 | 2008-04-02 | 2008-06-16 | 2008-05-29 | 2008-11-25 | Bulgaria, Greece, India, Portugal, Romania, Russian Federation, South Korea, Spain | Bulgaria (FPFV), Greece (Created), India (Created), Portugal (Created), Romania (Created), Russian Federation (Created), South Korea (Created), Spain (Created) | Bulgaria | 0 | 0 | 1 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00423 | CSR Approved | Safety Levocetirizine in Pediatric Patients 6 to 11 Months | Phase III | Double Blind | Clinical Development USA | TA Allergology / Respiratory | R & D | [7 empty] | No | A Multi-Center, Randomized, Double-Blind, Placebo-Controlled Parallel-Group Study of the Safety of Levocetirizine Dihydrochloride Oral Liquid Formulation in Children Aged 6 Months to 11 Months with Symptoms of Allergic Rhinitis or Chronic Urticaria | Indication for Dermato Allergo | Immunology |  | 2007-05-08 | 2007-06-18 | 2007-08-31 | 2007-10-26 | 2008-01-25 | 2008-03-20 | 2008-06-20 | 2008-09-03 | 2008-07-08 | 2008-09-17 | 2008-09-05 | 2008-10-20 | 2008-10-02 | 2008-11-26 | 2008-12-26 | 2009-01-30 | United States of America | United States of America (LPLV) | United States of America | 20 | 27 | 27 | 80 | 80 | 0 | 93 | 0 | 24 | 69 | 0 | 4 | 65
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00426 | CSR Approved | Levocetirizine in Pediatric Patients 1 to 6 years of Age | Phase III | Double Blind | Clinical Development USA | TA Allergology / Respiratory | R & D | Hughes L | [6 empty] | No | A Multi-Center, Randomized, Double-Blind, Placebo-Controlled Parallel-Group Study of the Safety of Levocetirizine Dihydrochloride Oral Liquid Formulation b.i.d. Dosing in Children Aged 1 to Less Than 6 Years Suffering from Allergic Rhinitis or Chronic Urticaria of Unknown Origin | Indication for Dermato Allergo | Immunology |  | 2007-07-06 | 2007-06-18 | 2007-08-31 | 2007-10-26 | 2008-01-25 | 2008-03-13 | 2008-06-20 | 2008-06-13 | 2008-08-10 | 2008-07-08 | 2008-09-05 | 2008-08-27 | 2008-10-02 | 2008-11-26 | 2008-12-26 | 2009-01-20 | United States of America | United States of America (LPLV) | United States of America | 25 | 30 | 30 | 150 | 150 | 0 | 265 | 0 | 92 | 173 | 0 | 4 | 169
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00428 | CSR Approved | BE drops vs tablets China | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A |  |  | Excel PharmaStudies, Inc. |  |  |  | Yes | Randomized, monocenter, open label, two-way crossover, single dose bioequivalence study of levocetirizine given as either 1mL oral drops formulation (5 mg/mL) or as a 5 mg oral tablet in 24 healthy fasting Chinese male subjects | Indication for Dermato Allergo | Immunology |  | 2007-06-25 |  | 2007-07-16 | 2007-07-18 | 2007-10-09 | 2007-10-09 | 2007-10-08 | 2007-10-09 | 2007-11-01 | 2007-10-26 | 2007-12-07 | 2007-12-07 | 2008-02-08 | 2008-02-08 | 2008-03-28 | 2008-03-24 | China | China (LPLV) | China | 1 | 1 | 1 | 48 | 24 | 24 | 35 | 0 | 11 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00430 | CSR Approved | Seasonal Allergic Rhinitis 1 | Phase IV | Double Blind | Affiliates | GMA Allergy/Respiratory/Inflam | Affiliates | Lenon W, Texter M | [6 empty] | No | A multi-center, randomized, double-blind, placebo-controlled, parallel-group study evaluating the efficacy and impact on health-related quality of life of levocetirizine 5 mg once daily given for 2 weeks in subjects 18 years of age and older with seasonal allergic rhinitis |  |  |  | 2007-06-22 | 2007-10-29 | 2007-11-30 | 2007-12-19 | 2008-03-03 | 2008-03-27 | 2008-05-05 | 2008-05-14 | 2008-06-02 | 2008-06-04 | 2008-06-20 | 2008-08-22 | 2008-07-21 | 2008-12-05 | 2008-10-10 | 2009-06-05 | United States of America | United States of America (LPLV) | United States of America | 40 | 44 | 30 | 730 | 556 | 278 | 791 | 0 | 195 | 596 | 0 | 15 | 581
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A00431 | CSR Approved | Seasonal Allergic Rhinitis 2 | Phase IV | Double Blind | Affiliates | GMA Allergy/Respiratory/Inflam | Affiliates | Lenon W, Texter M | [6 empty] | No | A multi-center, randomized, double-blind, placebo-controlled, parallel group study evaluating the efficacy and impact on health-related quality of life of levocetirizine 5mg once daily given for 2 weeks in subjects 18 years of age and older with seasonal allergic rhinitis |  |  |  | 2007-06-22 | 2007-10-29 | 2007-11-30 | 2007-12-19 | 2008-03-03 | 2008-04-25 | 2008-05-05 | 2008-06-18 | 2008-06-02 | 2008-07-14 | 2008-06-20 | 2008-09-30 | 2008-07-21 | 2008-12-05 | 2008-10-10 | 2009-05-05 | United States of America | United States of America (LPLV) | United States of America | 40 | 46 | 40 | 730 | 556 | 278 | 824 | 0 | 244 | 580 | 0 | 13 | 567
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A217 | Study Archived | Dose ranging SAR | Phase II |  | Clinical Development Europe | TA Allergology / Respiratory | R & D | Arendt C, Liard A | [6 empty] | No | Multicentre, randomized, parallel group, placebo-controlled double-blind trial comparing the efficacy and the safety of ucb 28556 tablets of 2.5 mg, 5 mg and 10 mg, given once a day per os for 2 weeks in adult patients with seasonal allergic rhinitis to g rass and/or weed pollen | [19 empty] | France, Germany | France (Created), Germany (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A219 | Study Archived | Dose ranging PAR | Phase II |  | Clinical Development Europe | TA Allergology / Respiratory | R & D | Pinelli M | [6 empty] | No | A randomised, multicentre, double-blind, phase II study with four parallel groups, comparing the efficacy and safety of 2,5 mg, 5 mg and 10 mg tablets of ucb 28556, versus placebo, administered orally, once a day, in the evening during four weeks, patien | [6 empty] | 2015-05-12: 1996-06-27; 2016-01-18: 1996-09-06; 2020-01-06: 1997-04-16; 2020-02-04: 1997-06-24; 2020-07-02: 1999-12-21 | France | France (LPLV) | France | 35 | 0 | 35 | 421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A221 | Study Archived | Comparison PK ucb28556 - cetirizine | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Voss G | [6 empty] | Yes | Open, randomized, two-way cross-over study to compare the oral disposition of ucb 28556 when given alone (10 mg) or as a racemate (cetirizine.2HCl - 20 mg) as a single dose of an extemporaneous solution in healthy volunteers under fasting conditions | [6 empty] | 2015-05-12: 1997-07-31; 2016-01-18: 1997-09-25; 2020-01-06: 1997-11-04; 2020-02-04: 1998-04-30; 2020-07-02: 1999-06-29 | Germany | Germany (LPLV) | Germany | 1 | 0 | 1 | 24 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A222 | Study Archived | Bridging SAR | Phase III |  | Clinical Development Europe | TA Allergology / Respiratory | R & D | Pinelli M | [6 empty] | No | A randomised multicentre double blind, phase III study, with three parallel group, comparing the efficacy and the safety of 5 mg ucb 28556, 10 mg cetirizine and placebo tablets, administered orally, once a day, in the evening, during one week, in patients suffering from seasonal allergic rhinitis to grass and/or weed pollen | [6 empty] | 2015-05-12: 1997-01-01; 2020-02-04: 1997-10-27; 2020-07-02: 1999-11-25 |  |  |  | 50 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A230 | Study Archived | PK renal impeirment | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Daoust A | [6 empty] | No | Open-label, not randomised, multicentre, single dose pharmacokinetics study of 5 mg of ucb 28556, orally administered in subjects with normal renal function or with different degrees of renal function impairment. | [6 empty] | 2015-05-12: 1997-09-11; 2016-01-18: 1997-11-10; 2020-01-06: 1998-03-30; 2020-02-04: 1998-06-30; 2020-07-02: 1999-03-26 | Belgium, Czech Republic | Belgium (LPLV), Czech Republic (LPLV) | Belgium, Czech Republic | 1 | 0 | 4 | 0 | 0 | 0 | 24 | 0 | 6 | 18 | 0 | 0 | 18
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A232 | Study Archived | Oral disposition 3 formulations | Phase I |  | Clinical Development Europe | TA Allergology / Respiratory | R & D | Daoust A | [6 empty] | Yes | Open, randomised ,3-way cross-over, single dose study to compare oral bioavailability of two formulations of ucb 28556 (5 mg tab. used in clinical trials, 5 mg tab. proposed for Marketing authorization purpose) to a 5mg extemporaneous sol. of ucb 28556 in normal healthy male and female volunteers under fasting condition | [6 empty] | 2015-05-12: 1997-10-30; 2016-01-18: 1997-12-23; 2020-01-06: 1998-01-30; 2020-02-04: 1998-06-08; 2020-07-02: 1999-11-25 | France | France (LPLV) | France | 1 | 0 | 1 | 24 | 0 | 0 | 31 | 0 | 7 | 24 | 24 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A233 | Study Archived | ADME | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Arendt C | [6 empty] | Yes | The excretion and plasma kinetics of total radioactivity in man following a single oral administration of [14C)-ucb 28556 , 5 mg in a gelatin capsule, An open study in Healthy volunteers | [6 empty] | 2015-05-12: 1997-11-27; 2016-01-18: 1997-12-09; 2020-01-06: 1998-01-07; 2020-02-04: 1999-04-01; 2020-07-02: 2000-01-11 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A234 | Study Archived | Renal impairment, hemodialysed | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Liard A | [6 empty] | No | Open-label, not randomized, monocentre, single dose pharmacokinetic study of 5 mg of ucb 28556, orally administered in subjects with end stage renal disease undergoing hemodialysis | [6 empty] | 2015-05-12: 1998-04-16; 2016-01-18: 1998-05-25; 2020-01-06: 1998-06-26; 2020-02-04: 1998-06-26; 2020-07-02: 1998-10-28 | Belgium | Belgium (LPLV) | Belgium | 1 | 0 | 1 | 5 | 0 | 0 | 7 | 0 | 2 | 5 | 0 | 0 | 5
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A238 | Study Archived | Food effect on bioavailability steady state | Phase I |  | Clinical Development Europe | Clinical Pharmaco | R & D | Liard A | [6 empty] | Yes | Open,rando.study to determine food effect on oral bioavail. of ucb28556(5mg tab) after single administ.,and to measure the PK parameters ucb28556(5 mg tab) at steady-state,after repeated administ for 8 days,in normal healthy M&F vol.in fasting condition | [6 empty] | 2015-05-12: 1998-02-11; 2016-01-18: 1998-04-08; 2020-01-06: 1998-05-29; 2020-02-04: 1999-02-19; 2020-07-02: 2000-01-25 | France | France (LPLV) | France | 1 | 0 | 1 | 20 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 1 | 20
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A239 | CSR Approved | ADME | Phase I |  | Clinical Development USA | Clinical Pharmaco | R & D | Decesare L | [6 empty] | Yes | The excretion and plasma kinetics of total radioactivity in main following a single oral administration of (14C) - ucb 28754, 30 mg in a gelatin capsule: an open study in healthy volunteers. | [6 empty] | 2015-05-12: 1998-02-20; 2016-01-18: 1998-02-27; 2020-01-06: 1998-03-12; 2020-02-04: 1999-03-26; 2020-07-02: 1999-07-30 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A245 | Study Archived | PAR - Pollinic chamber vs loratadine | Phase II |  | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | Gerard D | [6 empty] | No | A randomised double-blind, three way cross-over, placebo controlled study to assess the efficacy and safety of LEVOCETIRIZINE 5 mg od (oral capsules) and LORATADINE 10 mg od (oral capsules) in reducing symptoms of perennial allergic rhinitis in house dust | [6 empty] | 1999-03-16 | 1999-09-20 | 1999-10-18 |  |  | 1999-12-01 | 1999-12-01 | 2000-03-01 | 2000-05-30 |  | 2000-12-08 | 2000-06-01 | 2000-12-08 | Austria | Austria (LPLV) | Austria | 1 | 0 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A246 | Study Archived | Vigilance | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | Global Medical Affairs | Riethuisen J | [6 empty] | Yes | A double blind, mono-center, placebo-controlled, randomized, crossover study to investigate the equivalence between levocetirizine 5 mg o.d. and placebo capsules p.o. in single gdose and repeated dosing in over-the-road driving performance and psychomotor tests in healthy volunteers, with diphenhydr amine 50 mg capsules o.d. as active control. | Indication for Dermato Allergo | Immunology |  |  |  | 2000-02-10 | 2000-02-04 | 2000-03-31 | 2000-04-17 |  |  | 2001-03-31 | 2001-05-18 | 2001-05-30 | 2001-07-07 |  |  | 2001-09-01 | 2001-12-17 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 0 | 1 | 48 | 48 | 48 | 54 | 0 | 3 | 51 | 0 | 3 | 48
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A252 | Study Archived | Histamine Wheal and Flare | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | Global Medical Affairs | Moulaert B | [6 empty] | Yes | Double-blind, single oral dose, 6 way cross-over study to compare of Levocetirizine 5 mg, ebastine 10 mg, fexo 180 mg, lora 10 mg, mizolastine 10 mg and placebo on histamine induced wheals and flares during 24 hours in 18 healthy male subjects | Indication for Dermato Allergo | Immunology |  |  |  | 1999-04-22 | 1999-04-22 | 1999-05-14 | 1999-05-07 |  |  | 1999-07-10 | 1999-08-16 | 1999-09-02 | 1999-11-08 |  |  | 1999-12-20 | 2000-07-18 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 0 | 1 | 0 | 0 | 0 | 40 | 0 | 21 | 19 | 0 | 1 | 18
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A254 | Study Archived | Eosinophil recruitment | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | Global Medical Affairs | Daoust A | [6 empty] | No | Etude pharmacologique, monocentrique, croisée, randomisée, en double aveugle, contrôlée par un placébo, d'un comprimé de levocetirizine 5 mg administré pendant 6 jours dans la réaction cutanée d'hypersensibilité dépendante des IgE chez les patients allergiques aux pollens de graminées. | Indication for Dermato Allergo | Immunology |  |  |  | 1999-08-01 | 1999-08-05 | 1999-10-01 | 1999-10-28 |  |  | 2000-02-01 | 2000-03-13 | 2000-04-01 | 2000-06-09 |  |  | 2000-06-30 | 2000-12-04 | France | France (LPLV) | France | 1 | 0 | 1 | 0 | 0 | 0 | 25 | 0 | 10 | 15 | 0 | 0 | 15
Yes | Not assigned | Managing Type | 1 | XYZAL | Immunology | A256 | Study Archived | SAR - Pollinic chamber vs loratadine | Phase II |  | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | Gerard D | [6 empty] | No | A randomized double-blind, three way cross-over, placebo-controlled study to assess the efficacy and safety of LEVOCETIRIZINE 5 mg od (oral capsules) and LORATADINE 10 mg od (oral capsules) in reducing symptoms of seasonal allergic rhinitis in grass-polle | [5 empty] | 1999-09-30 | 1999-11-25 | 1999-12-15 | 1999-12-20 |  |  | 2000-02-15 | 2001-03-16 | 2000-05-01 | 2001-06-11 |  | 2001-08-24 | 2000-07-31 | 2001-11-22 | Austria | Austria (LPLV) | Austria | 1 | 0 | 1 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Zampilimab | Immunology | UP0029 | Study Archived | FiH study to evaluate the safety/tolerability and PK of SAD | Phase I | Double Blind | GED | Immunology | GED | Nicholl R | Grose-Hodge R | Parexel | PAREXEL | Yes | Yes | adults | Yes | A SUBJECT-BLIND, INVESTIGATOR-BLIND, RANDOMIZED, PLACEBO-CONTROLLED, FIRST IN HUMAN STUDY EVALUATING THE SAFETY/TOLERABILITY, PHARMACOKINETICS, EFFECT ON TRANSGLUTAMINASE 2 EXPRESSION, AND OCCUPANCY OF SINGLE ASCENDING INTRAVENOUS AND SUBCUTANEOUS DOSES OF UCB7858 IN HEALTHY SUBJECTS | All Indications; Healthy Volunteers | Immunology; Immunology |  | 2016-02-16 | 2016-02-15 |  | 2016-05-03 | 2016-06-29 | 2016-07-11 | 2017-06-10 | 2017-09-28 | 2017-08-21 | 2018-01-31 | 2017-09-18 | 2018-02-28 | 2017-10-25 | 2018-03-23 | 2018-01-18 | 2018-08-28 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 114 | 80 | 80 | 204 | 0 | 90 | 114 | 0 | 2 | 112
Yes | Not assigned | Managing Type | 1 | Zilucoplan | Central Nervous System | PNH002 | CSR Approved | RA101495-01.201 | Phase II |  | UCB Pharma Global | Neurology | UCB Pharma Global | [7 empty] | No |  | Paroxysmal Nocturnal Hemoglobinuria | Immunology | PNH002 is a feeder study of PNH001 |  |  |  | 2015-05-12: 2016-10-20; 2016-01-18: 2017-04-19; 2020-01-06: 2018-01-18; 2020-02-25: 2019-06-25; 2020-07-02: 2019-06-25 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Zilucoplan | Central Nervous System | PNH003 | CSR Approved | RA101495-01.203 | Phase II |  | UCB Pharma Global | Neurology | UCB Pharma Global | [7 empty] | No |  | Paroxysmal Nocturnal Hemoglobinuria | Immunology | PNH003 is a feeder study of PNH001 |  |  |  | 2015-05-12: 2016-10-20; 2016-01-18: 2017-09-07; 2020-01-06: 2018-02-08; 2020-07-02: 2019-06-25 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Zilucoplan | not defined | UP0112 | CSR Approved | RA101495-1001 | Phase I |  | UCB Pharma Global | Neurology | UCB Pharma Global | [7 empty] | No |  | Amyotrophic Lateral Sclerosis (ALS) | Central Nervous System |  |  |  |  | 2015-05-12: 2015-11-08; 2016-01-18: 2015-11-18; 2020-01-06: 2016-04-12; 2020-07-02: 2016-04-15 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Zilucoplan | not defined | UP0113 | CSR Approved | RA101495-01.102 | Phase I |  | UCB Pharma Global | Neurology | UCB Pharma Global | [7 empty] | No |  | Amyotrophic Lateral Sclerosis (ALS) | Central Nervous System |  |  |  |  | 2015-05-12: 2018-09-07; 2016-01-18: 2018-09-24; 2020-01-06: 2019-01-24; 2020-07-02: 2019-07-23 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | Zilucoplan | not defined | UP0114 | CSR Approved | RA101495-03.101 | Phase I |  | UCB Pharma Global | Neurology | UCB Pharma Global | [7 empty] | No |  | Amyotrophic Lateral Sclerosis (ALS) | Central Nervous System |  |  |  |  | 2015-05-12: 2017-08-08; 2016-01-18: 2017-12-12; 2020-01-06: 2018-07-03; 2020-07-02: 2019-01-03 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ZYRTEC | Immunology | 9322 | Study Archived | ETAC | Phase II |  | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | De Vleeschouwer C | [6 empty] | No | The early development of the atopic child (E.T.A.C.): evaluation of the efficacy and safety of cetirizine in preventing the onset of asthma in children at high risk who suffer from atopic dermatitis: a multi-country, double-blind, randomised, placebo con | [6 empty] | 2015-05-12: 1993-12-09; 2015-09-29: 1994-01-01; 2019-11-29: 1998-12-31; 2020-02-04: 1999-10-16; 2020-02-25: 2000-03-31; 2020-07-02: 2000-08-22 | Austria, Belgium, Canada, Czech Republic, France, Germany, Italy, Luxembourg, Netherlands, Norway, Spain, Sweden, Switzerland, United Kingdom | Austria (Created), Belgium (Created), Canada (Created), Czech Republic (Created), France (Created), Germany (Created), Italy (Created), Luxembourg (Created), Netherlands (Created), Norway (Created), Spain (Created), Sweden (Created), Switzerland (Created), United Kingdom (Created) |  | 61 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ZYRTEC | Immunology | 9643 | Study Archived | 2 weeks treatmt at nasal & bronchial level in young children | Phase II | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | Global Medical Affairs | Gerard D |  |  | M.B. Daubresse D. Gérard |  |  |  | No | Pilot, Double-Blind, Placebo controlled, randomized study: Evaluation of the pharmacological effect of a 2 week treatment with Cetirizine (drops, 0.25 mg/kg bid) at nasal and bronchial level in young children at the onset of asthma. | Indication for Dermato Allergo | Immunology |  |  |  |  | 1997-06-02 | 1998-01-01 | 1998-09-14 |  | 2000-12-18 | 1999-12-31 | 2001-01-02 |  | 2002-05-27 |  | 2002-07-26 |  | 2003-03-17 | Belgium, Czech Republic, France, United Kingdom | Belgium (LPLV), Czech Republic (LPLV), France (LPLV), Italy (1st Site Initiation (Cancelled)), United Kingdom (LPLV) | Belgium, Czech Republic, France, United Kingdom | 6 | 7 | 4 | 70 | 60 | 50 | 52 | 0 | 4 | 48 | 0 | 2 | 46
Yes | Not assigned | Managing Type | 1 | ZYRTEC | Immunology | 9706 | CSR Approved | Minimal persistent inflamation control by cetirizine | Phase III | Double Blind | Clinical Development Europe | TA Allergology / Respiratory | Affiliates - Italy | Segaut C | [6 empty] | No | Minimal persistent inflammation control by cetirizine during 3 months (oral drops, od, 5 to 10 mg) in children, 4-10 y with upper respiratory allergy to mites : a multicenter, plc controlled, DB study (open recue medication : cetirizine "on demand") | Indication for Dermato Allergo | Immunology |  |  |  |  | 2015-05-12: 1997-08-04; 2016-01-18: 1999-09-22; 2020-01-06: 2001-04-26; 2020-02-04: 2003-11-10; 2020-02-25: 2004-01-05; 2020-07-02: 2008-08-29 | Italy | Italy (LPLV) | Italy | 12 | 0 | 1 | 120 | 0 | 0 | 0 | 0 | 0 | 108 | 0 | 23 | 85
Yes | Not assigned | Managing Type | 1 | ZYRTEC | Immunology | 9716 | Study Archived | Corticoïd sparing effect - broch. Asthma | Phase III | Double Blind | Affiliates - France | TA Allergology / Respiratory | Affiliates - France | Liard A | [6 empty] | No | Etude comparative en double aveugle versus placebo de la cetirizine 20mg/j sur 6 mois pour réduire la consommation de corticoïdes inhalés chez des patients porteurs d'un asthme bronchique persistant modéré | Indication for Dermato Allergo | Immunology |  |  |  |  | 2015-05-12: 1997-06-05; 2016-01-18: 1997-10-16; 2020-01-06: 1999-11-16; 2020-02-04: 2000-02-29; 2020-07-02: 2003-03-25 | France | France (LPLV) | France | 15 | 0 | 1 | 200 | 200 | 0 | 203 | 0 | 1 | 202 | 0 | 30 | 172
Yes | Not assigned | Managing Type | 1 | ZYRTEC | Immunology | 9913 | Study Archived | ETAC - long-term follow-up | Phase II |  | Global Medical Affairs Europe | TA Allergology / Respiratory | Global Medical Affairs | Roobaert S | [6 empty] | No | The early treatment of atopic child (E.T.A.C.): evaluation of the efficacy and safety of ceti in preventing the onset of asthma in children at high risk who suffer from atopic dermatitis: a multi country, double-blind, randomized, placebo controlled trial. | [6 empty] | 1999-03-03 | 1999-09-15 | 1998-01-13 |  |  | 2001-01-01 | 2001-03-07 | 2001-03-01 | 2001-11-19 |  | 2002-01-17 | 2001-06-01 | 2003-01-23 | Belgium, Czech Republic, France, Germany, Italy, Netherlands, Sweden, United Kingdom | Belgium (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Netherlands (LPLV), Sweden (LPLV), United Kingdom (LPLV) | Belgium, Czech Republic, France, Germany, Italy, Netherlands, Sweden, United Kingdom | 22 | 0 | 21 | 400 | 400 | 400 | 0 | 0 | 0 | 335 | 0 | 0 | 335
Yes | Not assigned | Managing Type | 1 | ZYRTEC | Immunology | 9918 | Study Archived | PAR - children 2-12 y | Phase IV | Double Blind | Affiliates - France | TA Allergology / Respiratory | Affiliates - France | [7 empty] | No | Etude multicentrique en DB et groupes par. vs plc : éval. de l'eff. et tolérence de la ceti chez des enfants de 2 à 12 ans (5mg po (10 gouttes) pour enfants de (2-6) ans et 10 mg po (20 gouttes) pour enfants de (6-12) ans) présentant PAR traités pdt 28j | Indication for Dermato Allergo | Immunology |  |  |  |  | 2015-05-12: 1999-06-11; 2016-01-18: 1999-10-05; 2020-01-06: 2000-05-25; 2020-02-04: 2001-03-20; 2020-07-02: 2004-11-09 | France | France (LPLV) | France | 25 | 0 | 1 | 170 | 170 | 0 | 171 | 0 | 7 | 164 | 0 | 5 | 159
Yes | Not assigned | Managing Type | 1 | ZYRTEC | Immunology | 9920 | Study Archived | AIDS - Anti protease | Phase I | Open | Global Medical Affairs Europe | Clinical Pharmaco | Global Medical Affairs | Liard A, Moulaert B | [6 empty] | Yes | Etude comp,ouverte, menée en 3 périodes successives de l'interaction pharmacocinétique entre la cetirizine (10 mg/j 1 fois par jour per os) et le ritonavir, capsule (600 mg 3 fois par jour per os) à l'état d'équilibre chez des adultes volontaires sains de sexe masculin. | Indication for Dermato Allergo | Immunology |  |  | 1999-05-26 | 1999-09-21 | 1999-11-10 | 2000-03-01 | 2000-04-10 |  | 2000-06-19 | 2000-07-01 | 2000-08-31 | 2000-09-15 | 2001-09-17 |  | 2002-08-21 | 2000-12-31 | 2002-12-13 | France | France (LPLV) | France | 1 | 1 | 1 | 20 | 18 | 16 | 22 | 0 | 5 | 17 | 0 | 1 | 16
Yes | Not assigned | Managing Type | 1 | ZYRTEC | Immunology | A00275 | CSR Approved | CTZ Pediatric study in PAR | Phase III | Double Blind | Clinical Development Japan | Clinical Development Japan | R & D | Mashimo H | Matsuoka K | [5 empty] | No | Double-blind comparative study of cetirizine in children protocol : a confirmatory trial on pediatric perennial allergic rhinitis in comparison with ketotifen as the control drug. | Indication for Dermato Allergo | Immunology |  |  |  | 2001-10-01 | 2001-12-06 | 2002-06-15 | 2002-08-27 |  | 2003-02-15 | 2003-07-31 | 2003-03-10 | 2003-11-30 | 2003-09-12 |  |  | 2004-03-31 | 2005-10-18 | Japan | Japan (LPLV) | Japan | 17 | 0 | 17 | 250 | 150 | 0 | 0 | 0 | 0 | 149 | 0 | 4 | 145
Yes | Not assigned | Managing Type | 1 | ZYRTEC | Immunology | A00276 | Study Archived | Pharmacogenetic studies | Phase II | Open | Clinical Development Europe | TA Allergology / Respiratory | R & D | Pinelli M, Segaut C |  |  | Quintiles Innovex 1 CRA only (EVH) |  |  |  | No | Genetic studies of atopic dermatitis and atopy in the ETAC cohort (GenETAC) | Indication for Dermato Allergo | Immunology |  |  | 2000-10-19 | 2001-04-23 | 2001-05-09 | 2001-09-01 | 2002-08-06 |  | 2003-07-25 |  | 2003-07-25 | 2004-03-01 | 2005-07-27 |  |  | 2004-05-01 | 2005-07-31 | Czech Republic, France, Germany, Italy, Netherlands, Sweden, United Kingdom | Czech Republic (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Netherlands (LPLV), Sweden (LPLV), United Kingdom (LPLV) | Czech Republic, France, Germany, Italy, Netherlands, Sweden, United Kingdom | 20 | 0 | 18 | 400 | 400 | 400 | 0 | 0 | 0 | 262 | 0 | 0 | 262
Yes | Not assigned | Managing Type | 1 | ZYRTEC | Immunology | A00277 | Study Archived | Biobank | Phase II |  | Global Medical Affairs Europe | TA Allergology / Respiratory | Global Medical Affairs | Roobaert S | [6 empty] | No | Substudy IgE Birch and Peanuts | Indication for Dermato Allergo | Immunology |  |  |  |  | 2020-02-04: 2001-06-25; 2020-02-25: 2001-07-23; 2020-07-02: 2003-02-24 |  |  |  | 56 | 0 | 0 | 817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 1 | ZYRTEC | Immunology | A00291 | Study Archived | Wheal & Flare - Desloratadine | Phase I | Double Blind | Clinical Development Europe | Clinical Pharmaco | Global Medical Affairs | Melac M | [6 empty] | No | Double-blind, randomized, placebo controlled, single oral dose, cross-over trial to compare cetirizine (tablet 10mg) and desloratadine (tablet 5 mg) on histamine induced wheal and flare during 24 hours in 18 healthy volunteers | Indication for Dermato Allergo | Immunology |  |  |  | 2001-04-10 | 2001-04-10 | 2001-07-01 | 2001-06-25 |  |  | 2001-09-30 | 2001-08-17 | 2001-11-30 | 2001-11-15 |  |  | 2002-01-15 | 2002-04-09 | France | France (LPLV) | France | 1 | 0 | 1 | 0 | 0 | 0 | 20 | 0 | 2 | 18 | 0 | 0 | 18
Yes | Not assigned | Managing Type | 1 | ZYRTEC | Immunology | A00295 | Study Archived | Orodispersible tablet - bioequivalence | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Moulaert B | [6 empty] | Yes | Randomized, Monocenter, open label, crossover, single dose bioequivalence, study, of ceterizine,dichloride 10 mg orodispersible tablet, and ceterizine dichloride 10 mg oral tablet in 24 healthy fasting male and female subjects | Indication for Dermato Allergo | Immunology |  |  |  | 2001-01-22 | 2001-01-22 | 2001-03-02 | 2001-03-02 |  |  | 2001-03-30 | 2001-03-26 | 2001-05-11 | 2001-07-31 |  |  | 2001-08-10 | 2001-08-10 | Belgium | Belgium (LPLV) | Belgium | 1 | 0 | 1 | 0 | 0 | 0 | 29 | 0 | 5 | 24 | 0 | 0 | 24
Yes | Not assigned | Managing Type | 1 | ZYRTEC | Immunology | A00332 | Study Archived | CTZ Chewable | Phase I | Open | Clinical Development Europe | Clinical Pharmaco | R & D | Moulaert B |  |  | SGS Biopharma / UCB |  |  |  | Yes | Randomized, monocenter, open label, three-way crossover, bioequivalence study of cetirizine 10 mg chewable tablet taken without or with 240 mL of water, with cetirizine 10 mg reference tablet (Zyrtec), after single oral administration in 20 healthy subjects. | Indication for Dermato Allergo | Immunology |  |  |  | 2002-04-03 | 2002-04-09 | 2002-04-29 | 2002-04-25 |  |  | 2002-06-10 | 2002-06-20 | 2002-08-14 | 2002-09-23 |  | 2002-10-07 | 2002-11-20 | 2003-01-09 | Belgium | Belgium (LPLV) | Belgium | 1 | 0 | 1 | 33 | 20 | 20 | 33 | 0 | 13 | 20 | 0 | 0 | 20
Yes | Not assigned | Managing Type | 1 | ZYRTEC | Immunology | A00413 | CSR Approved | Pop PK Pediatric Japan | Meta-analysis |  | UCB Pharma Global | Clinical Pharmaco | R & D | [7 empty] | No | [7 empty] | 2020-07-02: 2006-08-29 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Not assigned | Managing Type | 2 | BIMZELX | Immunology | RA0123 | Study Archived | Combo RA | Phase II | Double Blind | GED | Immunology | UCB Pharma Global | Soranson J | Grose-Hodge R | PRA | PRA | No | Yes | adults | No | A DOUBLE-BLIND, RANDOMIZED, PLACEBO-CONTROLLED STUDY EVALUATING THE SAFETY, PHARMACOKINETICS, PHARMACODYNAMICS, AND EFFICACY OF MULTIPLE DOSES OF UCB4940 ADMINISTERED AS ADD-ON TO CERTOLIZUMAB PEGOL THERAPY IN SUBJECTS WITH MODERATE-TO-SEVERE RHEUMATOID ARTHRITIS | Rheumatoid Arthritis | Immunology |  | 2014-05-30 | 2014-06-19 |  | 2014-12-11 | 2015-04-24 | 2015-05-05 | 2016-03-15 | 2016-05-19 | 2017-02-07 | 2017-04-19 | 2017-02-21 | 2017-12-11 | 2017-03-21 | 2018-01-19 | 2017-06-13 | 2018-03-23 | Czech Republic, Hungary, Moldavia, Poland, Russian Federation, Slovakia, United Kingdom | Czech Republic (LPLV), Hungary (LPLV), Moldavia (LPLV), Poland (LPLV), Russian Federation (LPLV), Slovakia (LPLV), United Kingdom (LPLV) | Czech Republic, Hungary, Moldavia, Poland, Russian Federation, Slovakia, United Kingdom | 15 | 23 | 21 | 400 | 102 | 102 | 289 | 0 | 130 | 159 | 0 | 27 | 132
Yes | Not assigned | Managing Type | 2 | FERRO SANOL | Immunology | SP0986 | Study Archived | Comparative trial with Ferro Sanol & Niferex | Phase III | Double Blind / Double Dummy | UCB Pharma Global | Clinical Development Japan | UCB Pharma Global | Guo J | Grose-Hodge R | N/A | Tigermed |  |  | adults | No | A double-blind, double-dummy, parallel, active-controlled, randomized and multi-center trial to investigate efficacy and safety in subjects with iron deficiency anemia for Ferrous (II) Glycine Sulphate Complex versus Polyferose Capsules therapy | Iron Deficiency Anemia | Immunology |  | 2010-09-06 | 2010-04-02 |  | 2010-10-08 | 2011-03-29 | 2011-04-02 | 2011-11-25 | 2013-07-25 |  | 2013-11-14 |  | 2014-03-19 |  | 2014-04-25 |  | 2014-11-07 | China | China (LPLV) | China | 11 | 16 | 15 | 280 | 240 | 0 | 295 | 4 | 44 | 247 | 0 | 37 | 210
Yes | Not assigned | Non-managing Type | 2 | CIMZIA | Immunology | RA0123 | Study Archived | Combo RA | Phase II | Double Blind | GED | Immunology | UCB Pharma Global | Soranson J | Grose-Hodge R | PRA | PRA | No | Yes | adults | No | A DOUBLE-BLIND, RANDOMIZED, PLACEBO-CONTROLLED STUDY EVALUATING THE SAFETY, PHARMACOKINETICS, PHARMACODYNAMICS, AND EFFICACY OF MULTIPLE DOSES OF UCB4940 ADMINISTERED AS ADD-ON TO CERTOLIZUMAB PEGOL THERAPY IN SUBJECTS WITH MODERATE-TO-SEVERE RHEUMATOID ARTHRITIS | Rheumatoid Arthritis | Immunology |  | 2014-05-30 | 2014-06-19 |  | 2014-12-11 | 2015-04-24 | 2015-05-05 | 2016-03-15 | 2016-05-19 | 2017-02-07 | 2017-04-19 | 2017-02-21 | 2017-12-11 | 2017-03-21 | 2018-01-19 | 2017-06-13 | 2018-03-23 | Czech Republic, Hungary, Moldavia, Poland, Russian Federation, Slovakia, United Kingdom | Czech Republic (LPLV), Hungary (LPLV), Moldavia (LPLV), Poland (LPLV), Russian Federation (LPLV), Slovakia (LPLV), United Kingdom (LPLV) | Czech Republic, Hungary, Moldavia, Poland, Russian Federation, Slovakia, United Kingdom | 15 | 23 | 21 | 400 | 102 | 102 | 289 | 0 | 130 | 159 | 0 | 27 | 132
Yes | Not assigned | Non-managing Type | 2 | Polysaccharide Iron Complex | Immunology | SP0986 | Study Archived | Comparative trial with Ferro Sanol & Niferex | Phase III | Double Blind / Double Dummy | UCB Pharma Global | Clinical Development Japan | UCB Pharma Global | Guo J | Grose-Hodge R | N/A | Tigermed |  |  | adults | No | A double-blind, double-dummy, parallel, active-controlled, randomized and multi-center trial to investigate efficacy and safety in subjects with iron deficiency anemia for Ferrous (II) Glycine Sulphate Complex versus Polyferose Capsules therapy | Iron Deficiency Anemia | Immunology |  | 2010-09-06 | 2010-04-02 |  | 2010-10-08 | 2011-03-29 | 2011-04-02 | 2011-11-25 | 2013-07-25 |  | 2013-11-14 |  | 2014-03-19 |  | 2014-04-25 |  | 2014-11-07 | China | China (LPLV) | China | 11 | 16 | 15 | 280 | 240 | 0 | 295 | 4 | 44 | 247 | 0 | 37 | 210
Yes | Phase I | Managing Type | 1 | Bepranemab | Central Nervous System | PSP003 | Study Archived | Safety and PK evaluation of UCB0107 in PSP patients | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Van Den Steen B | Cain D | ICON | ICON | Yes | Yes | adults | No | A PARTICIPANT-BLIND, INVESTIGATOR-BLIND, PLACEBO CONTROLLED, PHASE 1B STUDY TO EVALUATE THE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF UCB0107 IN STUDY PARTICIPANTS WITH PROGRESSIVE SUPRANUCLEAR PALSY (PSP) | PSP Progressive supranuclear palsy | Central Nervous System | PSP003 is a parent study of PSP002 | 2019-06-12 08:00 | 2019-06-12 |  | 2019-07-12 | 2019-11-27 | 2019-12-03 | 2020-01-27 | 2020-10-22 | 2021-06-04 | 2021-11-17 | 2021-07-06 | 2022-03-10 | 2021-08-05 | 2022-03-16 | 2021-11-01 | 2022-06-01 | Belgium, Germany, Spain, United Kingdom | Belgium (LPLV), Germany (LPLV), Spain (LPLV), United Kingdom (LPLV) | Belgium, Germany, Spain, United Kingdom | 26 | 16 | 13 | 30 | 24 | 22 | 35 | 0 | 10 | 25 | 0 | 6 | 19
Yes | Phase I | Managing Type | 1 | Bepranemab | Central Nervous System | UP0047 | Study Archived | FIH UCB0107 Tau AB | Phase I | Double Blind | GED | NewMeds | UCB Pharma Global | Watanabe S | Cain D | Parexel | PAREXEL | No | Yes | adults | Yes | A SUBJECT-BLIND, INVESTIGATOR-BLIND, RANDOMIZED, PLACEBO-CONTROLLED, FIRST-IN-HUMAN STUDY TO EVALUATE SAFETY AND TOLERABILITY, PHARMACOKINETICS, AND PHARMACODYNAMICS OF SINGLE ASCENDING INTRAVENOUS DOSES OF UCB0107 IN HEALTHY MALE SUBJECTS | PSP Progressive supranuclear palsy; Healthy Volunteers | Central Nervous System; Central Nervous System |  |  | 2017-05-24 |  | 2017-10-27 | 2018-01-24 | 2018-02-16 | 2018-05-10 | 2018-06-12 | 2018-10-29 | 2018-12-01 | 2018-11-20 | 2019-01-09 | 2018-12-17 | 2019-02-05 | 2019-03-21 | 2019-04-25 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 104 | 52 | 52 | 258 | 0 | 206 | 52 | 0 | 0 | 52
Yes | Phase I | Managing Type | 1 | Bepranemab | Central Nervous System | UP0065 | Study Archived | A SINGLE-CENTRE, INVESTIGATOR/SUBJECT BLIND, RANDOMIZED, PLA | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global |  |  | Parexel | PAREXEL | Yes | Yes | adults | Yes | A SINGLE-CENTRE, INVESTIGATOR/SUBJECT BLIND, RANDOMIZED, PLACEBO CONTROLLED, SINGLE IV ASCENDING DOSE INVESTIGATION OF SAFETY AND TOLERABILITY, PHARMACOKINETICS AND PHARMACODYNAMICS OF UCB0107 IN HEALTHY JAPANESE SUBJECTS | Healthy Volunteers | Central Nervous System |  | 2017-11-30 | 2017-11-30 |  | 2018-04-05 | 2018-07-02 | 2018-07-24 | 2018-09-17 | 2018-10-03 | 2019-02-22 | 2019-03-11 | 2019-04-10 | 2019-04-05 | 2019-03-22 | 2019-05-23 | 2019-08-06 | 2019-08-05 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 48 | 24 | 24 | 49 | 0 | 25 | 24 | 0 | 0 | 24
Yes | Phase I | Managing Type | 1 | BIMZELX | Immunology | UP0033 | Study Archived | Bioequivalence Study for Bimekizumab in Healthy Volunteers | Phase I | Not Applicable | GCSO | NewMeds | UCB Pharma Global | Soranson J | Grose-Hodge R | Parexel | PAREXEL | Yes | Yes | adults | Yes | AN OPEN-LABEL, MULTICENTER, RANDOMIZED, PARALLEL-GROUP, 3-ARM, SINGLE-DOSE BIOEQUIVALENCE STUDY OF BIMEKIZUMAB INJECTED SUBCUTANEOUSLY EITHER BY A PREFILLED SYRINGE OR BY AN AUTO-INJECTOR IN ADULT HEALTHY PARTICIPANTS | Healthy Volunteers | Immunology |  |  |  |  | 2018-07-30 | 2018-10-15 | 2018-10-15 | 2019-01-11 | 2018-12-28 | 2019-06-04 | 2019-06-05 | 2019-08-06 | 2019-08-07 | 2019-08-28 | 2019-08-29 | 2019-11-27 | 2019-11-04 | Germany, United States of America | Germany (LPLV), United States of America (LPLV) | Germany, United States of America | 2 | 2 | 2 | 400 | 400 | 400 | 395 | 0 | 206 | 189 | 0 | 0 | 189
Yes | Phase I | Managing Type | 1 | BIMZELX | Immunology | UP0034 | Study Archived | Open label,Randomised, Healthy Volunteer Vaccine study | Phase I | Open | GCSO | NewMeds | UCB Pharma Global | Knowles S | Grose-Hodge R | ICON | ICON | Yes | Yes | adults | Yes | An Open-Label, Randomized, Parallel-Group, Single-Dose Study to Evaluate the Antibody Response of Influenza Vaccination Following Concomitant Exposure to Bimekizumab in Healthy Subjects | Healthy Volunteers | Immunology |  | 2018-01-10 | 2018-01-10 |  | 2018-11-15 | 2019-03-29 | 2019-04-02 | 2019-04-09 | 2019-04-26 | 2019-09-24 | 2019-10-04 | 2019-10-24 | 2019-10-31 | 2019-11-14 | 2019-11-22 | 2020-02-10 | 2020-01-23 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 56 | 56 | 48 | 137 | 0 | 81 | 56 | 0 | 1 | 55
Yes | Phase I | Managing Type | 1 | BIMZELX | Immunology | UP0067 | Study Archived | A RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED SINGLE DOSE S | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Xu S | Grose-Hodge R | Parexel | PAREXEL | No | No | adults | Yes | A RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED SINGLE DOSE STUDY TO EVALUATE THE PHARMACOKINETICS, SAFETY, AND TOLERABILITY OF BIMEKIZUMAB IN HEALTHY CHINESE SUBJECTS | Healthy Volunteers | Immunology |  | 2017-11-01 | 2017-09-15 |  | 2018-12-07 | 2019-06-05 | 2020-12-14 | 2020-03-20 | 2021-01-20 | 2020-08-28 | 2021-06-01 | 2020-09-25 | 2021-07-08 | 2020-11-20 | 2021-09-29 | 2021-03-31 | 2021-12-13 | China | China (LPLV) | China | 1 | 1 | 1 | 46 | 36 | 31 | 119 | 0 | 85 | 34 | 0 | 0 | 34
Yes | Phase I | Managing Type | 1 | BIMZELX | Immunology | UP0068 | Study Archived | Bioequivalent study of 2ml compared to 2x1ml, in safety syri | Phase I | Open | GCSO | NewMeds | UCB Pharma Global | Knowles S | Grose-Hodge R | Parexel | PAREXEL | No | Yes | adults | Yes | AN OPEN-LABEL, SINGLE-CENTER, RANDOMIZED, PARALLEL-GROUP, SINGLE-DOSE BIOEQUIVALENCE STUDY OF BIMEKIZUMAB GIVEN AS 1X2ML OR 2X1ML SUBCUTANEOUS INJECTION IN HEALTHY STUDY PARTICIPANTS | Healthy Volunteers | Immunology |  | 2019-04-29 | 2019-04-29 |  | 2019-12-04 | 2020-03-11 | 2020-02-12 | 2020-07-15 | 2020-12-03 | 2020-12-17 | 2021-04-26 | 2021-02-18 | 2021-09-22 | 2021-03-12 | 2021-12-10 | 2021-06-11 | 2022-02-03 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 204 | 71 | 71 | 204 | 0 | 133 | 71 | 0 | 0 | 71
Yes | Phase I | Managing Type | 1 | BIMZELX | Immunology | UP0074 | Study Archived | Open label,Randomised, Healthy Volunteer Tolerability study | Phase I | Open | GCSO | NewMeds | UCB Pharma Global | Knowles S | Grose-Hodge R | ICON | ICON | Yes | Yes | adults | Yes | AN OPEN LABEL, RANDOMIZED, PARALLEL-GROUP, SINGLE-DOSE STUDY TO EVALUATE THE PHARMACOKINETICS, SAFETY, AND TOLERABILITY OF BIMEKIZUMAB GIVEN AS 2X1ML OR 1X2ML SUBCUTANEOUS ADMINISTRATION IN HEALTHY SUBJECTS. | Healthy Volunteers | Immunology |  | 2018-03-05 | 2018-03-05 |  | 2018-04-13 | 2018-05-15 | 2018-05-15 | 2018-08-23 | 2018-09-14 | 2019-02-28 | 2019-02-10 | 2019-05-10 | 2019-05-16 | 2019-05-31 | 2019-07-31 | 2019-08-30 | 2019-10-02 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 48 | 24 | 24 | 92 | 0 | 55 | 37 | 0 | 1 | 36
Yes | Phase I | Managing Type | 1 | BIMZELX | Immunology | UP0119 | Study Archived | BE Study 2x1mL SS vs 2mL AI | Phase I | Open | GCSO | Immunology | UCB Pharma Global | Knowles S | Grose-Hodge R | Parexel | PAREXEL | Yes | Yes | adults | Yes | AN OPEN-LABEL, RANDOMIZED, PARALLEL-GROUP, SINGLE-DOSE BIOEQUIVALENCE STUDY OF BIMEKIZUMAB GIVEN AS 1X2ML OR 2X1ML SUBCUTANEOUS INJECTION USING AN AUTOINJECTOR IN HEALTHY STUDY PARTICIPANTS | Healthy Volunteers | Central Nervous System |  | 2021-09-15 | 2021-09-15 |  | 2021-11-23 | 2022-03-17 | 2022-03-17 | 2022-09-01 | 2022-08-22 | 2023-01-25 | 2023-01-09 | 2023-02-24 | 2023-02-07 | 2023-03-31 | 2023-03-24 | 2023-05-30 | 2023-05-19 | Germany, United States of America | Germany (LPLV), United States of America (LPLV) | Germany, United States of America | 2 | 2 | 2 | 600 | 120 | 120 | 191 | 0 | 98 | 93 | 0 | 0 | 93 | [22 empty] | yes
Yes | Phase I | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0101 | Study Archived | OPEN-LABEL TO EVALUATE PK & SAFETY IN HEALTHY CHINESE SUBJEC | Phase I | Open | GCSO | Neurology | UCB Pharma Global |  |  | Parexel | PAREXEL | No | Yes | adults | Yes | An Open-Label, Single-Arm Study to Evaluate the Pharmacokinetics and Safety of a Single and Multiple Oral Doses of Brivaracetam in Healthy Adult Chinese Subjects (Phase 1) Protocol EP0101 Amendment 2 | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2016-08-02 08:00 | 2016-08-02 | 2016-09-20 | 2016-09-29 | 2017-01-27 | 2021-05-19 | 2017-02-20 | 2021-05-21 | 2017-03-20 | 2021-06-08 | 2021-07-05 | 2021-08-30 | 2017-05-10 | 2021-09-22 | 2017-08-04 | 2022-01-20 | China | China (LPLV) | China | 1 | 1 | 1 | 60 | 12 | 12 | 49 | 0 | 37 | 12 | 0 | 0 | 12
Yes | Phase I | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0110 | Study Archived | Single-dose, BE (BRV tab vs dry syrup) in 24healthy Japanese | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Sasamoto H | Matsuo T | Parexel | PAREXEL | No | Yes | adults | Yes | A SINGLE-DOSE, OPEN-LABEL, RANDOMIZED, 2-WAY CROSS-OVER STUDY TO ASSESS THE BIOEQUIVALENCE BETWEEN BRIVARACETAM TABLET AND DRY SYRUP IN HEALTHY MALE JAPANESE STUDY PARTICIPANTS | Epilepsy | Central Nervous System |  | 2020-10-27 08:00 | 2020-10-27 |  | 2021-03-01 | 2022-01-31 | 2022-04-04 | 2022-03-14 | 2022-04-08 | 2022-04-04 | 2022-05-13 | 2022-05-11 | 2022-06-10 | 2022-06-01 | 2022-07-05 | 2022-09-08 | 2022-09-13 | Japan | Japan (LPLV) | Japan | 1 | 1 | 1 | 48 | 24 | 24 | 63 | 0 | 39 | 24 | 0 | 0 | 24
Yes | Phase I | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0113 | Study Archived | BRV pilot PK study to compare a range of MAGs and orally | Phase I | Not Applicable | GED | Neurology | UCB Pharma Global | Kadima H | Grose-Hodge R | Parexel | PAREXEL | Yes | Yes | adults | Yes | OPEN-LABEL, SINGLE-DOSE, PILOT STUDY TO COMPARE THE PHARMACOKINETICS, SAFETY, AND TOLERABILITY OF BRIVARACETAM FROM A RANGE OF MUCO-ADHESIVE GELS AND ORALLY-DOSED SOLUTION IN HEALTHY VOLUNTEERS | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2018-01-23 | 2018-02-01 |  | 2018-04-19 | 2018-11-15 | 2018-11-15 | 2019-02-06 | 2019-03-30 | 2019-05-01 | 2019-05-01 | 2019-06-04 | 2019-06-04 | 2019-06-28 | 2019-06-28 | 2019-09-17 | 2019-09-16 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 32 | 32 | 24 | 82 | 0 | 47 | 35 | 0 | 6 | 29
Yes | Phase I | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0115 | Study Archived | An open-label repeat single dose pilot study to compare PK o | Phase I | Open | GED | Neurology | UCB Pharma Global | Kadima H | Grose-Hodge R | PRA | PRA | Yes | Yes | adults | Yes | OPEN-LABEL, SINGLE-DOSE, SINGLE-CENTER, PILOT STUDY TO COMPARE THE PHARMACOKINETICS OF BRIVARACETAM FROM A RANGE OF ORALLY-DOSED TABLETS IN HEALTHY VOLUNTEERS | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2017-05-01 | 2017-05-18 | 2017-08-10 | 2017-07-24 | 2017-11-27 | 2018-04-16 | 2017-12-12 | 2019-01-14 | 2018-03-07 | 2019-03-08 | 2018-04-04 | 2019-04-11 | 2018-05-30 | 2019-06-07 | 2018-10-06 | 2019-09-26 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 12 | 12 | 12 | 100 | 0 | 50 | 50 | 0 | 2 | 48
Yes | Phase I | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0117 | Study Archived | EP0117 Japan BRV iv healty volunteer Open-label study | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Ikeda K | Matsuo T | Parexel | PAREXEL | No | No | adults | Yes | A SINGLE-CENTER,OPEN-LABEL,RANDOMIZED,SINGLE-DOSE, 3-WAY CROSSOVER STUDY TO EVALUATE THE PHARMACOKINETICS, SAFETY, AND TOLERABILITY OF BRIVARACETAM INTRAVENOUS FORMULATION GIVEN AS A 2-MINUTE IV BOLUS INJECTION, A 15-MINUTE IV INFUSION, AND AN ORALLY-DOSED TABLET IN HEALTHY MALE JAPANESE SUBJECTS | Epilepsy | Central Nervous System |  | 2017-09-01 | 2017-09-13 |  | 2017-12-14 | 2018-04-19 | 2018-04-19 | 2018-04-18 | 2018-04-20 |  | 2018-05-26 | 2018-07-11 | 2018-07-11 | 2018-08-02 | 2018-08-17 | 2018-11-07 | 2018-11-20 | Japan | Japan (LPLV) | Japan | 1 | 1 | 1 | 36 | 36 | 36 | 62 | 0 | 38 | 24 | 0 | 0 | 24
Yes | Phase I | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0120 | Study Archived | Relative BA of XR and IR open rando 2-way x-over | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Guiver S |  | Parexel | PAREXEL | No | Yes | adults | Yes | Open-label, single- and multiple-dose, randomized, 2-way crossover, relative bioavailability study with an extended release and immediate release formulation of Brivaracetam in healthy study participants. | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2019-10-01 08:00 | 2019-10-01 | 2019-12-10 | 2019-12-12 | 2020-04-15 | 2020-08-11 | 2020-05-26 | 2020-09-16 | 2020-07-01 | 2020-11-06 | 2020-07-31 | 2020-12-22 | 2020-08-28 | 2021-04-15 | 2020-11-27 | 2021-04-23 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 84 | 32 | 32 | 66 | 0 | 34 | 32 | 0 | 0 | 32
Yes | Phase I | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0131 | Study Archived | BRIV study to compare pharmacokinetics, safety and tolerabil | Phase I | Open | GED | Neurology | UCB Pharma Global | De Beule N | Grose-Hodge R | Parexel | PAREXEL | Yes | Yes | adults | Yes | OPEN-LABEL, SINGLE-DOSE, SEQUENTIAL DESIGN, PILOT STUDY TO COMPARE THE PHARMACOKINETICS, SAFETY, AND TOLERABILITY OF BRIVARACETAM FROM A RANGE OF ORAL THIN FILMS AND ORALLY DOSED SOLUTION IN HEALTHY STUDY PARTICIPANTS. | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2018-03-29 | 2018-03-08 |  | 2018-06-05 | 2018-10-16 | 2018-10-17 | 2019-03-22 | 2019-03-25 | 2019-04-19 | 2019-04-18 | 2019-05-21 | 2019-05-21 | 2019-06-17 | 2019-06-25 | 2019-09-11 | 2019-09-04 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 16 | 16 | 12 | 65 | 0 | 33 | 32 | 0 | 1 | 31
Yes | Phase I | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0231 | Study Archived | A multi-dose, open-label, randomized, 2-way cross-over study | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Soma T | Matsuo T | Parexel | PAREXEL | Yes | Yes | adults | Yes | A MULTIPLE-DOSE, OPEN-LABEL, RANDOMIZED, 2-WAY CROSS-OVER STUDY TO ASSESS THE BIOEQUIVALENCE BETWEEN BRIVARACETAM TABLET AND DRY SYRUP IN HEALTHY MALE JAPANESE PARTICIPANTS. | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2023-05-11 | 2023-05-15 | 2023-07-28 | 2023-07-28 | 2024-04-22 | 2024-03-25 | 2024-10-18 | 2024-05-17 | 2024-10-25 | 2024-06-04 | 2024-12-12 | 2024-07-29 | 2025-01-13 | 2024-09-11 | 2025-04-09 | 2024-10-25 | Japan | Japan (LPLV) | Japan | 1 | 1 | 1 | 140 | 96 | 96 | 130 | 0 | 66 | 64 | 0 | 1 | 63 | [22 empty] | yes
Yes | Phase I | Managing Type | 1 | BRIVIACT | Central Nervous System | UP0087 | Created (Cancelled) | Taste Assessment of Brivaracetam | Phase I |  | GCSO | Neurology | UCB Pharma Global | De Beule N | Grose-Hodge R | ICON |  | Yes | Yes | adults | No |  | All Indications | Central Nervous System | [17 empty] | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | CIMZIA | Immunology | PS0006 | Created (Cancelled) | CZP PK Study in Pediatric Pts with PsO | Phase I |  | GCSO | Immunology | GCSO |  |  | N/A |  |  |  |  | No |  | Psoriasis | Immunology |  | 2020-03-30 08:00 | [18 empty] | 4 | 0 | 0 | 22 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | CIMZIA | Immunology | RA0138 | Study Archived | PK Cimzia Adult US | Phase I | Open | GCSO | Immunology | UCB Pharma Global | White Y | Copetti C | Parexel | PAREXEL | No | Yes | adults | No | A MULTI-CENTER, OPEN-LABEL STUDY TO EVALUATE THE PHARMACOKINETICS OF CERTOLIZUMAB PEGOL IN ADULTS WITH ACTIVE RHEUMATOID ARTHRITIS USING AN ELECTROCHEMILUMINESCENT IMMUNO-ASSAY | Rheumatoid Arthritis | Immunology |  | 2020-01-30 08:00 | 2020-01-30 |  | 2020-03-27 | 2020-10-05 | 2021-02-11 | 2021-09-06 | 2021-10-05 | 2022-02-21 | 2022-06-27 | 2022-03-21 | 2022-08-30 | 2022-04-04 | 2022-11-07 | 2022-06-27 | 2023-01-27 | United States of America | United States of America (LPLV) | United States of America | 15 | 13 | 9 | 46 | 33 | 25 | 47 | 0 | 14 | 33 | 0 | 7 | 26 | [22 empty] | yes
Yes | Phase I | Managing Type | 1 | CIMZIA | Immunology | UP0085 | Study Archived | A MULTICENTER, LONGITUDINAL PROSPECTIVE PHARMACOKINETIC PHAS | Phase I | Not Applicable | GCSO | Immunology | UCB Pharma Global | Rice K | Bonny M | N/A | PPD | No | Yes | adults | No | A POSTMARKETING, MULTICENTER, LONGITUDINAL, PROSPECTIVE, PHARMACOKINETIC, PHASE 1B STUDY IN PREGNANT WOMEN WITH CHRONIC INFLAMMATORY DISEASES TREATED WITH CIMZIA (CERTOLIZUMAB PEGOL) | Ankylosing Spondylitis; Crohn's disease; Psoriatic Arthritis; Rheumatoid Arthritis | Immunology; Immunology; Immunology; Immunology |  | 2019-06-05 08:00 | 2019-06-05 | 2019-08-01 | 2019-08-02 | 2019-10-15 | 2020-06-19 | 2020-10-15 | 2022-06-23 | 2021-10-22 | 2023-05-23 | 2021-11-24 | 2023-06-29 | 2021-12-16 | 2023-08-21 | 2022-03-17 | 2023-11-09 | France, Germany, Netherlands, Spain, Switzerland, United States of America | Canada (1st Site Initiation (Cancelled)), France (LPLV), Germany (LPLV), Netherlands (LPLV), Spain (LPLV), Switzerland (LPLV), United States of America (LPLV) | France, Germany, Netherlands, Spain, Switzerland, United States of America | 11 | 11 | 9 | 20 | 20 | 12 | 27 | 0 | 5 | 22 | 0 | 6 | 16 | [22 empty] | yes
Yes | Phase I | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0103 | Created | Study of single doses of MT1621 in healthy subjects | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Pifer C | Tillery N | N/A |  | No | No | other | Yes | A Phase 1, Open-Label, Fixed-Sequence, Dose Escalation Study to Evaluate Safety, Tolerability, Pharmacokinetics, and Food-Effect of MT1621 (deoxycytidine and deoxythymidine) Administered as Single Doses in Healthy Adult Subjects | Thymidine kinase 2 (TK2) deficiency | Central Nervous System | [17 empty] | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 14 | 14 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0105 | CSR Approved | Study of single doses of MT1621 in healthy subjects | Phase I |  | GCSO | Neurology | UCB Pharma Global | Pifer C | Tillery N | N/A |  | No | No | other | No |  | Thymidine kinase 2 (TK2) deficiency | Central Nervous System |  |  |  |  | 2015-05-12: 2020-02-19; 2020-07-02: 2021-10-20 | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 15 | 15 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0106 | CSR Approved | PK and safety of single dose MT1621 in renal impairment | Phase I |  | GCSO | Neurology | UCB Pharma Global | Pifer C | Tillery N | N/A |  | No | No | other | No |  | Thymidine kinase 2 (TK2) deficiency | Central Nervous System |  |  |  |  | 2015-05-12: 2020-12-08; 2020-07-02: 2021-11-18 | United States of America | United States of America (Created) |  | 3 | 0 | 0 | 32 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | EVENITY | Bones | OP0001 | Created (Cancelled) | PK study in healthy Chinese | Phase I |  | UCB Pharma Global | Bone | UCB Pharma Global | Guo J | Grose-Hodge R | Parexel |  | Yes | Yes | adults | No |  | Healthy Volunteers | Bones |  | 2017-12-01 08:00 | [15 empty] | China | China (Created) |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | Fintepla | Central Nervous System | EP0200 | CSR Approved | DDI-PK (ZX008 + STP/CLB/VPA) and fed/fasted state ZX008-1505 | Phase I |  | GCSO | Neurology | UCB Pharma Global |  |  | N/A |  | No |  | other | No |  | Dravet Syndrome; Epilepsy | Central Nervous System; Central Nervous System |  |  |  |  | 2016-01-18: 2016-03-02; 2016-11-29: 2016-03-02; 2020-01-06: 2017-01-23; 2020-07-02: 2018-08-29 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1
Yes | Phase I | Managing Type | 1 | Fintepla | Central Nervous System | EP0201 | CSR Approved | DDI-PK (ZX008 + CBD) ZX008-1604 | Phase I |  | GCSO | Neurology | UCB Pharma Global |  |  | N/A |  |  |  | other | No |  | Dravet Syndrome; Epilepsy | Central Nervous System; Central Nervous System |  |  |  |  | 2016-01-18: 2016-01-15; 2016-11-29: 2016-01-15; 2020-01-06: 2017-08-15; 2020-07-02: 2018-12-22 | Canada | Canada (LPLV) | Canada | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1
Yes | Phase I | Managing Type | 1 | Fintepla | Central Nervous System | EP0203 | CSR Approved | PK of ZX008 in healthy adult Japanese and Caucasian voluntee | Phase I |  | GCSO | Neurology | UCB Pharma Global |  |  |  |  | No |  |  | No | An Open-label, 2-Period, Parallel-arm, 1-Way Treatment Sequence Study to Evaluate the Pharmacokinetic Profile of ZX008 (Fenfluramine Hydrochloride) Oral Solution Administered as a Single Oral Dose With and Without the Stiripentol Regimen (Stiripentol/Clobazam) in Healthy Adult Japanese and Caucasian Subjects | [6 empty] | 2020-07-02: 2021-03-12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | Fintepla | Central Nervous System | EP0204 | CSR Approved | Safety, tolerability, and PK of ZX008 in subjects with varyi | Phase I |  | GCSO | Neurology | UCB Pharma Global |  |  |  |  | No |  |  | No | A PHASE 1, OPEN-LABEL, SINGLE-DOSE, ADAPTIVE, MULTIPART STUDY TO EVALUATE THE EFFECTS OF RENAL IMPAIRMENT ON THE PHARMACOKINETICS OF ZX008 (FENFLURAMINE HYDROCHLORIDE) IN SUBJECTS WITH VARYING DEGREES OF IMPAIRED AND NORMAL RENAL FUNCTION | Dravet Syndrome; Epilepsy | Central Nervous System; Central Nervous System |  |  |  |  | 2020-07-02: 2021-06-01 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | Fintepla | Central Nervous System | EP0206 | CSR Approved | PK of ZX008 with and without fluvoxamine, paroxetine, and ri | Phase I |  | GCSO | Neurology | UCB Pharma Global | Schelstraete I | Driver D | N/A |  |  | No |  | No | A PHASE 1, OPEN-LABEL, 2-PERIOD, CROSSOVER, MULTIPART STUDY TO EVALUATE THE PHARMACOKINETICS OF ZX008 (FENFLURAMINE HYDROCHLORIDE) WITH AND WITHOUT FLUVOXAMINE (CYP1A2 INHIBITOR), PAROXETINE (CYP2D6 INHIBITOR), AND RIFAMPIN (CYP2B6 INDUCER) IN HEALTHY SUBJECTS | [6 empty] | 2015-05-12: 2019-09-11; 2016-01-18: 2020-01-31; 2016-11-29: 2020-01-31; 2020-01-06: 2020-03-23; 2020-07-02: 2020-07-20 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1
Yes | Phase I | Managing Type | 1 | Fintepla | Central Nervous System | EP0221 | CSR Approved | Healthy Volunteers | Phase I |  | UCB Pharma Global | Neurology | UCB Pharma Global | [7 empty] | No |  | Healthy Volunteers | Central Nervous System |  |  |  |  | 2016-01-18: 2017-07-14; 2016-11-29: 2017-07-14; 2020-01-06: 2017-10-13; 2020-07-02: 2018-11-07 | United States of America | United States of America (LPLV) | United States of America | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1
Yes | Phase I | Managing Type | 1 | Galvokimig | Immunology | UP0089 | CSR Approved | bispectific antibody targeting IL-13/IL-17 in healthy partic | Phase I | Single Blind | GCSO | Immunology | UCB Pharma Global | Sacre J | Copetti C | Parexel | PAREXEL | Yes | Yes | adults | Yes | A PHASE I/IIA, RANDOMIZED, PLACEBO-CONTROLLED, SINGLE-ASCENDING DOSE (PART A, PARTICIPANT- AND INVESTIGATOR-BLIND) AND REPEATED-DOSE (PART B, PARTICIPANT-, INVESTIGATOR-, AND SPONSOR-BLIND) STUDY TO INVESTIGATE THE SAFETY, PHARMACOKINETICS, AND EFFICACY OF UCB9741 IN HEALTHY STUDY PARTICIPANTS (PART A) AND IN STUDY PARTICIPANTS WITH MODERATE-TO-SEVERE ATOPIC DERMATITIS (PART B) | Atopic Dermatitis; Patients and Healthy Volunteers | Immunology; Immunology |  | 2020-07-19 08:00 | 2020-07-19 | 2020-07-27 | 2020-08-03 | 2020-08-03 | 2020-11-27 | 2019-01-30 | 2024-01-04 | 2019-01-30 | 2024-06-06 | 2019-03-01 | 2024-07-18 | 2019-03-22 | 2024-08-07 | 2023-02-21 | 2024-12-10 | Belgium, Bulgaria, Germany, Netherlands, Poland, Spain, United Kingdom | Belgium (1st Site Initiation), Bulgaria (LPLV), Germany (LPLV), Netherlands (LPLV), Poland (1st Site Initiation), Spain (1st Site Initiation), United Kingdom (LPLV) | Belgium, Bulgaria, Germany, Netherlands, Poland, Spain, United Kingdom | 25 | 24 | 10 | 113 | 113 | 113 | 274 | 0 | 167 | 107 | 0 | 25 | 82 | 2023-07-17 | 2023-07-17 | 2023-09-07 | 2023-09-27 | 2023-12-25 | 2023-12-25 | 2023-11-14 | 2023-12-04 | 2024-09-25 | 2024-09-25 | 2024-05-28 | 2024-06-18 | [10 empty] | yes
Yes | Phase I | Managing Type | 1 | Ginisortamab | Oncology | ONC001 | CSR Approved | ONC001 | Phase I | Open | GCSO | NewMeds | UCB Pharma Global | Sacre J | Copetti C | ICON | ICON | Yes | Yes | adults | No | A Phase 1/2 Open-Label, MULTICENTER Study to Assess the Safety, Pharmacokinetics, and Anti Tumor Activity of UCB6114 Administered Intravenously to Participants with Advanced Solid Tumors | Solid Malignant Tumors | Oncology |  | 2019-08-19 08:00 | 2019-08-19 |  | 2019-10-14 | 2020-03-04 | 2020-07-09 | 2023-08-21 | 2023-11-01 | 2024-02-19 | 2024-04-11 | 2024-03-18 | 2024-06-07 | 2024-05-13 | 2024-08-23 | 2024-09-19 | 2024-12-05 | United Kingdom, United States of America | United Kingdom (LPLV), United States of America (LPLV) | United Kingdom, United States of America | 15 | 10 | 9 | 134 | 94 | 82 | 133 | 0 | 40 | 93 | 0 | 58 | 35
Yes | Phase I | Managing Type | 1 | Glovadalen | Central Nervous System | TM0023 | Created (Cancelled) | Pet Study Potentiation | Phase I |  | GCSO | NewMeds | UCB Pharma Global | [7 empty] | No |  | All Indications | Central Nervous System |  | 2021-06-28 08:00 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | Glovadalen | Central Nervous System | UP0091 | Study Archived | FIM Study | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Lelij G | Tillery N | N/A | HAMMERSMITH | No | Hybrid | adults | Yes | A FIRST-IN-HUMAN, RANDOMIZED, PARTICIPANT-BLIND, INVESTIGATOR-BLIND, PLACEBO-CONTROLLED, SINGLE- AND MULTIPLE-DOSE, DOSE-ESCALATING STUDY EVALUATING THE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF UCB0022 IN HEALTHY PARTICIPANTS AND PARTICIPANTS WITH PARKINSON'S DISEASE | Patients and Healthy Volunteers; Parkinson's disease | Central Nervous System; Central Nervous System |  | 2020-09-01 08:00 | 2020-09-01 |  | 2021-01-29 | 2021-06-07 | 2021-04-29 | 2022-02-14 | 2023-01-23 | 2022-04-29 | 2023-02-27 | 2022-05-27 | 2023-04-20 | 2022-06-10 | 2023-07-11 | 2022-09-06 | 2023-09-12 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 92 | 68 | 68 | 254 | 0 | 154 | 100 | 0 | 9 | 91 | [22 empty] | yes
Yes | Phase I | Managing Type | 1 | Minzasolmin | New Medicines | TM0017 | Study Archived | Pet quantification of the radiolabeled UCB0599 compound | Phase I | Open | GED | NewMeds | GED | Nicholl R | Grose-Hodge R | Parexel | SPI PXL | No | No | adults | Yes | A SINGLE-CENTER, OPEN-LABEL STUDY IN HEALTHY VOLUNTEERS TO DETERMINE THE BRAIN BIODISTRIBUTION OF UCB0599 USING TRACER [11C]UCB0599 AND POSITRON EMISSION TOMOGRAPHY (PET) | Parkinson's disease | Central Nervous System |  | 2017-07-18 | 2017-07-18 |  | 2017-10-04 | 2018-01-04 | 2018-02-07 | 2018-04-16 | 2018-03-06 | 2018-04-30 | 2018-03-13 | 2018-05-26 | 2018-06-04 | 2018-07-23 | 2018-07-05 | 2018-11-29 | 2018-10-15 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 10 | 10 | 10 | 33 | 0 | 29 | 4 | 0 | 0 | 4
Yes | Phase I | Managing Type | 1 | Minzasolmin | New Medicines | UP0073 | Study Archived | Relative BA and ethnobridging study | Phase I | Double Blind to Open Label | GCSO | NewMeds | UCB Pharma Global | Dehaas C | Tillery N | Parexel | PAREXEL | Yes | Yes | adults | Yes | A 2-PART STUDY TO EVALUATE THE RELATIVE BIOAVAILABILTY OF 2 NEW FORMULATIONS OF MINZASOLMIN AND THE EFFECT OF ESOMEPRAZOLE ON THE PK OF MINZASOLMIN (UCB0599) (PART A) IN HEALTHY CAUCASIAN PARTICIPANTS AND TO ASSESS THE SAFETY/TOLERABILITY AND PK OF MINZASOLMIN (UCB0599) IN HEALTHY PARTICIPANTS OF JAPANESE AND CHINESE ORIGIN (PART B) | Healthy Volunteers; Parkinson's disease | Central Nervous System; Central Nervous System |  | 2024-04-01 | 2022-12-05 | 2023-12-05 | 2023-03-06 | 2024-02-29 | 2023-05-18 | 2024-10-07 | 2024-03-31 | 2024-11-04 | 2024-04-13 | 2024-12-02 | 2024-05-15 | 2025-01-13 | 2024-06-26 | 2025-05-22 | 2024-09-24 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 220 | 72 | 72 | 176 | 0 | 103 | 73 | 0 | 3 | 70 | [22 empty] | yes
Yes | Phase I | Managing Type | 1 | Minzasolmin | New Medicines | UP0077 | Study Archived | Placebo-controlled PK and safety study of UCB0599 in PD | Phase I | Double Blind | Affiliates | Neurology | UCB Pharma Global | Kadima H, Palmer S | Grose-Hodge R | ICON | ICON | Yes | Yes | adults | No | A DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTIPLE DOSE STUDY TO EVALUATE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF UCB0599 IN PATIENTS WITH PARKINSON’S DISEASE (PD) | Parkinson's disease | Central Nervous System |  | 2018-09-13 | 2018-10-10 |  | 2019-01-14 | 2019-05-02 | 2019-05-06 | 2020-03-27 | 2019-12-17 | 2020-05-15 | 2020-02-19 | 2020-06-16 | 2020-03-23 | 2020-07-07 | 2020-04-27 | 2020-10-01 | 2020-07-24 | United States of America | United States of America (LPLV) | United States of America | 5 | 6 | 6 | 30 | 27 | 27 | 59 | 0 | 28 | 31 | 0 | 2 | 29 | 2020-07-06 | 2020-07-06 | 2020-07-06 | 2020-04-27
Yes | Phase I | Managing Type | 1 | Minzasolmin | New Medicines | UP0078 | Study Archived | Food effect and drug-drug interaction study of UCB0599 in HV | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Slade L | Grose-Hodge R | N/A | HAMMERSMITH | No | Hybrid | adults | Yes | A PHASE 1 OPEN-LABEL STUDY TO ASSESS THE POTENTIAL EFFECT OF FOOD AND COADMINISTERED ITRACONAZOLE ON THE DISPOSITION OF UCB0599 AND ITS METABOLITES IN HEALTHY STUDY PARTICIPANTS | Healthy Volunteers | Central Nervous System |  | 2018-11-26 | 2018-11-21 |  | 2019-05-02 | 2019-07-25 | 2019-10-29 | 2019-08-26 | 2019-11-28 | 2019-09-23 | 2020-01-09 | 2019-10-23 | 2020-02-20 | 2019-12-18 | 2020-03-17 | 2020-04-27 | 2020-06-16 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 22 | 22 | 22 | 27 | 0 | 5 | 22 | 0 | 0 | 22
Yes | Phase I | Managing Type | 1 | NEUPRO | Central Nervous System | PD0002 | Study Archived | PD0002 BE Study for Otsuka | Phase I | Open | R & D |  | R & D | Watanabe S | Cain D | N/A |  |  |  |  | Yes | SINGLE-SITE, OPEN-LABEL, RANDOMIZED, CROSS-OVER STUDY IN HEALTHY JAPANESE SUBJECTS TO EVALUATE THE BIOEQUIVALENCE OF SINGLE DOSE ROTIGOTINE TRANSDERMAL PATCH (2MG/24h) COMPARING 2 DIFFERENT FORMULATIONS |  |  |  | 2011-10-19 |  |  | 2011-12-06 | 2012-03-08 | 2012-03-08 |  | 2012-06-15 |  | 2012-07-04 |  | 2012-09-13 |  | 2012-10-22 |  | 2013-02-27 | Germany | Germany (LPLV) | Germany | 1 | 1 | 1 | 50 | 38 | 38 | 51 | 0 | 13 | 38 | 0 | 11 | 27
Yes | Phase I | Managing Type | 1 | Padsevonil | Central Nervous System | UP0035 | Study Archived | OC DDI | Phase I | Open | GCSO | NewMeds | UCB Pharma Global | Watanabe S | Cain D | N/A | HAMMERSMITH | No | No | adults | Yes | AN OPEN-LABEL, RANDOMIZED TWO-WAY CROSSOVER STUDY TO INVESTIGATE THE POTENTIAL PHARMACOKINETIC INTERACTION OF PADSEVONIL WITH ORAL CONTRACEPTIVES IN HEALTHY FEMALE PARTICIPANTS | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2019-03-28 | 2019-03-11 |  | 2019-08-02 | 2019-10-25 | 2019-10-23 | 2020-06-01 | 2019-12-23 | 2020-07-15 | 2020-05-11 | 2020-08-14 | 2020-10-05 | 2020-09-04 | 2020-10-15 | 2020-11-27 | 2020-12-07 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 40 | 40 | 40 | 27 | 0 | 13 | 14 | 0 | 0 | 14
Yes | Phase I | Managing Type | 1 | Padsevonil | Central Nervous System | UP0039 | Study Archived | Japanese PK study with UCB0942 | Phase I | Double Blind | GED | Neurology | GED | Lelij G | Tillery N | PRA | PRA | No | Yes | adults | Yes | A SINGLE-CENTRE, INVESTIGATOR/SUBJECT BLIND, PLACEBO CONTROLLED, SINGLE AND MULTIPLE ORAL DOSE INVESTIGATION OF SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF UCB0942 IN HEALTHY JAPANESE AND CAUCASIAN SUBJECTS | Epilepsy | Central Nervous System |  | 2016-11-08 | 2016-11-09 |  | 2017-03-10 | 2017-05-05 | 2017-05-05 | 2017-07-13 | 2017-07-14 | 2017-09-07 | 2017-08-14 | 2017-09-28 | 2017-09-11 | 2017-10-26 | 2017-10-25 | 2018-04-09 | 2017-12-01 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 16 | 12 | 12 | 73 | 0 | 25 | 48 | 0 | 0 | 48
Yes | Phase I | Managing Type | 1 | Padsevonil | Central Nervous System | UP0050 | Study Archived | TQT study | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Watanabe S | Cain D | N/A | HAMMERSMITH | No | No | adults | Yes | A placebo-controlled safety and tolerability study comparing the pharmacodynamic effect of high dose padsevonil on cardiac repolarization, including moxifloxacin as a positive pharmacologic control, in healthy study participants. | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2019-03-04 08:00 | 2019-03-04 |  | 2019-07-24 | 2019-10-30 | 2019-10-23 | 2020-06-03 | 2020-01-30 | 2020-06-08 | 2020-03-24 | 2020-07-08 | 2020-09-17 | 2020-07-29 | 2020-12-18 | 2020-09-23 | 2020-12-14 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 52 | 52 | 52 | 94 | 0 | 40 | 54 | 0 | 20 | 34
Yes | Phase I | Managing Type | 1 | Padsevonil | Central Nervous System | UP0052 | Study Archived | A monocenter, randomized, double-blind, placebo and active | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | De Beule N | Grose-Hodge R | ICON | ICON | No | No | adults | No | A 2-PART, RANDOMIZED, DOUBLE-BLIND, PLACEBO- AND ACTIVE-CONTROLLED, ASCENDING DOSE AND CROSSOVER STUDY TO ASSESS THE ABUSE POTENTIAL OF PADSEVONIL IN HEALTHY RECREATIONAL CENTRAL NERVOUS SYSTEM DEPRESSANT USERS | Recreational CNS depressant use | Central Nervous System |  | 2019-05-09 | 2019-05-08 |  | 2019-10-17 | 2019-12-09 | 2019-11-12 | 2020-04-13 | 2020-03-23 | 2020-06-25 | 2020-03-23 | 2020-07-27 | 2020-08-27 |  | 2020-10-14 | 2020-11-11 | 2020-11-17 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 90 | 78 | 60 | 200 | 0 | 173 | 27 | 0 | 4 | 23
Yes | Phase I | Managing Type | 1 | Padsevonil | Central Nervous System | UP0053 | Study Archived | PK Elderly | Phase I | Open | GCSO | NewMeds | UCB Pharma Global | Leach S | Cain D | ICON | ICON | No | No | geriatrics | Yes | AN OPEN-LABEL, PARALLEL-GROUP, PHARMACOKINETIC, SAFETY AND TOLERABILITY STUDY OF SINGLE AND MULTIPLE ORAL ADMINISTRATIONS OF PADSEVONIL IN ADULT AND ELDERLY STUDY PARTICIPANTS | Healthy Volunteers | Central Nervous System |  | 2019-02-19 | 2019-02-19 | 2019-05-08 | 2019-05-07 | 2019-06-27 | 2019-07-09 | 2019-08-21 | 2019-09-06 | 2019-09-12 | 2019-10-03 | 2019-10-14 | 2019-11-08 | 2019-11-01 | 2019-12-09 | 2020-01-24 | 2020-02-20 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 28 | 28 | 28 | 54 | 0 | 26 | 28 | 0 | 0 | 28
Yes | Phase I | Managing Type | 1 | Padsevonil | Central Nervous System | UP0054 | Study Archived | Driving | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Slade L | Grose-Hodge R | ICON | ICON | No | No | adults | Yes | A placebo-controlled study assessing the effects of padsevonil on simulated driving performance, including alprazolam as a positive pharmacologic control, in healthy study participants. | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2019-05-30 | 2019-06-04 |  | 2019-10-23 | 2019-11-28 | 2020-01-09 | 2020-02-07 | 2020-01-28 | 2020-05-04 | 2020-03-31 | 2020-06-04 | 2020-09-17 | 2020-06-26 | 2020-10-29 | 2020-08-27 | 2021-01-06 | Canada | Canada (LPLV) | Canada | 1 | 1 | 1 | 72 | 32 | 32 | 104 | 0 | 72 | 32 | 0 | 3 | 29
Yes | Phase I | Managing Type | 1 | Padsevonil | Central Nervous System | UP0056 | Study Archived | Hepatic impairment PK | Phase I | Open | GCSO | NewMeds | UCB Pharma Global | Slade L | Grose-Hodge R | ICON | ICON | No | No | adults | Yes | An open-label, parallel-group, pharmacokinetic study of Padsevonil in study participants with either normal hepatic function or with moderately impaired hepatic function (child-pugh class B) | Patients and Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2019-02-19 | 2019-02-19 | 2019-07-16 | 2019-07-02 | 2019-10-22 | 2019-10-28 | 2019-11-19 | 2020-03-13 | 2020-06-04 | 2020-04-05 | 2020-07-06 | 2020-07-31 | 2020-07-27 | 2020-09-03 | 2020-09-21 | 2020-11-12 | United States of America | United States of America (LPLV) | United States of America | 2 | 1 | 1 | 24 | 24 | 24 | 16 | 0 | 4 | 12 | 0 | 1 | 11
Yes | Phase I | Managing Type | 1 | Padsevonil | Central Nervous System | UP0057 | Study Archived | DDI study with moderate CYP3A4 inhibitor(Erythromycin) | Phase I | Open | GED | NewMeds | UCB Pharma Global | Lelij G | Tillery N | Parexel | PAREXEL | No | Yes | adults | Yes | AN OPEN-LABEL, FIXED-SEQUENCE STUDY IN HEALTHY STUDY PARTICIPANTS TO EVALUATE THE EFFECT OF COADMINISTERED ERYTHROMYCIN ON THE PHARMACOKINETICS AND SAFETY OF PADSEVONIL | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2017-08-16 | 2017-12-13 |  | 2018-01-22 | 2018-03-06 | 2018-03-27 | 2018-06-04 | 2018-06-16 | 2018-09-06 | 2018-08-02 | 2018-09-27 | 2018-09-04 | 2018-10-25 | 2018-10-02 | 2018-12-17 | 2019-01-10 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 28 | 28 | 28 | 43 | 0 | 15 | 28 | 0 | 2 | 26
Yes | Phase I | Managing Type | 1 | Padsevonil | Central Nervous System | UP0070 | Study Archived | OXC PSL DDI | Phase I | Open | GCSO | NewMeds | UCB Pharma Global | Van Den Steen B | Cain D | ICON | ICON | No | No | adults | No | A MULTICENTER, OPEN-LABEL, PARALLEL-GROUP STUDY IN STUDY PARTICIPANTS WITH EPILEPSY TO EVALUATE THE EFFECT OF OXCARBAZEPINE ON THE PHARMACOKINETICS, SAFETY, AND TOLERABILITY OF PADSEVONIL. | Epilepsy | Central Nervous System |  | 2018-05-08 | 2018-05-08 |  | 2018-06-08 | 2018-09-24 | 2018-09-18 | 2019-02-08 | 2019-05-07 | 2019-03-22 | 2019-05-30 | 2019-04-19 | 2019-07-12 | 2019-05-17 | 2019-08-12 | 2019-09-25 | 2019-11-15 | Bulgaria, Netherlands | Bulgaria (LPLV), Netherlands (LPLV) | Bulgaria, Netherlands | 3 | 2 | 2 | 28 | 28 | 28 | 39 | 0 | 8 | 31 | 0 | 3 | 28
Yes | Phase I | Managing Type | 1 | Padsevonil | Central Nervous System | UP0071 | Study Archived | A double-blind, placebo-controlled, randomized, cross-over s | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Lelij G | Tillery N | N/A | TAPAS Group | No | Hybrid | adults | Yes | A DOUBLE-BLIND, PLACEBO-CONTROLLED, RANDOMIZED, SINGLE-CENTER, CROSS-OVER STUDY TO INVESTIGATE THE PHARMACODYNAMIC, PHARMACOKINETIC, SAFETY, AND TOLERABILITY PROFILES OF PADSEVONIL IN HEALTHY STUDY PARTICIPANTS RECEIVING EITHER ETHANOL OR CANNABIDIOL | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2019-01-14 | 2019-01-10 | 2019-05-01 | 2019-05-13 | 2019-07-16 | 2019-07-17 | 2019-11-19 | 2020-02-12 | 2020-01-15 | 2020-04-30 | 2020-02-14 | 2020-10-27 | 2020-03-06 | 2020-12-18 | 2020-05-01 | 2021-03-19 | Netherlands | Netherlands (LPLV) | Netherlands | 1 | 1 | 1 | 22 | 22 | 22 | 110 | 0 | 70 | 40 | 0 | 2 | 38
Yes | Phase I | Managing Type | 1 | Padsevonil | Central Nervous System | UP0075 | Study Archived | PSL Phase 1 China | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Niu H | Grose-Hodge R | Parexel | PAREXEL | No | No | adults | Yes | A RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED SINGLE DOSE STUDY TO EVALUATE THE PHARMACOKINETICS, SAFETY, AND TOLERABILITY OF PADSEVONIL IN HEALTHY CHINESE SUBJECTS | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2018-05-31 | 2018-05-31 |  | 2018-10-19 | 2019-12-06 | 2019-11-14 | 2020-01-10 | 2019-11-21 | 2020-02-24 | 2019-12-09 | 2020-03-25 | 2020-01-15 | 2020-04-15 | 2020-05-28 | 2020-06-10 | 2020-09-14 | China | China (LPLV) | China | 1 | 1 | 1 | 16 | 14 | 14 | 23 | 0 | 9 | 14 | 0 | 0 | 14
Yes | Phase I | Managing Type | 1 | Padsevonil | Central Nervous System | UP0081 | Study Archived | rBA/CMC design space/IV | Phase I | Open | GCSO | NewMeds | UCB Pharma Global | De Beule N | Grose-Hodge R | ICON | ICON | No | No | adults | Yes | AN OPEN-LABEL, RANDOMIZED, SINGLE-DOSE, 2-PART CROSSOVER STUDY IN HEALTHY STUDY PARTICIPANTS TO EVALUATE THE RELATIVE BIOAVAILABILITY OF 4 PADSEVONIL PRODUCT VARIANTS AND THE EFFECT OF FOOD ON PADSEVONIL | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2019-11-04 | 2019-10-22 | 2020-01-06 | 2020-01-04 | 2020-03-23 | 2020-02-24 | 2020-05-04 | 2020-02-24 | 2020-06-15 | 2020-03-11 | 2020-07-06 | 2020-07-06 | 2020-07-27 | 2020-07-07 | 2020-09-21 | 2020-09-19 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 72 | 46 | 46 | 47 | 0 | 47 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | Padsevonil | Central Nervous System | UP0083 | Study Archived | A PK, safety, and tolerability study of PSL in CYP2C19 genot | Phase I | Open | GCSO | NewMeds | UCB Pharma Global | Matsuo T | Beinhauer-Zellenka U | Parexel | PAREXEL | No | Yes | adults | Yes | N OPEN-LABEL, PARALLEL GROUP, SINGLE-CENTER STUDY TO INVESTIGATE THE PHARMACOKINETIC, SAFETY, AND TOLERABILITY PROFILES OF PADSEVONIL IN CYP2C19 GENOTYPED HEALTHY MALE JAPANESE STUDY PARTICIPANTS | Healthy Volunteers | Central Nervous System |  | 2019-03-01 | 2019-03-05 | 2019-05-09 | 2019-05-09 | 2019-10-01 | 2019-09-30 | 2019-12-05 | 2019-12-02 | 2020-02-13 | 2019-12-27 | 2020-03-16 | 2020-02-07 | 2020-04-06 | 2020-03-27 | 2020-06-01 | 2020-06-24 | Japan | Japan (LPLV) | Japan | 1 | 1 | 1 | 100 | 39 | 33 | 167 | 0 | 128 | 39 | 0 | 0 | 39
Yes | Phase I | Managing Type | 1 | Rystiggo | Central Nervous System | DV0008 | Protoc. Summary Approved (Cancelled) | THE PK AND PD OF ROZANOLIXIZUMAB ADMINISTERED TO HEALTHY VOL | Phase I |  | GCSO | Immunology | UCB Pharma Global | Tillery N | Beinhauer-Zellenka U |  |  | Yes | Yes | adults | Yes |  | Healthy Volunteers | Immunology |  | 2019-12-17 | 2019-12-17 | [14 empty] | United States of America | United States of America (Created) |  | 1 | 0 | 0 | 60 | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | Rystiggo | Central Nervous System | UP0060 | Study Archived | A SINGLE CENTRE, RANDOMIZED, SUBJECT-BLIND, INVESTIGATOR-BLI | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Watanabe S | Cain D | N/A | HAMMERSMITH | Yes | Yes | adults | Yes | A RANDOMIZED, PARTICIPANT-BLIND, INVESTIGATORBLIND, PLACEBO-CONTROLLED STUDY COMPARING SAFETY, TOLERABILITY, PHARMACOKINETICS, AND PHARMACODYNAMICS OF SINGLE ASCENDING SUBCUTANEOUS DOSES OF ROZANOLIXIZUMAB IN JAPANESE, CHINESE AND CAUCASIAN HEALTHY VOLUNTEER STUDY PARTICIPANTS | Chronic Inflammatory Demyelinating Polyr; Healthy Volunteers | Immunology; Immunology |  | 2018-09-28 | 2018-11-15 |  | 2019-01-07 | 2019-01-31 | 2019-03-18 | 2019-03-01 | 2020-02-18 | 2019-08-27 | 2020-04-28 | 2019-09-24 | 2020-06-12 | 2019-11-19 | 2020-07-11 | 2020-03-27 | 2020-10-21 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 80 | 44 | 44 | 143 | 0 | 78 | 65 | 0 | 1 | 64
Yes | Phase I | Managing Type | 1 | Rystiggo | Central Nervous System | UP0106 | Study Archived | Phase 1, PK PD single Rozanolixizumab doze, syringe or MP | Phase I | Double Blind | GCSO | Immunology | UCB Pharma Global | Watanabe S | Cain D | N/A | HAMMERSMITH | No | Yes | adults | Yes | A RANDOMIZED, PARTICIPANT-BLIND, INVESTIGATOR BLIND, PLACEBO-CONTROLLED STUDY TO EVALUATE THE SAFETY, TOLERABILITY, PHARMACOKINETICS, AND PHARMACODYNAMICS OF ROZANOLIXIZUMAB ADMINISTERED SUBCUTANEOUSLY VIA MANUAL PUSH VERSUS SYRINGE DRIVER TO HEALTHY PARTICIPANTS | Healthy Volunteers | Immunology |  | 2020-11-24 08:00 | 2020-11-24 |  | 2021-02-05 | 2021-03-31 | 2021-04-22 | 2021-08-18 | 2022-01-25 | 2021-11-02 | 2022-04-11 | 2021-11-30 | 2022-09-06 | 2021-12-21 | 2022-10-11 | 2022-03-17 | 2022-12-16 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 60 | 32 | 32 | 89 | 0 | 57 | 32 | 0 | 0 | 32
Yes | Phase I | Managing Type | 1 | Staccato Alprazolam | Central Nervous System | UP0099 | Study Archived | Adult Repeat Dosing Pulmonary Safety Study | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Watanabe S | Cain D | Parexel | PAREXEL | Yes | Yes | adults | Yes | A Phase 1 randomized, double-blind, placebo-controlled, 3-way crossover (Part A) and 2-arm parallel group (Part B) study to assess the pulmonary safety of staccato alprazolam in healthy study participants (Part A) and in study participants with mild asthma (Part B) | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2020-10-05 08:00 | 2020-10-05 |  | 2020-11-18 | 2021-02-02 | 2021-03-09 | 2021-04-14 | 2021-11-09 | 2021-05-24 | 2021-11-30 | 2021-06-22 | 2021-12-22 | 2021-07-13 | 2022-02-04 | 2021-10-08 | 2022-06-08 | United States of America | United States of America (LPLV) | United States of America | 2 | 2 | 2 | 90 | 78 | 78 | 126 | 0 | 47 | 79 | 0 | 9 | 70
Yes | Phase I | Managing Type | 1 | Staccato Alprazolam | Central Nervous System | UP0100 | Study Archived | Adolescent PK (12+) Study | Phase I | Open | GCSO | NewMeds | UCB Pharma Global | Blinder B |  | Parexel | PAREXEL | Yes | Yes | adolescents | No | A Multicenter, open-label study to evaluate the pharmacokinetics, Tolerability, and Safety of a Single dose of staccato alprazolam in adolescent STUDY participants with epilepsy | Epilepsy | Central Nervous System |  | 2020-10-06 | 2020-10-06 |  | 2020-12-07 | 2021-03-23 | 2021-04-28 | 2021-07-26 | 2022-03-18 | 2021-08-26 | 2022-04-05 | 2021-09-27 | 2022-05-11 | 2021-10-25 |  | 2021-11-30 | 2022-07-27 | United States of America | United States of America (LPLV) | United States of America | 10 | 9 | 8 | 30 | 14 | 12 | 20 | 0 | 5 | 15 | 0 | 0 | 15
Yes | Phase I | Managing Type | 1 | Staccato Alprazolam | Central Nervous System | UP0101 | Study Archived | Japanese PK Study | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Blinder B |  | Parexel | PXL | Yes | Yes | adults | Yes | A placebo-controlled, double-blind, randomized study to assess the safety, tolerability, and pharmacokinetics of Staccato Alprazolam In healthy Japanese, Chinese, and caucasian Participants | Healthy Volunteers | Central Nervous System |  | 2020-10-06 | 2020-10-06 |  | 2020-12-18 | 2021-03-03 | 2021-03-04 | 2021-04-15 | 2021-04-12 | 2021-05-31 | 2021-04-26 | 2021-06-29 | 2021-10-29 | 2021-07-20 | 2021-10-29 | 2021-09-02 | 2022-03-01 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 40 | 30 | 30 | 65 | 0 | 35 | 30 | 0 | 0 | 30
Yes | Phase I | Managing Type | 1 | Staccato Alprazolam | Central Nervous System | UP0104 | Study Archived | A single-centre study to assess the safety, tolerability and | Phase I | Not Applicable | GCSO | Neurology | UCB Pharma Global | Lelij G | Tillery N | Parexel | PAREXEL | Yes | Yes | adults | Yes | AN OPEN-LABEL, RANDOMIZED, SINGLE-DOSE, 2-WAY CROSSOVER STUDY TO EVALUATE THE RELATIVE BIOAVAILABILITY OF STACCATO ALPRAZOLAM COMPARED TO ORAL ALPRAZOLAM IN HEALTHY STUDY PARTICIPANTS | Healthy Volunteers; Epilepsy | Central Nervous System; Central Nervous System |  | 2022-11-01 08:00 | 2021-10-28 |  | 2015-05-12: 2022-09-23; 2016-01-18: 2022-12-28; 2016-11-29: 2023-02-07; 2020-01-06: 2023-02-24; 2020-02-04: 2023-04-25; 2020-02-25: 2023-05-30; 2020-07-02: 2023-10-11 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 65 | 20 | 20 | 54 | 0 | 33 | 21 | 0 | 1 | 20 | [22 empty] | yes
Yes | Phase I | Managing Type | 1 | Staccato Alprazolam | Central Nervous System | UP0151 | Study Archived | Human Abuse Potential (AMDC-002-102) | Phase I | Double Blind | GCSO | Neurology | UCB Pharma Global |  |  | N/A |  | No | No |  | Yes | Abuse Liability Study of Staccato® Alprazolam for Inhalation in Subjects with Histories of Sedative Abuse | Healthy Volunteers | Central Nervous System |  |  |  | 2007-11-14 | 2007-11-14 | 2008-03-06 | 2008-03-06 | 2008-03-06 | 2008-03-06 | 2009-01-14 | 2009-01-14 | 2022-10-03 | 2022-10-03 | 2023-04-11 | 2023-04-11 | 2023-09-29 | 2023-09-21 | United States of America | United States of America (LPLV) | United States of America | 1 | 0 | 1 | 24 | 21 | 14 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | [22 empty] | yes
Yes | Phase I | Managing Type | 1 | Tefidera | not defined | MS0007 | Protoc. Summary Approved (Cancelled) | Phase 1 two dose PK study with Chinese HV | Phase I |  | Affiliates | Neurology | UCB Pharma Global | Wang J | Wu G | Parexel | PXL SPI |  |  |  | No |  | Multiple sclerosis | Central Nervous System |  | 2014-12-03 | 2014-12-03 | [14 empty] | China | China (Created) |  | 1 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | UCB0159 (TrYbe) | Immunology | PS0019 | Study Archived | PoC to assess UCB0159 (TryBe) in patients with mild Psoriasi | Phase I | Double Blind | GED | Immunology | UCB Pharma Global | Soranson J | Grose-Hodge R | Parexel | PAREXEL | Yes | Yes | adults | Yes | A RANDOMIZED, SUBJECT-BLIND, INVESTIGATOR-BLIND, PLACEBO-CONTROLLED, SINGLE-DOSE, DOSE-ESCALATING STUDY EVALUATING THE SAFETY, PHARMACOKINETICS, AND PHARMACODYNAMICS OF UCB0159 IN SUBJECTS WITH MILD TO MODERATE PSORIASIS, AND SINGLE-DOSE PHARMACOKINETICS AND SAFETY IN HEALTHY SUBJECTS. | Psoriasis; Patients and Healthy Volunteers | Immunology; Immunology |  |  |  |  | 2017-06-05 | 2017-06-22 | 2017-06-23 | 2018-01-10 | 2018-08-22 | 2018-04-04 | 2018-12-08 | 2018-05-02 | 2019-02-19 | 2018-05-30 | 2019-02-25 | 2018-10-08 | 2019-05-16 | Germany, United Kingdom | Germany (LPLV), United Kingdom (LPLV) | Germany, United Kingdom | 1 | 2 | 2 | 217 | 54 | 54 | 217 | 0 | 163 | 54 | 0 | 0 | 54
Yes | Phase I | Managing Type | 1 | UCB0159 (TrYbe) | Immunology | PS0023 | Created (Cancelled) | Skin biopsy study following single dose of cimzia | Phase I |  | GED | Immunology | UCB Pharma Global | Jones A | Driver D |  |  | Yes | Yes | adults | No |  | Psoriasis | Immunology |  | 2017-08-04 | [18 empty] | 1 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | UCB4594 | Oncology | UP0123 | Protoc. Summary Approved (Cancelled) | FIM | Phase I |  | GCSO | Oncology | UCB Pharma Global | Leach S | Cain D | ICON |  | No | No |  | No |  | All Indications | Oncology |  | 2022-06-27 08:00 | 2022-06-07 | [17 empty] | 10 | 0 | 0 | 25 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | UCB6433 (anti IgE) | not defined | UP0061 | Created (Cancelled) | Phase 1 Biomarker Study | Phase I |  | GCSO | NewMeds | UCB Pharma Global | Nicholl R | Grose-Hodge R | Parexel |  | Yes | Yes | adults | No |  | Allergy; Asthma; Rhinitis Allergic | Immunology; Immunology; Immunology |  | 2018-06-05 08:00 | [15 empty] | Germany | Germany (Created) |  | 1 | 0 | 0 | 42 | 42 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | UCB7000 | not defined | PF0007 | Created (Cancelled) | MAD DB study in IPF subjects | Phase I | Double Blind | GED | Immunology | UCB Pharma Global |  |  | Parexel | PAREXEL | Yes | Yes | adults | Yes | A Randomised, Double-Blind, Placebo-Controlled, Multiple Ascending Dose Study Evaluating The Safety/Tolerability, Pharmacokinetics And Pharmacodynamics Of Inhaled Doses Of Ucb7000 In Idiopathic Pulmonary Fibrosis Subjects. | Idiopathic Pulmonary Fibrosis (IPF) | Immunology |  | 2020-08-14 08:00 | [15 empty] | United Kingdom | United Kingdom (Created) |  | 6 | 0 | 0 | 56 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | UCB7000 | not defined | UP0044 | Protoc. Summary Approved (Cancelled) | SAD DB study in healthy subjects | Phase I | Double Blind | GED | Immunology | GED |  |  | Parexel | PAREXEL | Yes | Yes | adults | Yes | A randomized, investigator-blind, subject-blind, placebo-controlled, single ascending dose study evaluating the safety/tolerability, pharmacokinetics, and pharmacodynamics of inhaled doses of ucb7000 in healthy subjects | Idiopathic Pulmonary Fibrosis (IPF) | Immunology |  | 2016-11-01 | 2016-11-01 | [14 empty] | United Kingdom | United Kingdom (Created) |  | 1 | 0 | 0 | 72 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | UCB7853 | not defined | UP0064 | Protocol Approved (Cancelled) | Multicenter, participant-blind, investigator-blind, randomiz | Phase I | Double Blind | GCSO | Neurology | UCB Pharma Global |  |  | Parexel | PAREXEL | Yes | Yes | adults | Yes | A MULTICENTER, PARTICIPANT-BLIND, INVESTIGATOR-BLIND, RANDOMIZED, PLACEBO-CONTROLLED STUDY TO EVALUATE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF SINGLE ASCENDING DOSES OF UCB7853 IN HEALTHY MALE STUDY PARTICIPANTS AND MULTIPLE ASCENDING DOSES IN PATIENTS WITH PARKINSON’S DISEASE | Patients and Healthy Volunteers; Parkinson's disease | Central Nervous System; Central Nervous System |  | 2019-07-02 08:00 | 2019-07-01 |  | 2015-05-12: 2019-12-09; 2015-09-29: 2020-02-28; 2016-04-08: 2021-06-15; 2019-11-29: 2022-02-09; 2020-02-04: 2022-03-09; 2020-02-07: 2022-03-30; 2020-05-05: 2022-06-22 | United States of America | United States of America (Created) |  | 5 | 0 | 0 | 128 | 64 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | UCB7853 | not defined | UP0092 | Study Archived | Multicenter, Participant Blind, Investigator Blind, Randomiz | Phase I | Double Blind | GCSO | Neurology | UCB Pharma Global | Rice K | Bonny M | Parexel | PAREXEL | Yes | Yes | adults | Yes | A MULTICENTER, PARTICIPANT-BLIND, INVESTIGATOR BLIND, RANDOMIZED, PLACEBO CONTROLLED STUDY TO EVALUATE SAFETY, TOLERABILITY, AND PHARMACOKINETICS OF SINGLE ASCENDING DOSES OF UCB7853 IN HEALTHY MALE STUDY PARTICIPANTS AND MULTIPLE ASCENDING DOSES IN PATIENTS WITH PARKINSON’S DISEASE. | Patients and Healthy Volunteers; Parkinson's disease | Central Nervous System; Central Nervous System |  | 2019-07-01 | 2019-07-01 |  | 2020-08-14 | 2020-12-03 | 2020-12-14 | 2021-10-13 | 2022-12-13 | 2022-06-08 | 2023-07-20 | 2022-07-06 | 2023-08-25 | 2022-07-29 | 2023-11-30 | 2022-10-21 | 2024-09-10 | Netherlands, United Kingdom | Netherlands (LPLV), United Kingdom (LPLV) | Netherlands, United Kingdom | 2 | 2 | 2 | 128 | 64 | 64 | 136 | 0 | 79 | 57 | 0 | 1 | 56 | [22 empty] | yes
Yes | Phase I | Managing Type | 1 | UCB8539 | not defined | UP0125 | Protocol Approved (Cancelled) | Randomised investigator blind placebo vs IMP study | Phase I | Single Blind | GCSO | Immunology | UCB Pharma Global | Dyer J | Russell R | Parexel | PAREXEL | Yes | Yes | adults | Yes | A Phase 1 RANDOMIZED, PLACEBO-CONTROLLED, SINGLE-ASCENDING DOSE, PARTICIPANT - AND INVESTIGATOR-BLIND STUDY TO INVESTIGATE THE SAFETY, PHARMACOKINETICS, AND PHARMACODYNAMICS OF UCB8539 IN HEALTHY STUDY PARTICIPANTS | Atopic Dermatitis | Immunology |  | 2023-02-08 | 2023-02-21 | 2023-06-27 | 2015-05-12: 2023-06-28; 2015-09-29: 2023-10-20; 2016-04-08: 2024-09-27; 2019-11-29: 2024-12-20; 2020-02-04: 2025-01-20; 2020-02-07: 2025-02-20; 2020-05-05: 2025-05-19 |  |  |  | 1 | 0 | 0 | 88 | 88 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | UCB8600 | Immunology | UP0086 | Study Archived | A RANDOMIZED, PARTICIPANT-BLIND, INVESTIGATOR-BLIND, PLACEBO | Phase I | Mixed Blind / Multiple Blind | GCSO | NewMeds | UCB Pharma Global | Gbenedio T, Leach S | Cain D | ICON | ICON | Yes | Yes | adults | Yes | A FIRST-IN-HUMAN, RANDOMIZED, PARTICIPANT-BLIND, INVESTIGATOR BLIND, PLACEBO-CONTROLLED, SINGLE- AND MULTIPLE-DOSE, DOSE ESCALATING STUDY EVALUATING THE SAFETY, TOLERABILITY, PHARMACOKINETICS, AND PHARMACODYNAMICS OF UCB8600 IN HEALTHY PARTICIPANTS, ATOPIC PARTICIPANTS, AND CHRONIC SPONTANEOUS URTICARIA PARTICIPANTS | Chronic Idiopathic Urticaria; Patients and Healthy Volunteers | Immunology; Immunology |  | 2019-08-04 08:00 | 2019-08-04 | 2019-10-28 | 2019-10-25 | 2020-03-09 | 2020-06-30 | 2021-03-23 | 2021-07-05 | 2021-06-07 | 2021-08-02 | 2021-07-06 | 2021-11-25 | 2021-07-27 | 2022-01-11 | 2021-09-24 | 2022-03-23 | Bulgaria | Bulgaria (LPLV) | Bulgaria | 1 | 1 | 1 | 210 | 162 | 162 | 74 | 0 | 34 | 40 | 0 | 0 | 40
Yes | Phase I | Managing Type | 1 | UCB9709 (Complement C5 inhibitor) | not defined | UP0098 | Protoc. Summary Approved (Cancelled) | FiH single and multiple ascending dose | Phase I |  | GCSO | NewMeds | UCB Pharma Global |  |  |  |  | No | No | adults | No |  | Healthy Volunteers | Immunology |  | 2020-10-19 | 2020-10-13 | [14 empty] | United Kingdom | United Kingdom (Created) |  | 1 | 0 | 0 | 68 | 68 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | VIMPAT | Central Nervous System | DV0001 | Created (Cancelled) | open-label,single-arm study of an ingestible event marker sy | Phase I |  | GCSO | Neurology | UCB Pharma Global | Murphy C | Russell R | Parexel | SPI PXL | No |  |  | No |  | Epilepsy | Central Nervous System |  | 2016-12-27 | [15 empty] | United States of America | United States of America (Created) |  | 2 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | VIMPAT | Central Nervous System | EP0010 | Created (Cancelled) | Lacosamide MR PK BE | Phase I |  | GED | Immunology | UCB Pharma Global |  |  | PRA | PRA SPI |  |  | adults | No |  |  |  |  | 2018-03-05 | [18 empty] | 1 | 0 | 0 | 44 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | VIMPAT | Central Nervous System | SP1001 | Study Archived | BE study for Vimpat syrup | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Wang J | Wu G | PRA | PRA | Yes | No | adults | No | A RANDOMIZED, OPEN-LABEL, SINGLE-DOSE, 2-PERIOD CROSSOVER STUDY TO INVESTIGATE THE BIOEQUIVALENCE OF LACOSAMIDE TABLET (200MG) AND SYRUP (15MG/ML) IN HEALTHY CHINESE MALE SUBJECTS | Epilepsy | Central Nervous System |  | 2010-06-08 | 2012-11-08 |  | 2016-01-19 | 2016-04-11 | 2017-02-27 | 2016-05-17 | 2017-03-06 | 2016-07-05 | 2017-04-27 | 2016-07-22 | 2017-06-29 | 2016-08-05 | 2017-08-04 | 2016-10-13 | 2018-08-23 | China | China (LPLV) | China | 1 | 1 | 1 | 24 | 24 | 18 | 68 | 0 | 45 | 23 | 0 | 1 | 22
Yes | Phase I | Managing Type | 1 | VIMPAT | Central Nervous System | SP1043 | Study Archived | BE Study as IV and Oral tablet in healthy Chinese subjects | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Ma L | Grose-Hodge R | PRA | PRA | No | No | adults | No | "A RANDOMIZED, OPEN-LABEL, SINGLE-DOSE, 2-WAY CROSSOVER STUDY TO INVESTIGATE THE BIOEQUIVALENCE OF LACOSAMIDE 200MG ADMINISTERED AS INTRAVENOUS SOLUTION AND AS ORAL TABLET IN HEALTHY CHINESE MALE SUBJECTS" | Epilepsy | Central Nervous System |  | 2011-08-31 |  |  | 2016-01-20 | 2017-02-27 | 2017-06-09 | 2017-03-04 | 2017-06-28 | 2017-07-28 | 2017-07-28 | 2017-10-06 | 2017-10-18 | 2017-05-13 | 2018-01-26 | 2017-07-03 | 2018-04-24 | China | China (LPLV) | China | 1 | 1 | 1 | 0 | 0 | 0 | 58 | 0 | 28 | 30 | 0 | 0 | 30
Yes | Phase I | Managing Type | 1 | Zampilimab | Immunology | UP0066 | Created (Cancelled) | Phase 1b | Phase I |  | GED | Immunology | UCB Pharma Global | Nicholl R | Grose-Hodge R | Parexel |  | Yes | Yes | adults | No |  | All Indications | Immunology |  | 2017-10-09 | [15 empty] | Belgium | Belgium (Created) |  | 3 | 0 | 0 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | Zampilimab | Immunology | UP0105 | Study Archived | Single ascending dose | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Leach S | Cain D | N/A | HAMMERSMITH | Yes | Hybrid | adults | Yes | A RANDOMIZED, PARTICIPANT-BLIND, INVESTIGATOR BLIND, PLACEBO-CONTROLLED STUDY EVALUATING SAFETY, TOLERABILITY, PHARMACOKINETICS, AND PHARMACODYNAMICS OF SINGLE ASCENDING INTRAVENOUS DOSES OF ZAMPILIMAB IN HEALTHY PARTICIPANTS | Healthy Volunteers; Chronic Allograft Injury | Immunology; Immunology |  | 2020-09-11 | 2020-09-11 | 2020-10-07 | 2020-10-13 | 2021-01-26 | 2021-01-11 | 2021-05-18 | 2021-03-25 | 2021-09-07 | 2021-07-28 | 2021-10-05 | 2021-10-18 | 2021-10-19 | 2021-11-16 | 2022-01-13 | 2022-02-08 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 1 | 1 | 1 | 38 | 16 | 16 | 38 | 0 | 22 | 16 | 0 | 0 | 16
Yes | Phase I | Managing Type | 1 | Zilucoplan | Central Nervous System | UP0093 | Study Archived | RA101495.02.101 QT (TQTc) study | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Babcock S | Padda A | Parexel | DSP CLINICAL RESEARCH | Yes | No | adults | Yes | A Phase 1, Randomized, Double-blind, Placebo- and Active-controlled, Parallel group Nested Cross-over Study of the Effects of Supratherapeutic Doses of Zilucoplan on Cardiac Repolarization in Healthy Adult Subjects | Healthy Volunteers | Central Nervous System |  | 2019-04-26 | 2019-04-26 |  | 2019-06-11 | 2020-01-22 | 2020-01-22 | 2021-01-28 | 2021-01-28 | 2021-04-01 | 2021-04-05 |  | 2021-05-20 | 2021-07-07 | 2021-10-01 | 2021-08-19 | 2022-01-26 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 128 | 64 | 64 | 65 | 0 | 1 | 64 | 0 | 3 | 61
Yes | Phase I | Managing Type | 1 | Zilucoplan | Central Nervous System | UP0094 | Study Archived | RA101495.02.102 Assess PK in Hepatic Function (HIP) | Phase I | Open | GCSO | NewMeds | UCB Pharma Global | Babcock S | Padda A | Parexel | N/A | Yes | No | adults | No | A Phase 1, Open-Label Study to Assess the Pharmacokinetics of Zilucoplan in Subjects with Impaired Hepatic Function and Subjects with Normal Hepatic Function | Impaired Hepatic Function; Normal Hepatic Function | Central Nervous System; Central Nervous System |  |  |  |  | 2020-02-14 | 2020-01-22 | 2020-06-30 | 2020-10-05 | 2020-10-05 | 2020-12-01 | 2020-12-01 | 2021-03-19 | 2021-03-22 | 2021-05-14 | 2021-06-08 | 2021-08-10 | 2022-01-14 | United States of America | United States of America (LPLV) | United States of America | 3 | 1 | 1 | 32 | 16 | 16 | 18 | 0 | 2 | 16 | 0 | 0 | 16
Yes | Phase I | Managing Type | 1 | Zilucoplan | Central Nervous System | UP0095 | Protocol Approved (Cancelled) | Ph1 SAD/MAD Fluid Crystal (RA101495-04.101) | Phase I | Double Blind | GCSO | NewMeds | UCB Pharma Global | Babcock S | Padda A | N/A | Quotient Sciences | No | No | adults | Yes | "A Phase 1, Randomised, Double-Blind, Placebo-Controlled, Single and Multiple Ascending Dose Study of the Safety and Pharmacokinetics of an Extended Release Formulation of Zilucoplan in Healthy Volunteers" | Healthy Volunteers | Central Nervous System |  |  |  | 2020-07-24 | 2015-05-12: 2020-07-24; 2015-09-29: 2020-11-24; 2016-04-08: 2021-05-10; 2019-11-29: 2021-08-09; 2020-02-04: 2021-08-24; 2020-02-07: 2021-10-07; 2020-05-05: 2021-12-09 | United Kingdom | United Kingdom (Created) |  | 1 | 0 | 0 | 64 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase I | Managing Type | 1 | Zilucoplan | not defined | UP0115 | Study Archived | Site injection study | Phase I | Open | GCSO | Neurology | UCB Pharma Global | Harvey B | Russell R | Parexel | PAREXEL | No | No | adults | No | A SINGLE-CENTER, RANDOMIZED, OPEN-LABEL, 2-WAY INCOMPLETE CROSSOVER STUDY IN HEALTHY PARTICIPANTS TO EVALUATE THE RELATIVE BIOAVAILABILITY, PHARMACODYNAMICS, SAFETY AND TOLERABILITY OF A SINGLE SUBCUTANEOUS INJECTION OF ZILUCOPLAN AT DIFFERENT ADMINISTRATION SITES | Amyotrophic Lateral Sclerosis (ALS) | Central Nervous System |  | 2021-05-20 08:00 | 2021-05-20 |  | 2021-07-27 | 2021-10-12 | 2021-10-13 | 2021-10-26 | 2021-12-06 | 2022-02-01 | 2022-03-14 | 2022-03-02 | 2022-03-31 | 2022-03-23 | 2022-04-14 | 2022-07-19 | 2022-06-16 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 12 | 12 | 12 | 41 | 0 | 25 | 16 | 0 | 2 | 14
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Bepranemab | Central Nervous System | PSP001 | Protocol Approved (Cancelled) | A double-blind, placebo-controlled, ph 3 study to evaluate e | Phase III | Double Blind | GCSO | NewMeds | UCB Pharma Global | Van Den Steen B | Cain D | ICON | ICON | Yes | Yes | adults | No | A DOUBLE-BLIND, PLACEBO-CONTROLLED, PHASE 3 STUDY TO EVALUATE THE EFFICACY, SAFETY, AND TOLERABILITY OF UCB0107 IN STUDY PARTICIPANTS WITH PROGRESSIVE SUPRANUCLEAR PALSY (PSP), FOLLOWED BY AN OPEN-LABEL EXTENSION TREATMENT PERIOD | PSP Progressive supranuclear palsy | Central Nervous System |  | 2018-12-03 | 2019-12-15 |  | 2015-05-12: 2020-03-16; 2015-09-29: 2020-07-09; 2016-04-08: 2021-07-09; 2019-11-29: 2024-11-11; 2020-02-04: 2024-12-11; 2020-02-07: 2025-01-10; 2020-05-05: 2025-04-15 | Australia, Austria, Belgium, Canada, France, Germany, Italy, Japan, Netherlands, Spain, United Kingdom, United States of America | Australia (Created), Austria (Created), Belgium (Created), Canada (Created), France (Created), Germany (Created), Italy (Created), Japan (Created), Netherlands (Created), Spain (Created), United Kingdom (Created), United States of America (Created) |  | 210 | 0 | 0 | 539 | 384 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | AS0009 | Study Archived | BIMAB phase 2b OLE study to assess safety and efficacy | Phase II | Open | GCSO | Immunology | GCSO | Forbes M | Bonny M | ICON | ICON | No | Yes | adults | No | A MULTICENTER, OPEN-LABEL EXTENSION STUDY TO EVALUATE THE LONG TERM SAFETY AND EFFICACY OF BIMEKIZUMAB IN SUBJECTS WITH ANKYLOSING SPONDYLITIS | Ankylosing Spondylitis | Immunology | AS0009 is an extension of AS0008 | 2016-08-02 08:00 | 2016-08-02 |  | 2017-05-15 | 2017-11-23 | 2017-11-28 | 2021-09-22 | 2018-07-02 16:15 | 2022-11-30 | 2022-10-19 | 2022-12-28 | 2023-01-20 | 2023-01-11 | 2023-02-10 | 2023-04-07 | 2023-05-15 | Bulgaria, Canada, Czech Republic, Germany, Hungary, Poland, Russian Federation, Spain, Ukraine, United States of America | Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), Germany (LPLV), Hungary (LPLV), Poland (LPLV), Russian Federation (LPLV), Spain (LPLV), Ukraine (LPLV), United States of America (LPLV) | Bulgaria, Canada, Czech Republic, Germany, Hungary, Poland, Russian Federation, Spain, Ukraine, United States of America | 53 | 51 | 50 | 297 | 278 | 278 | 0 | 0 | 0 | 254 | 0 | 55 | 201 |  |  | 2020-09-15 | 2020-09-15
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | AS0010 | Study Archived | BKZ phase 3, randomized, double-blind, placebo controlled | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Guo J, Raetz M | Bonny M, Grose-Hodge R | Parexel | PAREXEL | Yes | Yes | adults | No | A PHASE 3, MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED STUDY EVALUATING THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN SUBJECTS WITH ACTIVE NONRADIOGRAPHIC AXIAL SPONDYLOARTHRITIS | Non-Radiographic Axial Spondyloarthritis | Immunology | AS0010 is a "sister" study of AS0011 and is a feeder study of AS0014 | 2016-05-02 | 2016-05-02 |  | 2018-12-04 | 2019-05-08 | 2019-04-25 | 2020-11-16 | 2022-02-17 | 2022-04-11 | 2023-04-17 | 2022-05-09 | 2023-05-05 | 2022-05-23 | 2023-06-05 | 2022-08-17 | 2023-09-14 | Belgium, Bulgaria, China, Czech Republic, France, Germany, Hungary, Japan, Poland, Spain, Turkey, United Kingdom, United States of America | Belgium (LPLV), Bulgaria (LPLV), China (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Japan (LPLV), Netherlands (1st Site Initiation (Cancelled)), Poland (LPLV), Spain (LPLV), Turkey (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Bulgaria, China, Czech Republic, France, Germany, Hungary, Japan, Poland, Spain, Turkey, United Kingdom, United States of America | 97 | 96 | 83 | 840 | 274 | 247 | 878 | 0 | 604 | 274 | 0 | 38 | 236 | 2022-01-06 | 2022-01-06 | 2022-01-06 | 2022-01-06 |  |  | 2022-07-18 | 2022-07-15 | [14 empty] | yes
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | AS0011 | Study Archived | BKZ phase 3, randomized, double-blind, placebo controlled | Phase III | Double Blind | GCSO | Immunology | GCSO | Guo J, Raetz M | Bonny M, Grose-Hodge R | Parexel | PAREXEL | Yes | Yes | adults | No | A PHASE 3, MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED STUDY EVALUATING THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN SUBJECTS WITH ACTIVE ANKYLOSING SPONDYLITIS | Ankylosing Spondylitis | Immunology | AS0011 is a "sister" study of AS0010 and is a feeder study of AS0014 | 2016-05-02 | 2016-05-02 |  | 2018-11-27 | 2019-05-01 | 2019-04-25 | 2020-09-04 | 2021-04-21 | 2022-01-26 | 2022-08-08 | 2022-02-23 | 2022-09-09 | 2022-03-09 | 2022-09-30 | 2022-06-03 | 2023-01-31 | Belgium, Bulgaria, China, Czech Republic, France, Germany, Hungary, Japan, Netherlands, Poland, Spain, Turkey, United Kingdom, United States of America | Belgium (LPLV), Bulgaria (LPLV), China (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Japan (LPLV), Netherlands (LPLV), Poland (LPLV), Spain (LPLV), Turkey (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Bulgaria, China, Czech Republic, France, Germany, Hungary, Japan, Netherlands, Poland, Spain, Turkey, United Kingdom, United States of America | 97 | 93 | 83 | 612 | 332 | 299 | 642 | 0 | 310 | 332 | 0 | 34 | 298 | 2021-11-30 | 2021-11-30 | 2021-11-30 08:00 | 2021-11-30 |  |  | 2022-06-16 | 2022-06-16 | [14 empty] | yes
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | DV0002 | Study Archived | BKZ PSO Self-Injection of the safety syringe or the YpsoMed | Phase III | Open | GCSO | Immunology | UCB Pharma Global | Knapp B | Bonny M | Parexel | PAREXEL | Yes | No | adults | No | A MULTICENTER, RANDOMIZED, OPEN-LABEL STUDY TO EVALUATE THE SAFE AND EFFECTIVE USE OF THE PREFILLED SAFETY SYRINGES OR THE AUTO-INJECTOR FOR THE SUBCUTANEOUS SELF INJECTION OF BIMEKIZUMAB SOLUTION BY SUBJECTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIASIS. | Psoriasis | Immunology | DV0002 is a sub study of PS0014 | 2017-04-17 | 2018-01-17 | 2018-07-31 | 2018-07-26 | 2018-12-03 | 2018-12-20 | 2019-12-30 | 2020-05-19 | 2020-09-14 | 2020-09-08 | 2020-05-18 | 2020-11-06 | 2020-06-01 | 2020-12-07 | 2020-08-25 | 2021-05-03 | Canada, United States of America | Canada (LPLV), United States of America (LPLV) | Canada, United States of America | 60 | 48 | 39 | 300 | 300 | 120 | 172 | 0 | 0 | 172 | 0 | 11 | 161 | 2020-01-07 | 2020-01-07 | 2020-01-07 | 2020-01-07
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | DV0004 | CSR Approved | A MULTICENTER, RANDOMIZED, OPEN-LABEL STUDY TO EVALUATE THE | Phase III | Open | GCSO | Immunology | UCB Pharma Global | Heinrichs A | Bonny M | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, RANDOMIZED, OPEN-LABEL STUDY TO EVALUATE THE SAFE AND EFFECTIVE USE OF THE PREFILLED SAFETY SYRINGE OR AUTO-INJECTOR FOR THE SUBCUTANEOIUS SELF-INJECTION OF BIMEKIZUMAB SOLUTION BY SUBJECTS WITH ACTIVE PSOARIATIC ARTHRITIS | Psoriatic Arthritis | Immunology | DV0004 is a sub study of PA0012 | 2018-12-10 | 2018-12-10 | 2019-02-05 | 2019-02-05 | 2019-08-01 | 2019-08-13 | 2020-10-15 | 2020-10-06 | 2021-02-04 | 2020-11-13 | 2021-03-04 | 2022-01-17 | 2021-03-18 | 2022-01-31 | 2021-06-15 | 2022-04-07 | Czech Republic, Germany, Hungary, Poland, Russian Federation, United States of America | Czech Republic (LPLV), Germany (LPLV), Hungary (LPLV), Poland (LPLV), Russian Federation (LPLV), United States of America (LPLV) | Czech Republic, Germany, Hungary, Poland, Russian Federation, United States of America | 42 | 63 | 46 | 182 | 182 | 182 | 214 | 0 | 0 | 214 | 0 | 3 | 211
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | DV0006 | Study Archived | EU and Japan sub-study of PS0014 | Phase III | Not Applicable | GCSO | Immunology | UCB Pharma Global | Knapp B | Bonny M | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, RANDOMIZED, OPEN-LABEL STUDY TO EVALUATE THE SAFE AND EFFECTIVE USE OF THE PREFILLED SAFETY SYRINGE OR THE AUTO-INJECTOR FOR THE SUBCUTANEOUS SELF INJECTION OF BIMEKIZUMAB SOLUTION BY SUBJECTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIASIS. | Psoriasis | Immunology | DV0006 is a sub study of PS0014 | 2018-04-17 | 2018-03-14 |  | 2018-08-03 | 2019-04-18 | 2019-05-03 | 2020-05-18 | 2020-05-22 | 2020-07-16 | 2020-09-03 | 2020-10-01 | 2020-11-06 | 2020-10-15 | 2020-12-11 | 2021-01-08 | 2021-05-03 | Germany, Hungary, Japan, Poland | Germany (LPLV), Hungary (LPLV), Japan (LPLV), Poland (LPLV) | Germany, Hungary, Japan, Poland | 50 | 31 | 26 | 220 | 220 | 50 | 177 | 0 | 0 | 177 | 0 | 4 | 173
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | HS0001 | Study Archived | PoC to assess Bimekizumab in patients with mod to Severe HS | Phase II | Double Blind | GCSO | NewMeds | Affiliates | Knowles S | Grose-Hodge R | Parexel | PAREXEL | Yes | Yes | adults | No | A PHASE 2 MULTICENTER, INVESTIGATOR-BLIND, SUBJECT-BLIND, PLACEBO-CONTROLLED STUDY OF THE EFFICACY, SAFETY, AND PHARMACOKINETICS OF BIMEKIZUMAB IN SUBJECTS WITH MODERATE TO SEVERE HIDRADENITIS SUPPURATIVA | Hidradenitis Suppurativa | Immunology |  | 2017-03-02 | 2017-02-26 |  | 2017-05-31 | 2017-09-19 | 2017-09-22 | 2018-07-26 | 2018-07-06 | 2019-03-21 | 2019-02-21 | 2019-04-18 | 2019-03-28 | 2019-05-02 | 2019-06-25 | 2019-06-27 | 2019-10-28 | Australia, Belgium, Denmark, Germany, Greece, Norway, Russian Federation, United States of America | Australia (LPLV), Belgium (LPLV), Denmark (LPLV), Germany (LPLV), Greece (LPLV), Norway (LPLV), Russian Federation (LPLV), United States of America (LPLV) | Australia, Belgium, Denmark, Germany, Greece, Norway, Russian Federation, United States of America | 45 | 39 | 31 | 200 | 200 | 200 | 169 | 0 | 79 | 90 | 0 | 14 | 76
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | HS0003 | Study Archived | A Phase 3a, Randomized, Double-blind, Placebo-Controlled, Mu | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Byerly R | Bonny M | Parexel | PAREXEL | Yes | Yes | adults | No | A PHASE 3, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER STUDY EVALUATING THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN STUDY PARTICIPANTS WITH MODERATE TO SEVERE HIDRADENITIS SUPPURATIVA | Hidradenitis Suppurativa | Immunology | HS0003 is a "sister" study of HS0004 and is a feeder study of HS0005 | 2019-09-06 08:00 | 2019-09-06 | 2019-10-29 | 2019-10-29 | 2020-04-29 | 2020-02-19 | 2021-12-08 | 2021-10-27 | 2023-05-03 | 2023-02-19 | 2023-05-17 | 2023-03-10 | 2023-05-31 | 2023-04-03 | 2023-10-04 | 2023-10-13 | Australia, Belgium, Canada, Denmark, France, Germany, Greece, Israel, Italy, Netherlands, Norway, Spain, Switzerland, Turkey, United States of America | Australia (LPLV), Belgium (LPLV), Canada (LPLV), Denmark (LPLV), France (LPLV), Germany (LPLV), Greece (LPLV), Israel (LPLV), Italy (LPLV), Netherlands (LPLV), Norway (LPLV), Spain (LPLV), Switzerland (LPLV), Turkey (LPLV), United States of America (LPLV) | Australia, Belgium, Canada, Denmark, France, Germany, Greece, Israel, Italy, Netherlands, Norway, Spain, Switzerland, Turkey, United States of America | 103 | 96 | 88 | 759 | 490 | 490 | 806 | 0 | 288 | 518 | 0 | 181 | 333 |  |  | 2023-01-05 08:00 | [19 empty] | yes
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | HS0004 | Study Archived | A Phase 3a, Randomized, Double-blind, Placebo-Controlled, Mu | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Knowles S | Grose-Hodge R | Parexel | PAREXEL | Yes | Yes | adults | No | A PHASE 3, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER STUDY EVALUATING THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN STUDY PARTICIPANTS WITH MODERATE TO SEVERE HIDRADENITIS SUPPURATIVA | Hidradenitis Suppurativa | Immunology | HS0004 is a "sister" study of HS0003 and is a feeder study of HS0005 | 2019-05-17 08:00 | 2019-05-17 |  | 2019-10-29 | 2020-02-28 | 2020-03-02 | 2021-10-08 | 2021-07-28 | 2023-02-28 | 2022-09-28 | 2023-03-28 | 2022-10-12 | 2023-04-11 | 2022-11-11 | 2023-07-06 | 2023-02-08 | Australia, Bulgaria, Canada, Czech Republic, France, Germany, Hungary, Ireland, Israel, Japan, Poland, Spain, United Kingdom, United States of America | Australia (LPLV), Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Ireland (LPLV), Israel (LPLV), Japan (LPLV), Poland (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Bulgaria, Canada, Czech Republic, France, Germany, Hungary, Ireland, Israel, Japan, Poland, Spain, United Kingdom, United States of America | 117 | 100 | 91 | 761 | 490 | 490 | 754 | 1 | 236 | 517 | 22 | 128 | 368 |  |  | 2022-07-28 08:00 | 2022-08-12 | [18 empty] | yes
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PA0009 | Study Archived | BIMAB Open-label extension study to determine the safety of | Phase II | Open | GCSO | Immunology | GCSO | Forbes M | Bonny M | PRA | PRA | No | Yes | adults | No | "A MULTICENTER, OPEN-LABEL, FOLLOW-UP STUDY TO EVALUATE THE LONG-TERM SAFETY AND EFFICACY OF BIMEKIZUMAB IN SUBJECTS WITH PSORIATIC ARTHRITIS" | Psoriatic Arthritis | Immunology | PA0009 is an extension of PA0008 | 2016-08-03 | 2016-08-03 |  | 2017-05-15 | 2017-12-05 | 2017-11-21 | 2019-01-09 | 2018-07-16 | 2020-11-18 | 2020-10-29 04:00 | 2020-12-16 | 2020-11-23 | 2021-01-14 | 2020-12-15 | 2021-03-10 | 2021-04-30 | Czech Republic, Germany, Hungary, Poland, Russian Federation, United States of America | Czech Republic (LPLV), Germany (LPLV), Hungary (LPLV), Poland (LPLV), Russian Federation (LPLV), United States of America (LPLV) | Czech Republic, Germany, Hungary, Poland, Russian Federation, United States of America | 38 | 37 | 37 | 195 | 195 | 195 | 1 | 0 | 0 | 184 | 0 | 23 | 161
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PA0010 | Study Archived | BKZ A ph3, rand,double-blind, pbo-control & active reference | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Bonny M, Heinrichs A, Matano M | Bonny M, Grose-Hodge R, Matsuo T | Parexel | PAREXEL | Yes | Yes | adults | No | A PHASE 3, MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, ACTIVE REFERENCE (ADALIMUMAB) STUDY EVALUATING THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN THE TREATMENT OF SUBJECTS WITH ACTIVE PSORIATIC ARTHRITIS | Psoriatic Arthritis | Immunology | PA0010 is a "sister" study of PA0011 and is a feeder study of PA0012 | 2016-03-15 08:00 | 2016-03-15 |  | 2018-11-28 | 2019-03-28 | 2019-04-03 | 2021-03-02 | 2021-03-25 | 2022-07-11 | 2022-07-11 | 2022-07-25 | 2022-07-29 | 2022-08-09 | 2022-09-01 | 2022-10-17 | 2022-12-02 | Australia, Belgium, Canada, Czech Republic, France, Germany, Hungary, Italy, Japan, Poland, Russian Federation, Spain, United Kingdom, United States of America | Australia (LPLV), Belgium (LPLV), Canada (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Japan (LPLV), Poland (LPLV), Russian Federation (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Belgium, Canada, Czech Republic, France, Germany, Hungary, Italy, Japan, Poland, Russian Federation, Spain, United Kingdom, United States of America | 158 | 160 | 135 | 1250 | 840 | 714 | 1215 | 0 | 363 | 852 | 0 | 87 | 765 | 2021-11-11 | 2021-11-11 | 2021-11-11 | 2021-11-11 | 2022-05-30 | 2022-05-30 | 2022-06-07 | 2022-06-08
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PS0008 | Study Archived | BIMAB Phase 3 Operationally Seamless Active Comparator PsO S | Phase III | Double Blind | GCSO | Immunology | GCSO | Krautz I | Russell R | Parexel | PAREXEL | Yes | Yes | adults | No | A PHASE 3, MULTICENTER, RANDOMIZED, DOUBLE-BLIND STUDY WITH A 24-WEEK ACTIVE-CONTROLLED INITIAL TREATMENT PERIOD FOLLOWED BY A 32-WEEK, DOSE-BLIND MAINTENANCE TREATMENT PERIOD TO EVALUATE THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN ADULT SUBJECTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIASIS | Psoriasis | Immunology | PS0008 is a feeder study of PS0014 | 2016-03-01 | 2016-03-02 |  | 2017-08-05 | 2018-01-19 | 2018-01-26 | 2018-10-12 | 2018-09-14 | 2020-03-14 | 2020-02-26 | 2020-03-30 | 2020-04-09 | 2020-04-13 | 2020-04-30 | 2020-06-11 | 2020-10-13 | Australia, Canada, Germany, Hungary, Poland, Russian Federation, South Korea, Taiwan, United States of America | Australia (LPLV), Canada (LPLV), Germany (LPLV), Hungary (LPLV), Poland (LPLV), Russian Federation (LPLV), South Korea (LPLV), Taiwan (LPLV), United States of America (LPLV) | Australia, Canada, Germany, Hungary, Poland, Russian Federation, South Korea, Taiwan, United States of America | 96 | 79 | 77 | 800 | 478 | 455 | 635 | 0 | 157 | 478 | 0 | 58 | 420 |  |  |  | 2019-11-25
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PS0009 | Study Archived | BIMAB Phase 3 Active Comparator PsO Subjects | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Murphy C | Russell R | Parexel | PAREXEL | Yes | Yes | adults | No | A PHASE 3, MULTICENTER, randomized, double-blind, PLACEBO- AND ACTIVE COMPARATOR-CONTROLLED, parallel-group study to EVALUATE the EFFICACY AND safety of bimekizumab in adult subjects with moderate to severe chronic plaque psoriasis | Psoriasis | Immunology | PS0009 is a feeder study of PS0014 | 2016-03-01 | 2016-03-02 |  | 2017-08-05 | 2017-12-15 | 2017-12-06 | 2018-10-31 | 2018-08-20 | 2020-03-04 | 2019-12-13 | 2020-03-18 | 2020-02-07 | 2020-04-01 | 2020-02-23 | 2020-05-30 | 2020-09-21 | Australia, Belgium, Canada, Germany, Hungary, Italy, Japan, Poland, Russian Federation, United Kingdom, United States of America | Australia (LPLV), Belgium (LPLV), Canada (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Japan (LPLV), Poland (LPLV), Russian Federation (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Belgium, Canada, Germany, Hungary, Italy, Japan, Poland, Russian Federation, United Kingdom, United States of America | 132 | 112 | 105 | 749 | 560 | 482 | 746 | 0 | 179 | 567 | 0 | 75 | 492 |  |  | 2019-09-30 | 2019-09-30
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PS0013 | Study Archived | Bimekizumab PSO phase 3 treatment withdrawal to assess safe | Phase III | Double Blind | GCSO | Immunology | GCSO | Murphy C | Russell R | Parexel | PAREXEL | Yes | Yes | adults | No | A phase 3, MULTICENTER, double-blind, placebo controlled study with an Initial Treatment period FOLLOWED BY A randomized-withdrawal PERIOD TO EVALUATE THE EFFICACY and safety OF BIMEKIZUMAB IN ADULT SUBJECTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIASIS. | Psoriasis | Immunology | PS0013 is a feeder study of PS0014 | 2016-08-15 | 2016-05-01 |  | 2017-08-22 | 2018-01-29 | 2018-02-05 | 2018-09-29 | 2018-08-22 | 2020-02-29 | 2020-01-07 | 2020-03-14 | 2020-03-05 | 2020-03-30 | 2020-03-19 | 2020-05-28 | 2020-10-12 | Australia, Canada, Germany, Hungary, Poland, Russian Federation, South Korea, United Kingdom, United States of America | Australia (LPLV), Canada (LPLV), Germany (LPLV), Hungary (LPLV), Poland (LPLV), Russian Federation (LPLV), South Korea (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Canada, Germany, Hungary, Poland, Russian Federation, South Korea, United Kingdom, United States of America | 97 | 86 | 77 | 535 | 400 | 360 | 582 | 0 | 147 | 435 | 0 | 28 | 407 | 2020-01-04 | 2020-01-04 | 2019-10-18 | 2019-12-12
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PS0014 | CSR Approved | BIMAB Phase 3 OLE PsO Subjects | Phase III | Open | GCSO | Immunology | GCSO | Knapp B | Bonny M | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, OPEN-LABEL STUDY TO ASSESS THE LONG-TERM SAFETY, TOLERABILITY, AND EFFICACY OF BIMEKIZUMAB IN ADULT SUBJECTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIASIS | Psoriasis | Immunology | PS0014 is an extension of PS0008, PS0009, PS0013 and is linked to sub study DV0002, DV0006 | 2017-06-30 08:00 | 2017-06-30 |  | 2018-04-05 | 2018-12-05 | 2018-09-12 | 2020-04-08 | 2020-01-07 | 2021-09-25 | 2023-11-14 | 2021-10-23 | 2023-12-13 | 2021-11-08 | 2024-01-25 | 2022-02-02 | 2024-05-13 | Australia, Belgium, Canada, Germany, Hungary, Italy, Japan, Poland, Russian Federation, South Korea, Taiwan, United Kingdom, United States of America | Australia (LPLV), Belgium (LPLV), Canada (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Japan (LPLV), Poland (LPLV), Russian Federation (LPLV), South Korea (LPLV), Taiwan (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Belgium, Canada, Germany, Hungary, Italy, Japan, Poland, Russian Federation, South Korea, Taiwan, United Kingdom, United States of America | 190 | 189 | 189 | 1325 | 1325 | 1325 | 1368 | 0 | 12 | 1356 | 0 | 236 | 1119 |  |  | 2020-08-29 | 2020-08-29 |  |  | 2023-01-26 | 2023-01-26
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PS0015 | Study Archived | a multicenter, randomized, double-blind, secukinumab-control | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Kaspar M | Bonny M | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, RANDOMIZED, DOUBLE-BLIND, SECUKINUMAB-CONTROLLED, PARALLEL-GROUP STUDY TO EVALUATE THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN ADULT SUBJECTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIASIS. | Psoriasis | Immunology |  | 2017-08-25 08:00 | 2017-08-25 | 2017-11-10 | 2018-03-26 | 2018-09-26 | 2018-06-13 | 2019-09-10 | 2019-04-12 | 2020-12-15 | 2023-08-09 | 2021-01-12 | 2023-09-11 | 2021-01-26 | 2023-09-29 | 2021-04-22 | 2024-02-13 | Australia, Belgium, Canada, France, Germany, Netherlands, Poland, Spain, Turkey, United Kingdom, United States of America | Australia (LPLV), Belgium (LPLV), Canada (LPLV), France (LPLV), Germany (LPLV), Netherlands (LPLV), Poland (LPLV), Spain (LPLV), Turkey (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Belgium, Canada, France, Germany, Netherlands, Poland, Spain, Turkey, United Kingdom, United States of America | 89 | 82 | 77 | 937 | 700 | 700 | 1022 | 0 | 279 | 743 | 0 | 168 | 562 | 2020-05-19 | 2020-05-19 | 2020-07-13 | 2020-07-13 | [18 empty] | yes
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PS0018 | Study Archived | OLE study from PS0016 in PSO to understand time response/los | Phase II | Open | GCSO | NewMeds | UCB Pharma Global | Soranson J | Grose-Hodge R | Parexel | PAREXEL | Yes | Yes | adults | Yes | A MULTICENTER, 48-WEEK, OPEN-LABEL EXTENSION STUDY TO ASSESS THE LONG-TERM SAFETY, TOLERABILITY, AND EFFICACY OF BIMEKIZUMAB IN ADULT SUBJECTS WITH MODERATE TO SEVERE CHRONIC PLAQUE PSORIASIS | Psoriasis | Immunology | PS0018 is an extension of PS0016 |  |  |  | 2016-08-01 | 2017-03-15 | 2017-07-03 | 2017-10-17 | 2017-11-24 | 2019-03-05 | 2019-03-06 | 2019-05-21 | 2019-05-17 | 2019-04-30 | 2019-06-26 | 2019-09-03 | 2019-09-03 | Australia, Canada, Moldavia, United States of America | Australia (LPLV), Canada (LPLV), Moldavia (LPLV), United States of America (LPLV) | Australia, Canada, Moldavia, United States of America | 10 | 9 | 9 | 45 | 45 | 45 | 43 | 0 | 0 | 43 | 0 | 5 | 38
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BIMZELX | Immunology | PS0032 | Study Archived | Double-blind, randomized study of Bimekizumab in Korean | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Namgoong K | Beinhauer-Zellenka U | Parexel | PAREXEL | Yes | Yes | adults | No | A phase 3, multicenter, randomized, double blind, placebo-controlled, parallel group study to evaluate the efficacy and safety of Bimekizumab in adult Korean study participants with moderate to severe Plaque psoriasis | Psoriasis | Immunology |  | 2020-07-08 08:00 | 2020-07-08 |  | 2020-12-18 | 2021-06-18 | 2021-09-27 | 2021-12-17 | 2022-04-19 | 2022-09-02 | 2022-09-06 | 2022-09-30 | 2022-11-18 | 2022-10-14 | 2023-03-01 | 2023-01-10 | 2023-03-14 | South Korea | South Korea (LPLV) | South Korea | 9 | 9 | 9 | 54 | 45 | 38 | 87 | 0 | 40 | 47 | 0 | 1 | 46 | [22 empty] | yes
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0065 | Study Archived | Open-label pediatric iv Brivaracetam study | Phase II | Open | GCSO | Neurology | GCSO | Will E | Copetti C | PRA | PRA | Yes | Yes | paediatrics | No | A MULTICENTER, OPEN-LABEL STUDY TO EVALUATE THE PHARMACOKINETICS, SAFETY, AND TOLERABILITY OF INTRAVENOUS BRIVARACETAM IN SUBJECTS >=1 MONTH TO <16 YEARS OF AGE WITH EPILEPSY | Epilepsy | Central Nervous System | EP0065 is a feeder study of EP0156, N01266 | 2015-02-27 | 2015-03-20 |  | 2017-03-17 | 2018-01-17 | 2018-06-01 16:00 | 2020-12-30 | 2020-10-23 | 2020-04-16 | 2020-11-04 | 2020-04-28 | 2020-11-20 | 2020-05-08 | 2020-12-04 | 2020-06-26 | 2021-02-09 | Czech Republic, Germany, Hungary, Italy, Mexico, Spain, United States of America | Czech Republic (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Mexico (LPLV), Spain (LPLV), United States of America (LPLV) | Czech Republic, Germany, Hungary, Italy, Mexico, Spain, United States of America | 37 | 39 | 16 | 60 | 50 | 50 | 58 | 0 | 8 | 50 | 0 | 0 | 50
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0083 | Study Archived | EP0083 Asia BRV POS add-on study | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global | Chi O, Sasamoto H | Grose-Hodge R, Matsuo T | Parexel | PAREXEL | Yes | Yes | adults | No | A RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER, PARALLEL-GROUP STUDY TO EVALUATE THE EFFICACY AND SAFETY OF ADJUNCTIVE BRIVARACETAM IN SUBJECTS (> or =16 TO 80 YEARS OF AGE) WITH PARTIAL SEIZURES WITH OR WITHOUT SECONDARY GENERALIZATION. | Epilepsy | Central Nervous System | EP0083 is a parent study of EP0085 | 2016-06-15 08:00 | 2016-06-15 |  | 2016-10-17 | 2017-07-14 | 2017-08-22 | 2019-09-12 | 2022-01-29 | 2020-01-30 | 2022-06-30 | 2020-02-15 | 2022-08-23 | 2020-02-27 | 2022-09-05 | 2020-04-03 | 2022-12-05 | China, Japan, Malaysia, Philippines, Singapore, Taiwan, Thailand | China (LPLV), Japan (LPLV), Malaysia (LPLV), Philippines (LPLV), Singapore (LPLV), Taiwan (LPLV), Thailand (LPLV) | China, Japan, Malaysia, Philippines, Singapore, Taiwan, Thailand | 95 | 106 | 94 | 555 | 444 | 444 | 604 | 0 | 155 | 449 | 0 | 16 | 433
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0118 | Study Archived | EP0118 Japan BRV iv POS add-on Open-label study | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Sasamoto H | Matsuo T | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, OPEN-LABEL STUDY TO EVALUATE THE SAFETY AND TOLERABILITY OF INTRAVENOUS BRIVARACETAM AS REPLACEMENT FOR ORAL BRIVARACETAM IN JAPANESE SUBJECTS >=16 YEARS OF AGE WITH PARTIAL SEIZURES WITH OR WITHOUT SECONDARY GENERALIZATION | Epilepsy | Central Nervous System |  | 2017-09-14 | 2017-09-13 |  | 2018-03-01 | 2019-01-31 | 2019-01-04 | 2020-04-23 | 2021-03-21 | 2020-04-30 | 2021-03-27 | 2020-05-14 | 2021-05-25 | 2020-05-28 | 2021-06-15 | 2020-08-20 | 2021-09-14 | Japan | Japan (LPLV) | Japan | 8 | 9 | 7 | 10 | 10 | 9 | 10 | 0 | 0 | 10 | 0 | 0 | 10
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BRIVIACT | Central Nervous System | N01268 | Protoc. Summary Approved (Cancelled) | Ped Exclusivity 1 month-4Y | Phase III |  | GCSO | Neurology | UCB Pharma Global | Copetti C | Grose-Hodge R | [5 empty] | No |  | Epilepsy | Central Nervous System |  | 2016-11-04 | 2016-11-04 | [14 empty] | United States of America | United States of America (Created) |  | 50 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | BRIVIACT | Central Nervous System | N01349 | Study Archived | Phase 2/3, open‑label study, BRV in neonates with ENS | Phase III | Open | GCSO | Neurology | GCSO | Will E | Copetti C | PRA | PRA | Yes | Yes | paediatrics | No | A MULTICENTER, OPEN-LABEL, SINGLE-ARM STUDY TO EVALUATE THE Pharmacokinetics, EFFICACY, AND SAFETY OF BRIVARACETAM IN NEONATES WITH REPEATED electroencephalographic SEIZURES | Epilepsy | Central Nervous System | N01349 is a feeder study of EP0156, N01266 | 2015-05-13 08:00 | 2015-05-13 |  | 2016-10-17 | 2017-04-10 | 2019-05-07 10:00 | 2019-06-04 | 2021-05-27 10:00 | 2019-08-16 | 2021-05-30 10:00 | 2019-08-30 | 2022-02-09 | 2019-09-11 | 2022-02-22 | 2019-10-30 | 2022-04-11 | Belgium, France, Germany, Ireland | Belgium (LPLV), Czech Republic (1st Site Initiation (Cancelled)), France (LPLV), Germany (LPLV), Ireland (LPLV), Italy (1st Site Initiation (Cancelled)), Netherlands (1st Site Initiation (Cancelled)), United Kingdom (1st Site Initiation (Cancelled)) | Belgium, France, Germany, Ireland | 16 | 16 | 4 | 63 | 42 | 42 | 9 | 0 | 3 | 6 | 0 | 0 | 6
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | CIMZIA | Immunology | AS0018 | Protoc. Summary Approved (Cancelled) | Efficacy and Safety of CDP870 in Subjects with Axial SpA | Phase III |  | GCSO | Immunology | UCB Pharma Global |  |  | Parexel | PAREXEL | No | No | adults | No |  | Axial Spondyloarthritis (axSpA) | Immunology |  | 2016-06-30 | 2016-06-30 | [17 empty] | 40 | 0 | 0 | 600 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | CIMZIA | Immunology | CD0003 | Protocol Approved (Cancelled) | Cimzia Crohn Paediatric | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Jabbarzadegan P | Cain D | Parexel | PAREXEL | Yes | Yes | paediatrics | No | A PHASE 3, RANDOMIZED, DOUBLE-BLIND, MULTICENTER STUDY INCLUDING AN ACTIVE REFERENCE ARM TO EVALUATE EFFICACY, SAFETY, AND PHARMACOKINETICS OF CERTOLIZUMAB PEGOL IN CHILDREN AND ADOLESCENTS (6 TO 17 YEARS OF AGE) WITH MODERATELY TO SEVERELY ACTIVE CROHN'S DISEASE | Crohn's disease | Immunology |  |  |  | 2020-02-04 | 2015-05-12: 2020-02-03; 2015-09-29: 2021-01-25; 2016-04-08: 2023-02-06; 2019-11-29: 2026-04-17; 2020-02-04: 2026-08-12; 2020-02-07: 2026-08-26; 2020-05-05: 2026-11-20 | United States of America | United States of America (Created) |  | 20 | 0 | 0 | 300 | 150 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2029-11-27 08:00
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | CIMZIA | Immunology | CD0007 | Created (Cancelled) | Optimized Induction Dosing of Certolizumab Pegol in Crohn’s | Phase IV |  | GCSO | Immunology | UCB Pharma Global | Murphy C | Russell R | Parexel |  | Yes | Yes | adults | No |  | Crohn's disease | Immunology |  | 2018-08-01 08:00 | [18 empty] | 10 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | CIMZIA | Immunology | RA0098 | Study Archived | e-Device Clinical Use study | Phase III | Open | GCSO | Immunology | UCB Pharma Global | Murphy C | Russell R | Parexel | SPI PXL | Yes | No | adults | No | A Multicenter, Open-Label study to evaluate the safe and effective use of an electro-mechanical injection device (E-Device) for the subcutaneous self-injection of CERTOLIZUMAB PEGOL solution by subjects with moderate to severe active rheumatoid arthritis, active ankylosing spondylitis, active psoriatic arthritis, or moderately to severely active crohn’s disease | Rheumatoid Arthritis | Immunology |  | 2015-10-16 | 2016-04-29 |  | 2017-06-28 | 2018-06-22 | 2017-11-03 | 2019-01-15 | 2018-05-29 |  | 2018-07-02 |  | 2018-07-12 |  | 2018-07-31 |  | 2018-10-11 | United States of America | United States of America (LPLV) | United States of America | 30 | 25 | 22 | 60 | 60 | 51 | 70 | 0 | 2 | 68 | 0 | 3 | 65
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Dapirolizumab pegol | Immunology | SL0043 | Study Archived | Evaluation of efficacy and safety of Dapimab in active syste | Phase III | Double Blind | GCSO | Immunology | UCB Pharma Global | Conrath P | Copetti C | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL-GROUP STUDY TO EVALUATE THE EFFICACY AND SAFETY OF DAPIROLIZUMAB PEGOL IN STUDY PARTICIPANTS WITH MODERATELY TO SEVERELY ACTIVE SYSTEMIC LUPUS ERYTHEMATOSUS | Systemic Lupus Erythematosus | Immunology | SL0043 is a "sister" study of SL0044, SL0045 and is a feeder study of SL0046 | 2019-05-13 | 2019-05-13 |  | 2019-12-03 | 2020-02-17 | 2020-08-12 | 2021-09-21 | 2023-06-08 | 2022-10-19 | 2024-06-04 | 2022-11-15 | 2024-07-23 | 2022-11-29 | 2024-08-09 | 2023-02-23 | 2024-10-30 | Argentina, Australia, Austria, Belgium, Bulgaria, Canada, Chile, Colombia, Czech Republic, Denmark, France, Germany, Greece, Hong Kong, Hungary, Italy, Mexico, Peru, Philippines, Poland, Portugal, Romania, Serbia, South Korea, Spain, Taiwan, United Kingdom, United States of America | Argentina (LPLV), Australia (LPLV), Austria (LPLV), Belgium (LPLV), Bulgaria (LPLV), Canada (LPLV), Chile (LPLV), Colombia (LPLV), Czech Republic (LPLV), Denmark (LPLV), France (LPLV), Germany (LPLV), Greece (LPLV), Hong Kong (1st Site Initiation), Hungary (LPLV), Italy (LPLV), Mexico (LPLV), Peru (LPLV), Philippines (LPLV), Poland (LPLV), Portugal (1st Site Initiation), Romania (LPLV), Serbia (LPLV), South Korea (LPLV), Spain (LPLV), Taiwan (LPLV), United Kingdom (1st Site Initiation), United States of America (LPLV) | Argentina, Australia, Austria, Belgium, Bulgaria, Canada, Chile, Colombia, Czech Republic, Denmark, France, Germany, Greece, Hong Kong, Hungary, Italy, Mexico, Peru, Philippines, Poland, Portugal, Romania, Serbia, South Korea, Spain, Taiwan, United Kingdom, United States of America | 237 | 237 | 177 | 312 | 312 | 280 | 713 | 0 | 391 | 322 | 0 | 43 | 279 | 2023-04-26 | 2023-04-26 | 2023-06-09 | 2023-06-09 | [18 empty] | yes
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Dapirolizumab pegol | Immunology | SL0045 | Created (Cancelled) | Evaluation of efficacy and safety of Dapimab in active syste | Phase III |  | GCSO | Immunology | UCB Pharma Global | Conrath P | Copetti C | Parexel |  | No | No | adults | No |  | Systemic Lupus Erythematosus | Immunology | SL0045 is a "sister" study of SL0043, SL0044 and is a feeder study of SL0046 | 2019-08-08 08:00 | [15 empty] | Argentina, Australia, Belgium, Brazil, Bulgaria, Canada, Chile, France, Germany, Greece, Hungary, Italy, Lithuania, Mexico, Philippines, Poland, Romania, Russian Federation, Serbia, Singapore, South Africa, South Korea, Spain, Taiwan, Ukraine, United Kingdom, United States of America | Argentina (Created), Australia (Created), Belgium (Created), Brazil (Created), Bulgaria (Created), Canada (Created), Chile (Created), France (Created), Germany (Created), Greece (Created), Hungary (Created), Italy (Created), Lithuania (Created), Mexico (Created), Philippines (Created), Poland (Created), Romania (Created), Russian Federation (Created), Serbia (Created), Singapore (Created), South Africa (Created), South Korea (Created), Spain (Created), Taiwan (Created), Ukraine (Created), United Kingdom (Created), United States of America (Created) |  | 280 | 0 | 0 | 700 | 360 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0104 | Created (Cancelled) | Ph 3 efficacy and safety in treatment naive TK2d pts | Phase III |  | GCSO | Neurology | UCB Pharma Global | Chavan P |  | ICON |  | No | No | adults | No |  | Thymidine kinase 2 (TK2) deficiency; Mitochondrial DNA Depletion syndrome | Central Nervous System; Central Nervous System | [20 empty] | 6 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0108 | Created (Cancelled) | Randomized controlled trial in late onset patients < 12Y <18 | Phase III |  | GCSO | Neurology | UCB Pharma Global | [7 empty] | No | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | EVENITY | Bones | OP0002 | Study Archived | Phase III study in Chinese patients with osteoporosis | Phase III | Double Blind | GCSO | Bone | UCB Pharma Global | Gao L | Guo J | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO CONTROLLED STUDY TO EVALUATE THE EFFICACY, SAFETY AND TOLERABILITY OF ROMOSOZUMAB TREATMENT IN POSTMENOPAUSAL CHINESE WOMEN WITH OSTEOPOROSIS | Osteoporosis | Bones |  | 2018-03-12 08:00 | 2019-04-05 | 2019-04-05 | 2019-04-09 | 2020-02-28 | 2021-11-12 | 2021-03-26 | 2022-08-17 | 2022-06-10 | 2023-11-09 | 2022-07-08 | 2023-11-27 | 2022-07-22 | 2023-12-11 | 2022-10-18 | 2024-03-28 | China | China (LPLV) | China | 31 | 31 | 30 | 300 | 300 | 300 | 564 | 9 | 228 | 327 | 0 | 34 | 293 | 2023-03-31 | 2023-03-31 | 2023-03-31 | 2023-03-31
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Fintepla | Central Nervous System | EP0208 | CSR Approved | Multicenter, randomized, double-blind, placebo-controlled, e | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | [7 empty] | No | A Multicenter, Randomized, Double-blind, Parallel Group, Placebo-controlled Trial of Two Fixed Doses of ZX008 (Fenfluramine Hydrochloride Oral Solution) as an Adjunctive Therapy in Children and Young Adults with Dravet Syndrome |  |  | EP0208 is a feeder study of EP0212 |  |  |  | 2020-07-02: 2021-10-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Fintepla | Central Nervous System | EP0209 | CSR Approved | Multicenter, randomized, double-blind, placebo-controlled, e | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | [7 empty] | No | A Multicenter, Randomized, Double-blind, Parallel Group, Placebo[1]controlled Trial of Two Fixed Doses of ZX008 (Fenfluramine Hydrochloride) Oral Solution as an Adjunctive Therapy in Children and Young Adults with Dravet Syndrome |  |  | EP0209 is a feeder study of EP0212 |  |  |  | 2020-07-02: 2021-10-18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Fintepla | Central Nervous System | EP0210 | CSR Approved | 2-arm, multicentre, randomised, double-blind, parallel group | Phase III |  | UCB Pharma Global |  | UCB Pharma Global | [7 empty] | No |  |  |  | EP0210 is a feeder study of EP0212 |  |  |  | 2020-07-02: 2018-12-21 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Fintepla | Central Nervous System | EP0212 | CSR Approved | OL to evaluate safety and tolerability (Zogenix 1503) | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Chheda J | Copetti C | N/A | SYNEOS HEALTH | No | No | other | No | An Open-Label Extension Trial to Assess the Long-Term Safety of ZX008 (Fenfluramine Hydrochloride) Oral Solution as an Adjunctive Therapy in Children and Young Adults with Dravet Syndrome | Lennox Gastaut Syndrome (LGS) | Central Nervous System | EP0212 is an extension of EP0208, EP0209, EP0210 and is a feeder study of EP0215 | 2016-02-08 08:00 | 2016-01-01 | 2016-04-04 | 2016-03-01 | 2016-06-23 | 2016-07-05 | 2020-07-29 | 2021-12-10 | 2023-01-31 | 2023-01-27 |  | 2023-04-11 |  | 2023-06-26 |  | 2023-07-24 | Australia, Belgium, Canada, Denmark, France, Germany, Italy, Japan, Netherlands, Spain, United Kingdom, United States of America | Australia (LPLV), Belgium (LPLV), Canada (LPLV), Denmark (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Japan (LPLV), Netherlands (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Belgium, Canada, Denmark, France, Germany, Italy, Japan, Netherlands, Spain, United Kingdom, United States of America | 73 | 67 | 66 | 340 | 340 | 340 | 374 | 0 | 0 | 374 | 0 | 313 | 61
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Fintepla | Central Nervous System | EP0214 | CSR Approved | Randomized, double-blind, placebo controlled (Zogenix 1601) | Phase III | Double Blind to Open Label | GCSO | Neurology | UCB Pharma Global | Ozkan Y | Tillery N | N/A | SYNEOS HEALTH | No | No | other | No | A Two-Part Study of ZX008 in Children and Adults with Lennox-Gastaut Syndrome (LGS); Part 1: A Randomized, Double-blind, Placebo-controlled Trial of Two Fixed Doses of ZX008 (Fenfluramine Hydrochloride) Oral Solution as Adjunctive Therapy for Seizures in Children and Adults with LGS, Followed by Part 2: An Open-label Extension to Assess Long-Term Safety of ZX008 in Children and Adults with LGS | Lennox Gastaut Syndrome (LGS) | Central Nervous System | EP0214 is a feeder study of EP0215 | 2017-02-01 | 2017-07-13 |  | 2017-07-13 | 2017-11-27 | 2017-11-27 | 2021-03-10 | 2021-02-08 | 2025-01-10 | 2024-05-23 | 2025-02-07 | 2024-06-25 | 2025-03-13 | 2024-10-14 | 2025-06-09 | 2024-12-09 | Australia, Belgium, Canada, Denmark, France, Germany, Italy, Japan, Mexico, Netherlands, Poland, Spain, Sweden, United States of America | Australia (LPLV), Belgium (LPLV), Canada (LPLV), Denmark (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Japan (LPLV), Mexico (LPLV), Netherlands (LPLV), Poland (LPLV), Spain (LPLV), Sweden (LPLV), United States of America (LPLV) | Australia, Belgium, Canada, Denmark, France, Germany, Italy, Japan, Mexico, Netherlands, Poland, Spain, Sweden, United States of America | 65 | 79 | 72 | 335 | 335 | 250 | 367 | 0 | 72 | 295 | 0 | 115 | 180 | [22 empty] | yes
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | KEPPRA | Central Nervous System | EP0100 | Study Archived | open-label study with LEV add-on tx or monotherapy | Phase III | Open | GCSO | Neurology | Affiliates | Matsuo T | Beinhauer-Zellenka U | Parexel | PAREXEL | Yes | Yes | paediatrics | No | AN OPEN-LABEL, SINGLE-ARM, MULTICENTER STUDY OF LEVETIRACETAM AS MONOTHERAPY OR ADJUNCTIVE TREATMENT OF PARTIAL SEIZURES IN PEDIATRIC EPILEPTIC SUBJECTS RANGING FROM 1 MONTH TO LESS THAN 4 YEARS OF AGE | Epilepsy | Central Nervous System |  | 2016-10-19 08:00 | 2016-10-19 |  | 2017-02-07 | 2017-06-27 | 2017-11-30 | 2019-08-27 | 2021-04-15 | 2022-01-28 | 2023-07-28 | 2022-02-25 | 2023-08-29 | 2022-04-22 | 2023-09-12 | 2022-07-19 | 2023-11-17 | Japan | Japan (LPLV) | Japan | 22 | 22 | 21 | 52 | 48 | 48 | 43 | 0 | 5 | 38 | 0 | 23 | 15 |  |  | 2021-11-25 08:00 | 2021-11-25 |  |  | 2022-06-08 | 2022-05-11 | [14 empty] | yes
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | NEUPRO | Central Nervous System | RL0007 | Study Archived | Science 37 Extension study for Neupro Adolescent RLS | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Bullock E | Grose-Hodge R | Parexel | PAREXEL | No | No | paediatrics | No | An Open-Label, Long-Term Follow-Up Study to Determine the Safety, Tolerability, and Efficacy of Rotigotine Transdermal System as Monotherapy in Adolescents with Restless Legs Syndrome | Restless legs syndrome | Central Nervous System | RL0007 is an extension of SP1006 | 2018-02-10 08:00 | 2018-02-10 |  | 2018-04-13 | 2019-06-17 | 2019-12-03 | 2022-06-30 | 2022-06-29 | 2023-08-30 | 2022-09-01 | 2023-09-27 | 2023-04-26 | 2023-10-11 | 2023-06-08 | 2024-02-19 | 2023-09-13 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 92 | 92 | 92 | 10 | 0 | 0 | 10 | 0 | 2 | 8
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | NEUPRO | Central Nervous System | SP1006 | Study Archived | Science 37 metasite study | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global | Bullock E | Grose-Hodge R | Parexel | PAREXEL | No | Yes | paediatrics | No | A REMOTE, DOUBLE-BLIND, RANDOMIZED, PLACEBO-CONTROLLED STUDY OF ROTIGOTINE TRANSDERMAL SYSTEM IN ADOLESCENT SUBJECTS WITH IDIOPATHIC RESTLESS LEGS SYNDROME | Restless legs syndrome | Central Nervous System | SP1006 is a parent study of RL0007 | 2014-08-11 08:00 | 2014-08-11 |  | 2018-02-07 | 2018-07-18 | 2018-12-20 | 2023-05-17 | 2022-06-27 | 2023-10-04 | 2022-07-25 | 2023-11-14 | 2023-04-26 | 2024-02-01 | 2023-06-08 | 2024-02-02 | 2023-08-30 | United States of America | United States of America (LPLV) | United States of America | 1 | 1 | 1 | 198 | 138 | 125 | 48 | 0 | 25 | 23 | 0 | 4 | 19 | [22 empty] | yes
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Padsevonil | Central Nervous System | EP0091 | Study Archived | EFFICACY AND SAFETY - Adjunctive treatment of focal onset se | Phase II | Double Blind | GCSO | Neurology | UCB Pharma Global | Esch M | Copetti C | Parexel | PAREXEL | Yes | Yes | adults | No | A RANDOMIZED, DOUBLE-BLIND, DOUBLE-DUMMY, PLACEBO- AND ACTIVE-CONTROLLED, DOSE FINDING STUDY TO EVALUATE THE EFFICACY AND SAFETY OF PADSEVONIL AS ADJUNCTIVE TREATMENT OF FOCAL ONSET SEIZURES IN ADULT SUBJECTS WITH DRUG-RESISTANT EPILEPSY | Epilepsy | Central Nervous System | EP0091 is a feeder study of EP0093 | 2017-07-01 | 2017-06-29 |  | 2017-10-24 | 2018-02-02 | 2018-02-12 | 2019-04-30 | 2019-07-22 | 2019-10-29 | 2020-01-30 | 2019-12-16 | 2020-02-18 | 2019-12-31 | 2020-03-03 | 2020-08-21 | 2020-05-29 | Australia, Belgium, Bulgaria, Canada, Czech Republic, France, Germany, Hungary, Italy, Japan, Lithuania, Mexico, Poland, Portugal, Slovakia, Spain, Turkey, United Kingdom, United States of America | Australia (LPLV), Belgium (LPLV), Bulgaria (LPLV), Canada (LPLV), Czech Republic (LPLV), France (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Japan (LPLV), Lithuania (LPLV), Mexico (LPLV), Poland (LPLV), Portugal (LPLV), Slovakia (LPLV), Spain (LPLV), Turkey (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Belgium, Bulgaria, Canada, Czech Republic, France, Germany, Hungary, Italy, Japan, Lithuania, Mexico, Poland, Portugal, Slovakia, Spain, Turkey, United Kingdom, United States of America | 207 | 199 | 148 | 534 | 400 | 360 | 515 | 0 | 104 | 411 | 0 | 66 | 345
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Padsevonil | Central Nervous System | EP0092 | Study Archived | A RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, PARALLEL GRO | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global | Esch M | Copetti C | Parexel | PAREXEL | Yes | Yes | adults | No | A multicenter, randomized, double-blind, placebo-controlled, parallel group study to evaluate the efficacy and safety of padsevonil as adjunctive treatment of focal-onset seizures in adult subjects with drug-resistant epilepsy | Epilepsy | Central Nervous System | EP0092 is a feeder study of EP0093 | 2018-05-01 | 2018-06-21 |  | 2018-09-27 | 2019-01-18 | 2019-03-06 | 2020-07-06 | 2020-03-19 | 2021-01-11 | 2020-09-28 | 2021-01-25 | 2020-11-16 | 2021-02-08 | 2020-12-07 | 2021-04-08 | 2021-03-05 | Australia, Belgium, Bosnia - Herzegovine, Bulgaria, Croatia, Czech Republic, Denmark, Estonia, Finland, France, Germany, Greece, Hungary, Ireland, Italy, Japan, Norway, Poland, Portugal, Romania, Serbia, Slovakia, Spain, Sweden, Switzerland, Turkey, United Kingdom, United States of America | Australia (LPLV), Austria (1st Site Initiation (Cancelled)), Belgium (LPLV), Bosnia - Herzegovine (LPLV), Bulgaria (LPLV), Canada (1st Site Initiation (Cancelled)), Croatia (LPLV), Czech Republic (LPLV), Denmark (LPLV), Estonia (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Greece (LPLV), Hungary (LPLV), Ireland (LPLV), Italy (LPLV), Japan (LPLV), Mexico (1st Site Initiation (Cancelled)), Netherlands (1st Site Initiation (Cancelled)), Norway (LPLV), Poland (LPLV), Portugal (LPLV), Romania (LPLV), Serbia (LPLV), Slovakia (LPLV), Spain (LPLV), Sweden (LPLV), Switzerland (LPLV), Turkey (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Belgium, Bosnia - Herzegovine, Bulgaria, Croatia, Czech Republic, Denmark, Estonia, Finland, France, Germany, Greece, Hungary, Ireland, Italy, Japan, Norway, Poland, Portugal, Romania, Serbia, Slovakia, Spain, Sweden, Switzerland, Turkey, United Kingdom, United States of America | 265 | 258 | 141 | 650 | 544 | 437 | 361 | 0 | 129 | 232 | 0 | 72 | 160
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Padsevonil | Central Nervous System | EP0093 | Study Archived | OLE - Adjunctive treatment of focal onset seizure in patient | Phase II | Open | GCSO | Neurology | UCB Pharma Global | Reichel C | Anderson K | Parexel | PAREXEL | Yes | Yes | adults | No | Phase II/III AN OPEN-LABEL, MULTICENTER, EXTENSION STUDY TO EVALUATE THE SAFETY AND EFFICACY OF PADSEVONIL AS ADJUNCTIVE TREATMENT OF FOCAL-ONSET SEIZURES IN ADULT SUBJECTS WITH DRUG-RESISTANT EPILEPSY. | Epilepsy | Central Nervous System | EP0093 is a follow up of EP0091, EP0092 and is a feeder study of EP0136 | 2017-07-03 | 2017-06-29 |  | 2017-10-25 | 2018-06-28 | 2018-08-27 | 2024-08-15 | 2020-05-21 | 2023-03-10 | 2020-12-22 | 2023-04-07 | 2021-01-19 | 2023-04-21 | 2021-02-08 | 2023-07-18 | 2021-05-04 | Australia, Belgium, Bosnia - Herzegovine, Bulgaria, Canada, Croatia, Czech Republic, Denmark, Estonia, Finland, France, Germany, Greece, Hungary, Ireland, Italy, Japan, Lithuania, Mexico, Poland, Romania, Serbia, Slovakia, Spain, Turkey, United Kingdom, United States of America | Australia (LPLV), Belgium (LPLV), Bosnia - Herzegovine (LPLV), Bulgaria (LPLV), Canada (LPLV), Croatia (LPLV), Czech Republic (LPLV), Denmark (LPLV), Estonia (LPLV), Finland (LPLV), France (LPLV), Germany (LPLV), Greece (LPLV), Hungary (LPLV), Ireland (LPLV), Italy (LPLV), Japan (LPLV), Lithuania (LPLV), Mexico (LPLV), Poland (LPLV), Romania (LPLV), Serbia (LPLV), Slovakia (LPLV), Spain (LPLV), Turkey (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Belgium, Bosnia - Herzegovine, Bulgaria, Canada, Croatia, Czech Republic, Denmark, Estonia, Finland, France, Germany, Greece, Hungary, Ireland, Italy, Japan, Lithuania, Mexico, Poland, Romania, Serbia, Slovakia, Spain, Turkey, United Kingdom, United States of America | 314 | 166 | 155 | 688 | 688 | 342 | 407 | 0 | 0 | 407 | 0 | 395 | 12
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Padsevonil | Central Nervous System | EP0098 | Protoc. Summary Approved (Cancelled) | Multi Comparator Study for Drug Resistant Epilepsy | Phase III |  | GCSO | Neurology | UCB Pharma Global | Michaels K | Bonny M | Parexel |  | No | Yes | adults | No |  | Epilepsy | Central Nervous System | EP0098 is a feeder study of EP0136 | 2019-12-02 | 2019-10-03 | [14 empty] | Australia, Austria, Belgium, Bosnia - Herzegovine, Bulgaria, Canada, China, Croatia, Czech Republic, Denmark, Estonia, Finland, France, Germany, Greece, Hungary, Ireland, Italy, Japan, Lithuania, Mexico, Netherlands, Norway, Poland, Portugal, Romania, Slovakia, Spain, Sweden, Switzerland, Taiwan, Turkey, United Kingdom, United States of America | Australia (Created), Austria (Created), Belgium (Created), Bosnia - Herzegovine (Created), Bulgaria (Created), Canada (Created), China (Created), Croatia (Created), Czech Republic (Created), Denmark (Created), Estonia (Created), Finland (Created), France (Created), Germany (Created), Greece (Created), Hungary (Created), Ireland (Created), Italy (Created), Japan (Created), Lithuania (Created), Mexico (Created), Netherlands (Created), Norway (Created), Poland (Created), Portugal (Created), Romania (Created), Slovakia (Created), Spain (Created), Sweden (Created), Switzerland (Created), Taiwan (Created), Turkey (Created), United Kingdom (Created), United States of America (Created) |  | 264 | 0 | 0 | 635 | 500 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Padsevonil | Central Nervous System | EP0136 | Protocol Approved (Cancelled) | OLE Epilepsy Adult | Phase III |  | GCSO | Neurology | UCB Pharma Global | Akintola J | Grose-Hodge R | Parexel |  |  |  | adults | No |  | Epilepsy | Central Nervous System | EP0136 is an extension of EP0073, EP0093, EP0098 | 2020-01-31 08:00 | 2020-01-31 |  | 2015-05-12: 2020-03-10; 2015-09-29: 2020-11-03; 2016-04-08: 2023-09-19; 2019-11-29: 2024-12-16; 2020-02-04: 2025-01-13; 2020-02-07: 2025-01-27; 2020-05-05: 2025-04-23 | Canada | Canada (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Padsevonil | Central Nervous System | UP0055 | Protoc. Summary Approved (Cancelled) | Renal Impairment PK | Phase I |  | GCSO | NewMeds | UCB Pharma Global | Leach S | Cain D | ICON |  | No | No | adults | No |  | Epilepsy | Central Nervous System |  | 2019-02-19 | 2019-02-19 | [14 empty] | United States of America | United States of America (Created) |  | 3 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | RADIPRODIL | Central Nervous System | EP0078 | Study Archived | Open label Exploratory PK Safety in Infantile Spasm | Phase II | Open | GED | Neurology | UCB Pharma Global | De Beule N | Grose-Hodge R | Parexel | PAREXEL | Yes | Yes | paediatrics | No | AN OPEN-LABEL ADAPTIVE STUDY FOR THE ASSESSMENT OF SAFETY, TOLERABILITY, PHARMACOKINETICS AND EFFICACY OF MULTIPLE DOSES OF RADIPRODIL IN SUBJECTS WITH TREATMENT-RESISTANT INFANTILE SPASMS | Epilepsy | Central Nervous System |  | 2016-04-15 | 2016-04-12 |  | 2016-07-26 | 2016-09-16 | 2017-12-04 | 2017-05-18 | 2018-03-06 | 2017-10-04 | 2018-11-26 | 2020-01-06 | 2019-01-10 | 2020-03-02 | 2019-01-29 | 2020-07-09 | 2019-03-29 | France | Belgium (1st Site Initiation (Cancelled)), Bulgaria (1st Site Initiation (Cancelled)), France (LPLV), Germany (1st Site Initiation (Cancelled)), United Kingdom (1st Site Initiation (Cancelled)) | France | 12 | 7 | 1 | 120 | 60 | 60 | 3 | 0 | 0 | 3 | 0 | 0 | 3
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | AIE001 | Study Archived | Rozanolixizumab participants with LGI1 autoimmune encephal | Phase II | Double Blind | GCSO | Neurology | UCB Pharma Global | Jabbarzadegan P | Cain D | Parexel | PAREXEL | Yes | Yes | adults | No | A RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER, PHASE 2 STUDY TO EVALUATE THE EFFICACY, SAFETY, AND PHARMACOKINETICS OF ROZANOLIXIZUMAB IN ADULT STUDY PARTICIPANTS WITH LEUCINE-RICH GLIOMA INACTIVATED 1 AUTOIMMUNE ENCEPHALITIS | LGI1 Autoimmune Encephalitis | Central Nervous System |  | 2019-11-04 | 2019-11-04 |  | 2020-07-31 | 2020-08-04 | 2021-09-27 | 2021-08-10 | 2023-10-13 | 2022-01-25 | 2024-04-26 | 2022-02-22 | 2024-05-29 | 2022-03-08 | 2024-08-05 | 2022-06-02 | 2024-12-12 | Belgium, France, Germany, Italy, Netherlands, Spain, United Kingdom, United States of America | Australia (1st Site Initiation (Cancelled)), Belgium (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Netherlands (LPLV), Portugal (1st Site Initiation (Cancelled)), South Korea (1st Site Initiation (Cancelled)), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, France, Germany, Italy, Netherlands, Spain, United Kingdom, United States of America | 28 | 34 | 12 | 68 | 68 | 60 | 24 | 0 | 12 | 12 | 0 | 7 | 5 | [22 empty] | yes
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | APS001 | Protocol Approved (Cancelled) | Exploratory Phase II trial in Patients with APS | Phase II | Double Blind | GCSO | Neurology | UCB Pharma Global | Brown E, Theys A | Cain D, Tillery N | Parexel | PXL; UCB | No | Yes | adults | No | A RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER PHASE 2 EXPLORATORY STUDY TO EVALUATE THE EFFICACY, SAFETY, PHARMACOKINETICS, AND PHARMACODYNAMICS OF ROZANOLIXIZUMAB IN ADULT STUDY PARTICIPANTS WITH PRIMARY ANTIPHOSPHOLIPID SYNDROME | Antiphospholipid syndrome | Central Nervous System | APS001 is a parent study of APS002 | 2020-03-23 08:00 | 2020-03-23 |  | 2015-05-12: 2020-08-05; 2015-09-29: 2021-04-15; 2016-04-08: 2022-12-15; 2019-11-29: 2023-04-06; 2020-02-04: 2023-05-09; 2020-02-07: 2023-05-30; 2020-05-05: 2023-08-31 | Belgium, Bulgaria, Canada, Czech Republic, France, Germany, Hungary, Italy, Netherlands, Poland, Spain, United Kingdom, United States of America | Belgium (Created), Bulgaria (Created), Canada (Created), Czech Republic (Created), France (Created), Germany (Created), Hungary (Created), Italy (Created), Netherlands (Created), Poland (Created), Spain (Created), United Kingdom (Created), United States of America (Created) |  | 30 | 0 | 0 | 77 | 60 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | APS002 | Protocol Approved (Cancelled) | OLE study for APS patients from APS001 | Phase II | Open | GCSO | Neurology | UCB Pharma Global | Brown E, Theys A | Cain D, Tillery N | Parexel | PAREXEL;UCB | No | Yes | adults | No | A PHASE 2, MULTICENTER, OPEN-LABEL EXTENSION STUDY TO EVALUATE THE SAFETY AND TOLERABILITY OF ROZANOLIXIZUMAB IN ADULT STUDY PARTICIPANTS WITH PRIMARY ANTIPHOSPHOLIPID SYNDROME | Antiphospholipid syndrome | Central Nervous System | APS002 is an extension of APS001 | 2020-03-23 08:00 | 2020-03-23 | 2020-07-30 | 2015-05-12: 2020-08-06; 2015-09-29: 2021-02-24; 2016-04-08: 2022-10-20; 2019-11-29: 2023-12-14; 2020-02-04: 2023-12-28; 2020-02-07: 2024-01-19; 2020-05-05: 2024-04-23 | Belgium, Bulgaria, Canada, Czech Republic, France, Germany, Hungary, Italy, Netherlands, Poland, Spain, United Kingdom, United States of America | Belgium (Created), Bulgaria (Created), Canada (Created), Czech Republic (Created), France (Created), Germany (Created), Hungary (Created), Italy (Created), Netherlands (Created), Poland (Created), Spain (Created), United Kingdom (Created), United States of America (Created) |  | 25 | 0 | 0 | 47 | 45 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | CIDP01 | Study Archived | randomized, placebo-controlled POC study in CIDP | Phase II | Mixed Blind / Multiple Blind | GCSO | Neurology | UCB Pharma Global | Sacre J | Copetti C | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, RANDOMIZED, SUBJECT-BLIND, INVESTIGATOR-BLIND, PLACEBO-CONTROLLED, PARALLEL-GROUP STUDY EVALUATING THE EFFICACY, SAFETY, AND TOLERABILITY OF UCB7665 IN SUBJECTS WITH CHRONIC INFLAMMATORY DEMYELINATING POLYRADICULONEUROPATHY (CIDP) | Chronic Inflammatory Demyelinating Polyr | Central Nervous System | CIDP01 is a parent study of CIDP04 | 2016-04-22 | 2016-04-22 |  | 2018-11-15 | 2017-10-24 | 2019-03-26 | 2018-10-23 | 2020-12-02 | 2020-10-09 | 2021-03-31 | 2020-11-06 | 2021-05-28 | 2020-11-20 | 2021-07-30 | 2021-02-12 | 2021-10-06 | Belgium, Canada, Denmark, France, Germany, Netherlands, Spain, United Kingdom, United States of America | Belgium (LPLV), Canada (1st Site Initiation), Denmark (LPLV), France (LPLV), Germany (LPLV), Netherlands (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Canada, Denmark, France, Germany, Netherlands, Spain, United Kingdom, United States of America | 33 | 31 | 22 | 50 | 34 | 30 | 60 | 0 | 26 | 34 | 0 | 11 | 23
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | CIDP02 | Created (Cancelled) | Efficacy and Safety | Phase II |  | GCSO | Neurology | UCB Pharma Global | Sacre J | Copetti C | Parexel |  | Yes | Yes | adults | No |  | Chronic Inflammatory Demyelinating Polyr | Central Nervous System | CIDP02 is a parent study of CIDP03 | 2021-08-18 08:00 | [15 empty] | United States of America | United States of America (Created) |  | 100 | 0 | 0 | 385 | 200 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | CIDP03 | Created (Cancelled) | Safety | Phase III |  | GCSO | Neurology | UCB Pharma Global | Sacre J | Copetti C | Parexel |  | Yes | Yes | adults | No |  | Chronic Inflammatory Demyelinating Polyr | Central Nervous System | CIDP03 is a follow up of CIDP02 | 2021-08-31 08:00 | [15 empty] | United States of America | United States of America (Created) |  | 100 | 0 | 0 | 165 | 165 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | CIDP04 | Study Archived | Phase 2 OL Ext | Phase II | Open | GCSO | Neurology | UCB Pharma Global | Sacre J | Copetti C | Parexel | PAREXEL | No | No | adults | No | An open-label extension study to investigate the long-term safety, tolerability, and efficacy of rozanolixizumab in subjects with chronic inflammatory demyelinating polyradiculoneuropathy (CIDP) | Chronic Inflammatory Demyelinating Polyr | Central Nervous System | CIDP04 is a follow up of CIDP01 | 2018-10-31 08:00 | 2018-10-31 | 2018-12-14 | 2018-12-17 | 2019-07-29 | 2019-08-21 | 2020-12-15 | 2021-03-31 | 2021-07-27 | 2021-11-10 | 2021-08-24 | 2022-01-31 | 2021-09-07 | 2022-04-01 | 2021-12-02 | 2022-05-31 | Belgium, Denmark, France, Germany, Netherlands, United Kingdom, United States of America | Belgium (LPLV), Denmark (LPLV), France (LPLV), Germany (LPLV), Netherlands (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Denmark, France, Germany, Netherlands, United Kingdom, United States of America | 15 | 13 | 13 | 21 | 21 | 16 | 21 | 0 | 0 | 21 | 0 | 12 | 9
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | FM0001 | CSR Approved | A proof-of-concept study to evaluate the efficacy and safe | Phase II | Double Blind | GCSO | NewMeds | UCB Pharma Global | Watanabe S | Cain D | N/A | N/A | No | Yes | adults | No | A RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER, PHASE 2A, PROOF-OF-CONCEPT STUDY TO EVALUATE THE EFFICACY AND SAFETY OF ROZANOLIXIZUMAB TO TREAT ADULT STUDY PARTICIPANTS WITH SEVERE FIBROMYALGIA SYNDROME | Fibromyalgia | Immunology |  | 2022-04-05 | 2022-05-31 |  | 2022-06-24 | 2022-09-28 | 2022-12-21 | 2023-04-24 | 2023-11-01 | 2024-01-05 | 2024-07-09 | 2024-02-02 | 2024-08-30 | 2024-03-07 | 2024-09-23 | 2024-06-03 | 2024-12-09 | United Kingdom | United Kingdom (LPLV) | United Kingdom | 5 | 7 | 7 | 132 | 60 | 48 | 177 | 0 | 114 | 63 | 0 | 9 | 54 | [22 empty] | yes
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | MG0002 | Study Archived | Phase IIa POC of UCB7665 in Myasthenia Gravis | Phase II | Double Blind | GCSO | Neurology | GCSO | Tillery N | Beinhauer-Zellenka U | Parexel | PAREXEL | Yes | Yes | adults | No | A MULTICENTER, RANDOMIZED, INVESTIGATOR- AND SUBJECT-BLIND, PLACEBO-CONTROLLED, TREATMENT SEQUENCE STUDY EVALUATING THE SAFETY, TOLERABILITY, AND EFFICACY OF UCB7665 IN SUBJECTS WITH MODERATE TO SEVERE MYASTHENIA GRAVIS | Myasthenia gravis | Central Nervous System | MG0002 is a feeder study of MG0007 | 2016-03-31 | 2016-04-13 |  | 2016-10-21 | 2016-12-15 | 2017-05-15 | 2018-01-13 | 2018-04-18 | 2018-06-01 | 2018-08-06 | 2018-06-29 | 2018-09-04 | 2018-07-27 | 2018-09-27 | 2018-10-15 | 2018-12-15 | Belgium, Canada, Czech Republic, Denmark, Germany, Spain, United States of America | Belgium (LPLV), Canada (LPLV), Czech Republic (LPLV), Denmark (LPLV), Germany (LPLV), Spain (LPLV), United States of America (LPLV) | Belgium, Canada, Czech Republic, Denmark, Germany, Spain, United States of America | 30 | 30 | 21 | 40 | 36 | 36 | 69 | 1 | 25 | 43 | 0 | 1 | 42
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | MG0003 | Study Archived | A Randomized, double-blind, placebo-controlled, dose-selecti | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global | Teichmann R | Tillery N | Parexel | PAREXEL | Yes | Yes | adults | No | A PHASE 3, RANDOMIZED, DOUBL-BLIND, PLACEBO-CONTROLLED STUDY EVALUATING EFFICACY AND SAFETY OF ROZANOLIXIZUMAB IN ADULT PATIENTS WITH GENERALIZED MYASTHENIA GRAVIS | Myasthenia gravis | Central Nervous System | MG0003 is a feeder study of MG0007 and is a parent study of MG0004 | 2018-12-19 08:00 | 2018-12-19 |  | 2019-02-22 | 2019-05-31 | 2019-06-03 | 2020-11-30 | 2021-06-30 | 2021-11-29 | 2021-10-26 | 2021-12-27 | 2021-11-12 | 2022-01-10 | 2021-11-30 | 2022-04-04 | 2022-04-19 | Belgium, Canada, Czech Republic, Denmark, France, Georgia, Germany, Hungary, Italy, Japan, Poland, Russian Federation, Serbia, Spain, Taiwan, United Kingdom, United States of America | Belgium (LPLV), Canada (LPLV), Czech Republic (LPLV), Denmark (LPLV), France (LPLV), Georgia (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Japan (LPLV), Poland (LPLV), Russian Federation (LPLV), Serbia (LPLV), Spain (LPLV), Taiwan (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Belgium, Canada, Czech Republic, Denmark, France, Georgia, Germany, Hungary, Italy, Japan, Poland, Russian Federation, Serbia, Spain, Taiwan, United Kingdom, United States of America | 130 | 126 | 93 | 320 | 182 | 182 | 329 | 0 | 129 | 200 | 0 | 2 | 198
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | MG0004 | Study Archived | A RANDOMIZED, OPEN LABEL EXTENSION STUDY TO INVESTIGATE THE | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global | Kadima H | Grose-Hodge R | Parexel | PAREXEL | Yes | Yes | adults | No | A RANDOMIZED, OPEN LABEL EXTENSION STUDY TO INVESTIGATE THE LONG-TERM SAFETY, TOLERABILITY, AND EFFICACY OF ROZANOLIXIZUMAB IN ADULT PATIENTS WITH GENERALIZED MYASTHENIA GRAVIS | Myasthenia gravis | Central Nervous System | MG0004 is an extension of MG0003 and is a feeder study of MG0007 | 2018-12-19 08:00 | 2018-12-19 |  | 2019-03-21 | 2019-10-15 | 2019-10-29 | 2022-01-12 | 2021-06-03 | 2023-01-11 | 2021-09-01 | 2023-02-08 | 2021-10-01 | 2023-02-22 | 2021-12-13 | 2023-05-17 | 2022-04-19 | Belgium, Canada, Czech Republic, Denmark, France, Georgia, Germany, Hong Kong, Hungary, Italy, Japan, Poland, Russian Federation, Spain, Taiwan, United Kingdom, United States of America | Belgium (IRB / IEC Approval), Canada (LPLV), Czech Republic (LPLV), Denmark (LPLV), France (LPLV), Georgia (Created), Germany (LPLV), Hong Kong (Regulatory Approval), Hungary (IRB / IEC Approval), Italy (LPLV), Japan (LPLV), Poland (LPLV), Russian Federation (LPLV), Spain (LPLV), Taiwan (LPLV), United Kingdom (IRB / IEC Approval), United States of America (LPLV) | Belgium, Canada, Czech Republic, Denmark, France, Germany, Hong Kong, Hungary, Italy, Japan, Poland, Russian Federation, Spain, Taiwan, United Kingdom, United States of America | 80 | 44 | 37 | 66 | 66 | 40 | 71 | 0 | 0 | 71 | 0 | 55 | 16
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | MG0007 | CSR Approved | OL gMG Patients receiving additional Treatment Cycles | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Peele T | Tillery N | Parexel | PAREXEL | No | Yes | adults | No | AN OPEN-LABEL EXTENSION STUDY TO EVALUATE ROZANOLIXIZUMAB IN STUDY PARTICIPANTS WITH GENERALIZED MYASTHENIA GRAVIS | Myasthenia gravis | Central Nervous System | MG0007 is an extension of MG0002, MG0003, MG0004, MGC003 and is a "sister" study of MG0020 | 2020-07-09 | 2020-07-09 | 2020-07-31 | 2020-08-03 | 2020-12-01 | 2021-02-03 | 2022-04-26 | 2021-12-21 | 2023-03-28 | 2024-01-25 | 2023-04-13 | 2024-04-12 | 2023-04-27 | 2024-05-21 | 2023-07-24 | 2024-06-19 | Canada, Czech Republic, Denmark, France, Georgia, Germany, Italy, Japan, Poland, Russian Federation, Serbia, Spain, Taiwan, United States of America | Canada (LPLV), Czech Republic (LPLV), Denmark (LPLV), France (LPLV), Georgia (LPLV), Germany (LPLV), Hungary (1st Site Initiation (Cancelled)), Italy (LPLV), Japan (LPLV), Poland (LPLV), Russian Federation (LPLV), Serbia (LPLV), Spain (LPLV), Taiwan (LPLV), United States of America (LPLV) | Canada, Czech Republic, Denmark, France, Georgia, Germany, Italy, Japan, Poland, Russian Federation, Serbia, Spain, Taiwan, United States of America | 144 | 76 | 70 | 185 | 185 | 157 | 167 | 0 | 10 | 157 | 0 | 135 | 21
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | MG0020 | CSR Approved | Phase 3, open label, randomized self administration study | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Crespy A, Ikeda K | Matsuo T, Tillery N | Parexel | PAREXEL | Yes | Yes | adults | No | AN OPEN-LABEL, CROSSOVER STUDY TO EVALUATE ROZANOLIXIZUMAB SELF-ADMINISTRATION BY STUDY PARTICIPANTS WITH GENERALIZED MYASTHENIA GRAVIS | Myasthenia gravis | Central Nervous System |  | 2022-03-31 | 2022-03-31 |  | 2022-08-04 | 2022-12-02 | 2023-04-17 | 2023-08-01 | 2023-10-27 | 2024-01-22 | 2024-04-24 | 2024-02-19 | 2024-05-10 | 2024-03-22 | 2024-07-08 | 2024-06-18 | 2024-08-27 | Canada, Georgia, Germany, Italy, Japan, Poland, Serbia, Spain, United Kingdom, United States of America | Canada (LPLV), Georgia (LPLV), Germany (LPLV), Italy (LPLV), Japan (LPLV), Poland (LPLV), Serbia (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Canada, Georgia, Germany, Italy, Japan, Poland, Serbia, Spain, United Kingdom, United States of America | 34 | 29 | 27 | 33 | 33 | 30 | 75 | 0 | 13 | 62 | 0 | 16 | 46 | [22 empty] | yes
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | MGC003 | Created (Cancelled) | Study evaluating the safety and efficacy in Chinese patient | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global |  |  | Parexel |  | No | Yes | adults | No |  | Myasthenia gravis | Central Nervous System | MGC003 is a feeder study of MG0007 | 2019-09-03 08:00 | [15 empty] | China | China (Created) |  | 10 | 0 | 0 | 61 | 38 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | MOG002 | Protoc. Summary Approved (Cancelled) | OLE study to evaluate safety, tolerability in MOG | Phase III | Open | GCSO | Neurology | UCB Pharma Global | Webers T | Bonny M | Parexel |  |  | Yes | adults | No |  | MOG-AD Disease | Central Nervous System | MOG002 is an extension of MOG001 | 2020-04-10 | 2020-03-04 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | TP0003 | Study Archived | multicenter, double-blind, randomized, placebo-controlled | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global | Pendergast K | Bonny M | Parexel | PAREXEL | Yes | Yes | adults | No | "A PHASE 3 MULTICENTER, DOUBLE-BLIND, RANDOMIZED, PLACEBO-CONTROLLED STUDY TO EVALUATE THE EFFICACY, SAFETY, AND TOLERABILITY OF ROZANOLIXIZUMAB IN ADULT STUDY PARTICIPANTS WITH PERSISTENT OR CHRONIC IMMUNE THROMBOCYTOPENIA (ITP)" | Idiopathic Thrombocytopenic Purpura | Immunology | TP0003 is a "sister" study of TP0006 and is a feeder study of TP0004 | 2019-01-28 08:00 | 2019-01-28 |  | 2019-09-27 | 2019-07-30 | 2020-01-31 | 2020-10-29 | 2022-04-06 | 2021-01-27 | 2022-04-27 | 2021-02-24 | 2022-10-06 | 2021-03-26 | 2022-12-09 | 2021-06-18 | 2023-03-30 | Bulgaria, France, Georgia, Greece, Hungary, Italy, Japan, Moldavia, Poland, Romania, Russian Federation, South Korea, Taiwan, Ukraine, United Kingdom, United States of America | Austria (1st Site Initiation (Cancelled)), Belgium (1st Site Initiation (Cancelled)), Bulgaria (LPLV), Croatia (1st Site Initiation (Cancelled)), Czech Republic (1st Site Initiation (Cancelled)), France (LPLV), Georgia (LPLV), Greece (LPLV), Hungary (LPLV), Italy (LPLV), Japan (LPLV), Moldavia (LPLV), Poland (LPLV), Romania (LPLV), Russian Federation (LPLV), South Korea (LPLV), Spain (1st Site Initiation (Cancelled)), Taiwan (LPLV), Ukraine (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Bulgaria, France, Georgia, Greece, Hungary, Italy, Japan, Moldavia, Poland, Romania, Russian Federation, South Korea, Taiwan, Ukraine, United Kingdom, United States of America | 87 | 76 | 29 | 153 | 90 | 68 | 69 | 0 | 36 | 33 | 0 | 8 | 25 |  |  | 2022-11-03 | 2022-12-09
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | TP0004 | Study Archived | multicenter, open-label, randomized | Phase III | Open | GCSO | NewMeds | UCB Pharma Global | Li C, Pendergast K | Bonny M, Guo J | Parexel | PAREXEL | Yes | Yes | adults | No | "AN OPEN-LABEL EXTENSION STUDY TO INVESTIGATE THE LONG-TERM SAFETY, TOLERABILITY, AND EFFICACY OF ROZANOLIXIZUMAB IN STUDY PARTICIPANTS WITH PERSISTENT OR CHRONIC PRIMARY IMMUNE THROMBOCYTOPENIA (ITP)" | Idiopathic Thrombocytopenic Purpura | Immunology | TP0004 is an extension of TP0003, TP0006 | 2019-01-28 08:00 | 2019-01-28 |  | 2019-11-21 | 2019-12-09 | 2021-01-06 | 2021-03-11 | 2022-04-28 | 2022-05-05 | 2022-12-23 | 2022-06-02 | 2023-04-25 | 2022-06-30 | 2023-05-09 | 2022-09-26 | 2023-08-11 | China, Georgia, Germany, Hungary, Italy, Japan, Moldavia, Poland, Russian Federation, Spain, Taiwan, Ukraine, United Kingdom, United States of America | China (LPLV), Georgia (LPLV), Germany (LPLV), Hungary (LPLV), Italy (LPLV), Japan (LPLV), Moldavia (LPLV), Poland (LPLV), Russian Federation (LPLV), Spain (LPLV), Taiwan (LPLV), Ukraine (LPLV), United Kingdom (LPLV), United States of America (LPLV) | China, Georgia, Germany, Hungary, Italy, Japan, Moldavia, Poland, Russian Federation, Spain, Taiwan, Ukraine, United Kingdom, United States of America | 97 | 28 | 27 | 126 | 126 | 96 | 43 | 0 | 0 | 43 | 0 | 21 | 22
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Rystiggo | Central Nervous System | TP0006 | Study Archived | A PHASE 3 MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CON | Phase III | Double Blind | GCSO | Neurology | UCB Pharma Global | Li C, Pendergast K | Bonny M, Guo J | Parexel | PAREXEL | No | No | adults | No | A PHASE 3 MULTICENTER, DOUBLE-BLIND, RANDOMIZED, PLACEBO-CONTROLLED STUDY TO EVALUATE THE EFFICACY, SAFETY, AND TOLERABILITY OF ROZANOLIXIZUMAB IN ADULT STUDY PARTICIPANTS WITH PERSISTENT OR CHRONIC PRIMARY IMMUNE THROMBOCYTOPENIA (ITP) | Idiopathic Thrombocytopenic Purpura | Immunology | TP0006 is a "sister" study of TP0003 and is a feeder study of TP0004 | 2019-08-30 08:00 | 2019-08-30 |  | 2019-09-27 | 2020-02-27 | 2020-06-03 | 2021-05-31 | 2021-11-11 | 2022-02-23 | 2022-05-05 | 2022-03-24 | 2022-10-06 | 2022-04-27 | 2022-12-09 | 2022-07-22 | 2023-03-30 | Bulgaria, China, France, Germany, Poland, Russian Federation, Spain, Taiwan, Ukraine, United Kingdom, United States of America | Austria (1st Site Initiation (Cancelled)), Belgium (1st Site Initiation (Cancelled)), Bulgaria (LPLV), Canada (1st Site Initiation (Cancelled)), China (LPLV), Czech Republic (1st Site Initiation (Cancelled)), Denmark (1st Site Initiation (Cancelled)), France (LPLV), Germany (LPLV), Hong Kong (1st Site Initiation (Cancelled)), Italy (1st Site Initiation (Cancelled)), Poland (LPLV), Romania (1st Site Initiation (Cancelled)), Russian Federation (LPLV), Serbia (1st Site Initiation (Cancelled)), Spain (LPLV), Taiwan (LPLV), Turkey (1st Site Initiation (Cancelled)), Ukraine (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Bulgaria, China, France, Germany, Poland, Russian Federation, Spain, Taiwan, Ukraine, United Kingdom, United States of America | 86 | 66 | 29 | 153 | 90 | 84 | 88 | 0 | 58 | 30 | 0 | 8 | 22 |  |  | 2022-11-09
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Seletalisib | Immunology | APD002 | Protocol Approved (Cancelled) | Pivotal | Phase III |  | GCSO | Immunology | UCB Pharma Global | Flemm D | Beinhauer-Zellenka U | Parexel |  |  |  | other | No |  | Activated PI3K Delta Syndrome | Immunology | APD002 is a follow up of APD003 | 2017-04-07 | 2017-04-05 | 2017-07-26 | 2015-05-12: 2017-07-26; 2015-09-29: 2017-11-15; 2016-04-08: 2019-10-16; 2019-11-29: 2020-01-29; 2020-02-04: 2020-02-26; 2020-02-07: 2020-03-11; 2020-05-05: 2020-06-05 | France, Germany, Italy, Spain | France (Created), Germany (Created), Italy (Created), Spain (Created) |  | 12 | 0 | 0 | 15 | 12 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Seletalisib | Immunology | PS0024 | Protoc. Summary Approved (Cancelled) | Randomized, double-blind, placebo-controlled study in subjec | Phase II |  | GED | Immunology | UCB Pharma Global | Grasses T | Tillery N | Parexel |  | No | Yes | adults | No |  | Psoriasis | Immunology |  | 2018-05-30 | 2018-05-30 | [17 empty] | 38 | 0 | 0 | 275 | 196 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Staccato Alprazolam | Central Nervous System | EP0163 | Created (Cancelled) | A double-blind, placebo-controlled, Multicenter, outpatient, | Phase III |  | GCSO | Neurology | UCB Pharma Global | Brown E | Tillery N | Parexel |  | Yes | Yes |  | No |  | Epilepsy | Central Nervous System |  | 2022-01-31 08:00 | [15 empty] | Australia, France, Germany, Italy, Japan, Spain, United Kingdom, United States of America | Australia (Created), France (Created), Germany (Created), Italy (Created), Japan (Created), Spain (Created), United Kingdom (Created), United States of America (Created) |  | 100 | 0 | 0 | 350 | 350 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Tefidera | not defined | MS0001 | Protocol Approved (Cancelled) | Phase III placebo controlled DB study with Chinese RRMS | Phase III |  | GCSO | Neurology | UCB Pharma Global | Wang J | Wu G | Parexel | PXL SPI |  |  |  | No |  | Multiple sclerosis | Central Nervous System |  | 2014-12-01 | 2014-12-01 |  | 2015-05-12: 2017-05-02; 2015-09-29: 2018-04-19; 2016-04-08: 2019-05-24 | China | China (Created) |  | 30 | 0 | 0 | 250 | 200 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | UCB6673 MultipepT1De | not defined | DB0003 | Protoc. Summary Approved (Cancelled) | Study in pediatric subjects with Type 1 Diabetes. | Phase II |  | GED | Immunology | GED | Jensen L | Driver D | Parexel | SPI PXL | No | No |  | No |  | Diabetes/typeIdiabetes/insulin-dependent | Immunology |  | 2017-09-30 | 2017-07-12 | [14 empty] | United States of America | United States of America (Created) |  | 30 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | VIMPAT | Central Nervous System | EP0060 | Study Archived | Pediatric IV | Phase II | Open | GCSO | Neurology | UCB Pharma Global | Yates T | Bonny M | PRA | PRA | Yes | Yes | paediatrics | No | A MULTICENTER, OPEN-LABEL STUDY TO INVESTIGATE THE SAFETY AND TOLERABILITY OF INTRAVENOUS LACOSAMIDE IN CHILDREN (>=1 MONTH TO <17 YEARS OF AGE) WITH EPILEPSY | Epilepsy | Central Nervous System | EP0060 is an extension of SP0847, SP0848, SP0966, SP0969 and is a feeder study of SP0848 | 2014-02-21 | 2014-02-21 |  | 2014-12-16 | 2016-03-15 | 2017-05-30 07:00 | 2018-05-15 | 2019-06-14 10:00 | 2018-05-23 | 2019-06-28 | 2018-06-20 | 2019-08-12 | 2018-07-18 | 2019-08-28 | 2018-11-26 | 2019-11-14 | Hungary, Italy, Poland, Ukraine, United States of America | Germany (1st Site Initiation (Cancelled)), Hungary (LPLV), Italy (LPLV), Poland (LPLV), Ukraine (LPLV), United States of America (LPLV) | Hungary, Italy, Poland, Ukraine, United States of America | 34 | 32 | 23 | 120 | 103 | 103 | 113 | 0 | 10 | 103 | 0 | 0 | 103
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Zampilimab | Immunology | CAI001 | Study Archived | Phase 1/2 Proof of Concept | Phase II | Double Blind | GCSO | NewMeds | UCB Pharma Global | Jabbarzadegan P | Cain D | ICON | ICON | Yes | Yes | adults | No | A MULTICENTER, RANDOMIZED, PLACEBO-CONTROLLED INVESTIGATOR-BLIND, PARTICIPANT-BLIND STUDY TO EVALUATE SAFETY/TOLERABILITY, PHARMACOKINETICS, AND PHARMACODYNAMICS OF ZAMPILIMAB IN ADULT KIDNEY TRANSPLANT RECIPIENTS WITH CHRONIC ALLOGRAFT INJURY | Chronic Allograft Injury | Immunology | CAI001 is a parent study of CAI002 | 2017-08-11 | 2017-08-11 | 2018-08-31 | 2018-08-31 | 2018-12-28 | 2019-10-21 | 2020-12-01 | 2021-12-07 | 2022-02-23 | 2022-05-04 | 2022-03-23 | 2022-08-24 | 2022-05-18 | 2022-10-19 | 2022-09-26 | 2022-12-15 | Australia, Belgium, Spain, United Kingdom | Australia (LPLV), Belgium (LPLV), Spain (LPLV), United Kingdom (LPLV) | Australia, Belgium, Spain, United Kingdom | 28 | 8 | 5 | 12 | 12 | 12 | 10 | 0 | 7 | 3 | 0 | 0 | 3
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Zampilimab | Immunology | CAI002 | Protocol Approved (Cancelled) | AN OPEN LABEL, NON-COMPARATIVE, EXTENSION STUDY TO CAI001 | Phase II | Open | GCSO | NewMeds | UCB Pharma Global | Seaton G |  | ICON |  |  | Yes | adults | Yes |  | Chronic Allograft Injury | Immunology | CAI002 is an extension of CAI001 | 2020-02-03 | 2020-01-29 |  | 2015-05-12: 2020-04-27; 2015-09-29: 2021-07-20; 2016-04-08: 2023-06-09; 2019-11-29: 2025-12-10; 2020-02-04: 2026-01-07; 2020-02-07: 2026-01-21; 2020-05-05: 2026-04-17 | Australia, Belgium, Germany, Spain | Australia (Created), Belgium (Created), Germany (Created), Spain (Created) |  | 28 | 0 | 0 | 250 | 177 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Zilucoplan | Central Nervous System | IMNM01 | Study Archived | RA101495-02.202 Safety, Tolerability, and Efficacy | Phase II | Double Blind | GCSO | NewMeds | UCB Pharma Global | Harvey B | Russell R | N/A | ICON (PRA) | Yes | No | adults | No | A Phase 2, Multicenter, Randomized, Double-Blind, Placebo-Controlled Study to Evaluate the Safety, Tolerability, and Efficacy of Zilucoplan in Subjects with Immune-Mediated Necrotizing Myopathy (IMNM) | Immune-Mediated Necrotizing Myopathy | Central Nervous System |  |  |  | 2019-04-05 | 2019-04-01 | 2019-12-03 | 2019-11-07 | 2020-10-30 | 2020-12-29 | 2020-12-25 | 2021-06-14 | 2021-01-08 | 2021-08-02 | 2021-01-20 | 2021-08-24 | 2021-03-29 | 2021-12-16 | France, Netherlands, United Kingdom, United States of America | France (LPLV), Netherlands (LPLV), United Kingdom (LPLV), United States of America (LPLV) | France, Netherlands, United Kingdom, United States of America | 18 | 18 | 15 | 48 | 24 | 24 | 38 | 0 | 11 | 27 | 0 | 23 | 4
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0010 | CSR Approved | RA101495-02.301 Safety, Tolerability,& Preliminary Efficacy | Phase III | Double Blind / Double Dummy | GCSO | NewMeds | UCB Pharma Global | Krautz I, Moeltgen H | Russell R | N/A | A2 HEALTHCARE;PRA | Yes | No | adults | No | Phase 3, Multicenter, Randomized, Double-Blind, PBO-Controlled Study of Efficacy, Safety, and Tolerability of Zilucoplan in Subjects with Generalized Myasthenia Gravis | Myasthenia gravis | Central Nervous System | MG0010 is a feeder study of MG0011 |  |  | 2019-04-08 | 2019-05-15 | 2019-10-01 | 2019-09-17 | 2020-12-31 | 2021-09-10 | 2021-03-25 | 2021-12-30 | 2021-04-08 | 2022-01-18 | 2021-04-20 | 2022-03-25 | 2021-06-25 | 2022-07-14 | Canada, France, Germany, Italy, Japan, Norway, Poland, Spain, United Kingdom, United States of America | Canada (LPLV), France (LPLV), Germany (LPLV), Italy (LPLV), Japan (LPLV), Norway (LPLV), Poland (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Canada, France, Germany, Italy, Japan, Norway, Poland, Spain, United Kingdom, United States of America | 116 | 101 | 75 | 223 | 156 | 152 | 239 | 0 | 65 | 174 | 0 | 8 | 166
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Zilucoplan | Central Nervous System | MG0013 | Created (Cancelled) | Zilucoplan 24 week double blind study | Phase III |  | GCSO | Neurology | UCB Pharma Global |  |  |  |  | Yes | Yes |  | No |  | Myasthenia gravis | Central Nervous System |  | 2022-06-06 08:00 | [15 empty] | Belgium, Canada, Czech Republic, Denmark, France, Germany, Hungary, Italy, Japan, Norway, Poland, Russian Federation, Spain, United Kingdom, United States of America | Belgium (Created), Canada (Created), Czech Republic (Created), Denmark (Created), France (Created), Germany (Created), Hungary (Created), Italy (Created), Japan (Created), Norway (Created), Poland (Created), Russian Federation (Created), Spain (Created), United Kingdom (Created), United States of America (Created) |  | 88 | 0 | 0 | 149 | 112 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 1 | Zilucoplan | Central Nervous System | PNH001 | Study Archived | RA101495-01.202 PAROXYSMAL NOCTURNAL HEMOGLOBINURIA OLE | Phase II | Open | GCSO | Neurology | UCB Pharma Global | Babcock S | Padda A | N/A | PSI | No | No | adults | No | RA101495-01.202: A Multicenter, Open-label, Uncontrolled, Extension Study of RA101495 in Subjects with Paroxysmal Nocturnal Hemoglobinuria Who Have Completed a RA101495 Clinical Study | Paroxysmal Nocturnal Hemoglobinuria | Central Nervous System | PNH001 is an extension of PNH002, PNH003 | 2017-02-02 | 2017-02-02 |  | 2017-03-02 | 2017-07-14 | 2017-07-17 | 2018-02-09 | 2018-02-08 | 2022-01-03 | 2021-10-26 | 2022-03-08 | 2021-10-21 | 2022-03-22 | 2021-12-17 | 2022-04-15 | 2022-03-10 | Australia, Canada, Finland, Germany, Hungary, New Zealand, United Kingdom, United States of America | Australia (LPLV), Canada (LPLV), Finland (LPLV), Germany (LPLV), Hungary (LPLV), New Zealand (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Canada, Finland, Germany, Hungary, New Zealand, United Kingdom, United States of America | 10 | 12 | 12 | 11 | 11 | 11 | 19 | 0 | 0 | 19 | 0 | 8 | 11
Yes | Phase II to IV (including Full Support Registries) | Managing Type | 2 | BIMZELX | Immunology | AS0013 | Study Archived | multicenter, randomized, investigator and subject blind, cli | Phase II | Double Blind | GCSO | NewMeds | UCB Pharma Global | Teichmann R | Tillery N | Parexel | N/A | Yes | Yes | adults | No | A MULTICENTER, PHASE 2A, RANDOMIZED, INVESTIGATOR-BLIND, SUBJECT-BLIND, PARALLEL-GROUP STUDY TO EVALUATE THE EFFICACY AND SAFETY OF BIMEKIZUMAB AND CERTOLIZUMAB PEGOL IN SUBJECTS WITH ACTIVE ANKYLOSING SPONDYLITIS. | Ankylosing Spondylitis | Immunology |  | 2017-01-27 | 2017-02-17 |  | 2017-04-19 | 2017-07-27 | 2017-10-04 | 2017-10-27 | 2019-01-31 | 2019-03-01 | 2020-05-25 | 2019-03-29 | 2020-06-23 | 2019-04-12 | 2020-09-10 | 2019-07-09 | 2021-06-25 | Czech Republic, Germany, Greece, Moldavia, Netherlands, Poland, Russian Federation, United States of America | Australia (1st Site Initiation (Cancelled)), Czech Republic (LPLV), Germany (LPLV), Greece (LPLV), Moldavia (LPLV), Netherlands (LPLV), Poland (LPLV), Russian Federation (LPLV), United States of America (LPLV) | Czech Republic, Germany, Greece, Moldavia, Netherlands, Poland, Russian Federation, United States of America | 40 | 39 | 34 | 120 | 60 | 60 | 145 | 0 | 69 | 76 | 0 | 8 | 68 |  |  | 2021-05-17 | 2018-03-26
Yes | Phase II to IV (including Full Support Registries) | Non-managing Type | 2 | CIMZIA | not defined | AS0013 | Study Archived | multicenter, randomized, investigator and subject blind, cli | Phase II | Double Blind | GCSO | NewMeds | UCB Pharma Global | Teichmann R | Tillery N | Parexel | N/A | Yes | Yes | adults | No | A MULTICENTER, PHASE 2A, RANDOMIZED, INVESTIGATOR-BLIND, SUBJECT-BLIND, PARALLEL-GROUP STUDY TO EVALUATE THE EFFICACY AND SAFETY OF BIMEKIZUMAB AND CERTOLIZUMAB PEGOL IN SUBJECTS WITH ACTIVE ANKYLOSING SPONDYLITIS. | Ankylosing Spondylitis | Immunology |  | 2017-01-27 | 2017-02-17 |  | 2017-04-19 | 2017-07-27 | 2017-10-04 | 2017-10-27 | 2019-01-31 | 2019-03-01 | 2020-05-25 | 2019-03-29 | 2020-06-23 | 2019-04-12 | 2020-09-10 | 2019-07-09 | 2021-06-25 | Czech Republic, Germany, Greece, Moldavia, Netherlands, Poland, Russian Federation, United States of America | Australia (1st Site Initiation (Cancelled)), Czech Republic (LPLV), Germany (LPLV), Greece (LPLV), Moldavia (LPLV), Netherlands (LPLV), Poland (LPLV), Russian Federation (LPLV), United States of America (LPLV) | Czech Republic, Germany, Greece, Moldavia, Netherlands, Poland, Russian Federation, United States of America | 40 | 39 | 34 | 120 | 60 | 60 | 145 | 0 | 69 | 76 | 0 | 8 | 68 |  |  | 2021-05-17 | 2018-03-26
Yes | Real World Evidence | Managing Type | 1 | BRIVIACT | Central Nervous System | EP0159 | CSR Approved | EXPERIENCE | Non Interventional Study - Retrospective | Not Applicable | Real World Evidence | Neurology | UCB Pharma Global | Nolen L | [5 empty] | other | No | EXCHANGE OF CLINICAL PRACTICE AND REAL-LIFE TREATMENT WITH BRIVARACETAM (EXPERIENCE) | Epilepsy | Central Nervous System |  |  |  |  | 2015-05-12: 2020-02-13; 2015-09-29: 2020-07-01; 2016-01-18: 2020-11-27; 2019-11-29: 2021-08-31; 2020-01-06: 2022-01-09; 2020-05-05: 2021-12-31; 2020-07-02: 2022-07-19 | Australia, Germany, Spain, United Kingdom, United States of America | Australia (LPLV), Germany (LPLV), Spain (LPLV), United Kingdom (LPLV), United States of America (LPLV) | Australia, Germany, Spain, United Kingdom, United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Managing Type | 1 | CIMZIA | Immunology | PS0025 | CSR Approved | GENERAL DRUG USE-RESULT SURVEY | Non Interventional Study - Prospective |  | Affiliates | Immunology | UCB Pharma Global | Karino T, Tokumasu T | Hosoi K | N/A | N/A | No | No | adults | No | CIMZIA 200MG SYRINGE FOR S.C. INJECTION CIMZIA 200MG AUTOCLICKS FOR S.C. INJECTION GENERAL DRUG USE-RESULT SURVEY | Psoriasis | Immunology |  |  |  |  | 2015-05-12: 2019-09-27; 2015-09-29: 2020-04-29; 2016-01-18: 2020-03-17; 2019-11-29: 2022-12-30; 2020-01-06: 2022-08-16; 2020-05-05: 2023-12-20; 2020-07-02: 2024-02-14 | Japan | Japan (LPLV) | Japan | 100 | 0 | 0 | 250 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0107 | CSR Approved | Retrospective study to collect vital status data | Non Interventional Study - Retrospective |  | GCSO | Neurology | UCB Pharma Global | Pifer C | Tillery N | N/A |  | No | No |  | No | A Retrospective Study of the Combination of Pyrimidine Nucleos(t)ides in Subjects with Thymidine Kinase 2 Deficiency to Collect Vital Status Data and Supporting Information. | Thymidine kinase 2 (TK2) deficiency; Mitochondrial DNA Depletion syndrome | Central Nervous System; Central Nervous System |  |  |  | 2020-10-08 | 2015-05-12: 2020-10-12; 2015-09-29: 2021-07-27; 2019-11-29: 2021-08-20; 2020-05-05: 2023-06-12; 2020-07-02: 2023-06-09 |  |  |  | 20 | 0 | 0 | 61 | 61 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0112 | CSR Approved | Non-Interventional Data Collection project | Non Interventional Study - Prospective | Not Applicable | GCSO | Neurology | UCB Pharma Global | Pifer C | Tillery N | Parexel | N/A | Yes | Yes | other | No | SUPPLEMENTAL DATA COLLECTION ABOUT UNTREATED PARTICIPANTS FROM PUBLICATIONS CONTRIBUTING TO THE DOXECITINE AND DOXRIBTIMINE INTEGRATED SUMMARY OF EFFICACY MODIFIED UNTREATED PATIENT DATABASE | Thymidine kinase 2 (TK2) deficiency | Central Nervous System |  |  |  | 2023-05-03 | 2015-05-12: 2023-05-03; 2015-09-29: 2023-08-02; 2016-01-18: 2023-05-05; 2019-11-29: 2023-11-30; 2020-01-06: 2023-08-30; 2020-05-05: 2024-03-27; 2020-07-02: 2024-04-09 | United States of America | United States of America (LPLV) | United States of America | 18 | 0 | 0 | 85 | 85 | 85 | 0 | 0 | 0 | 49 | 0 | 0 | 49
Yes | Real World Evidence | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0114 | CSR Approved | Non-Interventional Data Collection project | Non Interventional Study - Prospective | Not Applicable | RWE/GCSO | Neurology | UCB Pharma Global | Pifer C | Tillery N | Parexel | N/A | Yes | Yes | other | No | Data collection for patients in the company supported expanded access program. | Thymidine kinase 2 (TK2) deficiency | Central Nervous System |  |  |  |  | 2015-05-12: 2023-05-20; 2015-09-29: 2023-09-21; 2016-01-18: 2023-08-02; 2019-11-29: 2023-09-13; 2020-01-06: 2024-04-25; 2020-05-05: 2024-02-16; 2020-07-02: 2024-09-17 | United States of America | United States of America (LPLV) | United States of America | 14 | 0 | 0 | 32 | 32 | 32 | 0 | 0 | 0 | 43 | 0 | 0 | 43
Yes | Real World Evidence | Managing Type | 1 | Doxecitine and Doxribtimine (MT1621) | Central Nervous System | TK0116 | CSR Approved | CHARACTERIZATION OF THYMIDINE KINASE 2 DEFICIENCY DISEASE | Non Interventional Study - Prospective |  | Real World Evidence | Neurology | UCB Pharma Global | Gerhart R, Harvey B, Pifer C | Russell R, Tillery N | N/A |  | No | No | other | No | Characterization of Thymidine Kinase 2 Deficiency Disease Course: METHODOLOGY DOCUMENT | [6 empty] | 2015-05-12: 2022-08-19; 2020-07-02: 2024-09-24 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Managing Type | 1 | EPILEPSY FRANCHISE | Central Nervous System | EPD249 | Created | Understanding epilepsy disease progression over time | Non Interventional Study - Retrospective | Not Applicable | Affiliates | Neurology | UCB Pharma Global | Segeth J | [5 empty] | adults | No | RETROSPECTIVE STUDY PROTOCOL / EPD 249 UNDERSTANDING EPILEPSY DISEASE PROGRESSION OVER TIME | Epilepsy | Central Nervous System | [17 empty] | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Managing Type | 1 | EVENITY | Bones | OP0008 | Protocol Approved (Cancelled) | Mandatory Post Launch Study on Evenity in France | Non Interventional Study - Retrospective | Not Applicable | Affiliates | Bone | UCB Pharma Global | Crochard A |  |  | N/A |  |  | adults | No | Mandatory Post Launch retrospective Study on Evenity in France, using the National Health Insurance database (SNDS) | Osteoporosis | Bones |  |  |  |  | 2015-05-12: 2021-10-14 | France | France (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Managing Type | 1 | NEUPRO | Central Nervous System | EPD199 | CSR Approved | NONINTERVENTIONAL RETROSPECTIVE CHART REVIEW TO CHARACTERIZE | Non Interventional Study - Retrospective | Not Applicable | Real World Evidence | Neurology | UCB Pharma Global | [6 empty] | adults | No | NONINTERVENTIONAL RETROSPECTIVE CHART REVIEW TO CHARACTERIZE AND ASSESS OUTCOMES IN PARKINSON’S DISEASE PATIENTS TREATED WITH NEUPRO | Parkinson's disease | Central Nervous System |  |  |  |  | 2015-05-12: 2018-08-27; 2016-01-18: 2018-12-17; 2020-01-06: 2019-06-07; 2020-07-02: 2019-06-20 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Managing Type | 1 | NEUPRO | not defined | EPD150 | CSR Approved | Comparing the incidence rate of falls and fractures in parki | Non Interventional Study - Retrospective |  | Epidemiology | Neurology | UCB Pharma Global | Foskett N | [5 empty] | adults | No | The characteristics and treatment patterns of Parkinson's disease patients in the US. | [6 empty] | 2015-05-12: 2016-01-01; 2016-01-18: 2016-01-22; 2020-01-06: 2017-01-17; 2020-07-02: 2018-08-30 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Managing Type | 1 | VIMPAT | Central Nervous System | EP0081 | CSR Approved | Vimpat Tablets Drug-use Survey for POS in Japan | Non Interventional Study - Prospective | Open | Affiliates | Neurology | Affiliates | Tokumasu T | Hosoi K | N/A | N/A | No | No | adults | No | Vimpat Tablets 50mg, Vimpat Tablets100mg, Vimpat Dry Syrup Drug Use Results Survey | Epilepsy | Central Nervous System |  |  |  |  | 2015-05-12: 2016-12-05; 2015-09-29: 2017-04-20; 2016-01-18: 2017-04-01; 2019-11-29: 2022-03-31; 2020-01-06: 2022-03-31; 2020-05-05: 2024-08-28; 2020-07-02: 2023-08-14 | Japan | Japan (LPLV) | Japan | 700 | 0 | 0 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 2707 | 1903 | 0 | 804
Yes | Real World Evidence | Managing Type | 1 | VIMPAT | Central Nervous System | EP0147 | CSR Approved | Retrospective loading dose LCM study in pediatrics | Non Interventional Study - Retrospective | Not Applicable | Real World Evidence | Neurology | UCB Pharma Global | Kaur M, Mcclung C | [5 empty] | paediatrics | No | Evaluating the occurrence of ADVERSE events among pediatric patients exposed to intravenous lacosamide (Vimpat®) using real world data | [6 empty] | 2015-05-12: 2019-12-01; 2015-09-29: 2019-08-13; 2016-01-18: 2020-01-31; 2019-11-29: 2019-12-17; 2020-01-06: 2020-07-15; 2020-05-05: 2020-08-14; 2020-07-02: 2020-09-16 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Managing Type | 1 | VIMPAT | Central Nervous System | EP0149 | CSR Approved | To study effectiveness and safety in neonates treated with L | Non Interventional Study - Retrospective | Not Applicable | Real World Evidence | Neurology | UCB Pharma Global | Kaur M | [5 empty] | paediatrics | No | Lacosamide to treat neonatal seizures | [6 empty] | 2016-01-18: 2020-01-31; 2020-01-06: 2022-10-27; 2020-07-02: 2023-01-05 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
Yes | Real World Evidence | Managing Type | 1 | VIMPAT | Central Nervous System | EP0155 | CSR Approved | Effectiveness, safety in neonates treated with Lacosamide | Non Interventional Study - Retrospective | Not Applicable | Real World Evidence | Neurology | UCB Pharma Global | Kaur M | [5 empty] | paediatrics | No | RETROSPECTIVE COHORT STUDY - PHARMACOKINETICS AND EXPOSURE OUTCOME IN NEONATES ADMINISTERED LACOSAMIDE | [6 empty] | 2016-01-18: 2020-04-01; 2020-01-06: 2020-11-30; 2020-07-02: 2022-02-28 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Managing Type | 1 | VIMPAT | Central Nervous System | EPD243 | CSR Approved | Healthcare Resource Utilization and Cost Before and After La | Non Interventional Study - Retrospective |  | Affiliates | Neurology | UCB Pharma Global | [6 empty] | adults | No | [7 empty] | 2016-01-18: 2009-01-01; 2020-01-06: 2016-07-01; 2020-07-02: 2019-04-26 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2171 | 0 | 0 | 2171
Yes | Real World Evidence | Managing Type | 1 | VIMPAT | Central Nervous System | EPD246 | Created (Cancelled) | Economic Evaluation of Adverse Drug Events of Antiepileptic | Non Interventional Study - Retrospective | Not Applicable | Affiliates | Neurology | UCB Pharma Global | Smith D | [5 empty] | adults | No | [20 empty] | United States of America | United States of America (Created) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Managing Type | 1 | VIMPAT | not defined | EP0234 | Created (Cancelled) | To evaluate the change of depression and anxiety symptoms | Non Interventional Study - Prospective |  | Real World Evidence | Neurology | UCB Pharma Global | [6 empty] | adults | No |  | Epilepsy | Central Nervous System | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Managing Type | 2 | KEPPRA | Central Nervous System | EPD172 | CSR Approved | Comparison of acute renal failure incidence in LEV and other | Non Interventional Study - Retrospective | Not Applicable | Epidemiology | Neurology | UCB Pharma Global | Beau-Lejstrom R, Qvistorff K | [5 empty] | adults | No | Comparing the incidence of acute renal failure in patients with epilepsy exposed to levetiracetam versus other antiepileptic drugs. | [6 empty] | 2015-05-12: 2018-05-17; 2016-01-18: 2008-01-01; 2020-01-06: 2017-12-31; 2020-07-02: 2020-06-30 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
Yes | Real World Evidence | Managing Type | 3 | BRIVIACT | Central Nervous System | EPD252 | CSR Approved | Treatment Characteristics Retrospective Chart Review | Non Interventional Study - Retrospective | Not Applicable | Affiliates | Neurology | UCB Pharma Global | Smith D | [5 empty] | adults | No | [7 empty] | 2016-01-18: 2014-01-06; 2020-01-06: 2016-10-28; 2020-07-02: 2018-02-28 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Managing Type | 3 | VIMPAT | Central Nervous System | EP0148 | CSR Approved | NISR Treatment pathways and safety in neonatal seizures | Non Interventional Study - Retrospective | Not Applicable | Real World Evidence | Neurology | UCB Pharma Global | Kaur M | [5 empty] | paediatrics | No | Retrospective cohort study describing treatment pathways through care and estimating potential adverse events in neonatal seizures | Epilepsy | Central Nervous System |  |  |  |  | 2015-09-29: 2008-10-21; 2016-01-18: 2020-04-01; 2019-11-29: 2009-05-05; 2020-01-06: 2021-07-31; 2020-05-05: 2010-01-01; 2020-07-02: 2022-07-15 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Non-managing Type | 2 | VIMPAT | not defined | EPD172 | CSR Approved | Comparison of acute renal failure incidence in LEV and other | Non Interventional Study - Retrospective | Not Applicable | Epidemiology | Neurology | UCB Pharma Global | Beau-Lejstrom R, Qvistorff K | [5 empty] | adults | No | Comparing the incidence of acute renal failure in patients with epilepsy exposed to levetiracetam versus other antiepileptic drugs. | [6 empty] | 2015-05-12: 2018-05-17; 2016-01-18: 2008-01-01; 2020-01-06: 2017-12-31; 2020-07-02: 2020-06-30 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1
Yes | Real World Evidence | Non-managing Type | 3 | BRIVIACT | Central Nervous System | EP0148 | CSR Approved | NISR Treatment pathways and safety in neonatal seizures | Non Interventional Study - Retrospective | Not Applicable | Real World Evidence | Neurology | UCB Pharma Global | Kaur M | [5 empty] | paediatrics | No | Retrospective cohort study describing treatment pathways through care and estimating potential adverse events in neonatal seizures | Epilepsy | Central Nervous System |  |  |  |  | 2015-09-29: 2008-10-21; 2016-01-18: 2020-04-01; 2019-11-29: 2009-05-05; 2020-01-06: 2021-07-31; 2020-05-05: 2010-01-01; 2020-07-02: 2022-07-15 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Non-managing Type | 3 | KEPPRA | Central Nervous System | EP0148 | CSR Approved | NISR Treatment pathways and safety in neonatal seizures | Non Interventional Study - Retrospective | Not Applicable | Real World Evidence | Neurology | UCB Pharma Global | Kaur M | [5 empty] | paediatrics | No | Retrospective cohort study describing treatment pathways through care and estimating potential adverse events in neonatal seizures | Epilepsy | Central Nervous System |  |  |  |  | 2015-09-29: 2008-10-21; 2016-01-18: 2020-04-01; 2019-11-29: 2009-05-05; 2020-01-06: 2021-07-31; 2020-05-05: 2010-01-01; 2020-07-02: 2022-07-15 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Non-managing Type | 3 | KEPPRA | Central Nervous System | EPD252 | CSR Approved | Treatment Characteristics Retrospective Chart Review | Non Interventional Study - Retrospective | Not Applicable | Affiliates | Neurology | UCB Pharma Global | Smith D | [5 empty] | adults | No | [7 empty] | 2016-01-18: 2014-01-06; 2020-01-06: 2016-10-28; 2020-07-02: 2018-02-28 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Real World Evidence | Non-managing Type | 3 | VIMPAT | Central Nervous System | EPD252 | CSR Approved | Treatment Characteristics Retrospective Chart Review | Non Interventional Study - Retrospective | Not Applicable | Affiliates | Neurology | UCB Pharma Global | Smith D | [5 empty] | adults | No | [7 empty] | 2016-01-18: 2014-01-06; 2020-01-06: 2016-10-28; 2020-07-02: 2018-02-28 | United States of America | United States of America (LPLV) | United States of America | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0